|  | PART ONE | ITEM NO. |
| --- | --- | --- |
| REPORT OF THE CITY TREASURER |
| TO THE: AUDIT & ACCOUNTS COMMITTEE ON: Wednesday 28th March 2012 |
| TITLE: STRATEGIC RISK REGISTER PROGRESS REPORT Q4 2011-12 |
| RECOMMENDATION: Members are requested to consider the contents of the report. |
| EXECUTIVE SUMMARY: The purpose of this report is to inform Members of progress on the Strategic Risk Register. |
| BACKGROUND DOCUMENTS: (Available for public inspection) Institute of Risk Management (IRM) / Association of Insurers & Risk Managers (AIRMIC) /Association of Local Authority Risk Managers (ALARM) produced A Risk Management Standard. Risk Management Strategy. |
| KEY DECISION: NO |
| DETAILS: See report attached. |
| KEY COUNCIL POLICIES: N/A |
| EQUALITY IMPACT ASSESSMENT AND IMPLICATIONS: N/A |
| ASSESSMENT OF RISK: Risk management activities undertaken throughout the Council ensure that risks are effectively identified and appropriately managed. |
| SOURCE OF FUNDING: Existing revenue budget. |
| LEGAL IMPLICATIONS Supplied by: N/A |
| FINANCIAL IMPLICATIONS Supplied by: The production of this report has no financial implications. |
| OTHER DIRECTORATES CONSULTED: N/A |
| CONTACT OFFICER: Cliff Peacock TEL. NO. 0161 607 6980 |
| WARD(S) TO WHICH REPORT RELATE(S): N/A |

| 1 | Background |
| --- | --- |
|  | Risk Management is a key component of local authorities’ corporate governance arrangements. It is essentially the systematic process by which key business risks / opportunities are identified, prioritised and controlled so as to ensure the achievement of council objectives and commitments. The purpose of this report is to inform Members of the Audit & Accounts Committee (AAC) of the current position on the key strategic risks currently being managed in the Strategic Risk Register. |
| 2 | Risk Management update |
|  | Progress on the Strategic Risk Register was last reported in January 2012.The current updated risks and opportunities are summarised in the attached appendix and are listed with the highest risk score first. |

Strategic Risk Register – Position Statement as at 16/03/2012

Updated for  28/03/12-  2012 Q4 by risk owner.

| Area of risk identified for the service | Direction of Travel Q1 Q2 Q3 Q4 | Detail & Actions (Detailed reports on progress are available on request via the responsible officer ) | Officer responsible for risk |
| --- | --- | --- | --- |
| SRR18. PUPILS & NUMBERS & DEMOGRAPHICS Scope of Risk: Failure to ensure adequate supply of primary school places to meet increased demand. |  |  | 16 | 16 | 500 Additional places have been created to accommodate increased numbers of pupils for September 2011 Further capacity is required for each year in the foreseeable future A Primary School Provision Programme (PSPP) has been established and managed through a fully integrated cross directorate approach and led by CSD. A Steering Group has been established comprising LA officers, diocesan and school representatives. The Steering Group will oversee the programme planning process and gain support of relevant stakeholders. The Steering Group will ensure effective communication of progress with all relevant parties For the anticipated September 2012 pupil demand, there is confidence that this can be met predominantly by utilising existing space in schools that has been recently used for other purposes. From September 2013 there is a need to create additional new physical capacity to expand the size of schools; this will require a strategic review of available assets and capital funding. Alignment of school place provision/demand with the Spatial Plan is essential. A work group of cross directorate internal and strategic partners is now progressing this as a collaborative task. A short term plan for 2012 increased provision is currently being negotiated with schools and a medium term plan for 2013-18 drafted for discussion before April 2012. Increasing the accuracy of demographic trend in sub areas of the city is a significant key to the efficient deployment of SCC resources in all directorates. A work group of both internal and external partners is now progressing this and will report in via the One Council Team to ensure the intelligence is collectively owned across all directorates. An OCT ‘portfolio’ priority area has been established to oversee this work. Active engagement with and involvement of all SCC directorates and partners will be essential to mitigating this risk. March 2012 | Jon Stonehouse reporting to Strategic Director Nick Page reporting to Portfolio Holder Cllr Morris |
| SRR 16. FINANCIAL IMPACT OF CSR (Replaces SSR10 : Financial Strategy) Scope of Risk: Failure to actively manage spending reductions to ensure that expenditure is within income following the Comprehensive Spending Review. I4XL4 | 16 | 16 | 16 | 12 | Balanced budget incorporating £40m of savings for 2011/12 approved by Council 2nd March 2011 following review of all options by strategic directors, lead members, CMT and B & EG CSR programme team in place to monitor the delivery of the savings targets and report monthly to CMT, B & EG and Budget Scrutiny Committee Monthly budget monitoring reports to directorate senior management, lead members, CMT, B & EG and Budget Scrutiny Committee have been produced each month from March onwards Mitigating steps have been taken to identify alternative savings where budgets have threatened to overspend or savings threatened to fall short of target Projected outturn for 2011/12 is showing a £2.5m underspend due to the tight controls imposed Financial planning for 2012/13 began in March 2011 with the forward projection of an £18m savings requirement and a Cabinet away day was held on 4th July to identify approach to deliver the required savings Directorates have prepared savings options; CMT and B & EG have considered strategic options. Budget plans for 2012/13 have been finalised and approved by Council in February 2012 Council should be in a healthier financial position going into 2012/13 but there remains the continuing threats from future Government spending cuts and demographic pressures that will require continued vigilance in delivering balanced budgets. March 2012 | John Spink reporting to Strategic Director Martin Vickers reporting to Portfolio Holder Cllr Hinds |
| SRR14. SAFEGUARDING. Scope of Risk: Practice in safeguarding children may develop with insufficient pace or sustainability. I4xL4 | 16 | 14 | 12 | 12 | Regular performance management of outcomes carried out via Safeguarding Improvement Board. Evidence of improved safeguarding practice in some areas, but this is at an early stage. Performance Management reporting in Safeguarding is well established via the “Report Card”. The Report Card is now fully established and each indicator is accompanied by a commentary from the appropriate senior social work manager which explains and contextualises performance. All indicators are showing month on month improvement Monitoring of progress and challenge carried out regularly both internally and externally by Ofsted and Department of Education. Progress is closely monitored and all actions are reviewed by internal audit as an objective critical friend. Phase 1 of the Safeguarding Action Plan has been actioned. Phase is 2 is now being implemented. Programme and project management resources in place to deliver the plan supported by resources from across the council including ICT, HR, marketing and communications and finance. The Safeguarding Improvement Programme has been refined to concentrate on the development of localities and integrated working in order to improve quality and effectiveness of work. This has included developing an early intervention and prevention strategy, providing a range of services to children and families. A Peer Review took place week beginning 12th September 2011 to 19th September 2011. The outcome of the review was positive and plans are currently being made to implement recommendations from the review. DFE review of the Improvement Notice took place on 10TH November 2011. A reviewed Improvement Notice is now in place. It is expected that an Ofsted re inspection will take place in Spring 2012. March 2012 | Gani Martins reporting to Strategic Director Nick Page reporting to Portfolio Holder Cllr Morris |
| SRR7. CIVIL CONTINGENCIES (INCLUDING EMERGENCY PLANNING AND BUSINESS CONTINUITY) Scope of Risk: Failure to recover after major incident. I3XL3 | 9 | 9 | 9 | 9 | Corporate Emergency Planning and Business Continuity Forum established and meeting every three months Directorate review of all business continuity plans completed Business continuity planning now included as part of the business planning process completed Provision of Beacon Centre as a nominated rest centre to replace Broadwalk with activation procedures in place. Exercise taking place in March 2012 in conjunction with CH&SC Directorate New Emergency Control Centre established (Innovation House). Exercise required in conjunction with AGMA Civil Contingencies and Resilience Unit Review being undertaken of rest centre provision with CH&SC Major incident Management Group EP/BC on agenda for school governing bodies during Autumn 2011 term completed Ongoing flood and reservoir inundation work across GM. GM Off site Reservoir Plan out for consultation March 2012 Review and re-issue of emergency planning and response documentation to be completed with an activation guide to be issued to directors in conjunction with AGMA Civil Contingencies & Resilience Unit New AGMA Civil Contingencies team will go live from 1 December and Salford will be working with its new business partner to agree priorities and focus on efforts to support resilience and response Business continuity and e-learning modules launched for staff and managers Representation on GM Resilience Forum Olympics 2012 sub-group and Salford ‘London 2012’ working group. BC Exercises for/Community, Health & Social Care and Sustainable Regeneration to take place in October and November completed. Children’s Services BC exercise to be planned for February 2012 Induction for new (volunteer) Emergency Control Centre Officers completed in September. This is the first part in strengthening the response in Salford and a paper to OCT for wider council participation is planned for March 2012 March 2012 | Olwyn Banner Reporting to David Hunter Reporting up to Strategic Director Martin Vickers Reporting to Portfolio Holder Cllr Hinds |
| SRR15. MEDIA CITY – PUBLIC SECTOR DELIVERY. Scope of Risk: Wider Public Sector cuts, International Flights, Public Sector Partnership Approach to Funding, Regional Competition for Inward Investment, Delivery of Public Transport Improvements & delivery of the Media Enterprise Centre. I3XL3 | 9 | 9 | 9 | 9 | Six weekly MediaCityUK Team Salford meetings are held which update on progress, risks and issues across the various activities. Key updates are provided to Leader’s Briefing and approvals sought where necessary. Alternative funding sources and implementation plans for public transport provision have successfully been secured. The new Salford QuaysLink bus service, which provides connectivity to MediaCityUK from across Salford, started on 3rd July 2011. Current patronage and revenue figures for both the Salford QuayslInk and metrolink services are within budgeted figures. The Media Enterprise Centre has been redefined to be more sustainable and cost effective with senior SCC input and close member input where appropriate. The target is to ensure the NWDA single programme and ERDF money is utilised. The NWDA monies have been claimed and the ERDFchange control is awaiting final approval. Regular updates are provided to the Leader and senior SCC colleagues. Some of these risks (transport and MEC) are ongoing and will remain so for some considerable time (otherwise no change). March 2012 | Karen Hirst reporting to Strategic Director Kevin Brady reporting to Portfolio Holder Cllr Merry |
| SSR17 & 19. WORKFORCE MANAGEMENT/& TRANSFORMATIONAL CHANGE ( replaces previous risk SRR5: Workforce Management ) Scope of Risk: Failure to actively manage the workforce impact of budget reductions and transform services to achieve savings. I4xL2 | 12 | 8 | 8 | 8 | Mass compulsory redundancy has been avoided in 2010/11. Arrangements are in place to manage displaced employees. A programme of support for managers in managing change has been rolled-out Policy and practice arrangements are in place to ensure compliance with statutory consultation requirements HR provide support to managers and directorates during restructures of business areas Regular and effective communication arrangements are in place with the trade unions Sickness, disciplinary and grievance cases are regularly monitored to ensure no significant increase. The Organisational Development (OD) offer will be strengthened through OCT portfolios. Each OCT portfolio owner’s responsibility includes any cross cutting related initiatives related to the OD element. Up to date policy arrangements are in place for supporting restructures March 2012 | Debbie Brown reporting to Strategic Director Martin Vickers reporting to Portfolio Holder Cllr Hinds |
| SRR21. PARTNERSHIP PRIORITIES Scope of Risk: | 4 | 4 | 4 | 4 | Major partnerships are in place with robust legal, governance and performance management arrangements. Partnerships are of long-term duration which allows for the partners to commit and support fully the Council’s objectives. Internal Audit carry out periodic audits on various elements of the partnerships operations including the effectiveness of the client side function, adherence to procurement regulations and in the case of secondment models, any staff related investigations. For Joint Venture Partnerships, annual due diligence is undertaken to validate the soundness of key partner organisations such as Capita Symonds and Galliford Try. Business continuity plans are in place for both the partnerships and the Council to support and direct any temporary difficulties in service delivery. Business Plans are either in place or imminently due to be in place for Urban Vision / Salix Homes (UV complete) March 2012 | Rob Pickering reporting to Strategic Director Paul Walker reporting to Portfolio Holder Cllr Hinds |