## Appendix 1
|  | Capital Programme 2004/05 | [17 empty] | Resources 2004/05
| SAP |  | 2004/05 Estimate | Contract |  | Actual spend | Profiled spend | [11 empty] | Profiled spend | Single capital pot | RING FENCED | Unsupported Borrowing |  | CAPITAL RECEIPTS
| REF |  |  | Start | Finish | to Oct 04 | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | to Oct 04 | SCE (R) | SCE (R) |  | RCCO |  | GRANT | OTHER | TOTAL | TSG | EP | NDS | Surestart | STANDARDS FUND | DFC | SEED | DFG | SRB | ERDF | NDC | Lottery | NWDA | HMRF | Home Office | Other | TOTAL | Notes
|  |  | £m |  |  | £m | [12 empty] | £m | £m | £m |  | £m | £m | £m | £m | £m | £m |  | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | bar: Profiled spend Apr to Profiled spend Mar
PRIVATE SECTOR HOUSING
Langwothy / Seedley
| summary | ACQUISITIONS-SHOPS/OTHER PROPERTIES | 2.149 |  |  | 0.956 | 0.664 | 0 | 0 | 0 | 0 | 0.353 | 0.353 | 0.353 | 0.353 | 0.353 | 0.353 | 0.353 | 1.37 | 0 | 0 | 0 | 0 | 0.195 | 1.954 | 0 | 2.149 | 0 | 0.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0.235 | 0 | 0 | 0 | 0.109 | 0.74 | 0 | 0 | 1.954
|  | SSA-Shops/Commercial Properties | 0.57 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.128 | 0.128 | 0.128 | 0.128 | 0.128 | 0.128 | 0.128 | 0.256 |  |  |  |  | 0.195 | 0.375 |  | 0.57 | [8 empty] | 0.235 |  |  |  |  | 0.14 |  |  | 0.375
|  | ACQUISITIONS-HOUSES | [16 empty] | 0 | [5 empty] | 0 |  | 0 | [16 empty] | 0
|  | SSA-Houses | 1.009 |  |  | 0.693 | 0.493 | 0 | 0 | 0 | 0 | 0.144 | 0.144 | 0.144 | 0.144 | 0.144 | 0.144 | 0.144 | 0.781 | [5 empty] | 1.009 |  | 1.009 |  | 0.87 | [10 empty] | 0.109 | 0.03 |  |  | 1.009
| h00578 | ACQUISITIONS-HOWARD HOUSE |  |  |  | 0 | [12 empty] | 0 | [5 empty] | 0 |  | 0 | [16 empty] | 0
|  | ACQUISITIONS-Landscape m'tce | [16 empty] | 0 | [5 empty] | 0 |  | 0 | [16 empty] | 0
|  | SSA-Maintenance/running costs | 0.02 |  |  | 0.009 | 0 | 0 | 0 | 0 | 0 | 0.002 | 0.002 | 0.002 | 0.002 | 0.002 | 0.002 | 0.002 | 0.004 | [5 empty] | 0.02 |  | 0.02 | [13 empty] | 0.02 |  |  | 0.02
|  | SECURING / MANAGEMENT | [16 empty] | 0 | [5 empty] | 0 |  | 0 | [16 empty] | 0
| calc +h00918, 919 | SSA-Securing /Managing properties | 0.55 |  |  | 0.254 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.1 | [5 empty] | 0.55 |  | 0.55 | [13 empty] | 0.55 |  |  | 0.55
|  | DEMOLITION / SITE TREATMENT | [16 empty] | 0 | [5 empty] | 0 |  | 0 | [16 empty] | 0
| h00575 h00915 | SSA -Demolition / Site Treatment | 0 |  |  |  | 0.171 | 0 | 0 | 0 | 0 | 0.029 | 0.029 | 0.029 | 0.029 | 0.029 | 0.029 | 0.029 | 0.229 | [5 empty] | 0 |  | 0 | [16 empty] | 0
| summary | HOMESWAPS | 1.423 |  |  | 0.639 | 0.581 | 0 | 0 | 0 | 0 | 0.13257 | 0.13257 | 0.13257 | 0.13257 | 0.13257 | 0.13257 | 0.13257 | 0.84614 | 0 | 0 | 0 | 0 | 0 | 1.423 | 0 | 1.423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.423 | 0 | 0 | 1.423
| h00932 | SHO-Langworthy north ph 1/2(15dw-dsd) | 0.025 |  |  | 0.001 | 0.001 | 0 | 0 | 0 | 0 | 0.0027143 | 0.0027143 | 0.0027143 | 0.0027143 | 0.0027143 | 0.0027143 | 0.0027143 | 0.0064286 | [5 empty] | 0.025 |  | 0.025 | [13 empty] | 0.025 |  |  | 0.025
|  | SHO-Langworthy north ph 3-dsd | [16 empty] | 0 | [5 empty] | 0 |  | 0 | [13 empty] | 0 |  |  | 0
| h01251 | SHO-Langworthy north ph 4-dsd | 0.264 |  |  | 0.223 | 0.213 | 0 | 0 | 0 | 0 | 0.016 | 0.016 | 0.016 | 0.016 | 0.016 | 0.016 | 0.016 | 0.245 | [5 empty] | 0.264 |  | 0.264 | [13 empty] | 0.264 |  |  | 0.264
|  | SHO-Langworthy north ph 5-dsd |  |  |  | 0 | [12 empty] | 0 | [5 empty] | 0 |  | 0 | [13 empty] | 0 |  |  | 0
| h00944 | SHO-Langworthy north ph 6-dsd | 0.208 |  |  | 0.021 | 0.008 | 0 | 0 | 0 | 0 | 0.032857 | 0.032857 | 0.032857 | 0.032857 | 0.032857 | 0.032857 | 0.032857 | 0.073714 | [5 empty] | 0.208 |  | 0.208 | [13 empty] | 0.208 |  |  | 0.208
|  | SHO-Seedley West ph 1-dsd | 0.151 |  |  | 0.127 | 0.127 | 0 | 0 | 0 | 0 | 0.003 | 0.003 | 0.003 | 0.003 | 0.003 | 0.003 | 0.003 | 0.133 | [5 empty] | 0.151 |  | 0.151 | [13 empty] | 0.151 |  |  | 0.151
|  | SHO-Seedley West ph 2-dsd | 0.345 |  |  | 0.031 | 0.031 | 0 | 0 | 0 | 0 | 0.045 | 0.045 | 0.045 | 0.045 | 0.045 | 0.045 | 0.045 | 0.121 | [5 empty] | 0.345 |  | 0.345 | [13 empty] | 0.345 |  |  | 0.345
| h00936-h00943, h00945-h00950 | SHO-Homeswaps -dsd -individual schemes | 0.315 |  |  | 0.182 | 0.163 | 0 | 0 | 0 | 0 | 0.022 | 0.022 | 0.022 | 0.022 | 0.022 | 0.022 | 0.022 | 0.207 | [5 empty] | 0.315 |  | 0.315 | [13 empty] | 0.315 |  |  | 0.315
| h00931 | Homeswaps -general spend(SHO) | 0.115 |  |  | 0.054 | 0.038 | 0 | 0 | 0 | 0 | 0.011 | 0.011 | 0.011 | 0.011 | 0.011 | 0.011 | 0.011 | 0.06 | [5 empty] | 0.115 |  | 0.115 | [13 empty] | 0.115 |  |  | 0.115
| summary | RELOCATION GRANTS | 0.1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.014286 | 0.014286 | 0.014286 | 0.014286 | 0.014286 | 0.014286 | 0.014286 | 0.028571 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0.1
|  | SHO-Individual relocation grants | 0.1 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.014286 | 0.014286 | 0.014286 | 0.014286 | 0.014286 | 0.014286 | 0.014286 | 0.028571 | [5 empty] | 0.1 |  | 0.1 | [13 empty] | 0.1 |  |  | 0.1
| summary | RENOVATION GRANTS | 0.25 |  |  | 0.209 | 0.196 | 0 | 0 | 0 | 0 | 0.008 | 0.008 | 0.008 | 0.008 | 0.008 | 0.008 | 0.008 | 0.212 | 0 | 0 | 0 | 0 | 0.25 | 0 | 0 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Individual Renovation Grants(HI) | 0.25 |  |  | 0.209 | 0.196 | 0 | 0 | 0 | 0 | 0.008 | 0.008 | 0.008 | 0.008 | 0.008 | 0.008 | 0.008 | 0.212 |  |  |  |  | 0.25 | 0 |  | 0.25 | [16 empty] | 0
| summary | GROUP REPAIR / ENVIRONMENTALS | 2.219 |  |  | 1.288 | 1.06 | 0 | 0 | 0 | 0 | 0.061286 | 0.061286 | 0.061286 | 0.061286 | 0.062429 | 0.062429 | 0.062429 | 1.1826 | 0 | 0 | 0 | 0 | 1.375 | 0.844 | 0 | 2.219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.62 | 0 | 0 | 0 | 0 | 0.224 | 0 | 0 | 0.844
| h00563 | Alleyway refurb -dsd | -0.001 |  |  | -0.001 | -0.001 | 0 | 0 | 0 | 0 | -0.00014286 | -0.00014286 | -0.00014286 | -0.00014286 | -0.00014286 | -0.00014286 | -0.00014286 | -0.0012857 |  |  |  |  | -0.001 | 0 |  | -0.001 | [16 empty] | 0
| H00453 | HI-Langworthy North ph 1-dsd | 0.005 |  |  | 0.004 | 0.004 | 0 | 0 | 0 | 0 | -0.00014286 | -0.00014286 | -0.00014286 | -0.00014286 | 0.001 | 0.001 | 0.001 | 0.0037143 | [5 empty] | 0.005 |  | 0.005 | [8 empty] | 0.005 | [7 empty] | 0.005
| H00455 | HI-Langworthy North ph 2-dsd | 0.011 |  |  | 0.008 | 0 | 0 | 0 | 0 | 0 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0031429 |  |  |  |  | 0.006 | 0.005 |  | 0.011 | [8 empty] | 0.005 | [7 empty] | 0.005
| calc | HI-Langworthy North ph 3-dsd | 0.111 |  |  | 0.096 | 0.066 | 0 | 0 | 0 | 0 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.078 |  |  |  |  | 0.015 | 0.096 |  | 0.111 | [8 empty] | 0.096 | [7 empty] | 0.096
| H01251 | HI-Langworthy North ph 4-dsd | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.012 | [5 empty] | 0 |  | 0 | [16 empty] | 0
| H01253 | HI-Langworthy North ph 5-dsd | 0.501 |  |  | 0.311 | 0.202 | 0 | 0 | 0 | 0 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.214 |  |  |  |  | 0.341 | 0.16 |  | 0.501 | [8 empty] | 0.091 |  |  |  |  | 0.069 |  |  | 0.16
| H01255 | HI-Langworthy North ph 6-dsd | 0.348 |  |  | 0.336 | 0.332 | 0 | 0 | 0 | 0 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.344 |  |  |  |  | 0.271 | 0.077 |  | 0.348 | [13 empty] | 0.077 |  |  | 0.077
| h00460 | HI-Seedley west remodel ph 1- dsd | 0.367 |  |  | 0.224 | 0.213 | 0 | 0 | 0 | 0 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.225 |  |  |  |  | 0.289 | 0.078 |  | 0.367 | [13 empty] | 0.078 |  |  | 0.078
| h01254 | HI-Seedley west remodel ph 2-dsd | 0.712 |  |  | 0.273 | 0.209 | 0 | 0 | 0 | 0 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.221 |  |  |  |  | 0.327 | 0.385 |  | 0.712 | [8 empty] | 0.385 | [7 empty] | 0.385
| h00456 | West of Seedley pk rd ph 2 (mmha)(HI) | 0.011 |  |  | 0.011 | 0.011 | 0 | 0 | 0 | 0 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.023 |  |  |  |  | 0.011 | 0 |  | 0.011 | [16 empty] | 0
| h01256 | West of Seedley pk rd ph 3 (dsd)(HI)-dsd | 0.038 |  |  | 0.019 | 0.019 | 0 | 0 | 0 | 0 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.031 |  |  |  |  | 0 | 0.038 |  | 0.038 | [8 empty] | 0.038 | [7 empty] | 0.038
| h01306 | Environmental work(3/4 New Starts)(SN) | 0.115 |  |  | 0.006 | 0.004 | 0 | 0 | 0 | 0 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.016 |  |  |  |  | 0.115 | 0 |  | 0.115 | [16 empty] | 0
| h01257 | Highfield / Fitzwarren alleygating(SN) | 0.001 |  |  | 0.001 | 0.001 | 0 | 0 | 0 | 0 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.013 |  |  |  |  | 0.001 | 0 |  | 0.001 | [16 empty] | 0
| summary | SHOP REFURBISHMENTS | 0.99 |  |  | 0.533 | 0.399 | 0 | 0 | 0 | 0 | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | 0.559 | 0 | 0 | 0 | 0 | 0.345 | 0.645 | 0 | 0.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.645
| H00566 h00580, h00981 | phase 1 (dsd) | 0.943 |  |  | 0.53 | 0.38 |  |  |  |  | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | 0.54 |  |  |  |  | 0.323 | 0.62 |  | 0.943 | [8 empty] | 0.62 | [7 empty] | 0.62
|  | car park/layby | 0.025 | [21 empty] | 0.025 |  | 0.025 | [8 empty] | 0.025 | [7 empty] | 0.025
| calc | phase 2(dsd) | 0.022 |  |  | 0.003 | Profiled spend Apr: 0.019 | 0.019 |  |  |  |  | 0.022 | 0 |  | 0.022 | [16 empty] | 0
| summary | GAP FUNDING | 0.02 |  |  | 0.005 | 0 | 0 | 0 | 0 | 0 | 0.003 | 0.003 | 0.003 | 0.003 | 0.003 | 0.003 | 0.003 | 0 | 0 | 0 | 0 | 0 | 0 | 0.02 | 0 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.02 | 0 | 0 | 0.02
|  | SD-Urban Splash | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | [16 empty] | 0
|  | SD-Marketing and Publicity | 0.02 |  |  | 0.005 | Profiled spend Sep: 0.003; Profiled spend Oct: 0.003; Profiled spend Nov: 0.003; Profiled spend Dec: 0.003; Profiled spend Jan: 0.003; Profiled spend Feb: 0.003; Profiled spend Mar: 0.003 | [6 empty] | 0.02 |  | 0.02 | [13 empty] | 0.02 |  |  | 0.02
| summary | LIVING ENVIRONMENT TEAM | 0.2 |  |  | 0.084 | 0.073 | 0 | 0 | 0 | 0 | 0.018143 | 0.018143 | 0.018143 | 0.018143 | 0.018143 | 0.018143 | 0.018143 | 0.10929 |  |  |  |  | 0.079 | 0.121 |  | 0.2 | [8 empty] | 0.102 | 0.019 | [6 empty] | 0.121
| 7.351 | [23 empty] | 0 |  | 0 | [16 empty] | 0
|  | Private sector housing excluding SRB 5 | [17 empty] | 0 | 0 | 0 | 0
| summary | NEW DEAL/ NORTH IRWELL | 2.85 |  |  | 0.459 | 0.273 | 0 | 0 | 0 | 0 | 0.39914 | 0.39914 | 0.39914 | 0.39914 | 0.39914 | 0.39914 | 0.39914 | 1.0713 | 0.361 | 0 | 0 | 0 | 0 | 2.489 | 0 | 2.85 | 0 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.154 | 0 | 0 | 1.175 | 0 | 0 | 2.489
|  | SSA-Auckland Drive / Britannia St | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.036 | 0.036 | 0.036 | 0.036 | 0.036 | 0.036 | 0.036 | 0.072 | [5 empty] | 0.252 |  | 0.252 | [10 empty] | 0.05 |  |  | 0.202 |  |  | 0.252
|  | SSA-Oaklands Rd RTB's | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | [16 empty] | 0
|  | SSA-Homeswap-acquisitions |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | [16 empty] | 0
|  | SSA-Security /Boarding up | 0.043 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.0061429 | 0.0061429 | 0.0061429 | 0.0061429 | 0.0061429 | 0.0061429 | 0.0061429 | 0.012286 | [5 empty] | 0.043 |  | 0.043 | [10 empty] | 0.043 | [5 empty] | 0.043
|  | SSA-Littleton Rd (15/19) | 1.252 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.14286 | 0.14286 | 0.14286 | 0.14286 | 0.14286 | 0.14286 | 0.28571 | [5 empty] | 1 |  | 1 |  | 0.16 | [8 empty] | 0.15 |  |  | 0.69 |  |  | 1
|  | HI-Whit Lane RTB's |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | [16 empty] | 0
|  | HI-Lower Kersal RTB's |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | [16 empty] | 0
| H01053 | HI-Littleton Rd/Ayrshire facelifts (phase 1)(dsd) | 0.371 |  |  | 0.324 | 0.183 | 0 | 0 | 0 | 0 | 0.022286 | 0.022286 | 0.022286 | 0.022286 | 0.022286 | 0.022286 | 0.022286 | 0.22757 | 0.139 |  |  |  |  | 0.232 |  | 0.371 | [10 empty] | 0.227 |  |  | 0.005 |  |  | 0.232
| H01054 | HI-Norfolk / Gerald / Suffolk st-rear yard walls(dsd) | 0.068 |  |  | 0.053 | 0.049 | 0 | 0 | 0 | 0 | 0.0027143 | 0.0027143 | 0.0027143 | 0.0027143 | 0.0027143 | 0.0027143 | 0.0027143 | 0.054429 | [5 empty] | 0.068 |  | 0.068 | [10 empty] | 0.068 | [5 empty] | 0.068
|  | HI- Gerald Rd / Levens St | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | [16 empty] | 0
|  | HI- Arrowhead (Beeley St) refurbishment | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | [16 empty] | 0
|  | littleton rd ph 1(dsd) see HI-Littleton rd facelifts | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | [13 empty] | 0 |  |  | 0
|  | littleton rd ph 2(dsd) | 0.274 |  |  | 0.02 | 0.001 | 0 | 0 | 0 | 0 | 0.038714 | 0.038714 | 0.038714 | 0.038714 | 0.038714 | 0.038714 | 0.038714 | 0.078429 | 0.102 |  |  |  |  | 0.172 |  | 0.274 | [10 empty] | 0.072 |  |  | 0.1 |  |  | 0.172
|  | littleton rd ph3 (dsd) | 0.12 |  |  | 0 | 0.006 | 0 | 0 | 0 | 0 | 0.016286 | 0.016286 | 0.016286 | 0.016286 | 0.016286 | 0.016286 | 0.016286 | 0.038571 | [5 empty] | 0.12 |  | 0.12 | [10 empty] | 0.12 | [5 empty] | 0.12
|  | littleton rd ph 4(dsd) | 0.11 |  |  | 0.001 | 0 | 0 | 0 | 0 | 0 | 0.015714 | 0.015714 | 0.015714 | 0.015714 | 0.015714 | 0.015714 | 0.015714 | 0.031429 | [5 empty] | 0.11 |  | 0.11 | [10 empty] | 0.1 |  |  | 0.01 |  |  | 0.11
|  | littleton rd ph 5(dsd) | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | [16 empty] | 0
| H01055 | arrowhead ph 1 (dsd)- assumed resources from arrowh'd/beeley refurb-hmr/hi | 0.29 |  |  | 0.018 | 0.011 | 0 | 0 | 0 | 0 | 0.047143 | 0.047143 | 0.047143 | 0.047143 | 0.047143 | 0.047143 | 0.047143 | 0.10529 | 0.087 |  |  |  |  | 0.203 |  | 0.29 | [10 empty] | 0.15 |  |  | 0.053 |  |  | 0.203
|  | arrowhead ph 2 (dsd) | 0.092 |  |  | 0.011 | 0.003 | 0 | 0 | 0 | 0 | 0.0098571 | 0.0098571 | 0.0098571 | 0.0098571 | 0.0098571 | 0.0098571 | 0.0098571 | 0.022714 | 0.02 |  |  |  |  | 0.072 |  | 0.092 | [10 empty] | 0.072 | [5 empty] | 0.072
|  | arrowhead ph 3 (dsd)-assumed resources from gerard/levens hmr/hi | 0.207 |  |  | 0.016 | 0.01 | 0 | 0 | 0 | 0 | 0.059571 | 0.059571 | 0.059571 | 0.059571 | 0.059571 | 0.059571 | 0.059571 | 0.12914 | [5 empty] | 0.207 |  | 0.207 | [10 empty] | 0.092 |  |  | 0.115 |  |  | 0.207
| H00131 | grants | 0.02 |  |  | 0.015 | 0.01 | 0 | 0 | 0 | 0 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.012857 | 0.01 |  |  |  |  | 0.01 |  | 0.02 | [10 empty] | 0.01 | [5 empty] | 0.01
|  | norfolk / gerald / suffolk st-environmental(dsd) | 0.003 |  |  | 0.001 | 0 | 0 | 0 | 0 | 0 | 0.00042857 | 0.00042857 | 0.00042857 | 0.00042857 | 0.00042857 | 0.00042857 | 0.00042857 | 0.00085714 | 0.003 |  |  |  |  | 0 |  | 0.003 | [16 empty] | 0
| summary | Higher Broughton | 8.945 |  |  | 1.647 | 1.163 | 0 | 0 | 0 | 0 | 1.2106 | 1.2106 | 1.2106 | 1.2106 | 1.2106 | 1.2106 | 1.2106 | 3.5841 | 0.751 | 0 | 0 | 0 | 0.182 | 8.012 | 0 | 8.945 | 0 | 3.739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.273 | 0 | 0 | 8.012
|  | SSA-Broughton -demolitions/site treatment | 0.151 |  |  | 0.099 | 0.043 | 0 | 0 | 0 | 0 | 0.015429 | 0.015429 | 0.015429 | 0.015429 | 0.015429 | 0.015429 | 0.015429 | 0.073857 | [5 empty] | 0.151 |  | 0.151 | [13 empty] | 0.151 |  |  | 0.151
|  | SSA-Broughton -security / disconnections | 0.116 |  |  | 0.079 | 0.067 | 0 | 0 | 0 | 0 | 0.007 | 0.007 | 0.007 | 0.007 | 0.007 | 0.007 | 0.007 | 0.081 | [5 empty] | 0.116 |  | 0.116 | [13 empty] | 0.116 |  |  | 0.116
| H00640 | SSA-Broughton-Top/bottom Streets | 1.75 |  |  | 0.656 | 0.514 | 0 | 0 | 0 | 0 | 0.17657 | 0.17657 | 0.17657 | 0.17657 | 0.17657 | 0.17657 | 0.17657 | 0.86714 | [5 empty] | 1.75 |  | 1.75 | [13 empty] | 1.75 |  |  | 1.75
|  | SSA-Broughton -Granyte st ground lease | 0.008 |  |  | 0.008 | 0.008 | 0 | 0 | 0 | 0 | 0.00042857 | 0.00042857 | 0.00042857 | 0.00042857 | 0.00042857 | 0.00042857 | 0.00042857 | 0.0088571 | [5 empty] | 0.008 |  | 0.008 | [13 empty] | 0.008 |  |  | 0.008
| H00643 | SSA-Broughton -5 portfolios | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | [16 empty] | 0
|  | SSA-Broughton -House That Jack Built Pub | 0.28 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.05 | [5 empty] | 0.28 |  | 0.28 |  | 0.175 | [11 empty] | 0.105 |  |  | 0.28
|  | SSA-Broughton -Commercial relocation packages | 0.075 |  |  | 0.032 | 0 | 0 | 0 | 0 | 0 | 0.010714 | 0.010714 | 0.010714 | 0.010714 | 0.010714 | 0.010714 | 0.010714 | 0.021429 | [5 empty] | 0.075 |  | 0.075 | [13 empty] | 0.075 |  |  | 0.075
| H00637 | SSA-Broughton -Acq Earl /Kempster | 0.65 |  |  | 0.304 | 0.179 | 0 | 0 | 0 | 0 | 0.067286 | 0.067286 | 0.067286 | 0.067286 | 0.067286 | 0.067286 | 0.067286 | 0.31357 | [5 empty] | 0.65 |  | 0.65 | [13 empty] | 0.65 |  |  | 0.65
|  | SSA-Broughton -Acq Gt Cheetham st(490/502) | 0.07 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.02 | [5 empty] | 0.07 |  | 0.07 | [13 empty] | 0.07 |  |  | 0.07
|  | SSA-Broughton -Acq-Moss St | 0.08 |  |  | 0.015 | 0 | 0 | 0 | 0 | 0 | 0.050714 | 0.050714 | 0.050714 | 0.050714 | 0.050714 | 0.050714 | 0.050714 | 0.10143 | [5 empty] | 0.08 |  | 0.08 | [13 empty] | 0.08 |  |  | 0.08
|  | SSA-Broughton -Acq-1 Wellington St | 0.25 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.035714 | 0.035714 | 0.035714 | 0.035714 | 0.035714 | 0.035714 | 0.035714 | 0.071429 | [5 empty] | 0.25 |  | 0.25 |  | 0.25 | [14 empty] | 0.25
|  | SSA-Broughton -Wellington St | 2.874 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.41057 | 0.41057 | 0.41057 | 0.41057 | 0.41057 | 0.41057 | 0.41057 | 0.82114 | [5 empty] | 2.874 |  | 2.874 |  | 2.874 | [14 empty] | 2.874
|  | SSA-Broughton - Hanover court demolition | 0.44 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.062857 | 0.062857 | 0.062857 | 0.062857 | 0.062857 | 0.062857 | 0.062857 | 0.12571 | [5 empty] | 0.44 |  | 0.44 |  | 0.44 | [14 empty] | 0.44
|  | SSA-Broughton - Meadow Road | 0.3 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.042857 | 0.042857 | 0.042857 | 0.042857 | 0.042857 | 0.042857 | 0.042857 | 0.085714 | 0.3 |  |  |  |  | 0 |  | 0.3 | [16 empty] | 0
|  | SSA-Broughton - Land at Feney St(16-22) | 0.005 |  |  | 0.005 | [18 empty] | 0.005 |  | 0.005 | [13 empty] | 0.005 |  |  | 0.005
| H01603 | SD-Broughton -Gap funding-site investigation/remedial | 0.877 |  |  | 0.188 | 0.166 | 0 | 0 | 0 | 0 | 0.10157 | 0.10157 | 0.10157 | 0.10157 | 0.10157 | 0.10157 | 0.10157 | 0.36914 | [5 empty] | 0.877 |  | 0.877 | [13 empty] | 0.877 |  |  | 0.877
|  | SSA-Broughton - Albert Park development | 0.05 |  |  | 0.05 | 0 | 0 | 0 | 0 | 0 | 0.010714 | 0.010714 | 0.010714 | 0.010714 | 0.010714 | 0.010714 | 0.010714 | 0.021429 | [5 empty] | 0.05 |  | 0.05 | [13 empty] | 0.05 |  |  | 0.05
|  | SHO-Broughton -Homeswaps | 0.2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.095429 | 0.095429 | 0.095429 | 0.095429 | 0.095429 | 0.095429 | 0.095429 | 0.19086 | [5 empty] | 0.2 |  | 0.2 | [13 empty] | 0.2 |  |  | 0.2
| H00041 | HI-Broughton-Home Improvement Grants | 0.3 |  |  | 0.046 | 0.046 | 0 | 0 | 0 | 0 | 0.036286 | 0.036286 | 0.036286 | 0.036286 | 0.036286 | 0.036286 | 0.036286 | 0.11857 | 0.3 |  |  |  |  | 0 |  | 0.3 | [16 empty] | 0
|  | HI-Broughton -Facelifts -Gt Cheetham st west | 0.104 |  |  | 0.003 | 0.003 | 0 | 0 | 0 | 0 | 0.014429 | 0.014429 | 0.014429 | 0.014429 | 0.014429 | 0.014429 | 0.014429 | 0.031857 | [5 empty] | 0.104 |  | 0.104 | [13 empty] | 0.104 |  |  | 0.104
|  | HI-Broughton -Facelifts-lower broughton road phase 1 | 0.096 |  |  | 0.004 | 0.001 | 0 | 0 | 0 | 0 | 0.014429 | 0.014429 | 0.014429 | 0.014429 | 0.014429 | 0.014429 | 0.014429 | 0.029857 | 0.064 |  |  |  |  | 0.032 |  | 0.096 | [13 empty] | 0.032 |  |  | 0.032
|  | HI-Broughton -refurbishments | 0.15 |  |  | 0.039 | 0.031 | 0 | 0 | 0 | 0 | 0.017 | 0.017 | 0.017 | 0.017 | 0.017 | 0.017 | 0.017 | 0.065 | 0.087 |  |  |  | 0.063 | 0 |  | 0.15 | [16 empty] | 0
| H00524 | Broughton -Gt Clowes St ph 2 env (SN 3/4 )(dsd) | 0.119 |  |  | 0.119 | 0.105 | 0 | 0 | 0 | 0 | 0.0055714 | 0.0055714 | 0.0055714 | 0.0055714 | 0.0055714 | 0.0055714 | 0.0055714 | 0.11614 |  |  |  |  | 0.119 | 0 |  | 0.119 | [16 empty] | 0
|  | Broughton site investigation | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | [16 empty] | 0
| summary | CLAREMONT / WEASTE | 2.818 |  |  | 0.576 | 0.364 | 0 | 0 | 0 | 0 | 0.34057 | 0.34057 | 0.34057 | 0.34057 | 0.34057 | 0.34057 | 0.34057 | 1.0451 | 0 | 0 | 0 | 0 | 0.78 | 2.038 | 0 | 2.818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.038 | 0 | 0 | 2.038
|  | SSA-Claremont / Weaste--acquisitions-Duchy | 0.4 |  |  | 0.07 | 0.021 | 0 | 0 | 0 | 0 | 0.054143 | 0.054143 | 0.054143 | 0.054143 | 0.054143 | 0.054143 | 0.054143 | 0.12929 | [5 empty] | 0.4 |  | 0.4 | [13 empty] | 0.4 |  |  | 0.4
|  | SSA-Claremont / Weaste-acq-Weaste La/Kennedy | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.0071429 | 0.0071429 | 0.0071429 | 0.0071429 | 0.0071429 | 0.0071429 | 0.0071429 | 0.014286 | [5 empty] | 0 |  | 0 | [16 empty] | 0
| H00853 | SSA-Claremont / Weaste-security/disconnections | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | [16 empty] | 0
|  | SSA-Claremont / Weaste-demolition/site treatment | 0.06 |  |  | 0.003 | 0.001 | 0 | 0 | 0 | 0 | 0.0084286 | 0.0084286 | 0.0084286 | 0.0084286 | 0.0084286 | 0.0084286 | 0.0084286 | 0.017857 | [5 empty] | 0.06 |  | 0.06 | [13 empty] | 0.06 |  |  | 0.06
|  | SD-Claremont / Weaste-redevelopment Duchy | 0.889 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.127 | 0.127 | 0.127 | 0.127 | 0.127 | 0.127 | 0.127 | 0.254 | [5 empty] | 0.889 |  | 0.889 | [13 empty] | 0.889 |  |  | 0.889
|  | SHO-Claremont / Weaste-Homeswaps Duchy | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | [16 empty] | 0
|  | SHO-Claremont / Weaste-Relocation grants | 0.125 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.017857 | 0.017857 | 0.017857 | 0.017857 | 0.017857 | 0.017857 | 0.017857 | 0.035714 | [5 empty] | 0.125 |  | 0.125 | [13 empty] | 0.125 |  |  | 0.125
| H00812 | HI-Claremont / Weaste-Kennedy Rd(Weaste ph 1 facelift)(dsd) | 0.109 |  |  | 0.089 | 0.089 | 0 | 0 | 0 | 0 | 0.0028571 | 0.0028571 | 0.0028571 | 0.0028571 | 0.0028571 | 0.0028571 | 0.0028571 | 0.094714 |  |  |  |  | 0.07 | 0.039 |  | 0.109 | [13 empty] | 0.039 |  |  | 0.039
|  | HI-Claremont / Weaste -Weaste rd ph 2 qs/ assumed ph 4 hmr (dsd) | 0.149 |  |  | 0.003 | 0.001 | 0 | 0 | 0 | 0 | 0.021143 | 0.021143 | 0.021143 | 0.021143 | 0.021143 | 0.021143 | 0.021143 | 0.043286 |  |  |  |  | 0.031 | 0.118 |  | 0.149 | [13 empty] | 0.118 |  |  | 0.118
| H00818 | HI-Claremont / Weaste-Barff Rd block impts(assumed ph 2 hmr) (dsd) | 0.417 |  |  | 0.174 | 0.085 | 0 | 0 | 0 | 0 | 0.047143 | 0.047143 | 0.047143 | 0.047143 | 0.047143 | 0.047143 | 0.047143 | 0.17929 |  |  |  |  | 0.225 | 0.192 |  | 0.417 | [13 empty] | 0.192 |  |  | 0.192
|  | HI-Claremont / Weaste-Glendore/New Cross(ph 4qs-assumed ph 3/5 hmr) (dsd | 0.224 |  |  | 0.01 | 0 | 0 | 0 | 0 | 0 | 0.015714 | 0.015714 | 0.015714 | 0.015714 | 0.015714 | 0.015714 | 0.015714 | 0.031429 |  |  |  |  | 0.129 | 0.095 |  | 0.224 | [13 empty] | 0.095 |  |  | 0.095
|  | RSL-Claremont / Weaste -Weaste Home Ownership | 0.12 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.017143 | 0.017143 | 0.017143 | 0.017143 | 0.017143 | 0.017143 | 0.017143 | 0.034286 | [5 empty] | 0.12 |  | 0.12 | [13 empty] | 0.12 |  |  | 0.12
|  | Claremont / Weaste street lighting | 0.003 |  |  | 0.003 | [17 empty] | 0.003 | 0 |  | 0.003
|  | Claremont / Weaste Weaste Clear up | 0.002 |  |  | 0.002 | [17 empty] | 0.002 | 0 |  | 0.002
| H00091 | Claremont / Weaste HI-grants | 0.09 |  |  | 0.055 | 0.033 | 0 | 0 | 0 | 0 | 0.0048571 | 0.0048571 | 0.0048571 | 0.0048571 | 0.0048571 | 0.0048571 | 0.0048571 | 0.042714 |  |  |  |  | 0.09 | 0 |  | 0.09 | [16 empty] | 0
| H00814 | Claremont / Weaste-Duchy facelift (dsd) | 0.149 |  |  | 0.145 | 0.113 | 0 | 0 | 0 | 0 | 0.0042857 | 0.0042857 | 0.0042857 | 0.0042857 | 0.0042857 | 0.0042857 | 0.0042857 | 0.12157 |  |  |  |  | 0.149 | 0 |  | 0.149 | [16 empty] | 0
| H00816 | Claremont / Weaste SN-Weaste drying yard (dsd) | 0.014 |  |  | 0.01 | 0.009 | 0 | 0 | 0 | 0 | 0.00071429 | 0.00071429 | 0.00071429 | 0.00071429 | 0.00071429 | 0.00071429 | 0.00071429 | 0.010429 |  |  |  |  | 0.014 | 0 |  | 0.014 | [16 empty] | 0
|  | Weaste - Gore Crescent Disturbance | 0.012 |  |  | 0.012 | 0.012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.012 |  |  |  |  | 0.012 | 0 |  | 0.012
|  | Claremont / Weaste-Broomhall Rd (dsd) | 0.055 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.012143 | 0.012143 | 0.012143 | 0.012143 | 0.012143 | 0.012143 | 0.012143 | 0.024286 |  |  |  |  | 0.055 | 0 |  | 0.055 | [16 empty] | 0
| summary | ENTERPRISE PARK | 0.473 |  |  | 0.146 | 0.133 | 0 | 0 | 0 | 0 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 | 0.209 | 0 | 0 | 0 | 0 | 0.045 | 0.428 | 0 | 0.473 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.328 | 0 | 0 | 0.428
| H00851-852 | SSA-Stowell / Bridson acquisitions | 0.063 |  |  | 0.021 | 0.018 | 0 | 0 | 0 | 0 | 0.0064286 | 0.0064286 | 0.0064286 | 0.0064286 | 0.0064286 | 0.0064286 | 0.0064286 | 0.030857 | [5 empty] | 0.063 |  | 0.063 | [13 empty] | 0.063 |  |  | 0.063
|  | SSA - Bridson ph 2 acquisitions | 0.08 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.011429 | 0.011429 | 0.011429 | 0.011429 | 0.011429 | 0.011429 | 0.011429 | 0.022857 | [5 empty] | 0.08 |  | 0.08 | [13 empty] | 0.08 |  |  | 0.08
|  | SSA - Nelson st acquisitions | 0.1 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.014286 | 0.014286 | 0.014286 | 0.014286 | 0.014286 | 0.014286 | 0.014286 | 0.028571 | [5 empty] | 0.1 |  | 0.1 | [13 empty] | 0.1 |  |  | 0.1
|  | SSA-Security /Disconnections | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | [16 empty] | 0
| H01804 | SSA-Demolition / Site Treatment | 0.026 |  |  | 0.023 | 0.018 | 0 | 0 | 0 | 0 | 0.0011429 | 0.0011429 | 0.0011429 | 0.0011429 | 0.0011429 | 0.0011429 | 0.0011429 | 0.020286 | [5 empty] | 0.026 |  | 0.026 | [13 empty] | 0.026 |  |  | 0.026
|  | SHO-Eccles New Rd relocation | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | [16 empty] | 0
| H00813 | HI-Eccles New Rd facelift (dsd) | 0.098 |  |  | 0.096 | 0.095 | 0 | 0 | 0 | 0 | 0.00042857 | 0.00042857 | 0.00042857 | 0.00042857 | 0.00042857 | 0.00042857 | 0.00042857 | 0.095857 |  |  |  |  | 0.041 | 0.057 |  | 0.098 | [13 empty] | 0.057 |  |  | 0.057
|  | HI-Grants | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.0042857 | 0.0042857 | 0.0042857 | 0.0042857 | 0.0042857 | 0.0042857 | 0.0042857 | 0.0085714 | [5 empty] | 0 |  | 0 | [16 empty] | 0
|  | Pendleton-SSA-Sutton House Demolition | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | [16 empty] | 0
|  | Pendleton-SSA-Bethany Worship Mission | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | [16 empty] | 0
|  | Pendleton-SSA Masterplanning | 0.1 | [21 empty] | 0.1 |  | 0.1 |  | 0.1 | [14 empty] | 0.1
|  | EP Street Lighting | 0.004 |  |  | 0.004 | [17 empty] | 0.004 | 0 |  | 0.004
|  | Pendleton-SSA-Acq-Kingsley Court | 0.002 |  |  | 0.002 | 0.002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.002 | [5 empty] | 0.002 |  | 0.002 | [13 empty] | 0.002 |  |  | 0.002
| summary | ORDSALL | 0.541 |  |  | 0.041 | 0.007 | 0 | 0 | 0 | 0 | 0.071429 | 0.071429 | 0.071429 | 0.071429 | 0.071429 | 0.071429 | 0.071429 | 0.14986 | 0 | 0 | 0 | 0 | 0 | 0.541 | 0 | 0.541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.541 | 0 | 0 | 0.541
|  | SSA - Knowsley Green Acquisitions/demlition | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | [16 empty] | 0
|  | SSA - Legendary properties | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | [16 empty] | 0
|  | Demolition / Site Treatment-( H booth) need forecast | 0.041 |  |  | 0.041 | 0.007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.007 | [5 empty] | 0.041 |  | 0.041 | [13 empty] | 0.041 |  |  | 0.041
|  | SD-Views -Gap Funding | 0.5 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.071429 | 0.071429 | 0.071429 | 0.071429 | 0.071429 | 0.071429 | 0.071429 | 0.14286 | [5 empty] | 0.5 |  | 0.5 | [13 empty] | 0.5 |  |  | 0.5
| summary | NON AREA BASED | 1.302 |  |  | 0.016 | 0.014 | 0 | 0 | 0 | 0 | 0.28029 | 0.28029 | 0.28029 | 0.28029 | 0.28029 | 0.28029 | 0.28029 | 0.57457 | 0 | 0 | 0 | 0 | 0 | 1.302 | 0 | 1.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.059 | 0 | 0 | 0 | 1.243 | 0 | 0 | 1.302
|  | SSA-Site investigation | 0.179 |  |  | 0.005 | 0.005 | 0 | 0 | 0 | 0 | 0.020714 | 0.020714 | 0.020714 | 0.020714 | 0.020714 | 0.020714 | 0.020714 | 0.046429 | [5 empty] | 0.179 |  | 0.179 | [13 empty] | 0.179 |  |  | 0.179
|  | SSA-Site investigation / Contamination | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.0041429 | 0.0041429 | 0.0041429 | 0.0041429 | 0.0041429 | 0.0041429 | 0.0041429 | 0.0082857 | [5 empty] | 0 |  | 0 | [16 empty] | 0
|  | HI - enforcement | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.0064286 | 0.0064286 | 0.0064286 | 0.0064286 | 0.0064286 | 0.0064286 | 0.0064286 | 0.012857 | [5 empty] | 0 |  | 0 | [16 empty] | 0
|  | HI-Energy Efficiency | 0.125 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.017857 | 0.017857 | 0.017857 | 0.017857 | 0.017857 | 0.017857 | 0.017857 | 0.035714 | [5 empty] | 0.125 |  | 0.125 | [13 empty] | 0.125 |  |  | 0.125
|  | HI-Residential Property Security | 0.203 |  |  | 0.009 | 0.007 | 0 | 0 | 0 | 0 | 0.028 | 0.028 | 0.028 | 0.028 | 0.028 | 0.028 | 0.028 | 0.063 | [5 empty] | 0.203 |  | 0.203 | [13 empty] | 0.203 |  |  | 0.203
|  | SN-Neighbourhood Master Plan | 0.209 |  |  | 0.002 | 0.002 | 0 | 0 | 0 | 0 | 0.043857 | 0.043857 | 0.043857 | 0.043857 | 0.043857 | 0.043857 | 0.043857 | 0.089714 | [5 empty] | 0.209 |  | 0.209 | [9 empty] | 0.059 |  |  |  | 0.15 |  |  | 0.209
|  | SN-Wardens | 0.01 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0028571 | [5 empty] | 0.01 |  | 0.01 | [13 empty] | 0.01 |  |  | 0.01
|  | SN-Neighbourhood Maintenance | 0.036 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.0051429 | 0.0051429 | 0.0051429 | 0.0051429 | 0.0051429 | 0.0051429 | 0.0051429 | 0.010286 | [5 empty] | 0.036 |  | 0.036 | [13 empty] | 0.036 |  |  | 0.036
|  | SN-Streetscape/Env Improvements | 0.54 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.10986 | 0.10986 | 0.10986 | 0.10986 | 0.10986 | 0.10986 | 0.10986 | 0.21971 | [5 empty] | 0.54 |  | 0.54 | [13 empty] | 0.54 |  |  | 0.54
|  | SN-Central Salford Design Competition | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.042857 | 0.042857 | 0.042857 | 0.042857 | 0.042857 | 0.042857 | 0.042857 | 0.085714 | [5 empty] | 0 |  | 0 | [16 empty] | 0
|  | SN-Dundee Project |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | [16 empty] | 0
| summary | OUTER AREA / CITYWIDE | 3.136 |  |  | 0.993 | 0.659 | 0 | 0 | 0 | 0 | 0.37514 | 0.37514 | 0.37514 | 0.37514 | 0.37514 | 0.37514 | 0.37514 | 1.4093 | 0 | 0 | 0 | 0 | 2.406 | 0.73 | 0 | 3.136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.73
| H00001-10 | D.F.G.'s | 1.33 |  |  | 0.78 | 0.445 | 0 | 0 | 0 | 0 | 0.12643 | 0.12643 | 0.12643 | 0.12643 | 0.12643 | 0.12643 | 0.12643 | 0.69786 |  |  |  |  | 0.6 | 0.73 |  | 1.33 | [7 empty] | 0.73 | [8 empty] | 0.73
| H01201 | B.R.I | 0.25 |  |  | 0.055 | 0.031 | 0 | 0 | 0 | 0 | 0.031286 | 0.031286 | 0.031286 | 0.031286 | 0.031286 | 0.031286 | 0.031286 | 0.093571 |  |  |  |  | 0.25 | 0 |  | 0.25 | [16 empty] | 0
| H00166-170 | Repairs with DFG's | 0.15 |  |  | 0.088 | 0.06 | 0 | 0 | 0 | 0 | 0.0081429 | 0.0081429 | 0.0081429 | 0.0081429 | 0.0081429 | 0.0081429 | 0.0081429 | 0.076286 |  |  |  |  | 0.15 | 0 |  | 0.15 | [16 empty] | 0
| H00302-310 | H.I.A's | 0.5 |  |  | 0.195 | 0.172 | 0 | 0 | 0 | 0 | 0.046857 | 0.046857 | 0.046857 | 0.046857 | 0.046857 | 0.046857 | 0.046857 | 0.26571 |  |  |  |  | 0.5 | 0 |  | 0.5 | [16 empty] | 0
|  | Handyperson scheme | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.035714 | 0.035714 | 0.035714 | 0.035714 | 0.035714 | 0.035714 | 0.035714 | 0.071429 | [5 empty] | 0 |  | 0 | [16 empty] | 0
|  | Enforcement | 0.2 |  |  | 0.002 | 0 | 0 | 0 | 0 | 0 | 0.028571 | 0.028571 | 0.028571 | 0.028571 | 0.028571 | 0.028571 | 0.028571 | 0.057143 |  |  |  |  | 0.2 | 0 |  | 0.2 | [16 empty] | 0
|  | Landlord Accreditation | 0.14 | [20 empty] | 0.14 | 0 |  | 0.14
|  | Solar Electic Plan | 0.006 | [20 empty] | 0.006 | 0 |  | 0.006
|  | Grants-Little Hulton | 0.016 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.0022857 | 0.0022857 | 0.0022857 | 0.0022857 | 0.0022857 | 0.0022857 | 0.0022857 | 0.0045714 |  |  |  |  | 0.016 | 0 |  | 0.016 | [16 empty] | 0
| H00221 | Empty Properties Citywide (repayment of grant) | -0.065 |  |  | -0.065 | -0.037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.037 |  |  |  |  | -0.065 | 0 |  | -0.065 | [16 empty] | 0
| H00265 | Grants-HMO's (repayment of grant) | -0.083 |  |  | -0.083 | -0.033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.033 |  |  |  |  | -0.083 | 0 |  | -0.083 | [16 empty] | 0
|  | Group Repair-Little Hulton(dsd) | 0.01 |  |  | 0.004 | 0.004 | 0 | 0 | 0 | 0 | 0.00085714 | 0.00085714 | 0.00085714 | 0.00085714 | 0.00085714 | 0.00085714 | 0.00085714 | 0.0057143 |  |  |  |  | 0.01 | 0 |  | 0.01 | [16 empty] | 0
|  | Group Repair-Legh St / George St(dsd) | 0.002 |  |  | 0.002 | 0.002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.002 |  |  |  |  | 0.002 | 0 |  | 0.002 | [16 empty] | 0
| H00407 | Group Repair-Oxford St(dsd) | 0.013 |  |  | 0.013 | 0.013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.013 |  |  |  |  | 0.013 | 0 |  | 0.013 | [16 empty] | 0
|  | Group Repair-Police/Cromwell(dsd) | 0.001 |  |  | 0.001 | 0.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.001 |  |  |  |  | 0.001 | 0 |  | 0.001 | [16 empty] | 0
| H00581 | Clearance-Little Hulton | 0.001 |  |  | 0.001 | 0.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.001 |  |  |  |  | 0.001 | 0 |  | 0.001 | [16 empty] | 0
|  | capsals to be reallocated | 0.665 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.095 | 0.095 | 0.095 | 0.095 | 0.095 | 0.095 | 0.095 | 0.19 |  |  |  |  | 0.665 | 0 |  | 0.665 | [16 empty] | 0 | .300 broughton meadow road
| summary | Underprogramming | 1.566 |  |  | 0 | [12 empty] | 0 |  |  |  |  | 0.211 | 1.055 | 0.3 | 1.566 | [10 empty] | 0.146 |  | 0.006 | 0.903 |  |  | 1.055
| 18.497 | PRIVATE SECTOR HOUSING -TOTAL | 28.982 |  |  | 7.592 | 5.586 | 0 | 0 | 0 | 0 | 3.3854 | 3.3854 | 3.3854 | 3.3854 | 3.3866 | 3.3866 | 3.3866 | 12.3509 | 1.112 | 0 | 0 | 0 | 5.868 | 21.702 | 0.3 | 28.982 | 0 | 4.869 | 0 | 0 | 0 | 0 | 0 | 0.73 | 1.602 | 0.078 | 1.3 | 0 | 0.115 | 13.008 | 0 | 0 | 21.702
PUBLIC SECTOR HOUSING
Page 2 | summary | 2004/5 NEW STARTS | 13.204 |  |  | 1.406 | 0.178 | 0 | 0 | 0 | 0 | 2.0471 | 2.0471 | 2.0471 | 2.0471 | 2.0471 | 2.0471 | 2.0471 | 4.2723 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Structural-spruce | 0.495 |  |  | 0.011 | 0.011 | 0 | 0 | 0 | 0 | 0.069143 | 0.069143 | 0.069143 | 0.069143 | 0.069143 | 0.069143 | 0.069143 | 0.14929
|  | Lifts-newbank / riverbank | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sheltered homes -extra care work | 0.3 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.096857 | 0.096857 | 0.096857 | 0.096857 | 0.096857 | 0.096857 | 0.096857 | 0.19371
|  | Area office disabled adaptations | 0.188 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.026857 | 0.026857 | 0.026857 | 0.026857 | 0.026857 | 0.026857 | 0.026857 | 0.053714
|  | Multi storey satellite tv | 0.335 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.046 | 0.046 | 0.046 | 0.046 | 0.046 | 0.046 | 0.046 | 0.092
|  | Refurb of acquireds | 0.044 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.030714 | 0.030714 | 0.030714 | 0.030714 | 0.030714 | 0.030714 | 0.030714 | 0.061429
|  | Structural repairs-ad hoc | 0.107 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.015286 | 0.015286 | 0.015286 | 0.015286 | 0.015286 | 0.015286 | 0.015286 | 0.030571
|  | Security | 0.039 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.0077143 | 0.0077143 | 0.0077143 | 0.0077143 | 0.0077143 | 0.0077143 | 0.0077143 | 0.015429
|  | Turnpike office alterations | 0.011 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0031429
|  | Right to Buy reacquisitions | 0.026 |  |  | 0.026 | 0.009 | 0 | 0 | 0 | 0 | 0.0024286 | 0.0024286 | 0.0024286 | 0.0024286 | 0.0024286 | 0.0024286 | 0.0024286
|  | PRE PARTNERING |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Wardley partial rewire | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.0078571 | 0.0078571 | 0.0078571 | 0.0078571 | 0.0078571 | 0.0078571 | 0.0078571 | 0.015714
|  | Temple drive electrical upgrade | 0.11 |  |  | 0.02 | 0 | 0 | 0 | 0 | 0 | 0.0084286 | 0.0084286 | 0.0084286 | 0.0084286 | 0.0084286 | 0.0084286 | 0.0084286 | 0.016857
|  | Dudley rd heating | 0.215 |  |  | 0.018 | 0 | 0 | 0 | 0 | 0 | 0.061143 | 0.061143 | 0.061143 | 0.061143 | 0.061143 | 0.061143 | 0.061143 | 0.12229
|  | Meadows heating | 0.144 |  |  | 0.131 | 0 | 0 | 0 | 0 | 0 | 0.023 | 0.023 | 0.023 | 0.023 | 0.023 | 0.023 | 0.023 | 0.046
|  | Baines ave roofing | 0.213 |  |  | 0.213 | 0.158 | 0 | 0 | 0 | 0 | 0.0058571 | 0.0058571 | 0.0058571 | 0.0058571 | 0.0058571 | 0.0058571 | 0.0058571 | 0.16971
|  | Crossfields roofing | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Warren st roofing | 0.042 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.0038571 | 0.0038571 | 0.0038571 | 0.0038571 | 0.0038571 | 0.0038571 | 0.0038571 | 0.0077143
|  | Mitchell st rewire/kitchens | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Peel green rd rewire,kitchen/bath | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | City wide surveys | 0.041 |  |  | 0.041
PARTNERING
|  | Worsley package 1 | 0.524 |  | 2005-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0.067571 | 0.067571 | 0.067571 | 0.067571 | 0.067571 | 0.067571 | 0.067571 | 0.13514
|  | Eccles package 1 | 0.695 |  | 2005-04-01 | 0.133 | 0 | 0 | 0 | 0 | 0 | 0.10186 | 0.10186 | 0.10186 | 0.10186 | 0.10186 | 0.10186 | 0.10186 | 0.20371
|  | Eccles package 2 | 0.591 |  | 2005-01-01 | 0.099 | 0 | 0 | 0 | 0 | 0 | 0.099286 | 0.099286 | 0.099286 | 0.099286 | 0.099286 | 0.099286 | 0.099286 | 0.19857
|  | Eccles package 3 | 1.096 |  | 2005-02-01 | 0.088 | 0 | 0 | 0 | 0 | 0 | 0.116 | 0.116 | 0.116 | 0.116 | 0.116 | 0.116 | 0.116 | 0.232 | [24 empty] | 0
|  | Eccles package 4 | 0.551 |  | 2005-02-01 | 0.162 | 0 | 0 | 0 | 0 | 0 | 0.10443 | 0.10443 | 0.10443 | 0.10443 | 0.10443 | 0.10443 | 0.10443 | 0.20886 | [24 empty] | 0
|  | Swinton package 1 | 2.14 |  | 2005-01-01 | 0.165 | 0 | 0 | 0 | 0 | 0 | 0.32186 | 0.32186 | 0.32186 | 0.32186 | 0.32186 | 0.32186 | 0.32186 | 0.64371
|  | Swinton package 2 | 0.378 |  | 2005-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0.12071 | 0.12071 | 0.12071 | 0.12071 | 0.12071 | 0.12071 | 0.12071 | 0.24143
|  | Swinton package 3 | 0.854 |  | 2005-02-01 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0.12414 | 0.12414 | 0.12414 | 0.12414 | 0.12414 | 0.12414 | 0.12414 | 0.24829 | [24 empty] | 0
|  | Salford south package 1 | 1.159 |  | 2005-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0.20614 | 0.20614 | 0.20614 | 0.20614 | 0.20614 | 0.20614 | 0.20614 | 0.41229 | [24 empty] | 0
|  | Salford south package 2 | 0.476 |  | 2005-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0.088857 | 0.088857 | 0.088857 | 0.088857 | 0.088857 | 0.088857 | 0.088857 | 0.17771 | [24 empty] | 0
|  | Salford south package 3 | 0.517 |  | 2005-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0.073714 | 0.073714 | 0.073714 | 0.073714 | 0.073714 | 0.073714 | 0.073714 | 0.14743 | [24 empty] | 0
|  | Salford north package 1 | 0.914 |  | 2005-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0.11529 | 0.11529 | 0.11529 | 0.11529 | 0.11529 | 0.11529 | 0.11529 | 0.23057 | [24 empty] | 0
|  | Ppr package 1 | 0.999 |  |  | 0.179 | 0 | 0 | 0 | 0 | 0 | 0.10057 | 0.10057 | 0.10057 | 0.10057 | 0.10057 | 0.10057 | 0.10057 | 0.20114 | [24 empty] | 0
Page 3 | summary | 2004/5 INSULATION SCHEMES | 1.019 |  |  | 0.139 | 0 | 0 | 0 | 0 | 0 | 0.20186 | 0.20186 | 0.20186 | 0.20186 | 0.20186 | 0.20186 | 0.20186 | 0.40371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Package 1 | 0.017 |  | 2004-07-01 | 0.009 | 0 | 0 | 0 | 0 | 0 | 0.007 | 0.007 | 0.007 | 0.007 | 0.007 | 0.007 | 0.007 | 0.014 | [24 empty] | 0
|  | Package 2 | 0.05 |  | 2004-07-01 | 0.022 | 0 | 0 | 0 | 0 | 0 | 0.0081429 | 0.0081429 | 0.0081429 | 0.0081429 | 0.0081429 | 0.0081429 | 0.0081429 | 0.016286
|  | Package 3 | 0.132 |  | 2004-09-01 | 0.036 | 0 | 0 | 0 | 0 | 0 | 0.022571 | 0.022571 | 0.022571 | 0.022571 | 0.022571 | 0.022571 | 0.022571 | 0.045143
|  | Package 4 | 0.105 |  | 2004-09-01 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0.012143 | 0.012143 | 0.012143 | 0.012143 | 0.012143 | 0.012143 | 0.012143 | 0.024286
|  | Package 5 | 0.017 |  | 2004-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0.0034286 | 0.0034286 | 0.0034286 | 0.0034286 | 0.0034286 | 0.0034286 | 0.0034286 | 0.0068571
|  | Package 6 | 0.007 |  | 2004-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0031429
|  | Package 7 | 0.021 |  | 2004-09-01 | 0.006 | 0 | 0 | 0 | 0 | 0 | 0.0055714 | 0.0055714 | 0.0055714 | 0.0055714 | 0.0055714 | 0.0055714 | 0.0055714 | 0.011143
|  | Package 8 | 0.055 |  | 2004-11-01 | 0.003 | 0 | 0 | 0 | 0 | 0 | 0.016714 | 0.016714 | 0.016714 | 0.016714 | 0.016714 | 0.016714 | 0.016714 | 0.033429
|  | Package 9 | 0.031 |  | 2004-11-01 |  | 0 | 0 | 0 | 0 | 0 | 0.0075714 | 0.0075714 | 0.0075714 | 0.0075714 | 0.0075714 | 0.0075714 | 0.0075714 | 0.015143
|  | Package 10 | 0.031 |  | 2004-12-01 |  | 0 | 0 | 0 | 0 | 0 | 0.012143 | 0.012143 | 0.012143 | 0.012143 | 0.012143 | 0.012143 | 0.012143 | 0.024286
|  | Package 11 | 0.069 |  | 2004-12-01 |  | 0 | 0 | 0 | 0 | 0 | 0.0098571 | 0.0098571 | 0.0098571 | 0.0098571 | 0.0098571 | 0.0098571 | 0.0098571 | 0.019714
|  | Package 12 | 0.054 |  | 2005-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0.0077143 | 0.0077143 | 0.0077143 | 0.0077143 | 0.0077143 | 0.0077143 | 0.0077143 | 0.015429
|  | Package 13 | 0.065 |  | 2005-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0.0092857 | 0.0092857 | 0.0092857 | 0.0092857 | 0.0092857 | 0.0092857 | 0.0092857 | 0.018571
|  | Package 14 | 0.07 |  | 2005-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Package 15 | 0.096 |  | 2005-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Package 16 | 0.06 |  | 2005-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Package 17 |  |  | 2005-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Package 18 |  |  | 2005-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Package 19 | 0 |  | 2004-11-01 |  | 0 | 0 | 0 | 0 | 0 | 0.031429 | 0.031429 | 0.031429 | 0.031429 | 0.031429 | 0.031429 | 0.031429 | 0.062857
|  | Package 20 | 0.062 |  | 2004-09-01 | 0.036 | 0 | 0 | 0 | 0 | 0 | 0.021571 | 0.021571 | 0.021571 | 0.021571 | 0.021571 | 0.021571 | 0.021571 | 0.043143
|  | Package 21 | 0.07 |  | 2005-12-01 |  | 0 | 0 | 0 | 0 | 0 | 0.025143 | 0.025143 | 0.025143 | 0.025143 | 0.025143 | 0.025143 | 0.025143 | 0.050286
|  | Package 22 |  |  | 2005-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Package 23 |  |  | 2004-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Citywide insulation | 0.007 |  |  | 0.007 | 0.006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Page 4 | summary | 2003/4 NEW STARTS | 1.476 |  |  | 1.236 | 1.021 | 0 | 0 | 0 | 0 | 0.065 | 0.065 | 0.065 | 0.065 | 0.065 | 0.065 | 0.065 | 1.148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| h50710 | Thorn Court Partnering scheme | 0.555 |  |  | 0.555 | 0.455 | 0 | 0 | 0 | 0 | 0.0065714 | 0.0065714 | 0.0065714 | 0.0065714 | 0.0065714 | 0.0065714 | 0.0065714 | 0.46814
| h50868 | Ash drive | 0.004 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.00057143 | 0.00057143 | 0.00057143 | 0.00057143 | 0.00057143 | 0.00057143 | 0.00057143 | 0.0011429
| h50641 d |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| h50641 f | Jackson st | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| h50812 | Racecourse ph 1/2 | 0.032 |  |  | 0.031 | 0.031 | 0 | 0 | 0 | 0 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0015714 | 0.034143
| h50954 | Fairhope | 0.01 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0028571
| h51107 | Higher irlam ph 4 | 0.001 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00028571
| h50869 | Pendleway | 0.123 |  |  | 0.112 | 0 | 0 | 0 | 0 | 0 | 0.019143 | 0.019143 | 0.019143 | 0.019143 | 0.019143 | 0.019143 | 0.019143 | 0.038286
| h50711 | Kinder | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.00085714 | 0.00085714 | 0.00085714 | 0.00085714 | 0.00085714 | 0.00085714 | 0.00085714 | 0.0017143
| h50957 | Hereford rd/salisbury rd | 0.001 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00028571
| h50908 | St georges ct/peel pk cres | 0.003 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.00042857 | 0.00042857 | 0.00042857 | 0.00042857 | 0.00042857 | 0.00042857 | 0.00042857 | 0.00085714
| h50955 | De traffords | 0.001 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00028571
| h50652 | Structural repairs | 0.006 |  |  | 0.005 | 0.005 | 0 | 0 | 0 | 0 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.0052857
| h50653 | Concrete floors | 0.007 |  |  | 0.006 | 0.006 | 0 | 0 | 0 | 0 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.0062857
| h51106 | Admiralty / LHDC | 0.187 |  |  | 0.13 | 0.13 | 0 | 0 | 0 | 0 | 0.0081429 | 0.0081429 | 0.0081429 | 0.0081429 | 0.0081429 | 0.0081429 | 0.0081429 | 0.14629
| h50956 | Peel green | 0.152 |  |  | 0.09 | 0.09 | 0 | 0 | 0 | 0 | 0.0088571 | 0.0088571 | 0.0088571 | 0.0088571 | 0.0088571 | 0.0088571 | 0.0088571 | 0.10771
| h50910 | Eccles/l hulton | 0.301 |  |  | 0.261 | 0.261 | 0 | 0 | 0 | 0 | 0.0057143 | 0.0057143 | 0.0057143 | 0.0057143 | 0.0057143 | 0.0057143 | 0.0057143 | 0.27243
| h50867 | Green avenue ,swinton | 0.031 |  |  | 0.014 | 0.014 | 0 | 0 | 0 | 0 | 0.0024286 | 0.0024286 | 0.0024286 | 0.0024286 | 0.0024286 | 0.0024286 | 0.0024286 | 0.018857
|  | Ninian Gardens |  |  |  |  | 0.003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | solid fuel heating | 0.001
| h50814 | Greyfriars court | 0.008 |  |  | 0.005 | 0 | 0 | 0 | 0 | 0 | 0.0011429 | 0.0011429 | 0.0011429 | 0.0011429 | 0.0011429 | 0.0011429 | 0.0011429 | 0.0022857
| h50815 | Black/whitefriars | 0.004 |  |  | 0.004 | 0.004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.004
| h50712 | Apple/pear/peach | 0.008 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.0047143 | 0.0047143 | 0.0047143 | 0.0047143 | 0.0047143 | 0.0047143 | 0.0047143 | 0.0094286
| h50709 | Lombardy Court | 0.001 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00028571
| h51105 | Elderly adaptations | 0.01 |  |  | 0.003 | 0.002 | 0 | 0 | 0 | 0 | 0.0011429 | 0.0011429 | 0.0011429 | 0.0011429 | 0.0011429 | 0.0011429 | 0.0011429 | 0.0042857
| h50813 | Salford north office improvements | 0.03 |  |  | 0.02 | 0.02 | 0 | 0 | 0 | 0 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.022857
Page 5 | summary | ROLLING PROGRAMMES | 2.419 |  |  | 1.193 | 0.785 | 0 | 0 | 0 | 0 | 0.22671 | 0.22671 | 0.22671 | 0.22671 | 0.22671 | 0.22671 | 0.22671 | 1.2384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50001 | 2004/5 D.F.G.s | 1.25 |  |  | 0.777 | 0.506 | 0 | 0 | 0 | 0 | 0.10629 | 0.10629 | 0.10629 | 0.10629 | 0.10629 | 0.10629 | 0.10629 | 0.71857
| H50001A | D.F.G.s in future years | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50643A | Capitalised salaries (dpu/ct) | 0.11 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.015714 | 0.015714 | 0.015714 | 0.015714 | 0.015714 | 0.015714 | 0.015714 | 0.031429
| H50643 | Advance fees | 0.04 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.0057143 | 0.0057143 | 0.0057143 | 0.0057143 | 0.0057143 | 0.0057143 | 0.0057143 | 0.011429
| H54001 | 2004/5 burglary reduction initiative | 0.5 |  |  | 0.102 | 0 | 0 | 0 | 0 | 0 | 0.071429 | 0.071429 | 0.071429 | 0.071429 | 0.071429 | 0.071429 | 0.071429 | 0.14286
|  | Peel ph 5 environment | 0.045 |  |  | 0.012
|  | 2002/3 NEW STARTS (DSD SCHEMES) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50250 | Peel ph 4 environment | 0.237 |  |  | 0.185 | 0.177 | 0 | 0 | 0 | 0 | 0.0085714 | 0.0085714 | 0.0085714 | 0.0085714 | 0.0085714 | 0.0085714 | 0.0085714 | 0.19414
| H50270 | Armitage ph 3 environment | 0.023 |  |  | 0.013 | 0.011 | 0 | 0 | 0 | 0 | 0.0018571 | 0.0018571 | 0.0018571 | 0.0018571 | 0.0018571 | 0.0018571 | 0.0018571 | 0.014714
| H50249 | Mount skip ph 2 environment | 0.042 |  |  | 0.042 | 0.041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.041
| H51202 | Rockley gardens | 0.007 |  |  | 0.001 | 0.001 | 0 | 0 | 0 | 0 | 0.00085714 | 0.00085714 | 0.00085714 | 0.00085714 | 0.00085714 | 0.00085714 | 0.00085714 | 0.0027143
|  | 2001/2 NEW STARTS (DSD SCHEMES) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50485 | Floral court car park | 0.058 |  |  | 0.053 | 0.047 | 0 | 0 | 0 | 0 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0015714 | 0.050143
| H50625 | Birch rd / old clough env't | 0.005 |  |  | 0.005 | 0.002 | 0 | 0 | 0 | 0 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.0022857
| H50610 | Admiralty environment | 0.011 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0031429
| H50519 | Philip st phase 2 security | 0.001 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00028571
| H50486 | Greengate car parking | 0.03 |  |  | 0.001 | 0 | 0 | 0 | 0 | 0 | 0.0042857 | 0.0042857 | 0.0042857 | 0.0042857 | 0.0042857 | 0.0042857 | 0.0042857 | 0.0085714
| H50297 | Jennings / tamworth / wesley | 0.006 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.00085714 | 0.00085714 | 0.00085714 | 0.00085714 | 0.00085714 | 0.00085714 | 0.00085714 | 0.0017143
| H50565 | Tootal drive ph 3 environment | 0.015 |  |  | 0.001 | 0.001 | 0 | 0 | 0 | 0 | 0.002 | 0.002 | 0.002 | 0.002 | 0.002 | 0.002 | 0.002 | 0.005
| H50593 | Castleway ph 1 environment | -0.003 |  |  | -0.003 | -0.003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.003
| H50595 | Valley ph 2 environment | 0.012 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.0017143 | 0.0017143 | 0.0017143 | 0.0017143 | 0.0017143 | 0.0017143 | 0.0017143 | 0.0034286
| H50269 | Armitage ph 2 environment | 0.014 |  |  | 0.001 | 0.001 | 0 | 0 | 0 | 0 | 0.0018571 | 0.0018571 | 0.0018571 | 0.0018571 | 0.0018571 | 0.0018571 | 0.0018571 | 0.0047143
| H50246 | Peel ph 3 environment | 0.012 |  |  | 0.003 | 0.001 | 0 | 0 | 0 | 0 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0041429
| H50804 | Melbourne st environment | 0.004 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.00057143 | 0.00057143 | 0.00057143 | 0.00057143 | 0.00057143 | 0.00057143 | 0.00057143 | 0.0011429
Page 6 | summary | NEW DEAL KERSAL/CHARLESTOWN | 1.588 |  |  | 0.73 | 0.528 | 0 | 0 | 0 | 0 | 0.165 | 0.165 | 0.165 | 0.165 | 0.165 | 0.165 | 0.165 | 0.858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2002/3 NEW STARTS |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H54101 | District Heating-London St / Lissadel St | 0.005 |  |  | 0.005 | 0.005 | 0 | 0 | 0 | 0 | -0.00028571 | -0.00028571 | -0.00028571 | -0.00028571 | -0.00028571 | -0.00028571 | -0.00028571 | 0.0044286
|  | 2003/4 NEW STARTS |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Whit lane / littleton rd |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| h50550 | Littleton rd water pipes | 0.078 |  |  | 0.078 | 0.077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.077
| H54104 | Littleton rd internals | 0.226 |  |  | 0.205 | 0.205 | 0 | 0 | 0 | 0 | 0.003 | 0.003 | 0.003 | 0.003 | 0.003 | 0.003 | 0.003 | 0.211
| H54105 | Whit lane internals | 1.24 |  |  | 0.435 | 0.239 | 0 | 0 | 0 | 0 | 0.143 | 0.143 | 0.143 | 0.143 | 0.143 | 0.143 | 0.143 | 0.525
| H54106 | Littleton rd externals | 0.02 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.019286 | 0.019286 | 0.019286 | 0.019286 | 0.019286 | 0.019286 | 0.019286 | 0.038571
| H54107 | Whit lane externals | 0.019 |  |  | 0.007 | 0.002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.002
Page 7 | summary | S.R.B. 2 | 1.373 |  |  | 0.925 | 0.775 | 0 | 0 | 0 | 0 | 0.073143 | 0.073143 | 0.073143 | 0.073143 | 0.073143 | 0.073143 | 0.073143 | 0.92129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50103 | Lower broughton env'l ph 1 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50122 | Lower broughton env'l ph 2 | 0.002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.00028571 | 0.00028571 | 0.00028571 | 0.00028571 | 0.00028571 | 0.00028571 | 0.00028571 | 0.00057143
| H50124 | Lower broughton env'l ph 3a/4a | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50123 | Lower broughton env'l ph 3 | -0.007 |  |  | -0.008 | -0.008 | 0 | 0 | 0 | 0 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | -0.0077143
| H50125 | Lower broughton env'l ph 4 | 0.013 |  |  | 0.001 | 0.001 | 0 | 0 | 0 | 0 | 0.0017143 | 0.0017143 | 0.0017143 | 0.0017143 | 0.0017143 | 0.0017143 | 0.0017143 | 0.0044286
| H50126 | Lower broughton temp. Treatm't ph 2 | 0.004 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.00057143 | 0.00057143 | 0.00057143 | 0.00057143 | 0.00057143 | 0.00057143 | 0.00057143 | 0.0011429
|  | SPIKE ISLAND |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50183 | Spike island-ptp ph 1 | 0.001 |  |  | 0.001 | 0.001 | 0 | 0 | 0 | 0 | 0.00071429 | 0.00071429 | 0.00071429 | 0.00071429 | 0.00071429 | 0.00071429 | 0.00071429 | 0.0024286
| H50185 | District heating ph 1/2 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50186 | Environment ph 1 | 0.007 |  |  | 0.001 | 0.001 | 0 | 0 | 0 | 0 | 0.0011429 | 0.0011429 | 0.0011429 | 0.0011429 | 0.0011429 | 0.0011429 | 0.0011429 | 0.0032857
| H50187 | Environment ph 2 | 0.012 |  |  | 0.002 | 0.001 | 0 | 0 | 0 | 0 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0041429
| H50188 | Environment ph 3 | 0.031 |  |  | 0.021 | 0 | 0 | 0 | 0 | 0 | 0.0044286 | 0.0044286 | 0.0044286 | 0.0044286 | 0.0044286 | 0.0044286 | 0.0044286 | 0.0088571
| H50189 | Environment ph 4 | 0.021 |  |  | 0.009 | 0.003 | 0 | 0 | 0 | 0 | 0.003 | 0.003 | 0.003 | 0.003 | 0.003 | 0.003 | 0.003 | 0.009
| H50190 | Environment ph 5 | 0.579 |  |  | 0.458 | 0.368 | 0 | 0 | 0 | 0 | 0.027143 | 0.027143 | 0.027143 | 0.027143 | 0.027143 | 0.027143 | 0.027143 | 0.42229
| H50191 | Environment ph 6 | 0.198 |  |  | 0.154 | 0.141 | 0 | 0 | 0 | 0 | 0.0095714 | 0.0095714 | 0.0095714 | 0.0095714 | 0.0095714 | 0.0095714 | 0.0095714 | 0.16014
| H50192 | Environment ph 7 | 0.512 |  |  | 0.286 | 0.267 | 0 | 0 | 0 | 0 | 0.022857 | 0.022857 | 0.022857 | 0.022857 | 0.022857 | 0.022857 | 0.022857 | 0.31271
Page 8 | summary | PPR PROGRAMME | 1.404 |  |  | 0.528 | 0.441 | 0 | 0 | 0 | 0 | 0.13671 | 0.13671 | 0.13671 | 0.13671 | 0.13671 | 0.13671 | 0.13671 | 0.71443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H53001 | Commitments | 0.034 |  |  | 0.017 | 0.017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.017
| H53178 | Alder park | 0.015 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.0021429 | 0.0021429 | 0.0021429 | 0.0021429 | 0.0021429 | 0.0021429 | 0.0021429 | 0.0042857
| H53179 | FALCON CRES | 0.002 |  |  | 0.002 | 0.002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.002
| H53188 | Lancaster rd | 0.014 |  |  | 0.002 | 0.002 | 0 | 0 | 0 | 0 | 0.0017143 | 0.0017143 | 0.0017143 | 0.0017143 | 0.0017143 | 0.0017143 | 0.0017143 | 0.0054286
| H53189 | Brookhouse ph 1 | 0.026 |  |  | 0.001 | 0.001 | 0 | 0 | 0 | 0 | 0.0028571 | 0.0028571 | 0.0028571 | 0.0028571 | 0.0028571 | 0.0028571 | 0.0028571 | 0.0067143
| H53192 | Brookhouse ph 2 | 0.019 |  |  | 0.019 | 0.001 | 0 | 0 | 0 | 0 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.0012857
| H53193 | TOOTAL DR PH 1ACKWORTH RD/TEMPLE DR | 0.001 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00028571
| H53194 | Tootal dr ph 2 / victory rd | 0.015 |  |  | 0.002 | 0.002 | 0 | 0 | 0 | 0 | 0.0018571 | 0.0018571 | 0.0018571 | 0.0018571 | 0.0018571 | 0.0018571 | 0.0018571 | 0.0057143
| H53200 | Advance fees / surveys | 0.029 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.0055714 | 0.0055714 | 0.0055714 | 0.0055714 | 0.0055714 | 0.0055714 | 0.0055714 | 0.011143
| H53203 | Cloughfield | 0.004 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.00057143 | 0.00057143 | 0.00057143 | 0.00057143 | 0.00057143 | 0.00057143 | 0.00057143 | 0.0011429
| H53204 | Hospital road | 0.003 |  |  | 0.001 | 0.001 | 0 | 0 | 0 | 0 | 0.00028571 | 0.00028571 | 0.00028571 | 0.00028571 | 0.00028571 | 0.00028571 | 0.00028571 | 0.0015714
| H53205 | New islington | 0.02 |  |  | 0.011 | 0.011 | 0 | 0 | 0 | 0 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.013857
| H53206 | Mossfield rd | 0.001 |  |  | 0.001 | 0 | 0 | 0 | 0 | 0 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00028571
| H53208 | Wardley | 0.001 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.00057143 | 0.00057143 | 0.00057143 | 0.00057143 | 0.00057143 | 0.00057143 | 0.00057143 | 0.0011429
| H53209 | Brookhouse ph 3 | 0.012 |  |  | 0.002 | 0 | 0 | 0 | 0 | 0 | 0.0017143 | 0.0017143 | 0.0017143 | 0.0017143 | 0.0017143 | 0.0017143 | 0.0017143 | 0.0034286
| H53210 | Castleway | 0.156 |  |  | 0.001 | 0.001 | 0 | 0 | 0 | 0 | 0.022143 | 0.022143 | 0.022143 | 0.022143 | 0.022143 | 0.022143 | 0.022143 | 0.045286
| H53212 | Grosvenor ph 1 | 0.659 |  |  | 0.274 | 0.214 | 0 | 0 | 0 | 0 | 0.063857 | 0.063857 | 0.063857 | 0.063857 | 0.063857 | 0.063857 | 0.063857 | 0.34171
| H53214 | Lane end | 0.003 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0031429
| H53215 | Cawdor st | 0.034 |  |  | 0.033 | 0.031 | 0 | 0 | 0 | 0 | 0.00042857 | 0.00042857 | 0.00042857 | 0.00042857 | 0.00042857 | 0.00042857 | 0.00042857 | 0.031857
| H53216 | Brentwood | 0.017 |  |  | 0.008 | 0.008 | 0 | 0 | 0 | 0 | 0.0011429 | 0.0011429 | 0.0011429 | 0.0011429 | 0.0011429 | 0.0011429 | 0.0011429 | 0.010286
| H53217 | Duchy ph 1 | 0.012 |  |  | 0.002 | 0.001 | 0 | 0 | 0 | 0 | 0.003 | 0.003 | 0.003 | 0.003 | 0.003 | 0.003 | 0.003 | 0.007
| H53218 | Duchy ph 2 | 0.012 |  |  | 0.004 | 0.001 | 0 | 0 | 0 | 0 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0041429
| H53219 | Hill top ph 1 | 0.01 |  |  | 0.004 | 0.004 | 0 | 0 | 0 | 0 | 0.00085714 | 0.00085714 | 0.00085714 | 0.00085714 | 0.00085714 | 0.00085714 | 0.00085714 | 0.0057143
| H53220 | Hill top ph 2/3 | 0.305 |  |  | 0.144 | 0.144 | 0 | 0 | 0 | 0 | 0.023 | 0.023 | 0.023 | 0.023 | 0.023 | 0.023 | 0.023 | 0.19
Page 9 | summary | DEMOLITIONS | 0.841 |  |  | 0.343 | 0.311 | 0 | 0 | 0 | 0 | 0.075714 | 0.075714 | 0.075714 | 0.075714 | 0.075714 | 0.075714 | 0.075714 | 0.38043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Schemes funded from 2004/5 new start allocation |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| h52001 a | Available for new starts | 0.221 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.041 | 0.041 | 0.041 | 0.041 | 0.041 | 0.041 | 0.041
| h52009 | Hanover Court | 0.006 |  |  | 0.006 | 0.006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.006
| h52024 | Florence St | 0.027 |  |  | 0.027 | 0.027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.027
| h52018 | Kestrel Avenue | 0.03 |  |  | 0.03 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.03
| h52019 | Wheatersfield | 0.044 |  |  | 0.044 | 0.032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.032
| H52006 | Little Hulton Cottage Flats | 0.117 |  |  | 0.117 | 0.111 | 0 | 0 | 0 | 0 | -0.00028571 | -0.00028571 | -0.00028571 | -0.00028571 | -0.00028571 | -0.00028571 | -0.00028571 | 0.11043
| H52003 | Poets Corner | 0.006 |  |  | 0.006 | 0.006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.006
| h52008 | Ladywell Avenue | 0.003 |  |  | 0.003 | 0.003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.003
|  | Cedar Place | 0.005 |  |  | 0.005
|  | Aspinall Drive | 0.014
|  | SCHEMES FUNDED FROM PREVIOUS YEARS ALLOCATIONS |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| h52023 | Lime Court | 0.1 |  |  | 0.069 | 0.069 | 0 | 0 | 0 | 0 | 0.0044286 | 0.0044286 | 0.0044286 | 0.0044286 | 0.0044286 | 0.0044286 | 0.0044286 | 0.077857
| h52025 | Meadowside | 0.022 |  |  | 0.02 | 0.018 | 0 | 0 | 0 | 0 | 0.00057143 | 0.00057143 | 0.00057143 | 0.00057143 | 0.00057143 | 0.00057143 | 0.00057143 | 0.019143
| h52026 | Hulton Ave launderette | 0.015 |  |  | 0.006 | 0.006 | 0 | 0 | 0 | 0 | 0.0012857 | 0.0012857 | 0.0012857 | 0.0012857 | 0.0012857 | 0.0012857 | 0.0012857 | 0.0085714
| h52027 | Windsor Avenue | 0.027 |  |  | 0.002 | 0 | 0 | 0 | 0 | 0 | 0.0025714 | 0.0025714 | 0.0025714 | 0.0025714 | 0.0025714 | 0.0025714 | 0.0025714 | 0.0051429
| h52020 | Shakespeare Rd / Blantyre St | 0.054 |  |  | 0.002 | 0.001 | 0 | 0 | 0 | 0 | 0.0075714 | 0.0075714 | 0.0075714 | 0.0075714 | 0.0075714 | 0.0075714 | 0.0075714 | 0.016143
| H51002 | Birley Court | 0.066 |  |  | 0.005 | 0.002 | 0 | 0 | 0 | 0 | 0.0091429 | 0.0091429 | 0.0091429 | 0.0091429 | 0.0091429 | 0.0091429 | 0.0091429 | 0.020286
| H52010 | Duchy Bank | 0.053 |  |  | 0.001 | 0 | 0 | 0 | 0 | 0 | 0.005 | 0.005 | 0.005 | 0.005 | 0.005 | 0.005 | 0.005 | 0.01
| H51001 | Ruthin Court | 0.031 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.0044286 | 0.0044286 | 0.0044286 | 0.0044286 | 0.0044286 | 0.0044286 | 0.0044286 | 0.0088571
Page 10 | summary | RETENTIONS | 0.619 |  |  | 0.297 | 0.279 | 0 | 0 | 0 | 0 | 0.056571 | 0.056571 | 0.056571 | 0.056571 | 0.056571 | 0.056571 | 0.056571 | 0.39214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | OLD SCHEMES |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50624 | Energy eff.lead pipes | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50482 | High rise prog -canon green | 0.002 |  |  | 0.002 | 0.002 | 0 | 0 | 0 | 0 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.0022857
| H50504 | Beech st environment ph 1 | 0.004 |  |  | 0.004 | 0.003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.003
|  | 2000/1 NEW STARTS (DSD) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50562 | Tootal drive phase 2 | 0.002 |  |  | 0.002 | 0.001 | 0 | 0 | 0 | 0 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.0012857
| H50564 | Meadowgate | 0.002 |  |  | 0.002
| H50584 | Valley environment ph 1 | 0.019 |  |  | 0.019 | 0.018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.018
| H50585 | cliveley Environment ph 1 | 0.001 |  |  | 0.001
| H50295 | Goodiers drive highway works | 0.022 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.0031429 | 0.0031429 | 0.0031429 | 0.0031429 | 0.0031429 | 0.0031429 | 0.0031429 | 0.0062857
|  | 2001/2 NEW STARTS (HPMS) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50702 | Structural repairs-thorn court | 0.065 |  |  | 0.065 | 0.065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.065
| H50534 | Security-argosy/beech/mitch/scotch | 0.001 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00028571
| H50706 | Security-wrotham close | 0.022 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.0031429 | 0.0031429 | 0.0031429 | 0.0031429 | 0.0031429 | 0.0031429 | 0.0031429 | 0.0062857
|  | Security of Open spaces | 0.002 |  |  | 0.002
| H50705 | Security-albion / spruce | 0.002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.00057143 | 0.00057143 | 0.00057143 | 0.00057143 | 0.00057143 | 0.00057143 | 0.00057143 | 0.0011429
|  | 2002/3 NEW STARTS (HPMS-SERVICES) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50559 | Security-heraldic | 0.018 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.0025714 | 0.0025714 | 0.0025714 | 0.0025714 | 0.0025714 | 0.0025714 | 0.0025714 | 0.0051429
| H50857 | Heating/rewires-wyndham | 0.002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.00028571 | 0.00028571 | 0.00028571 | 0.00028571 | 0.00028571 | 0.00028571 | 0.00028571 | 0.00057143
| H50860 | Heating/rewires-deans court | 0.003 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.00042857 | 0.00042857 | 0.00042857 | 0.00042857 | 0.00042857 | 0.00042857 | 0.00042857 | 0.00085714
| H51104 | Gas heating-moss vale ph 1 | 0.03 |  |  | 0.027 | 0.027 | 0 | 0 | 0 | 0 | 0.0032857 | 0.0032857 | 0.0032857 | 0.0032857 | 0.0032857 | 0.0032857 | 0.0032857 | 0.033571
| H50864 | Gas heating-beehive | 0.003 |  |  | 0.003 | 0.003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.003
| H50572 | Gas heating-lancaster rd | 0.003 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.00042857 | 0.00042857 | 0.00042857 | 0.00042857 | 0.00042857 | 0.00042857 | 0.00042857 | 0.00085714
| H50810 | Gas heating-l broughton rd | 0.008 |  |  | 0.007 | 0.007 | 0 | 0 | 0 | 0 | 0.0062857 | 0.0062857 | 0.0062857 | 0.0062857 | 0.0062857 | 0.0062857 | 0.0062857 | 0.019571
| H50811 | Heating boiler-alex gardens | 0.001 |  |  | 0.001 | 0.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.001
| h50809 | Security-stoney knoll/gloverfield | 0.001 |  |  | 0.001 | 0.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.001
|  | Security-South King Street | 0.001 |  |  | 0.001
|  | 2002/3 NEW STARTS (HPMS-BUILDING) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50570 | Walkways-seedley terrace/ailsa | 0.001 |  |  | 0.001 | 0.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.001
| H50807 | Kitchens-l broughton ph 1/tootal ph 1 | 0.033 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.0047143 | 0.0047143 | 0.0047143 | 0.0047143 | 0.0047143 | 0.0047143 | 0.0047143 | 0.0094286
| H50620 | Internals-admiralty | 0.008 |  |  | 0.007 | 0.007 | 0 | 0 | 0 | 0 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.00014286 | 0.0072857
| H50571 | Internals-meadowgate | 0.005 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.00071429 | 0.00071429 | 0.00071429 | 0.00071429 | 0.00071429 | 0.00071429 | 0.00071429 | 0.0014286
| H50859 | Internals-cliveley | 0.221 |  |  | 0.08 | 0.08 | 0 | 0 | 0 | 0 | 0.020143 | 0.020143 | 0.020143 | 0.020143 | 0.020143 | 0.020143 | 0.020143 | 0.12029
| H50904 | Internals-amblecote | 0.022 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.0031429 | 0.0031429 | 0.0031429 | 0.0031429 | 0.0031429 | 0.0031429 | 0.0031429 | 0.0062857
|  | EA SCHEMES |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50402 | Amersham st phase 1 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50488 | Albion towers | 0.004 |  |  | 0.004 | 0.005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.005
| H50422 | Fitzwarren court refurbishment | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50285 | Ordsall-linden gr ph 3(nwo ph 2) | 0.002 |  |  | 0.002 | 0 | 0 | 0 | 0 | 0 | 0.00028571 | 0.00028571 | 0.00028571 | 0.00028571 | 0.00028571 | 0.00028571 | 0.00028571 | 0.00057143
| H50287 | Ordsall-burnett (nwo ph 3) | 0.011 |  |  | 0.011 | 0.004 | 0 | 0 | 0 | 0 | 0.00071429 | 0.00071429 | 0.00071429 | 0.00071429 | 0.00071429 | 0.00071429 | 0.00071429 | 0.0054286
|  | Srb /cc schemes |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50083 | Broadwalk west phase 2 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50223 | Peel environment ph 2 | 0.009 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.0012857 | 0.0012857 | 0.0012857 | 0.0012857 | 0.0012857 | 0.0012857 | 0.0012857 | 0.0025714
| H50230 | Amblecote environment | 0.012 |  |  | 0.012 | 0.012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.012
| H50228 | Mt skip environment | 0.033 |  |  | 0.033 | 0.032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.032
| H50251 | Peel homes for all | 0.034 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.0048571 | 0.0048571 | 0.0048571 | 0.0048571 | 0.0048571 | 0.0048571 | 0.0048571 | 0.0097143
| H50263 | Armitage environment ph 1 | 0.01 |  |  | 0.01 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01
| summary | Resources and overprogramming | -2.399 |  |  |  | Profiled spend Mar: -2.399 |  | 4.369 |  |  |  |  | 0.399 | 16.776 | 21.544 | [11 empty] | 0.002 | 0.097 |  |  | 0.3 | 0.399 | 0.678 grant extra care housing fund
|  | PUBLIC SECTOR HOUSING - TOTAL | 21.544 |  |  | 6.797 | 4.318 | 0 | 0 | 0 | 0 | 3.0479 | 3.0479 | 3.0479 | 3.0479 | 3.0479 | 3.0479 | 0.64886 | 10.3287 | 4.369 | 0 | 0 | 0 | 0 | 0.399 | 16.776 | 21.544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.002 | 0.097 | 0 | 0 | 0.3 | 0.399 | 16.100MRA, 0.676 HRA, 0.678 extra care housing fund
|  | HOUSING TOTAL | 50.526 |  |  | 14.389 | 9.904 | 0 | 0 | 0 | 0 | 6.4333 | 6.4333 | 6.4333 | 6.4333 | 6.4344 | 6.4344 | 4.0354 | 22.6796 | 5.481 | 0 | 0 | 0 | 5.868 | 22.101 | 17.076 | 50.526 | 0 | 4.869 | 0 | 0 | 0 | 0 | 0 | 0.73 | 1.602 | 0.078 | 1.3 | 0.002 | 0.212 | 13.008 | 0 | 0.3 | 22.101
0
EDUCATION
|  | ACG Minor Works | 0.017 | 2004-04-01 | 2005-03-31 | 0 | Profiled spend Mar: 0.017 | 0.017 | 0.017 |  |  |  |  | 0 |  | 0.017 | [16 empty] | 0
| e02005 | Capitalised Salaries | 0.134 | 2004-04-01 | 2005-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.134 | 0.134 | 0.134 |  |  |  |  | 0 |  | 0.134 | [16 empty] | 0
|  | Class Size Reduction | 0.002 |  | 2005-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.002 | 0 | 0.002 |  |  |  |  | 0 |  | 0.002 | [16 empty] | 0
| E02028 | Moorfield CP Fire Damage |  |  |  | 0.015 | [12 empty] | 0
| E04613 | DFC Alder Park |  |  |  | 0.021 | [12 empty] | 0
| E04614 | DFC Barton Moss |  |  |  | 0.003 | [12 empty] | 0 | [24 empty] | 0
| E04615 | DFC Beech Street |  |  |  | 0.014 | [12 empty] | 0 | [24 empty] | 0
| E04618 | DFC Broadoak |  |  |  | 0.039 | [12 empty] | 0
| E04619 | DFC Cadishead |  |  |  | 0.004 | [12 empty] | 0
| E04621 | DFC Clarendon Road |  |  |  | 0.002
| E04624 | DFC Dukesgate |  |  |  | 0.017 | [12 empty] | 0 | [24 empty] | 0
| E04627 | DFCThe Friars |  |  |  | 0.0011555 | [12 empty] | 0 | [24 empty] | 0
| E04629 | DFC Hilton Lane |  |  |  | 0.019 | [12 empty] | 0 | [24 empty] | 0
| E04630 | DFC Irlam |  |  |  | 0.013 | [12 empty] | 0 | [24 empty] | 0
| E04631 | DFC James Brindley |  |  |  | 0.021 | [12 empty] | 0 | [24 empty] | 0
| E04632 | DFC Langworhy Road |  |  |  | 0.011 | [12 empty] | 0 | [24 empty] | 0
| E04634 | DFC Lewis Street |  |  |  | 0.008
| E04638 | DFC Marlborough Road |  |  |  | 0.000831 | [12 empty] | 0 | [24 empty] | 0
| E04639 | DFC Mesne Lea |  |  |  | 0.008 | [12 empty] | 0
| E04640 | DFC Monton Green |  |  |  | 0.036 | [12 empty] | 0 | [24 empty] | 0
| E04642 | DFC Moorside |  |  |  | 0.001 | [12 empty] | 0 | [24 empty] | 0
| E04643 | DFC Mossfield |  |  |  | 0.004 | [12 empty] | 0 | [24 empty] | 0
| E04644 | DFC North Grecian Street |  |  |  | 0.006 | [12 empty] | 0 | [24 empty] | 0
| E04647 | DFC Radclyffe |  |  |  | 0.029 | [12 empty] | 0 | [24 empty] | 0
| E04648 | DFC Seedley |  |  |  | 0.032 | [12 empty] | 0
| E04651 | DFC Westwood Park |  |  |  | 0.003
| E04655 | DFC Irlam Endowed |  |  |  | 0.051 | [12 empty] | 0 | [24 empty] | 0
| E04656 | DFC St Andrews CE Eccles |  |  |  | 0.025 | [12 empty] | 0 | [24 empty] | 0
| E04659 | DFC St Clements Egerton |  |  |  | 0.002 | [12 empty] | 0 | [24 empty] | 0
| E04661 | DFC St Johns CE |  |  |  | 0.01 | [12 empty] | 0
| E04662 | DFC St Lukes CE |  |  |  | 0.001 | [12 empty] | 0
| E04663 | DFC St Marys CE |  |  |  | 0.028 | [12 empty] | 0 | [24 empty] | 0
| E04664 | DFC St Pauls CE Neville Road |  |  |  | 0.017
| E04666 | DFC St Pauls Peel CE |  |  |  | 0.0074692 | [12 empty] | 0 | [24 empty] | 0
| E04667 | DFC Wardley CE |  |  |  | 0.007 | [12 empty] | 0
| E04668 | DFC Buile Hill |  |  |  | 0.028 | [12 empty] | 0 | [24 empty] | 0
| E04669 | DFC Harrop Fold |  |  |  | 0.008 | [12 empty] | 0
| E04672 | DFC Moorside High |  |  |  | 0.127 | [12 empty] | 0
| E04673 | DFC The Swinton |  |  |  | 0.025 | [12 empty] | 0 | [24 empty] | 0
| E04674 | DFC Walkden |  |  |  | 0.014 | [12 empty] | 0
| E04675 | DFC Wentworth |  |  |  | 0.031 | [12 empty] | 0
#REF! | E04677 | DFC Newcroft |  |  |  | 0.007 | [12 empty] | 0 | [24 empty] | 0
| E04678 | DFC Oakwood |  |  |  | 0 | [12 empty] | 0
| E04685 | DFC Bradshaw Early Years |  |  |  | 0.006 | [12 empty] | 0 | [24 empty] | 0
| E04686 | DFC Little Hulton Early Years Centre |  |  |  | 0.0011425 | [12 empty] | 0 | [24 empty] | 0
| E04687 | DFC Winton Early Years Centre |  |  |  | 0.002 | [12 empty] | 0 | [24 empty] | 0
| summary | Devolved Capital Formula | 2.002 | 2004-04-01 | 2005-03-31 | 0.6906 | 0 | 0 | 0 | 0 | 0.222 | 0.222 | 0.222 | 0 | 0 | 0 | 0 | 1.436 | 0.666 | [5 empty] | 2.002 |  | 2.002 | [5 empty] | 2.002 | [10 empty] | 2.002
|  | Harrop Fold Surplus Place Removal |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | [16 empty] | 0
|  | Hope High / Buille Hill High Surplus Places |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | [16 empty] | 0
| E03022 | Ph 2 Roofing -Little Hulton High |  |  |  | 0.0016785 | [12 empty] | 0 | [24 empty] | 0
| summary | NDS 2 & 3 | 0.019 |  | 2005-03-01 | 0.0016785 | Profiled spend Apr: 0.002; Profiled spend Mar: 0.017 | 0.002 | 0.019 |  |  |  |  | 0 |  | 0.019 | [16 empty] | 0
| E03052 | NDS4 - Joseph Eastham High School Laboratories |  |  |  | 0.002
| E03058 | NDS4 - Swinton High School Laboratories |  |  |  | 0.002
| E03063 | NDS4 Brentnall CP - Refurbishment |  |  |  | 0.008 | [37 empty] | 0
| summary | NDS 4 | 0.062 |  | 2005-03-01 | 0.012 | 0 | 0 | 0 | 0.009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.053 | 0.009 | [5 empty] | 0.062 |  | 0.062 |  |  | 0.062 | [13 empty] | 0.062
| E03065 | NDS Cond Light Oaks Jnr&Inf -Re-roof |  |  |  | 0.00094258 | [12 empty] | 0 | [24 empty] | 0
| E03075 | NDS Cond St Newcroft High H&S issues |  |  |  | 0.001 | [12 empty] | 0 | [24 empty] | 0
| E03061 | NDS Condition Wharton CP - toilets |  |  |  | 0.005 | [12 empty] | 0 | [24 empty] | 0
| E03076 | Modcon St Mary's CE (Cad) Library/staff | [16 empty] | 0
| E03077 | ModCon Marlborough Road CP Boiler |  |  |  | 0.005 | [12 empty] | 0 | [24 empty] | 0
| E03078 | ModCon Lower Kersal PS |  |  | 2004-08-01 | 0.223 | [12 empty] | 0 | [24 empty] | 0
| E03079 | Modcon Moorside High Boiler replacement | [16 empty] | 0
| E03084 | NDS Cond Moorside CP - Electrical Work |  |  |  | 0.004 | [12 empty] | 0 | [24 empty] | 0
| E03085 | NDS Cond Moorside HS - Electrical Works |  |  | 2004-08-01 | 0.014 | [12 empty] | 0 | [24 empty] | 0
| E03086 | NDS Cond - Broadoak CP - Electrical Works |  |  |  | 0.021 | [12 empty] | 0
| E03087 | NDS Cond - Walkden HS - Electrical Work |  |  | 2004-08-01 | 0.328 | [12 empty] | 0 | [24 empty] | 0
| E03089 | NDS Cond - St Pauls H/Side Roof & Vent |  |  |  | 0.002
| E03094 | NDS Cond Light Oaks PS Pipework |  |  |  | 0.012 | [12 empty] | 0 | [24 empty] | 0
| E03095 | NDS Cond cadishead PS Boiler replacement |  |  |  | 0.012 | [12 empty] | 0 | [24 empty] | 0
| E03096 | NDS Cond Moorside High Roofing |  |  |  | 0.015
| E03098 | NDS Cond Mossfield CP Roofing |  |  |  | 0.162
| E03100 | [17 empty] | 0
| E03101 | NDS Cond The Friars CP roofing |  |  |  | 0.001 | [12 empty] | 0
| E03102 | NDS Cond St Pauls Peel CP |  |  |  | 0.003 | [12 empty] | 0
| E03103 | NDS Cond St Pauls Neville Road Window replacement |  |  |  | 0.001 | [12 empty] | 0
| E03106 | NDS Cond Moorside High Window Replacement |  |  |  | 0.072
| E03108 | NDS condition lightoaks junior window replacement |  |  |  | 0.004
| E03109 | NDS Cond St Pauls Peel Window replacement |  |  |  | 0.047 | [12 empty] | 0
| E03110 | NDS Cond Moorside CP window replacement |  |  |  | 0.001
| E03111 | NDS Cond Irlam & Cad High Window Repl. |  |  |  | 0.006 | [12 empty] | 0 | [24 empty] | 0
| E03115 | Swinton High Window Replacement |  |  | 2004-08-01 | 0.118 | [12 empty] | 0 | [24 empty] | 0
| E03117 | Clarendon Road Window Replacement |  |  | 2004-08-01 | 0.028 | [12 empty] | 0 | [24 empty] | 0
| E03119 | Lightoaks Infant Fencing |  |  |  | 0.044
| E03121 | Lower Kersal CP Fencing |  |  |  | 0.009 | [12 empty] | 0 | [24 empty] | 0
| E03122 | North Grecian St Fencing |  |  |  | 0.055 | [12 empty] | 0
| E03124 | St Georges CE Fencing |  |  |  | 0.034 | [12 empty] | 0
| E03125 | St Lukes CE Fencing |  |  |  | 0.063 | [12 empty] | 0
| E03126 | Langworthy Road Playground |  |  |  | 0.047
| E03127 | Larkhill Playground Works |  |  |  | 0.123 | [12 empty] | 0
| E03129 | Irlam Endowed Playground Works |  |  |  | 0.001 | [12 empty] | 0
| E03130 | Lewis st Toilets Refurbishment |  |  |  | 0.065 | [12 empty] | 0 | [24 empty] | 0
| E03131 | Lightoaks Jun/Infant Toilets Refurb |  |  |  | 0.004 | [12 empty] | 0
| E03133 | Wharton CP Boiler Replaecment |  |  |  | 0.01
| E03135 | NDS Cond Harropfold Drainage works |  |  |  | 0.029
| E03136 | NDS Cond Hilton Lane heating works |  |  |  | 0.006
| E03137 | NDS Cond Peel Hall CP Flagging works |  |  |  | 0.009
| E03139 | NDS Cond Dukesgate CP Playground |  |  |  | 0.01
| E03140 | NDS Cond Grosvenor Road Playground |  |  |  | 0.017
| E03141 | NDS Cond Marlborough Road Playground |  |  |  | 0.05
| E03142 | NDS Cond Moorfield CP Playground |  |  |  | 0.022
| E03143 | NDS Cond Bridgewater CP boiler replacement |  |  |  | 0.07
| summary | New Deal Condition / Modernisation | 4.082 | 2004-04-01 | 2005-08-31 | 1.7539 | Profiled spend Aug: 1.173; Profiled spend Sep: 0.324; Profiled spend Oct: 0.275; Profiled spend Mar: 2.31 | 1.772 | 1.917 |  |  |  | 0 | 2.165 |  | 4.082 |  |  | 2.165 | [13 empty] | 2.165
| E02026 | PFI 2 Preliminary Works |  |  |  | 0.031 | [12 empty] | 0 | [24 empty] | 0
|  | PFI 2 3 New high schools |  | 2003-04-01 | 2006-09-30 | [13 empty] | 0 | [5 empty] | 0 |  | 0 | [16 empty] | 0
| E00515 | Temp.Accom. Buille Hill/Harropfold/Hope |  |  |  | 0.395 | [12 empty] | 0 | [24 empty] | 0
| E01502 | Newcroft HS - PMLD Unit |  |  |  | 0
| summary | PFI Bid new facilities - 3 Secondary Schools fees | 0.463 | 2003-03-01 | 2005-05-01 | 0.426 |  |  | 0.046 | 0.046 | 0.046 | 0.046 | 0.046 | 0.046 | 0.046 | 0.046 | 0.046 | 0.046 | 0.23 | 0.116 |  |  |  | 0 | 0.347 |  | 0.463 |  |  | 0.121 |  |  | 0.1 | [9 empty] | 0.126 | 0.347
summary | E00510 | The Albion | 0.175 | 2001-04-01 | 2005-03-01 | 0.077 | 0 | 0 | 0 | 0.014 | 0.032 | 0 | 0 | 0.1 | 0.1 | 0 | 0 | 0.216 | 0.046 | 0.175 |  |  |  |  | 0 |  | 0.175 | [16 empty] | 0
| E00005 | Irlam Endowed - Alterations to Hall |  |  |  | 0.026 | [12 empty] | 0
| E00006 | Moorside Primary Schools Renewal Challenge Arch Fees
| E00505 | Joseph Eastham High - refurb of labs |  |  |  | 0.001
| summary | Old schemes |  |  |  | 0.027
| E04755 | Playgroup Conversion | 0.037 | 2004-04-30 | 2006-03-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.037 | 0 | 0 | 0 | 0.015 | 0 | [5 empty] | 0.037 |  | 0.037 |  |  |  | 0.037 | [12 empty] | 0.037
| E02012 | Belvedere Nursery - Community Facilities |  |  |  | 0.001 | [12 empty] | 0 | [24 empty] | 0
| E02027 | Adult & Community Learning |  |  |  | 0.011 | [12 empty] | 0 | [24 empty] | 0
| E04750 | Winton Nursery Centre |  |  |  | 0.006 | Profiled spend Sep: 0.005; Profiled spend Oct: 0.024; Profiled spend Nov: 0.048; Profiled spend Dec: 0.036; Profiled spend Jan: 0.048; Profiled spend Feb: 0.048; Profiled spend Mar: 0.042 | 0.029 | [24 empty] | 0 | surestart to be invoiced
| E04751 | Barton Moss Neighbourhood Nursery |  |  |  | 0.361 | [12 empty] | 0 | [24 empty] | 0 | surestart to be invoiced
| summary | Surestart | 0.505 | 2004-03-01 | 2004-09-01 | 0.367 | 0 | 0 | 0 | 0 | 0.224 | 0.09 | 0.085 | 0 | 0 | 0 | 0 | 0.029 | [6 empty] | 0.505 |  | 0.505 |  |  |  | 0.305 | [7 empty] | 0.2 |  |  |  |  | 0.505 | surestart to be invoiced
| E04555 | Nursery Education in Disadvantaged Areas | 0.254 | 2003-04-01 | 2004-08-01 | 0.243 | 0 | 0 | 0 | 0 | 0.254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.254 |  |  |  | 0.186 |  | 0.068 |  | 0.254 | [15 empty] | 0.068 | 0.068
| E00018 | Primary Review Allocation | [16 empty] | 0
| E00019 | Primary Review Boothstown Methodists |  |  |  | 0.001 | [12 empty] | 0
| E00020 | Primary Review Grosvenor Road |  |  |  | 0.029 | [12 empty] | 0
| E00021 | Primary Review Wharton CP |  |  |  | 0.014 | [12 empty] | 0
| E00022 | Primary Review Westwood Park |  |  |  | 0.07 | [12 empty] | 0 | [24 empty] | 0
| E00024 | Primary Review North Grecian Street |  |  |  | 0.019
| E00026 | Primary Review Beech Street |  |  |  | 0.088 | [12 empty] | 0
| E00027 | Clarendon Road CP |  |  |  | 0.087
| E00029 | Portage Team |  |  |  | 0.015 | [12 empty] | 0 | [24 empty] | 0
| E00030 | Lower Kersal Primary School |  |  |  | 0.1 | [12 empty] | 0 | [24 empty] | 0
| E00031 | Moorside Primary re Primary Review |  |  |  | 0.043 | [12 empty] | 0
| E00032 | Moorfield Primary Review |  |  |  | 0.003 | [12 empty] | 0
| summary | Primary Review | 1.49 | 2004-02-01 | 2006-03-01 | 0.468 | Profiled spend Aug: 0.775; Profiled spend Mar: 3.051 | 0.775 | 0.776 |  |  |  |  | 0.649 | 0.065 | 1.49 | [15 empty] | 0.649 | 0.649
| E02004 | SCA Schools Access Initiative |  |  |  | 0.319 | [12 empty] | 0 | [24 empty] | 0
| summary | Schools Access Initiative | 0.514 | 2004-04-01 | 2005-08-31 | 0.319 | 0.054 | 0.029 | 0.032 | 0.004 | 0.149 | 0 | 0 | 0 | 0 | 0 | 0 | 0.246 | 0.268 | 0.272 |  |  |  |  | 0.242 |  | 0.514 |  |  | 0.242 | [13 empty] | 0.242
| E04603 | Seed Challenge 03/04 Schemes |  |  |  | 0.018 | [12 empty] | 0 | [24 empty] | 0
| summary | Seed Challenge | 0 | 2004-04-01 | 2005-08-31 | 0.018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | [16 empty] | 0
|  | St Augustines CoE |  | 2003-04-30 | 2007-03-31 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | [16 empty] | 0
| E01503 | Springwood | 0.007 |  |  | 0.032 | 0 | 0 | 0 | 0.007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.007 | 0.007 |  |  |  |  | 0 |  | 0.007 | [16 empty] | 0
| E00017 | Surplus Place Removal St Clements / Radclyffe | 0.068 | 2004-04-30 | 2006-08-31 | 0.009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.068 | 0 | 0.068 |  |  |  |  | 0 |  | 0.068 | [16 empty] | 0
| E02029 | Zoneparcs (Sporting playgrounds) | 0.192 | 2005-08-01 | 2005-03-01 | 0.027 | Profiled spend Mar: 0.192 | 0 | [5 empty] | 0.192 |  | 0.192 | [15 empty] | 0.192 | 0.192
| E04851 | The Beacon Centre (Young Peoples Resource Centre) | 1.686 | 2004-05-01 | 2004-11-01 | 0.572 | 0 | 0 | 0 | 0.198 | 0.105 | 0.433 | 0.185 | 0.185 | 0.195 | 0.15 | 0.155 | 0.08 | 0.921 | 0.614 |  |  | 0.043 |  | 1.029 |  | 1.686 | [10 empty] | 1.029 | [5 empty] | 1.029 | contribution from E&L
| E04552 | Staff Workspaces | 0.019 |  | 2004-08-01 | 0.019 | 0 | 0 | 0 | 0 | 0.019 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.019 | [5 empty] | 0.019 |  | 0.019 | [15 empty] | 0.019 | 0.019
| E01008 | VA Minor Works | 0.066 | 2004-04-01 | 2005-03-31 | 0.062 | 0 | 0 | 0 | 0 | 0.066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.066 | 0.066 |  |  |  |  | 0 |  | 0.066 | [16 empty] | 0
| E00514 | Wentworth High School | 0.036 | 2004-04-01 | 2005-03-31 | 0.009 | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.023 | 0.007 | 0.036 |  |  |  |  | 0 |  | 0.036 | [16 empty] | 0
|  | Winton | 0.386 | [21 empty] | 0.386 |  | 0.386 |  |  |  | 0.294 | [11 empty] | 0.092 | 0.386 | 0.092 employment project fund
|  | Larkhilll Childrens Centre | 0.15 | [21 empty] | 0.15 |  | 0.15 |  |  |  | 0.15 | [12 empty] | 0.15
|  | EDUCATION - TOTAL | 12.366 |  |  | 5.1609 | 0.057 | 0.03 | 0.079 | 0.279 | 3.066 | 1.121 | 0.838 | 0.417 | 0.378 | 0.245 | 0.25 | 7.977 | 5.222 | 4.219 | 0 | 0 | 0.229 | 0 | 7.853 | 0.065 | 12.366 | 0 | 0 | 2.59 | 0.786 | 0 | 2.102 | 0 | 0 | 0 | 0 | 1.029 | 0.2 | 0 | 0 | 0 | 1.146 | 7.853
spend on 7027, unapportioned on 7015 |  | HIGHWAYS | [41 empty] | 0
| D00500 | Bridge Inspections and Assessments | 0.005 | 2004-04-01 | 2005-03-01 | 0.001 | 0 | 0 | 0 | 0 | 0 | 0.00071429 | 0.00071429 | 0.00071429 | 0.00071429 | 0.00071429 | 0.00071429 | 0.00071429 | 0.0014286
| D00501 | Bridges general | 0.01 | 2004-04-01 | 2005-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0028571
| D00503 | Subways | 0.005 | 2004-04-01 | 2005-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0.00071429 | 0.00071429 | 0.00071429 | 0.00071429 | 0.00071429 | 0.00071429 | 0.00071429 | 0.0014286
| D00504 | Agecroft Road Railway Bridge | 0 | 2002-03-01 | 2002-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| D00510 | Railtrack Assessments |  |  |  | 0.001
| D00512 | Eccles Old Road Underpass | 0.067 | 2004-01-01 | 2004-04-01 | 0.004 | 0.062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.062
| D00514 | Eccles Rd/ East Lancs Rd Footbridge | 0.001 | 2003-08-01 | 2003-09-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| D00517 | Palatine Bridge | 0 | 2001-11-01 | 2002-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| D00518 | Waterloo Bridge | 0 | 2002-01-01 | 2002-05-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| D00520 | Carlton Footbridge | 0.002 | 2003-08-01 | 2004-03-01 | 0.001 | 0.00016667 | 0.00016667 | 0.00016667 | 0.00016667 | 0.00016667 | 0.00016667 | 0.00016667 | 0.00016667 | 0.00016667 | 0.00016667 | 0.00016667 | 0.00016667 | 0.0011667
| D00523 | Station Rd Rway Bridge - F'way Protection | 0 | 2003-01-01 | 2003-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| D00524 | Pendleton Roundabout Parapets ph1 | 0.067 | 2003-09-01 | 2004-05-01 | 0.067 | 0.062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.062
| D00525 | Rail Track Incursion works | 0.175 | 2003-10-01 | 2005-03-01 | 0.025 | 0.018 | 0 | 0 | 0 | 0 | 0.022429 | 0.022429 | 0.022429 | 0.022429 | 0.022429 | 0.022429 | 0.022429 | 0.062857
| D00526 | Eccles Old Road Underpass |  |  |  | 0.063
| D00527 | Culvert Safety Improvement Programme | 0.02 | 2004-09-01 | 2005-03-01 | 0.001 | 0 | 0 | 0 | 0 | 0 | 0.0028571 | 0.0028571 | 0.0028571 | 0.0028571 | 0.0028571 | 0.0028571 | 0.0028571 | 0.0057143
| D00528 | Wallness Bridge | 0.061 | 2004-05-01 | 2004-06-01 | 0.058 | 0.026 | 0.026 | 0.026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.078
| D00529 | West Egerton Street Bridge | 0.005 | 2004-02-01 | 2004-07-01 |  | 0.001 | 0.001 | 0.001 | 0.002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.005
| D00530 | Woden Street Footbridge | 0.152 | 2004-07-01 | 2004-10-01 | 0.105 | 0.001 | 0 | 0 |  |  | 0.034 | 0.034 | 0.034 | 0.05 | 0 | 0 | 0 | 0.069
| D00531 | Eccles Road Footbridge Painting | 0.051 | 2004-07-01 | 2004-10-01 | 0.047 | 0.012 | 0 | 0 | 0.01 | 0.0125 | 0.0102 | 0.0102 | 0.00344 | 0 | 0 | 0 | 0 | 0.0549
| D00532 | Hough Lane Footbridge | 0.157 | 2004-08-01 | 2004-10-01 | 0.04 | 0.001 | 0 | 0 | 0 | 0.0242 | 0.0244 | 0.0244 | 0.01764 | 0 | 0 | 0 | 0 | 0.074
| D00533 | Stott Lane Railway Bridge | 0.044 | 2005-01-01 | 2005-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.015 | 0.015 | 0.014 | 0
|  | East Ordsall Lane Canal Bridge | 0.03 | 2004-04-01 | 2004-09-01 |  | Profiled spend Oct: 0.03
| D00534 | Heywood Way Subway Infill | 0 |  |  |  | 0.0093333 | 0.0093333 | 0.0093333 | 0.0093333 | 0.0093333 | 0.0093333 | 0.0093333 | 0.0093333 | 0.0093333 | 0.0093333 | 0.0093333 | 0.0093333 | 0.065333
spend on d99999 7015 144k | D00535 | Pendleton Roundabout Parapets ph 2 | 0.144 | 2004-10-01 | 2004-12-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.048 | 0.048 | 0.048 | 0 | 0 | 0 | 0.048
| summary | Bridge Assessment and Strengthening Schemes | 0.996 | 2004-04-01 | 2005-03-01 | 0.413 | 0.1925 | 0.0365 | 0.0365 | 0.0215 | 0.0462 | 0.10624 | 0.18424 | 0.14072 | 0.13564 | 0.052643 | 0.052643 | 0.051643 | 0.62369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
summary | D00003 | Cadishead Way Stage 1 | 0.075 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.010714 | 0.010714 | 0.010714 | 0.010714 | 0.010714 | 0.010714 | 0.010714 | 0.021429
summary | D00004 | Cadishead Way Stage 2 | 14.514 | 2004-02-01 | 2006-02-01 | 5.697 | 3.92 | 0 | 0 | 0 | 0 | 1.5134 | 1.5134 | 1.929 | 1.409 | 1.409 | 1.409 | 1.409 | 6.9469 | 0 | 7.257 |  |  |  | 7.257 |  | 14.514 | 7.257 | [15 empty] | 7.257
| D00101 | Anti-skid Surfacing Programme | 0.05 | 2004-04-01 | 2005-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0.0071429 | 0.0071429 | 0.0071429 | 0.0071429 | 0.0071429 | 0.0071429 | 0.0071429 | 0.014286
| D00103 | Accident Investigation | 0.02 | 2004-04-01 | 2005-03-01 | 0.001 | 0.001 | 0 | 0 | 0 | 0 | 0.0027143 | 0.0027143 | 0.0027143 | 0.0027143 | 0.0027143 | 0.0027143 | 0.0027143 | 0.0064286
| D00104 | White Lining Programme | 0.01 | 2004-04-01 | 2005-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0028571
| D00105 | Road Safety Strategy | 0 | - | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| D00111 | Westwood Park Area - 20mph Zone | 0.006 | 2002-03-01 | 2003-07-01 | 0.002 | 0.001 | 0.001 | 0.001 | 0.001 | 0.002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.006
| D00119 | Barton Lane Ped Improvements | 0.02 | 2005-03-01 | 2005-05-01 | 0.002 | 0 | 0 | 0 | 0 | 0 | 0.0028571 | 0.0028571 | 0.0028571 | 0.0028571 | 0.0028571 | 0.0028571 | 0.0028571 | 0.0057143
| D00121 | A6 High Street/ Campbell Way | 0.05 | 2004-10-01 | 2005-01-01 |  | 0 | 0 | 0 | 0 | 0 | 0.015714 | 0.015714 | 0.015714 | 0.015714 | 0.015714 | 0.015714 | 0.015714 | 0.031429
| D00132 | Broughton Park Area Scheme | 0.001 | 2001-12-01 | 2004-03-01 | 0.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| D00133 | East Lancs Rd/ Moorside Camera | 0 | 2002-12-01 | 2003-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| D00135 | Pendleton Roundabout | 0.001 | 2004-01-01 | 2004-03-01 | 0.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| D00139 | Hilton Lane Traffic Calming | 0.001 | 2002-02-01 | 2002-04-01 | 0.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| D00141 | Moorside Rd/Wardley Ind Estate Area Sch | 0.04 | 2004-12-01 | 2005-03-01 | 0.003 | Profiled spend Apr: 0; Profiled spend May: 0; Profiled spend Jun: 0; Profiled spend Jul: 0; Profiled spend Aug: 0; Profiled spend Mar: 0.04 | 0
| D00142 | B5229 Monton Centre Scheme | 0.01 | 2005-04-01 | 2005-07-01 | 0.003 | 0 | 0 | 0 | 0 | 0 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0028571
| D00143 | Cadishead NW Area Safety Scheme | 0.03 | 2003-12-01 | 2004-03-01 | 0.003 | 0.0025 | 0.0025 | 0.0025 | 0.0025 | 0.0025 | 0.0025 | 0.0025 | 0.0025 | 0.0025 | 0.0025 | 0.0025 | 0.0025 | 0.0175
| D00148 | A6 Chorley Road Route Scheme | 0 | 2005-05-01 | 2005-08-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| D00149 | Lttleton Rd Pedestrian Safety Scheme | 0.003 | 2002-03-01 | 2003-03-01 | -0.004 | 0 | 0 | 0 | 0 | 0 | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.002
| D00151 | A57/ M60 Peel Green Roundabout | 0.002 | 2005-11-01 | 2006-03-01 |  | 0.00016667 | 0.00016667 | 0.00016667 | 0.00016667 | 0.00016667 | 0.00016667 | 0.00016667 | 0.00016667 | 0.00016667 | 0.00016667 | 0.00016667 | 0.00016667 | 0.0011667
| D00161 | Trafford Road, Eccles, Speed Management | 0.088 | 2004-09-01 | 2004-11-01 | 0.008 | 0 | 0 | 0 | 0 | 0 |  | 0.022 | 0.022 | 0.044 | 0 | 0 | 0 | 0.022
| D00170 | Cantebury Gardens - Traffic Calming | -0.004 | 2003-01-01 | 2003-07-01 | -0.003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| D00171 | Camera Site Speed Surveys | 0 | 2003-04-01 | 2004-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| D00172 | Kersal Area Traffic Calming | 0 | 2003-03-01 | 2004-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| D00173 | New Lane, Winton | 0.06 | 2005-01-01 | 2005-03-01 | 0.002 | 0 | 0 | 0 | 0 | 0 | 0.0085714 | 0.0085714 | 0.0085714 | 0.0085714 | 0.0085714 | 0.0085714 | 0.0085714 | 0.017143
| D00174 | Speed Management Policy | 0.01 | 2004-04-01 | 2005-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0028571
| D00175 | Amendments to Early T Calming Schemes | 0.003 | 2004-04-01 | 2005-03-01 | 0.004 | 0 | 0 | 0 | 0 | 0 | 0.0071429 | 0.0071429 | 0.0071429 | 0.0071429 | 0.0071429 | 0.0071429 | 0.0071429 | 0.014286
| D00176 | Dealing with Disadvantage Initiative | 0.04 | 2004-04-01 | 2005-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0.0057143 | 0.0057143 | 0.0057143 | 0.0057143 | 0.0057143 | 0.0057143 | 0.0057143 | 0.011429
| D00177 | Liverpool Rd, Cad, Speed Management | 0.004 | 2005-06-01 | 2005-08-01 |  | 0 | 0 | 0 | 0 | 0 | 0.00057143 | 0.00057143 | 0.00057143 | 0.00057143 | 0.00057143 | 0.00057143 | 0.00057143 | 0.0011429
|  | Safer Routes to Schools Programme | 0.005 | 2005-04-01 | 2005-07-01 |  | 0 | 0 | 0 | 0 | 0 | 0.00071429 | 0.00071429 | 0.00071429 | 0.00071429 | 0.00071429 | 0.00071429 | 0.00071429 | 0.0014286
| D00179 | Oxford Road Remedial Traffic Calming | 0.03
| D00178 | Greenleach Lane, Worsley | 0.02 | 2005-03-01 | 2005-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0.0028571 | 0.0028571 | 0.0028571 | 0.0028571 | 0.0028571 | 0.0028571 | 0.0028571 | 0.0057143
| summary | Local Safety schemes | 0.5 | 2004-04-01 | 2005-03-01 | 0.024 | 0.0046667 | 0.0036667 | 0.0036667 | 0.0036667 | 0.0046667 | 0.061952 | 0.083952 | 0.083952 | 0.10595 | 0.061952 | 0.061952 | 0.10195 | 0.16624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
summary | D00005 | Manchester/Salford Inner Relief Route | 6.12 | 2001-02-01 | 2004-08-01 | 1.069 | 0.71 |  |  |  |  | 0.2305 | 0.2305 | 0.2305 | 0.2305 | 3.668 | 0.2305 | 0.2305 | 1.171 |  | 0.616 |  |  |  | 5.504 |  | 6.12 | 5.504 | [15 empty] | 5.504 | £1.145m from 03/04, 5.075 from 03/04
| D00901 | GM Local Transport Plan | 0.04 | 1999-04-01 | 2005-03-01 | 0.001 | 0 | 0 | 0 | 0 | 0 | 0.0057143 | 0.0057143 | 0.0057143 | 0.0057143 | 0.0057143 | 0.0057143 | 0.0057143 | 0.011429
| D00902 | Salford's Green Transport Plan | 0.015 | 2005-01-01 | 2005-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0.0035714 | 0.0035714 | 0.0035714 | 0.0035714 | 0.0035714 | 0.0035714 | 0.0035714 | 0.0071429
| D00903 | M60/ PRN Signing | 0.055 | 1998-04-01 | 2005-03-01 | 0.006 | 0 | 0 | 0 | 0 | 0 | 0.0078571 | 0.0078571 | 0.0078571 | 0.0078571 | 0.0078571 | 0.0078571 | 0.0078571 | 0.015714
| D00905 | Demand Management Measures | 0 | 2000-04-01 | 2002-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| D00909 | AGMA countywide Advertising | 0.004 | 2000-04-01 | 2005-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0.00057143 | 0.00057143 | 0.00057143 | 0.00057143 | 0.00057143 | 0.00057143 | 0.00057143 | 0.0011429
| D00912 | Disabled Facilities at Ped Crossings | 0.3 | 2003-04-01 | 2005-03-01 | 0.147 | 0.1 | 0 | 0 | 0 | 0 | 0.028571 | 0.028571 | 0.028571 | 0.028571 | 0.028571 | 0.028571 | 0.028571 | 0.15714
| D00917 | Barton SES Studies | 0.001 | 2003-06-01 | 2004-03-01 | 0.001 | 0.001 | 8.3333e-05 | 8.3333e-05 | 8.3333e-05 | 8.3333e-05 | 8.3333e-05 | 8.3333e-05 | 8.3333e-05 | 8.3333e-05 | 8.3333e-05 | 8.3333e-05 | 8.3333e-05 | 0.0015
| D00918 | Chapel St Pedestrian Route Improve'ts | 0.041 | 2004-08-01 | 2004-10-01 | 0.005 | 0 | 0 | 0 | 0 | 0 | 0.013 | 0.013 | 0.015 |  |  |  |  | 0.026
| D00919 | GMATS 2001 Surveys | 0 | 2001-04-01 | 2004-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| D00923 | Little Moss Lane | 0.08 | 2003-11-01 | 2004-07-01 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0.012429 | 0.012429 | 0.012429 | 0.012429 | 0.012429 | 0.012429 | 0.012429 | 0.024857
| D00924 | Miscellaneous SRTS Works | 0.005 | 2003-08-01 | 2005-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0.0021429 | 0.0021429 | 0.0021429 | 0.0021429 | 0.0021429 | 0.0021429 | 0.0021429 | 0.0042857
| D00925 | GMTU Non-core Modelling Work | 0.01 | 2003-06-01 | 2005-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0028571
| D00926 | Public Rights of Way Signing | 0.01 | 2005-01-01 | 2006-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0028571
| D00928 | Barton Rd/Barton Ln J'n Improvement | 0.285 | 2004-12-01 | 2005-02-01 |  | 0 | 0 | 0 | 0 | 0.002 | 0.006 | 0.055 | 0.055 | 0.08 | 0.08 | 0.015 | 0.015 | 0.063
| D00931 | Chapel St/New Bailey St Ped Facilities | 0.08
| D00929 | Liverpool Rd, Cadishead, Town Centre | 0.002 | 2005-08-01 | 2006-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0.0011429 | 0.0011429 | 0.0011429 | 0.0011429 | 0.0011429 | 0.0011429 | 0.0011429 | 0.0022857
| D00927 | Public Rights of Way Improvements | 0.05 | 2004-12-01 | 2005-03-01 | 0.001 | 0 | 0 | 0 | 0 | 0 | 0.0071429 | 0.0071429 | 0.0071429 | 0.0071429 | 0.0071429 | 0.0071429 | 0.0071429 | 0.014286
| D00932 | Station Road Puffin Crossing | 0.03
| D00930 | Oaklands Road | 0.017 |  |  | 0.006 | 0 | 0 | 0 | 0 | 0 | 0.0024286 | 0.0024286 | 0.0024286 | 0.0024286 | 0.0024286 | 0.0024286 | 0.0024286 | 0.0048571
| summary | Other Minor Schemes | 1.025 | 2004-04-01 | 2005-03-01 | 0.187 | 0.101 | 8.3333e-05 | 8.3333e-05 | 8.3333e-05 | 0.0020833 | 0.093512 | 0.14251 | 0.14451 | 0.15451 | 0.15451 | 0.089512 | 0.089512 | 0.33936 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| D00602 | A6 Chapel Street (Adelphi Street - Trinity Way) | 0 | 2001-01-01 | 2002-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| D00601 | A57 Liverpool Road, Cadishead | 0.001 |  |  | 0.001
| D00605 | Deflectograph survys | 0.017 | 2003-08-01 | 2003-12-01 | 0.017 | 0.017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.017
| D00606 | A57 Liverpool Rd (Boysnope - Barton Moss Road) | 0 | 2005-01-01 | 2005-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| D00608 | Principal Road Maintenance - General | 0.02 | 2004-04-01 | 2005-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0.0028571 | 0.0028571 | 0.0028571 | 0.0028571 | 0.0028571 | 0.0028571 | 0.0028571 | 0.0057143
| D00610 | A575 Walkden Road (Manchester Road - Park Road) | 0.215 | 2004-01-01 | 2004-06-01 | 0.13 | 0 | 0 | 0 | 0 | 0 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 | 0.064
| D00611 | A576 Cromwell Road | 0.002 | 2002-02-01 | 2002-06-01 | 0.002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| D00612 | A6 Manchester Road (Bolton Road - Smithfold Lane) | 0.05 | 2003-01-01 | 2003-08-01 | 0.002 | 0 | 0 | 0 | 0 | 0 | 0.0071429 | 0.0071429 | 0.0071429 | 0.0071429 | 0.0071429 | 0.0071429 | 0.0071429 | 0.014286
| D00613 | A5082 Armitage Avenue (Manchester Road - Boundary) | 0.019 | 2003-01-01 | 2003-07-01 | -0.008 | 0 | 0 | 0 | 0 | 0 | 0.0058571 | 0.0058571 | 0.0058571 | 0.0058571 | 0.0058571 | 0.0058571 | 0.0058571 | 0.011714
| D00614 | Structural Maintenance of Minor Roads | 0.325 | 2003-10-01 | 2005-03-01 | 0.027 | 0 | 0 | 0 | 0 | 0 | 0.073429 | 0.073429 | 0.073429 | 0.073429 | 0.073429 | 0.073429 | 0.073429 | 0.14686
| D00616 | A56 Bury New Road (Bury Boundary - Singleton Rd) | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| D00601 | A57 Liverpool Road, Cadishead | 0 | 2006-01-01 | 2006-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | (New Moss Road - Fir Street) | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| D00617 | A5066 Adelphi Street & Silk Street | 0.38 | 2004-01-01 | 2005-01-01 | 0.012 | 0 | 0 | 0 | 0 | 0 | 0.031429 | 0.031429 | 0.031429 | 0.031429 | 0.031429 | 0.031429 | 0.031429 | 0.062857
| D00618 | A5066 Oldfield Road | 0.175 | 2004-12-01 | 2005-03-01 | 0.004 | 0 | 0 | 0 | 0 | 0 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.05
|  | (Ordsall Lane - Regent Road) | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| D00619 | A5066 Oldfield Road | 0.31 | 2005-01-01 | 2205-03-01 | 0.005 | 0 | 0 | 0 | 0 | 0 | 0.044286 | 0.044286 | 0.044286 | 0.044286 | 0.044286 | 0.044286 | 0.044286 | 0.088571
|  | (Regent Road - Crescent) | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| D00620 | A575 Cleggs Lane | 0 | 2005-01-01 | 2005-04-01 | 0.003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | A6 - Bolton Boundary) | 0.35 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.1
| summary | Principal Roads Structural Maintenance | 1.864 | 2004-04-01 | 2005-03-01 | 0.195 | 0.017 | 0 | 0 | 0 | 0 | 0.272 | 0.272 | 0.272 | 0.272 | 0.272 | 0.272 | 0.272 | 0.561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| D00700 | A576 Eccles Old Road Bus Priority and Cycling Facilities | 0 | 1998-05-01 | 1999-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| D00701 | A57 Liverpool Rd Bus Priorities and Cycling Facilities | 0.003 | 2000-01-01 | 2000-06-01 | 0.003 | 0.00016667 | 0.00016667 | 0.00016667 | 0.00016667 | 0.00016667 | 0.00016667 | 0.00016667 | 0.00016667 | 0.00016667 | 0.00016667 | 0.00016667 | 0.00016667 | 0.0011667
| D00703 | A56 Quality Bus Corridor | 0.32 | 2003-11-01 | 2004-12-01 | 0.121 | 0.101 | 0 | 0 | 0 | 0 | 0.018429 | 0.018429 | 0.018429 | 0.018429 | 0.018429 | 0.018429 | 0.018429 | 0.13786
| D00707 | Blackfriars St Improvement | 0.01 | 2004-11-01 | 2004-12-01 | 0.001 | 0 | 0 | 0 | 0 | 0 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0028571
|  | Central Station Study | .050 moved to chief execs central station |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.0071429 | 0.0071429 | 0.0071429 | 0.0071429 | 0.0071429 | 0.0071429 | 0.0071429
| summary | Public Transport Schemes | 0.333 |  |  | 0.125 | 0.10117 | 0.00016667 | 0.00016667 | 0.00016667 | 0.00016667 | 0.027167 | 0.027167 | 0.027167 | 0.027167 | 0.027167 | 0.027167 | 0.027167 | 0.14188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| D00802 | A666 Cycling Facilities | 0 | 2005-09-01 | 2005-11-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| D00803 | Barton Cycling Facilities | 0.05 | 2004-11-01 | 2005-01-01 | 0.005 | 0 | 0 | 0 | 0 | 0 | 0.017714 | 0.017714 | 0.017714 | 0.017714 | 0.017714 | 0.017714 | 0.017714 | 0.035429
| D00805 | Cycle Parking Facilities | 0.02 | 2004-09-01 | 2005-03-01 | 0.002 | 0 | 0 | 0 | 0 | 0 | 0.0028571 | 0.0028571 | 0.0028571 | 0.0028571 | 0.0028571 | 0.0028571 | 0.0028571 | 0.0057143
| D00806 | Sustrans Routes | 0.03 | 2005-01-01 | 2005-03-01 | 0.001 | 0 | 0 | 0 | 0 | 0 | 0.014286 | 0.014286 | 0.014286 | 0.014286 | 0.014286 | 0.014286 | 0.014286 | 0.028571
| D00807 | Cycling Projects Grant Fund | 0.02 | 2005-01-01 | 2005-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0.0035714 | 0.0035714 | 0.0035714 | 0.0035714 | 0.0035714 | 0.0035714 | 0.0035714 | 0.0071429
| summary | Schemes to Assist Cycling | 0.12 | 2004-04-01 | 2005-03-01 | 0.008 | 0 | 0 | 0 | 0 | 0 | 0.038429 | 0.038429 | 0.038429 | 0.038429 | 0.038429 | 0.038429 | 0.038429 | 0.076857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| D00050 | Pavement Improvements Pilot Works | 1 | [15 empty] | 0 |  |  | 1 |  |  | 0 |  | 1 | [16 empty] | 0 | funded from savings on tripping claims
summary | D07230-d07259 | Improvements to the Highway network | 0.25 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.071429 | 0.071429 | 0.071429 | 0.071429 | 0.071429 | 0.071429 | 0.071429 | 0.14286 |  |  |  |  | 0.25 |  |  | 0.25
D99999 7015 contains 0.159 bfwd, 0.500 highways improvement less overprogramming of 0.391 |  | Overprogramming | -0.232 |  |  |  | Profiled spend Mar: -0.232 | -0.232 | 4.522 |  |  |  | 0.159 | 0 |  | 4.681 | [16 empty] | 0 | .159 carry forwar cap receipts from 03/04 due to unused BCA
|  | HIGHWAYS - TOTAL | 26.565 |  |  | 7.718 | 5.0463 | 0.040417 | 0.040417 | 0.025417 | 0.053117 | 2.4254 | 2.5744 | 2.9484 | 2.4553 | 5.7658 | 2.2633 | 2.0703 | 9.9592 | 4.522 | 7.873 | 1 | 0 | 0.409 | 12.761 | 0 | 26.565 | 12.761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.761
SOCIAL SERVICES
| S00001 | Alterations to Property | 0.025 | 2004-09-01 | 2005-03-01 | 0.013 | 0 | 0 | 0 | 0 | 0 | 0.0035714 | 0.0035714 | 0.0035714 | 0.0035714 | 0.0035714 | 0.0035714 | 0.0035714 | 0.0071429 |  |  |  | 0.025 |  | 0 |  | 0.025 | [16 empty] | 0
| S00501 | IT for look after children | 0.053 | 2004-09-01 | 2005-03-01 | 0.006 | 0.005 | 0 | 0 | 0 | 0 | 0.0068571 | 0.0068571 | 0.0068571 | 0.0068571 | 0.0068571 | 0.0068571 | 0.0068571 | 0.018714 |  |  |  | 0.053 |  | 0 |  | 0.053 | [16 empty] | 0 | 0.006 receipt carry forward from 03/04
| S04004 | Mental health SCA (2002/2004) | 0.074 | 2004-09-01 | 2005-03-01 | 0.036 | 0.002 | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.011 | 0.011 | 0.022 | [5 empty] | 0 | 0.074 | 0.074 | [16 empty] | 0
| S04005 | Mental health SCA (2003) |  |  |  | 0.016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | [16 empty] | 0 | 0.074 PCT
| S04006 | Mental health SCE (R.) | 0.126 | 2004-04-01 | 2005-03-01 | 0.082 | 0 | 0 | 0 | 0 | 0 | 0.018 | 0.018 | 0.018 | 0.018 | 0.018 | 0.018 | 0.0177 | 0.036 |  | 0.126 |  |  |  | 0 |  | 0.126 | [16 empty] | 0
| S05004 | 262 Liverpool Road | 0.01 | 2005-01-01 | 2005-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0.01 |  |  |  |  | 0 |  | 0.01 | [16 empty] | 0
| S05005 | 20 Devonshire Road | 0.01 | complete |  | 0.004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0.01 |  |  |  |  | 0 |  | 0.01 | [16 empty] | 0
| S05052 | Barton Moss Expension (New Unit) | 0.003 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.003 | 0 |  |  |  |  | 0.003 | 0 |  | 0.003 | [16 empty] | 0
| S05103 | Brynheys - Car park | 0.01 | 2005-03-01 | 2005-03-01 | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 |  |  |  |  | 0.01 | 0 |  | 0.01
| S05106 | The Limes - Fire Safety | 0.028 | 2005-01-01 | 2005-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.012 | 0.013 | 0 | 0 | 0.025 |  |  |  | 0.003 | 0 |  | 0.028 | [16 empty] | 0
| S05107 | White Meadows - Fire Safety | 0.025 | 2005-01-01 | 2005-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.012 | 0.013 | 0 | 0 |  |  |  |  | 0.025 | 0 |  | 0.025 | [16 empty] | 0
| S05108 | The Withies New Lift | 0.01 | complete |  | 0.011 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.004 | 0.004 | 0.005 | 0.005 | 0 | 0 |  |  |  |  | 0.01 | 0 |  | 0.01
| S05301 | New Granville - Fire Safety & Safety Glazing | 0.018 | 2004-11-01 | 2005-02-01 | 0.002 | 0.002 | 0 | 0 | 0 | 0 | 0 | 0 | 0.022 | 0.022 | 0.022 | 0.023 | 0 | 0.002 | 0.018 |  |  |  |  | 0 |  | 0.018 | [16 empty] | 0
| S06054 | Alexandra House - Bathroom & Toilets | 0.091 | 2004-11-01 | 2005-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0.013 | 0.013 | 0.013 | 0.013 | 0.013 | 0.013 | 0.0134 | 0.026 | 0.05 |  |  |  | 0.041 | 0 |  | 0.091 | [16 empty] | 0
| S06101 | St Georges - Re-roofing & Car Park | 0.04 | 2005-01-01 | 2005-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.02 | 0.02 | 0 | 0 | 0.04 |  |  |  |  | 0 |  | 0.04 | [16 empty] | 0
| S06152 | Craig Hall - Re-roofing | 0.002 |  |  |  | 0.002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.002 |  |  |  | 0.002 |  | 0 |  | 0.002 | [16 empty] | 0
| S06153 | Waterside Resource Centre - Re-roofing | 0.001 |  |  |  | 0.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.001 |  |  |  | 0.001 |  | 0 |  | 0.001 | [16 empty] | 0
| S08060 | Refurbishment of Crompton House Reception |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | [16 empty] | 0
| S08054 | Improving Information Management 2002/2003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | [16 empty] | 0
| S08055 | Modernising ICT Infrastructure 3/4 |  |  |  | 0.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | [16 empty] | 0
| S08056 | Modernising ICT Infrastructure | 0.251 | 2004-04-01 | 2005-03-01 | 0.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0.042 | 0.042 | 0.042 | 0.042 | 0.042 | 0.041 | 0.042 |  |  |  |  | 0.1 | 0.151 |  | 0.251 | [15 empty] | 0.151 | 0.151 | management information grant
| S09001 | Beesley Green | 0.063 | 2004-11-01 | 2005-01-01 | 0.042 | 0.042 | 0 | 0 | 0 | 0 | 0 | 0 | 0.007 | 0.007 | 0.007 | 0 | 0 | 0.042 |  |  |  | 0.014 |  | 0.029 | 0.02 | 0.063 | [11 empty] | 0.029 |  |  |  |  | 0.029
| S09003 | Boothstown Community Centre | 0.109 | 2004-05-01 | 2004-08-01 | 0.059 | 0.029 | 0.008 | 0.008 | 0.008 | 0.008 | 0.008 | 0 | 0.012 | 0.012 | 0.012 | 0.004 | 0 | 0.069 | [5 empty] | 0.109 |  | 0.109 | [11 empty] | 0.109 |  |  |  |  | 0.109 | 0.020 community contributions
| S09004 | Guild Hall Community Centre | 0.112 |  |  | 0.124 | 0.069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.014 | 0.014 | 0.015 | 0 | 0.069 |  |  |  |  | 0.07 | 0.042 |  | 0.112 | [11 empty] | 0.042 |  |  |  |  | 0.042
| S09005 | Wardley Community Centre | 0.051 | 2004-03-31 | 2004-07-02 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.017 | 0.017 | 0.017 | 0 | 0 | 0 | [5 empty] | 0.002 | 0.049 | 0.051 | [11 empty] | 0.002 |  |  |  |  | 0.002 | community contribtuions 0.073
| S09006 | Kenyon Way - Replacement of heating system | 0.05 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0 | 0.01 | [5 empty] | 0 | 0.05 | 0.05 | [16 empty] | 0 | 0.003 community contributions, 0.070 DDA
| S09008 | Day Services Modernisation | 0.036 | 2004-06-01 | 2005-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0356 | 0 |  |  |  |  | 0.036 | 0 |  | 0.036 | [16 empty] | 0
| S09051 | Eccles Town Hall Office Move | 0.015 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.006 | 0.0014286 | 0.0014 | 0.0028571 |  |  |  | 0.005 | 0.01 | 0 |  | 0.015 | [16 empty] | 0
|  | SOCIAL SERVICES -TOTAL | 1.213 |  |  | 0.437 | 0.152 | 0.008 | 0.008 | 0.008 | 0.018 | 0.060857 | 0.10486 | 0.16686 | 0.19086 | 0.23043 | 0.20886 | 0.13353 | 0.35971 | 0.153 | 0.126 | 0 | 0.1 | 0.308 | 0.333 | 0.193 | 1.213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.182 | 0 | 0 | 0 | 0.151 | 0.333
0
|  | ENVIRONMENTAL SERVICES | [41 empty] | 0
| F00004 | Roadway Works - Cemeteries | 0.06 | 2004-09-01 | 2005-03-01 | 0.03 | 0.03 | 0 | 0 | 0 | 0 | 0.0042857 | 0.0042857 | 0.0042857 | 0.0042857 | 0.0042857 | 0.0042857 | 0.0042857 | 0.038571 |  |  |  |  | 0.06 |  |  | 0.06
| F00007 | Buille Hill Park Restoration | 0.174 | 2004-09-01 | 2005-03-01 | 0.006 | 0 | 0 | 0 | 0 | 0 | 0.024857 | 0.024857 | 0.024857 | 0.024857 | 0.024857 | 0.024857 | 0.024857 | 0.049714 |  |  |  |  | 0.174 | 0 |  | 0.174 | [16 empty] | 0
| F00008 | Headstones - Cemeteries | 0.072 | 2004-09-01 | 2005-03-01 | 0.062 | 0.032 | 0 | 0 | 0 | 0 | 0.0057143 | 0.0057143 | 0.0057143 | 0.0057143 | 0.0057143 | 0.0057143 | 0.0057143 | 0.043429 |  |  |  |  | 0.072 | 0 |  | 0.072 | [16 empty] | 0
| F00012 | Oakwood Play area | [16 empty] | 0 | [5 empty] | 0 |  | 0 | [16 empty] | 0 | section 106 from G Wimpey
| F00013 | Beechfarm | 0.106 | 2004-11-01 | 2004-12-01 |  | Profiled spend Dec: 0.106 | 0 | [5 empty] | 0.106 |  | 0.106 | [11 empty] | 0.106 |  |  |  |  | 0.106
| F00014 | Princes Park | 0.016 | 2004-09-01 | 2005-03-01 | 0.012 | 0.005 | 0 | 0 | 0 | 0 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0015714 | 0.0081429 | [5 empty] | 0 | 0.016 | 0.016 | [16 empty] | 0 | community contribution on 2802es
| F00015 | Poynt Chase | 0.005 | [15 empty] | 0 | [6 empty] | 0.005 | 0.005 | [17 empty] | section 106 £4551
| F00016 | Blackleach Drive, Walkden Play Area | 0.011 |  |  | 0.011 | 0.011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.011 | [6 empty] | 0.011 | 0.011 | [16 empty] | 0 | section 106 11k
| F00017 | Croal Irwell Access/Fencing | 0.024 | 2004-09-01 | 2005-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0.0034286 | 0.0034286 | 0.0034286 | 0.0034286 | 0.0034286 | 0.0034286 | 0.0034286 | 0.0068571 | [6 empty] | 0.024 | 0.024 | [16 empty] | 0 | section 106 24k
| F00018 | Sharp Street, Walkden | 0.04 | 2004-11-01 | 2005-01-01 |  | Profiled spend Jan: 0.02; Profiled spend Feb: 0.02 | 0 | [5 empty] | 0 | 0.04 | 0.04 | [17 empty] | section 106
| F00019 | Milner St, Swinton | 0.024 | [21 empty] | 0 | 0.024 | 0.024
| F00021 | Chestnut Ave Depot | 0.05 | 2004-09-01 | 2005-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0.0071429 | 0.0071429 | 0.0071429 | 0.0071429 | 0.0071429 | 0.0071429 | 0.0071429 | 0.014286 |  |  |  |  | 0.05 | 0 |  | 0.05 | [16 empty] | 0
| F00022 | Parks Infrastructure Improvements | 0.1 | 2004-09-01 | 2005-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0.014286 | 0.014286 | 0.014286 | 0.014286 | 0.014286 | 0.014286 | 0.014286 | 0.028571 |  |  |  |  | 0.1 | 0 |  | 0.1 | [16 empty] | 0
| F00023 | Recycling Bring Sites | 0.03 | 2004-09-01 | 2005-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0.0042857 | 0.0042857 | 0.0042857 | 0.0042857 | 0.0042857 | 0.0042857 | 0.0042857 | 0.0085714 |  |  |  |  | 0.03 | 0 |  | 0.03 | [16 empty] | 0
| F00024 | Crofters Heights site investigation | 0.033 | 2004-09-01 | 2005-03-01 | 0.019 | 0.015 | 0 | 0 | 0 | 0 | 0.002 | 0.002 | 0.002 | 0.002 | 0.002 | 0.002 | 0.002 | 0.019 |  | 0.033 |  |  |  | 0 |  | 0.033 | [16 empty] | 0
| F00025 | Peel Park | 0.024 | 2004-11-01 | 2004-12-01 |  | Profiled spend Dec: 0.024 | 0 | [5 empty] | 0 | 0.024 | 0.024 | [17 empty] | section 106
| F00026 | Boundary Road Irlam | 0.052 |  |  | 0.052 | [12 empty] | 0 | [5 empty] | 0 | 0.052 | 0.052 | [16 empty] | 0
|  | ENVIRONMENTAL SERVICES - TOTAL | 0.821 |  |  | 0.192 | 0.093 | 0 | 0 | 0 | 0 | 0.067571 | 0.067571 | 0.067571 | 0.19757 | 0.087571 | 0.087571 | 0.067571 | 0.22814 | 0 | 0.033 | 0 | 0 | 0.486 | 0.106 | 0.196 | 0.821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.106 | 0 | 0 | 0 | 0 | 0.106
|  | ARTS & LEISURE | [41 empty] | 0
| w00001 | Citywide investment programme | 0.195 | 2004-08-01 | 2006-03-01 | 0.016 | 0 | 0 | 0 | 0 | 0 | 0 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 |  |  | 0.195 |  |  | 0 |  | 0.195 | [17 empty] | 195k for 04/05 and again in 05/06 funded from DSO reveneu surplus £40k per year
|  | Conserving and Developing Ordsall Hall | 0.031 | [19 empty] | 0.005 | 0.026 | 0 |  | 0.031
| E05701 | Library Service - Computerisation | 0.02 | 2004-09-01 | 2005-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0028571 | 0.0028571 | 0.0028571 | 0.0028571 | 0.0028571 | 0.0028571 | 0.0028571 | 0.0057143 |  |  |  |  | 0.02 | 0 |  | 0.02 | [16 empty] | 0
| E05703 | Winton Community Library | 0.169 | 2004-01-01 | 2004-05-01 | 0.172 | 0.169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.169 |  |  |  | 0.008 |  | 0.161 |  | 0.169 |  |  |  | 0.161 | [12 empty] | 0.161 | .032 reduction in scheme to reflect dev services cost centre exp in 03/04
| E05705 | Hope Library office moves | 0.051 |  |  | 0.046 | 0.013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.013 |  |  |  |  | 0.013 | 0 | 0.038 | 0.051 | [16 empty] | 0 | 0.031hope hospital contribution, 0.005 DDA, 0.002 other contribution
| E05003 | Leisure Trust Consultancy |  |  |  | 0.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | [16 empty] | 0
| E05004 | SPACE Marlborough Road | 0.01 |  |  | 0.008 | 0.024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.024 | [5 empty] | 0.01 |  | 0.01 | [11 empty] | 0.01 |  |  |  |  | 0.01
| E05005 | SPACE Moorfield Road | 0.003 |  |  | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0.003 |  | 0.003 | [11 empty] | 0.003 |  |  |  |  | 0.003
| E05006 | SPACE St Peter's Primary | 0.003 |  |  | 0.008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0.003 |  | 0.003 | [11 empty] | 0.003 |  |  |  |  | 0.003
| E05007 | SPACE Dukesgate primary | 0.019 |  |  | 0.031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0.019 |  | 0.019 | [11 empty] | 0.019 |  |  |  |  | 0.019
| E05009 | Fit City Signage | 0.003 |  |  | 0.005 | 0.00025 | 0.00025 | 0.00025 | 0.00025 | 0.00025 | 0.00025 | 0.00025 | 0.00025 | 0.00025 | 0.00025 | 0.00025 | 0.00025 | 0.00175 |  |  |  |  | 0.003 | 0 |  | 0.003 | [16 empty] | 0
| E05010 | Cleavley playing fields |  |  |  | 0.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [16 empty] | 0
| E05030 | Cleavley Athletic Track | 0.226 | 2004-09-01 | 2005-03-01 | 0.147 | 0.132 | 0 | 0 | 0 | 0 | 0.013429 | 0.013429 | 0.013429 | 0.013429 | 0.013429 | 0.013429 | 0.013429 | 0.15886 |  |  |  |  | 0.091 | 0.135 |  | 0.226 | [15 empty] | 0.135 | 0.135 | £135k sport england
| E05016 | Jewish Orthodox Schools NOF |  |  |  | 0.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | [16 empty] | 0
| E05031 | DDA improvements | 0.474 | 2004-09-01 | 2005-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0.067714 | 0.067714 | 0.067714 | 0.067714 | 0.067714 | 0.067714 | 0.067714 | 0.13543 |  |  |  |  | 0.124 | 0.35 |  | 0.474 | [11 empty] | 0.35 |  |  |  |  | 0.35
| E05032 | Efficiency improvements-Pool filters | 0.027 | 2004-09-01 | 2005-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0038571 | 0.0038571 | 0.0038571 | 0.0038571 | 0.0038571 | 0.0038571 | 0.0038571 | 0.0077143 |  |  |  |  | 0.027 | 0 |  | 0.027 | [16 empty] | 0
| E05033 | Littleton Road Development | 0.398 | 2004-09-01 | 2005-03-01 | 0.069 | 0 | 0 | 0 | 0 | 0 | 0.066 | 0.066 | 0.066 | 0.066 | 0.066 | 0.066 | 0.066 | 0.132 |  |  |  |  | 0.212 | 0.186 |  | 0.398 | [10 empty] | 0.186 |  |  |  |  | 0 | 0.186 | £400k from Football foundation, £300k football association
| E05028 | Management Information System | 0.077 | 2004-09-01 | 2005-03-01 | 0.066 | 0.034 | 0 | 0 | 0 | 0 | 0.0061429 | 0.0061429 | 0.0061429 | 0.0061429 | 0.0061429 | 0.0061429 | 0.0061429 | 0.046286 |  |  |  |  | 0.077 | 0 |  | 0.077 | [16 empty] | 0
| E05029 | Ordsall Recreation Centre | 0.095 | 2004-09-01 | 2005-03-01 | 0.001 | 0 | 0 | 0 | 0 | 0 | 0.013571 | 0.013571 | 0.013571 | 0.013571 | 0.013571 | 0.013571 | 0.013571 | 0.027143 |  |  |  | 0.095 |  | 0 |  | 0.095 | [16 empty] | 0
| E05011 | Lledr Hall NOF/PE | 0.081 | 2004-09-01 | 2005-03-01 | 0.033 | 0.007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.321 | 0.321 | 0.321 | 0.007 | [5 empty] | 0.081 |  | 0.081 | [11 empty] | 0.081 |  |  |  |  | 0.081
| E05013 | Irlam Pool NOF/PE | 0.106 | 2004-09-01 | 2005-03-01 | 0.003 | 0.002 | 0 | 0 | 0 | 0 | 0.016429 | 0.016429 | 0.016429 | 0.016429 | 0.016429 | 0.016429 | 0.016429 | 0.034857 | [5 empty] | 0.106 |  | 0.106 | [11 empty] | 0.106 |  |  |  |  | 0.106
| E05015 | Clarendon Pool NOF/PE | 0.175 | 2004-09-01 | 2005-03-01 | 0.001 | [18 empty] | 0.175 |  | 0.175 | [11 empty] | 0.175 |  |  |  |  | 0.175
| E05017 | Irlam Bulkehead | 0.082 | 2004-09-01 | 2005-03-01 | [19 empty] | 0.082 |  | 0.082 | [11 empty] | 0.082
| E05019 | St Ambrose Barlow NOF/PE | 0.075 | 2004-09-01 | 2005-03-01 | 0.06 | [18 empty] | 0.075 |  | 0.075 | [11 empty] | 0.075 |  |  |  |  | 0.075
| E05021 | St Patricks | 0.075 | 2004-09-01 | 2005-03-01 | [19 empty] | 0.075 |  | 0.075 | [11 empty] | 0.075
| E05025 | Portfolio Manager/ Comm sports Dev Officers | 0.05 | 2004-09-01 | 2005-03-01 | [19 empty] | 0.05 |  | 0.05 | [11 empty] | 0.05
| E05034 | Jewish School Talmud Torah | 0.015 | 2004-09-01 | 2005-03-01 | [19 empty] | 0.015 |  | 0.015 | [11 empty] | 0.015
| E05035 | Jewish School Girls School | 0.001 | 2004-09-01 | 2005-03-01 | [19 empty] | 0.001 |  | 0.001 | [11 empty] | 0.001
| E05036 | Jewish School | 0.143 | 2004-09-01 | 2005-03-01 | [19 empty] | 0.143 |  | 0.143 | [11 empty] | 0.143
| E05027 | Worsley Pool NOF/PE | 0.071 | 2004-09-01 | 2005-03-01 | 0.017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0.071 |  | 0.071 | [11 empty] | 0.071 |  |  |  |  | 0.071
|  | ARTS & LEISURE - TOTAL | 2.675 |  |  | 0.696 | 0.38125 | 0.00025 | 0.00025 | 0.00025 | 0.00025 | 0.19025 | 0.22025 | 0.22025 | 0.22025 | 0.54125 | 0.54125 | 0.54125 | 0.79275 | 0 | 0 | 0.195 | 0.108 | 0.593 | 1.741 | 0.038 | 2.675 | 0 | 0 | 0 | 0.161 | 0 | 0 | 0 | 0 | 0 | 0 | 0.186 | 0.572 | 0 | 0 | 0 | 0.135 | 1.054
0
|  | CORPORATE SERVICES | [41 empty] | 0
| c00064 | Council Tax benefits replacement system | 0.51 |  |  | 0.3 | 0.0425 | 0.0425 | 0.0425 | 0.0425 | 0.0425 | 0.0425 | 0.0425 | 0.0425 | 0.0425 | 0.0425 | 0.0425 | 0.0425 | 0.2975 |  |  | 0.51 |  |  | 0 |  | 0.51 | [17 empty] | from customer services revenue budget 51k per year
planned spend on c99999 7027 |  | Swinton Library Temporary Relocation | 0.186 | 2004-07-05 | 2006-09-23 | 0 | 0.002 | 0.004 | 0.004 | 0.065 | 0.023 | 0.016 | 0.016 | 0.02 | 0.016 | 0.02 | 0 | 0 | 0.13 | [5 empty] | 0 | 0.186 | 0.186 | [17 empty] | lift enabling fund
| C00063 | Relocation of Data centre and provision of UPSS | 0.2 | 2004-11-01 | 2005-02-01 | 0 | Profiled spend Nov: 0.05; Profiled spend Dec: 0.05; Profiled spend Jan: 0.05; Profiled spend Feb: 0.05; Profiled spend Mar: 0 | 0 |  |  | 0.2 |  |  | 0 |  | 0.2 | [17 empty] | from savings in maintenance contract and saving on oralce licenses
| C00061 | Lift Company | 0 |  |  | 0 | [12 empty] | 0 | [5 empty] | 0 |  | 0
| C00059 | Office refurbishment/relocations unallocated | 0.732 | 2005-03-01 | 2005-03-01 | 0 | Profiled spend Mar: 0.732 | 0 |  |  |  |  | 0.732 | 0 |  | 0.732 | [16 empty] | 0
d5106 | C00062 | Highways Depot | 0.041 | 2005-03-01 | 2005-03-01 | 0 | 0.0034167 | 0.0034167 | 0.0034167 | 0.0034167 | 0.0034167 | 0.0034167 | 0.0034167 | 0.0034167 | 0.0034167 | 0.0034167 | 0.0034167 | 0.0034167 | 0.023917 |  |  |  |  | 0.041 | 0 |  | 0.041
|  | VERs | 0.7 | 2005-03-01 | 2005-03-01 | 0.259 | 0.058333 | 0.058333 | 0.058333 | 0.058333 | 0.058333 | 0.058333 | 0.058333 | 0.058333 | 0.058333 | 0.058333 | 0.058333 | 0.058333 | 0.40833 |  |  |  |  | 0.7 | 0 |  | 0.7
| C00059 | Capitalisation of Revenue | 3 | 2005-03-01 | 2005-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  |  | 3 | 0 |  | 3 | [16 empty] | 0
|  | CORPORATE SERVICES - TOTAL | 5.369 |  |  | 0.559 | 0.10625 | 0.10825 | 0.10825 | 0.16925 | 0.12725 | 0.12025 | 0.12025 | 0.17425 | 0.17025 | 0.17425 | 0.15425 | 3.8362 | 0.85975 | 0 | 0 | 0.71 | 0 | 4.473 | 0 | 0.186 | 5.369 | [16 empty] | 0
0
|  | CHIEF EXECUTIVE | [41 empty] | 0
New Deal for Communities
| A00402 | Business Security Grant | 0.064 | 2004-09-01 | 2005-03-01 | 0.002 | 0.001 | 0 | 0 | 0 | 0 | 0.009 | 0.009 | 0.009 | 0.009 | 0.009 | 0.009 | 0.009 | 0.019 |  |  |  |  | 0.014 | 0.05 |  | 0.064 | [10 empty] | 0.05 | [5 empty] | 0.05
| A00405 | CCTV | 0.176 | 2004-09-01 | 2005-03-01 | 0.094 | 0.087 | 0 | 0 | 0 | 0 | 0.012714 | 0.012714 | 0.012714 | 0.012714 | 0.012714 | 0.012714 | 0.012714 | 0.11243 | [5 empty] | 0.176 |  | 0.176 | [10 empty] | 0.176 | [5 empty] | 0.176
| A00404 | Salford Play Resource Unit | 0.17 | 2004-09-01 | 2005-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0.024286 | 0.024286 | 0.024286 | 0.024286 | 0.024286 | 0.024286 | 0.024286 | 0.048571 | [5 empty] | 0.17 |  | 0.17 | [10 empty] | 0.17 | [5 empty] | 0.17
| A00409 | Sports Village |  |  |  | 0.001
| A00410 | Riverside Bowling | 0.217 | 2004-09-01 | 2005-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0.031 | 0.031 | 0.031 | 0.031 | 0.031 | 0.031 | 0.031 | 0.062 | [5 empty] | 0.217 |  | 0.217 | [10 empty] | 0.217 | [5 empty] | 0.217
| A00411 | START 2 Healthy Options | 0.006 | 2004-09-01 | 2005-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0.00085714 | 0.00085714 | 0.00085714 | 0.00085714 | 0.00085714 | 0.00085714 | 0.00085714 | 0.0017143 | [5 empty] | 0.006 |  | 0.006 | [10 empty] | 0.006 | [5 empty] | 0.006
| A00413 | Physical Design Strategy |  |  |  | 0.016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [24 empty] | 0
| A00009 | Environ/Shop Front Improvements & Expanding Boundaries | 0.7 | 2004-09-01 | 2005-03-01 | 0.06 | 0.004 | 0 | 0 | 0 | 0 | 0.099429 | 0.099429 | 0.099429 | 0.099429 | 0.099429 | 0.099429 | 0.099429 | 0.20286 |  |  |  |  | 0.025 | 0.675 |  | 0.7 | [9 empty] | 0.35 | 0.225 |  |  |  |  | 0.1 | 0.675 | .100 NRF, 0.025 cap receipts from chapel st regeneration
|  | Gateway |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 | [16 empty] | 0
| A40100 | Greengate | 0.025 | [21 empty] | 0.025 |  | 0.025 | [12 empty] | 0.025
| A40101 | Transport Strategy | 0.025 | [21 empty] | 0.025 |  | 0.025 | [12 empty] | 0.025
| A40102 | Not the Aquarium | 0.012 | [21 empty] | 0.012 |  | 0.012 | [12 empty] | 0.012
| A40103 | Crescent Station | 0.059 | [21 empty] | 0.059 |  | 0.059 |  | 0.059
| A40300 | Policing projects | 0.03 | [21 empty] | 0.03 |  | 0.03 | [15 empty] | 0.03 |  | 0.030 NRF
| A40301 | Innovation Park | 0.015 | [21 empty] | 0.015 |  | 0.015 | [15 empty] | 0.015 |  | 0.015 NRF
| A40200 | Project Management Fees | 0.128 |  |  | 0.093 | [18 empty] | 0.06 | 0.068 | 0.128 | [12 empty] | 0.06
| A40201 | Project Design Fees | 0.252 |  |  | 0.095 | [13 empty] | 0.05 |  |  |  | 0.05 | 0 | 0.152 | 0.252 | [17 empty] | .152 from GMPTE, 0.050 from highways cap prog block 3
|  | Central Station | [22 empty] | 0 |  | 0
| A20001 | SPV set up costs |  |  |  | 0.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [16 empty] | 0
| A20002 | SPV start up costs |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [16 empty] | 0
| A20005 | Aquarium Attraction |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [24 empty] | 0
| A20006 | Project LDC |  |  |  | 0.011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [16 empty] | 0
| A20007 | Medialink |  |  |  | 0.004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [16 empty] | 0
| A20008 | Salford Innovation Park |  |  |  | 0.031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [16 empty] | 0
| A21000 | General Competition Costs |  |  |  | 0.001 | [37 empty] | 0
| A21002 | Panel Costs |  |  |  | 0.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [25 empty] | 0
| A21003 | Fleisham/Creative Concern |  |  |  | 0.004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [25 empty] | 0
| A21006 | Consortia Fees |  |  |  | 0.005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [25 empty] | 0
|  | International Competition | [41 empty] | 0
| A30001 | Liverpool Road Eccles |  |  |  | 0.001 | [12 empty] | 0 | [24 empty] | 0
|  | Site Assembly / Acquisition Temp Treatment Works | 0.195 | 2004-09-01 | 2005-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0.027857 | 0.027857 | 0.027857 | 0.027857 | 0.027857 | 0.027857 | 0.027857 | 0.055714 | [5 empty] | 0.195 |  | 0.195 | [10 empty] | 0.195 | [5 empty] | 0.195
|  | Irwell Corridor EDZ | 0.425 | 2004-09-01 | 2005-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0.060714 | 0.060714 | 0.060714 | 0.060714 | 0.060714 | 0.060714 | 0.060714 | 0.12143 | [5 empty] | 0.425 |  | 0.425 | [9 empty] | 0.225 | [5 empty] | 0.2 | 0.425 | £0.200m private contributions
|  | Identifying Oppurtunities | 0.03 | 2004-09-01 | 2005-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0.0042857 | 0.0042857 | 0.0042857 | 0.0042857 | 0.0042857 | 0.0042857 | 0.0042857 | 0.0085714 | [5 empty] | 0.03 |  | 0.03 | [10 empty] | 0.03 | [5 empty] | 0.03
|  | Living Environment Team | 0.124 | 2004-09-01 | 2005-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0.017714 | 0.017714 | 0.017714 | 0.017714 | 0.017714 | 0.017714 | 0.017714 | 0.035429 | [5 empty] | 0.124 |  | 0.124 | [10 empty] | 0.124 | [5 empty] | 0.124
|  | CHIEF EXECUTIVE - TOTAL | 2.653 |  |  | 0.42 | 0.092 | 0 | 0 | 0 | 0 | 0.28786 | 0.28786 | 0.28786 | 0.28786 | 0.28786 | 0.28786 | 0.28786 | 0.66771 | 0.05 | 0 | 0 | 0 | 0.089 | 2.294 | 0.22 | 2.653 | 0 | 0.059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.575 | 1.193 | 0 | 0.122 | 0 | 0 | 0.345 | 2.068
DEVELOPMENT SERVICES
d99999 7027 contains unallocated grouped spend |  | Liverpool Road Area Eccles | 0.1 | 2004-09-01 | 2005-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0.014286 | 0.014286 | 0.014286 | 0.014286 | 0.014286 | 0.014286 | 0.014286 | 0.028571 |  |  |  |  | 0 | 0.1 |  | 0.1 | [15 empty] | 0.1 | 0.1 | £0.100m Neighbourhood renewal fund
on sap d99999 7027 |  | Restoration of Manchester, Bolton and Bury Canal | 0.04 | 2004-09-01 | 2005-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0.0057143 | 0.0057143 | 0.0057143 | 0.0057143 | 0.0057143 | 0.0057143 | 0.0057143 | 0.011429 |  |  |  |  | 0.04 | 0 |  | 0.04 | [16 empty] | 0
| D01027 | King Street Depot |  |  |  | 0 | [18 empty] | 0 |  | 0 | [16 empty] | 0
|  | Acquisitions | [22 empty] | 0 |  | 0 | [16 empty] | 0
| D01040 | By pass construction |  |  |  | 0.003 | [18 empty] | 0 |  | 0
|  | Eccles Town Centre | [22 empty] | 0 |  | 0
| D01050 | Relocation Eccles Permanent Market |  |  |  | 0 | [18 empty] | 0 |  | 0 | [16 empty] | 0
|  | Relocation Eccles Market | [22 empty] | 0 |  | 0 | [16 empty] | 0
| D01075 | Relocation Fees Eccles Town Hall |  |  |  | 0 | [18 empty] | 0 |  | 0 | [16 empty] | 0
|  | Relocation Fees Eccles Town Hall | [22 empty] | 0 |  | 0 | [16 empty] | 0
| D01080 | CPO Inquiry Costs/ Fees |  |  |  | 0 | [18 empty] | 0 |  | 0 | [16 empty] | 0
|  | CPO Inquiry Costs/ Fees | [22 empty] | 0 |  | 0 | [16 empty] | 0
|  | Eccles Town Centre | 0.589 | 2004-09-01 | 2005-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0.084143 | 0.084143 | 0.084143 | 0.084143 | 0.084143 | 0.084143 | 0.084143 | 0.16829 |  |  |  |  | 0.589 | 0 |  | 0.589 | [16 empty] | 0
| D01100 | Phase One |  |  |  | 0.009 | [18 empty] | 0 |  | 0 | [16 empty] | 0
| D01101 | Phase Two |  |  |  | 0.002 | [18 empty] | 0 |  | 0 | [16 empty] | 0
|  | Eccles Town Hall | 0 |  |  | 0.011 | [18 empty] | 0 |  | 0 | [16 empty] | 0
| not on sap yet | Trinity Park Improvements | 0.07 | 2005-01-01 | 2005-03-01 |  | Profiled spend Jan: 0.01; Profiled spend Feb: 0.05; Profiled spend Mar: 0.01 | 0 |  |  |  |  | 0.038 | 0.02 | 0.012 | 0.07 | [13 empty] | 0.02 |  |  | 0.02 | section 106 from development of site of former Lima public house
| D01428 | Chapel Street Web Site |  |  |  | 0.001 | [18 empty] | 0 |  | 0 | [16 empty] | 0
| D01425 | Other Consultants Fees |  |  |  | 0.002 | [18 empty] | 0 |  | 0 | [16 empty] | 0
| D01450 | Harold Riley Archive Centre |  |  |  | 0.009 | [18 empty] | 0 |  | 0 | [16 empty] | 0
| D01500 | Replacement of Adelphi Place |  |  |  | 0.009 | [18 empty] | 0 |  | 0
|  | Harold Riley Archive Centre | [22 empty] | 0 |  | 0 | [16 empty] | 0
|  | Chapel Street | 0.426 | 2004-09-01 | 2005-03-01 | 0.021 | 0.011 | 0 | 0 | 0 | 0 | 0.068 | 0.068 | 0.068 | 0.068 | 0.068 | 0.068 | 0.068 | 0.147 |  |  |  |  | 0.426 | 0 |  | 0.426 | [16 empty] | 0
|  | Countryside Programme | 0.01 | 2004-09-01 | 2005-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0028571 |  |  |  |  | 0.01 | 0 |  | 0.01 | [16 empty] | 0
|  | Barton SES | 0.075 | 2004-09-01 | 2005-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0.010714 | 0.010714 | 0.010714 | 0.010714 | 0.010714 | 0.010714 | 0.010714 | 0.021429 |  |  |  |  | 0.075 | 0 |  | 0.075 | [16 empty] | 0
|  | LIVIA | 0.069 | 2004-09-01 | 2005-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0.0098571 | 0.0098571 | 0.0098571 | 0.0098571 | 0.0098571 | 0.0098571 | 0.0098571 | 0.019714 |  |  |  |  | 0.006 | 0.063 |  | 0.069 | [12 empty] | 0.052 |  |  | 0.011 | 0.063
| D02051 | Quays Campus | 0.1 | 2004-07-01 | 2004-07-01 | 0.155 | [17 empty] | 0.1 | 0 |  | 0.1 | [16 empty] | 0
|  | Ordsall | [22 empty] | 0 |  | 0 | [16 empty] | 0
| D03006 | Hilton Lane Ph 2 |  |  |  | 0.003 | [18 empty] | 0 |  | 0
|  | Engllish Partnership | [22 empty] | 0 |  | 0
| D03501 | Pendleton Church Area Study |  |  |  | 0.08 | [18 empty] | 0 |  | 0 | [16 empty] | 0
| D03502 | Highway & Community Safety Imp Works | 0.03 | 2004-09-01 | 2005-03-01 | 0.011 | 0 | 0 | 0 | 0 | 0 | 0.0042857 | 0.0042857 | 0.0042857 | 0.0042857 | 0.0042857 | 0.0042857 | 0.0042857 | 0.0085714 | [5 empty] | 0.03 |  | 0.03 | [10 empty] | 0.03 | [5 empty] | 0.03
| D03503 | Minor Works Fund | 0.01 | 2004-09-01 | 2005-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0014286 | 0.0028571 | [5 empty] | 0.01 |  | 0.01 | [10 empty] | 0.01
| D03504 | Site Assembly (Acquisition) |  |  |  | 0.001 | [18 empty] | 0 |  | 0 | [16 empty] | 0
| D03505 | Physical design strategy |  |  |  | 0.003 | [18 empty] | 0 |  | 0
| D03506 | Mini Bus Project | 0.014 | 2004-09-01 | 2005-03-01 | 0.001 | 0.0011667 | 0 | 0 | 0 | 0 | 0.002 | 0.002 | 0.002 | 0.002 | 0.002 | 0.002 | 0.0011667 | 0.0051667 | [5 empty] | 0.014 |  | 0.014 | [10 empty] | 0.014 | [5 empty] | 0.014
| D03507 | Littleton Road Sports Village |  |  |  | 0.006 | [18 empty] | 0 |  | 0 | [16 empty] | 0
|  | New Deal for Communities | [22 empty] | 0 |  | 0 | [16 empty] | 0
| D04006 | Clarendon Park |  |  |  | 0.001413 | [18 empty] | 0 |  | 0 | [16 empty] | 0
|  | SRB1 | [22 empty] | 0 |  | 0 | [16 empty] | 0
|  | SRB2 | 0.003 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.00042857 | 0.00042857 | 0.00042857 | 0.00042857 | 0.00042857 | 0.00042857 | 0.00042857 | 0.00085714 |  |  |  |  | 0.003 | 0 |  | 0.003 | [16 empty] | 0
| D04044 | Industrial Estates CCTV |  |  |  | 0 | [18 empty] | 0 |  | 0 | [16 empty] | 0
|  | SRB3 | [22 empty] | 0 |  | 0 | [16 empty] | 0
| D05004 | Digital World Centre Phase 2 |  |  |  | 0.148 | [18 empty] | 0 |  | 0 | [16 empty] | 0
|  | ERDF Schemes | 0.148 |  |  | 0.148 | 0.148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.148 | [5 empty] | 0.148 |  | 0.148 | [9 empty] | 0.148 | [6 empty] | 0.148
| D05502 | Little Moss Farm |  |  |  | 0 | [18 empty] | 0 |  | 0 | [16 empty] | 0
|  | Red Rose Schemes | [22 empty] | 0 |  | 0 | [16 empty] | 0
| D06066 | Robin Hood Sidings |  |  |  | 0.0088545 | [18 empty] | 0 |  | 0 | [16 empty] | 0
| D06068 | Granyte Acquisition |  |  |  | 0.002 | [18 empty] | 0 |  | 0 | [16 empty] | 0
| D06069 | Acquisition Cleminson Street |  |  |  | 0.023 | [18 empty] | 0 |  | 0 | [16 empty] | 0
|  | NWDA Headroom Projects |  |  |  | 0.033854 | [18 empty] | 0 |  | 0 | [16 empty] | 0
| D06101 | Broadwalk Resource Unit |  |  |  | 0 | [18 empty] | 0 |  | 0 | [16 empty] | 0
| D06103 | Disposal general associated costs |  |  |  | 0.003175 | [18 empty] | 0 |  | 0 | [16 empty] | 0
| D06107 | Demolition Greenwood School |  |  | 2004-12-01 | 0.002 | [18 empty] | 0 |  | 0 | [16 empty] | 0
| D06108 | Demolition Windsor School |  |  |  | 0 | [18 empty] | 0 |  | 0 | [16 empty] | 0
| D06109 | Disposal Chasley Field |  |  |  | 0.0041 | [18 empty] | 0 |  | 0 | [16 empty] | 0
| D06110 | Disposal Buille Hill Mining Museum
| D06111 | Disposal Springfield Lane |  |  |  | 0.009 | [18 empty] | 0 |  | 0 | [16 empty] | 0
| D06112 | Works at Taylorson Street |  |  |  | 0.007 | [18 empty] | 0 |  | 0 | [16 empty] | 0
| D06113 | Kersal High School |  |  | 2005-03-01 | 0.014 | [18 empty] | 0 |  | 0 | [16 empty] | 0
| D06114 | Brentnal High School |  |  | 2005-09-01 | 0 | [18 empty] | 0 |  | 0 | [16 empty] | 0
| D06116 | PCL 101/115 Chapel St |  |  |  | 0.002
0 | D06117 | Salford Shopping City |  |  | 2005-03-01 | 0.002 | [18 empty] | 0 |  | 0 | [16 empty] | 0
| D06119 | Islington Way/Park st Security Measures |  |  |  | 0.001 | [18 empty] | 0 |  | 0 | [16 empty] | 0
on sap d99999 7027 |  | Disposal Costs | 0.044275 |  |  | 0.044275 | Profiled spend Apr: 0.044275 | 0.044275 |  |  |  |  | 0.044275 | 0 |  | 0.044275 | [16 empty] | 0
empty c00060 | D07008 | ORDSALL NEIGH.OFFICE WORKS | 0.01 | 2004-09-01 | 2005-03-01 | 0.005 | 0.002 | 0 | 0 | 0 | 0 | 0.00071429 | 0.00071429 | 0.00071429 | 0.00071429 | 0.00071429 | 0.00071429 | 0.00071429 | 0.0034286 |  |  |  | 0 | 0.01 | 0 | 0 | 0.01 |  |  |  | 0 | [12 empty] | 0 | 0.015 outstanding fire insurance money
| D07009 | Safety Camera partnership |  |  |  | 0.001014 | [18 empty] | 0 |  | 0 | [16 empty] | 0
| D07010 | Office relocation The Parade |  |  |  | 0.006 | [18 empty] | 0 |  | 0
| D07011 | OFFICE RELOCATION ST JAMES HOUSE | 0.035 |  |  | 0.038 | 0.041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.041 |  |  |  |  | 0.035 | 0 |  | 0.035
| D07012 | Relocation of Tourist Information Centre | 0.024 |  |  | 0.022 | 0.023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.023 |  |  |  |  | 0.024 | 0 |  | 0.024
| D07013 | Relocation of Soc servs to Emerson House | 0.08 | 2004-12-01 | 2005-02-01 |  | Profiled spend Dec: 0.013; Profiled spend Jan: 0.013; Profiled spend Feb: 0.013; Profiled spend Mar: 0.013 | 0 | [5 empty] | 0 | 0.08 | 0.08 | [17 empty] | 0.080 Lift enabling fund
|  | Miscellaneous | [22 empty] | 0 |  | 0 | [16 empty] | 0
| D07300 | Christ Church - Consultants Fees |  |  |  | 0.001 | [18 empty] | 0 |  | 0
| D08018 | Salford Shopping food retail development |  |  |  | 0.007 | [18 empty] | 0 |  | 0
| D08053 | Salford Methodist Church Design comp/n |  |  |  | 0.014 | [18 empty] | 0 |  | 0
|  | Salford Shopping food retail development |  |  |  | 0.022 | [18 empty] | 0 |  | 0
| D08004 | Seedley/Langworthy urban designer |  |  |  | 0.001 | [18 empty] | 0 |  | 0
| D08013 | Ordsall Hall Brief framing |  |  |  | 0.001 | [18 empty] | 0 |  | 0
| D08014 | Eccles Town Hall Auditorium | 0.024 | 2004-09-01 | 2005-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0.0034286 | 0.0034286 | 0.0034286 | 0.0034286 | 0.0034286 | 0.0034286 | 0.0034286 | 0.0068571 |  |  |  |  | 0.024 | 0 |  | 0.024 | [16 empty] | 0
| D08026 | Higher Broughton Regeneration Strategy | 0.076 | 2004-09-01 | 2005-03-01 | 0.045 | 0.044 | 0 | 0 | 0 | 0 | 0.0045714 | 0.0045714 | 0.0045714 | 0.0045714 | 0.0045714 | 0.0045714 | 0.0045714 | [6 empty] | 0 | 0.076 | 0.076 | [16 empty] | 0 | 0.076 other contributions
| D08029 | Security CCTV Home Office |  |  |  | 0.00084 | [18 empty] | 0 |  | 0 | [16 empty] | 0
| D08030 | Manchester/Bolton Canal Restoration |  |  |  | 0.002
| D08031 | Chapel Street Plans and Designs |  |  |  | 0.001 | [18 empty] | 0 |  | 0
| D08034 | Swinton Desigin Plans |  |  |  | 0.008 | [18 empty] | 0 |  | 0 | [16 empty] | 0
| D08035 | Oakwood Section 106 | 0.064 | 2004-06-14 | 2004-08-06 | 0.052 | 0 | 0 | 0 | 0.027 | 0.037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.064 | [5 empty] | 0 | 0.064 | 0.064 | [16 empty] | 0 | section 106 from G Wimpey
| D08036 | Lift Project |  |  |  | 0.016 | [18 empty] | 0 |  | 0 | [16 empty] | 0
| D08037 | Salford Vision Plan |  |  |  | 0.001 | [18 empty] | 0 |  | 0
| D08038 | Royal Chelsea Hospital Site |  |  |  | 2.925e-05 | [18 empty] | 0 |  | 0 | [16 empty] | 0
| D08040 | Salford Sports Village |  |  |  | 0.035 | [18 empty] | 0 |  | 0 | [16 empty] | 0
| D08045 | Ordsall Primary School |  |  |  | 0.01 | [18 empty] | 0 |  | 0 | [16 empty] | 0
| D08047 | Wellington Employment Park |  |  |  | -0.001 | [18 empty] | 0 |  | 0 | [16 empty] | 0
| D08048 | New Leaf - Worsley Delph |  |  |  | 0.001 | [18 empty] | 0 |  | 0
| D08051 | Newlands Initiative |  |  |  | 0.001 | [18 empty] | 0 |  | 0
| D08052 | Walkden Pool Refurbishment |  |  |  | 0.01 | [18 empty] | 0 |  | 0 | [16 empty] | 0
| D08055 | Primary School Review - Grosvenor Road |  |  |  | 0.013 | [18 empty] | 0 |  | 0 | [16 empty] | 0
| D08056 | Primary School Review - Wharton PS |  |  |  | 0.004 | [18 empty] | 0 |  | 0 | [16 empty] | 0
| D08057 | Primary School Review - Boothtown Meth't |  |  |  | 0.004 | [18 empty] | 0 |  | 0 | [16 empty] | 0
| D08058 | Primary School Review - St Andrews B'twn |  |  |  | 0.002 | [18 empty] | 0 |  | 0 | [16 empty] | 0
| D08060 | Chapel Street - Pedestrianisation |  |  |  | 0.003 | [18 empty] | 0 |  | 0 | [16 empty] | 0
| D08061 | East Ordsal lane/Trintiy Way |  |  |  | 0.003 | [18 empty] | 0 |  | 0 | [16 empty] | 0
| D08062 | South Chapel Street - Footpath repair |  |  |  | 0.003
| D08063 | Eccles Car Park - Security |  |  |  | 0.008 | [18 empty] | 0 |  | 0
| D08064 | City Academy-Verdant lane survey |  |  |  | 0.001
on sap d99999 7027 |  | Advance Fees | 0.12787 |  |  | 0.22487 | Profiled spend Apr: 0.22487 | 0.22487 |  |  |  |  | 0.12787 | 0 |  | 0.12787 | [16 empty] | 0
| D07200-d07229 | DDA Buildings | 0.17 |  |  | 0.001 | [17 empty] | 0.17 | 0 |  | 0.17 | [16 empty] | 0
| D07260-D07299 | DDA Footpaths | 0.5 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.024286 | 0.024286 | 0.024286 | 0.024286 | 0.024286 | 0.024286 | 0.024286 | 0.048571 |  |  |  |  | 0.5 | 0 |  | 0.5 | [16 empty] | 0
|  | DEVELOPMENT SERVICES - TOTAL | 2.8391 |  |  | 0.84243 | 0.53931 | 0 | 0 | 0.027 | 0.037 | 0.23529 | 0.23529 | 0.23529 | 0.24829 | 0.25829 | 0.29829 | 0.25745 | 1.0207 | 0 | 0 | 0 | 0 | 2.2221 | 0.385 | 0.232 | 2.8391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.148 | 0.054 | 0 | 0.052 | 0.02 | 0 | 0.111 | 0.385
|  | 04/05 PROGRAMME TOTAL | 105.0271 |  |  | 30.4143 | 16.3711 | 0.18692 | 0.23592 | 0.50892 | 3.3016 | 10.9417 | 10.8817 | 10.9508 | 10.5817 | 14.0249 | 10.5258 | 19.2067 | 41.7895 | 14.425 | 8.032 | 1.905 | 0.437 | 14.4481 | 47.574 | 18.206 | 105.0271 | 12.761 | 4.928 | 2.59 | 0.947 | 0 | 2.102 | 0 | 0.73 | 1.602 | 0.801 | 3.762 | 1.062 | 0.386 | 13.028 | 0 | 2.188 | 46.661
|  | Education slippage | [17 empty] | 0.425 |  |  |  | -0.425 |  |  | 0
|  | EFFECT OF 03/04 OUTTURN | 2.67 |  |  | 2.67 | [12 empty] | 2.67 | 0 | 0 | 0 | 0 | 0 | 4.304 | 0.591 | 4.895 | 0 | 0 | 0 | 0.099 | 0 | 0 | 0 | 0 | 0 | 0.019 | 0 | 0.266 | 0.198 | 3.617 | 0 | 0.105 | 4.304
|  | PROGRAMME TOTAL | 107.6971 |  |  | 33.0843 | 16.3711 | 0.18692 | 0.23592 | 0.50892 | 3.3016 | 10.9417 | 10.8817 | 10.9508 | 10.5817 | 14.0249 | 10.5258 | 19.2067 | 44.4595 | 14.85 | 8.032 | 1.905 | 0.437 | 14.0231 | 51.878 | 18.797 | 109.9221 | 12.761 | 4.928 | 2.59 | 1.046 | 0 | 2.102 | 0 | 0.73 | 1.602 | 0.82 | 3.762 | 1.328 | 0.584 | 16.645 | 0 | 2.293 | 50.965
Timing adjustments
|  | HMRF | [22 empty] | 3.617 |  | 3.617 | [13 empty] | 3.617 |  |  | 3.617
|  | NWDA | [22 empty] | 0.198 |  | 0.198 | [12 empty] | 0.198 |  |  |  | 0.198
|  | surestart | [22 empty] | 0.02 |  | 0.02 |  |  |  | 0.02 | [12 empty] | 0.02
|  | ERDF | [22 empty] | 0.019 |  | 0.019 | [9 empty] | 0.019 | [6 empty] | 0.019
|  | School Contributions | [22 empty] | 0 | 0.176 | 0.176 | [16 empty] | 0
|  | Insurance Clifton Primary / Broadwalk | [22 empty] | 0 | 0.262 | 0.262 | [16 empty] | 0
|  | Dept of Health Barton Moss Expansion | [22 empty] | 0.017 |  | 0.017 | [15 empty] | 0.017 | 0.017
|  | Sure Start (Winton linrary) | [22 empty] | 0.079 |  | 0.079 |  |  |  | 0.079 | [12 empty] | 0.079
|  | Beesley Green NOF | [22 empty] | 0.021 |  | 0.021 | [11 empty] | 0.021 |  |  |  |  | 0.021
|  | air pollution LA contributions on 2802 | [23 empty] | 0.005 | 0.005
|  | NOF/PE Sports | [22 empty] | 0.012 |  | 0.012 | [11 empty] | 0.012 |  |  |  |  | 0.012
|  | SPACE | [22 empty] | 0.233 |  | 0.233 | [11 empty] | 0.233 |  |  |  |  | 0.233
|  | Central salford | [22 empty] | 0.088 |  | 0.088 | [15 empty] | 0.088 | 0.088
|  | Chapel Wharf | [22 empty] | 0 | 0.146 | 0.146 | [16 empty] | 0
|  | Red Rose Scheme | [22 empty] | 0 | 0.003 | 0.003 | [16 empty] | 0
|  | Total | [17 empty] | 0 | 0 | 0 | 0 | 0 | 4.304 | 0.592 | 4.896 | 0 | 0 | 0 | 0.099 | 0 | 0 | 0 | 0 | 0 | 0.019 | 0 | 0.266 | 0.198 | 3.617 | 0 | 0.105 | 4.304
|  | Resources total (includes receipts required) | 109.9231 | [16 empty] | 14.425 | 8.032 | 1.905 | 0.437 | 14.4481 | 51.878 | 18.798 | 109.9231 | 12.761 | 4.928 | 2.59 | 1.046 | 0 | 2.102 | 0 | 0.73 | 1.602 | 0.82 | 3.762 | 1.328 | 0.584 | 16.645 | 0 | 2.293 | 50.965
|  | adjust for actual reciepts | #REF! | [20 empty] | #REF!
|  | Resources adjusted for forecast receipts | #REF! | [16 empty] | 14.425 | 8.032 | 1.905 | 0.437 | #REF! | 51.878 | 18.798 | #REF!
|  | programme including unfunded from 03/04 | 107.6971
|  | Sufplus/(shortfall) in resources over programme | #REF!
-5.934
-5.934
Note on V2: City of Salford: single capital pot 9001
Note on W2: City of Salford: ringfenced 9003
Note on Z2: City of Salford: 9007 COLUMN SHOWS CAP RECEIPTS REQUIRED NOT THOSE AVAILABLE
Note on AG2: City of Salford: 9027
Note on AP2: City of Salford: 9029
Note on AO2: City of Salford: 9057
Note on AH2: City of Salford: 9055
Note on AJ2: City of Salford: 9045
Note on AK2: City of Salford: 9043
Note on AD2: City of Salford: 9035 other govt grants 9037 other grants 9039 privat sector cont 9041 other cont
Note on D766: City of Salford: all planned spend held on one scheme at moment
Note on B784: City of Salford: included in planning level for C00059
Note on C780: City of Salford: need to sort a exp code for unsupported borrwoing currently it is on 9001 BCA
Note on D784: City of Salford: bfwd .279 0.013 hope library AandL 0.024 tourist information centre
Note on D897: City of Salford: bfwd 35k
Note on D630: City of Salford: bfwd 5.075tsg
Note on Z691: City of Salford: bfwd 0.159 from 03/04
Note on D716: City of Salford: bfwd 0.039 nof
Note on D717: City of Salford: bfwd 0.040NOF
Note on AB697: City of Salford: bfwd PCT 0.037 on 2802ss
Note on D765: City of Salford: bfwd ed rcco 37k
Note on AH750: City of Salford: bfwd 0.022
Note on Y750: City of Salford: bfwd 0.008 DS rcco
Note on D750: City of Salford: bfwd 0.030
Note on D767: City of Salford: bfwd NOF 117k
Note on D691: City of Salford: bfwd cap receipt 0.159
Note on D757: City of Salford: bfwd 0.003
Note on D753: City of Salford: bfwd 0.025 SPACE
Note on D764: City of Salford: bfwd 47k
Note on AN799: City of Salford: bfwd exp boundaries 0.341erdf
Note on D799: City of Salford: bfwd 0.341 erdf
Note on D792: City of Salford: bfwd 0.014
Note on Z792: City of Salford: bfwd 0.014
Note on D794: City of Salford: bfwd NDC 0.357
Note on AT854: City of Salford: 0.003 biffa 0.008 gmwda
Note on Z894: City of Salford: office moves budget
Note on AH947: City of Salford: winton and belvedere
Note on AB959: City of Salford: received in 04/05 apply in financing in 04/05
Note on AB949: City of Salford: 0.176 school contributions
Note on AT951: City of Salford: dept of health
Note on D841: City of Salford: carry forward 0.629 less eccles town hall negative carry forward -.040
Note on D844: City of Salford: carry forward -0.04
Note on D851: City of Salford: carry forward 0.039
Note on D873: City of Salford: brought forward 0.139-.004
Note on D854: City of Salford: bfwd 0.006LIVIA 0.063 slackbrook
Note on D907: City of Salford: bfwd 0.024
Note on D864: City of Salford: bfwd 14
Note on D860: City of Salford: bfwd 30
Note on C904: City of Salford: to be funded from the tesco site capital receipt on its sale
Note on B691: City of Salford: overprogramming Darrens report of 408k less 159k carry forward receipts
Note on Z932: City of Salford: cap receipts required to match spend
Note on Z893: City of Salford: cap receipts required to match spend
Note on C894: City of Salford: journal spend from c00060
Note on C690: City of Salford: D07260-d07299
Note on C934: City of Salford: £0.250m on DDA access to buildings 0.250m on DDA highway works
Note on D933: City of Salford: 0.070 to social services for community centres
Note on Y748: City of Salford: education and leisure
Note on D894: City of Salford: slip spend to 05/06
Note on G844: City of Salford: overspend funded from capital receipts?
Note on Y2: City of Salford: 9011
Note on AT2: City of Salford: 9037
Note on Z721: City of Salford: 0.010 DAA money
Note on Z718: City of Salford: 0.070 DAA money
Note on Z808: City of Salford: from chapel st cap receipts
Note on V691: City of Salford: 0.050 moved to chief executives for salford central station
Note on V808: City of Salford: 0.050 from highways block 3
Note on AP766: City of Salford: all planned spend held on one scheme at moment
Note on AP767: City of Salford: bfwd NOF 117k
Note on C829: City of Salford: speak with Ruth Shields 2349
Note on D829: City of Salford: slipped from 280 to 100 100 cap receipts 80 nrf

## Appendix 2
2004/05 ESTIMATED CAPITAL RECEIPTS
ASSET | CAPITAL |  | USABLE
| RECEIPT | Prop'n | Amount
| £000s | % | £000s
COMPLETED DISPOSALS
Housing Right-to-Buy | 11854 | 25 | 2963.5
Housing Land
29 and 29a Fairhurst Drive | 73 | 25 | 18.25
67 Wordsworth Road | 38 | 25 | 9.5
24 Parkway | 31 | 25 | 7.75
2 Watson Street | 56 | 25 | 14
13 Pemberton St | 48 | 25 | 12
3 Pemberton St deposit | 51 | 25 | 12.75
200 204 Liverpool Road | 15 | 25 | 3.75
Rovers Return | 20 | 25 | 5
2 Kersal Avenue | 10 | 25 | 2.5
Sale of land 20 Worcester Road | 17 | 25 | 4.25
General Fund - Properties and Land
Lift Properties | 2151 | 100 | 2151
Chasley fields | 550 | 100 | 550
land at Brettargh Street | 25 | 100 | 25
Melville st/Cleminson st | 17 | 100 | 17
Overage rights Quays campus | 44 | 100 | 44
Land at Watkin Street | 10 | 100 | 10
John St/Bury St Blackfriars | 145 | 100 | 145
Unit P, Highfield Rd industrial estate | 16 | 100 | 16
Hope Street | 15 | 100 | 15
Sale of Land Canalside, Monton Green | 11 | 100 | 11
3 Plots of land Cleggs lane/Ravencraig Road | 15 | 100 | 15
Land at Salford University | 175 | 100 | 175
TOTAL COMPLETED | 15387 |  | 6227.25
APPROVED DISPOSALS
Housing Right-to-Buy | 6146 | 25 | 1536.5
Housing Land & Property | 655 | 25 | 163.75
General Fund - Properties and Land | 4339 | 100 | 4339
TOTAL ESTIMATED DISPOSALS | 11140 |  | 6039.25
TOTAL ESTIMATED RECEIPTS | 26527 |  | 12266.5
Less - Costs to be set against capital receipts |  |  | 500
NET ESTIMATED RECEIPTS 04/05 |  |  | 11766.5
RECEIPTS BROUGHT FORWARD |  |  | 2225
ESTIMATED RECEIPTS FOR 2004/05 |  |  | 13991.5
RECEIPTS REQUIRED FOR 2004/05 CAPITAL PROGRAMME |  |  | 14023.1442
SURPLUS/(SHORTFALL) IN CAPITAL RECEIPTS |  |  | -31
Note on C49: City of Salford: CAPITAL RECEIPTS LINE 5
Note on C13: City of Salford: CAPITAL RECEIPTS Line 1
Note on C41: City of Salford: SHOULD EQUAL LINE 2
Note on C45: City of Salford: CAPITAL RECEIPTS LINE 3
Note on C47: City of Salford: CAPITAL RECEIPTS LINE 4
Note on C53: City of Salford: SHOULD EQUAL LINE 6

## Appendix 3
CAPITAL RECEIPTS 2004/05
TIMESCALES-RECEIPTS IN EXCESS OF £100,000
Disposal | Estimated Receipt | Preliminaries/Marketing | Legal/Planning | Completion
£m
Lift Sites | 2.121 |  |  | Completed 01/04/2004
Chasley fields | 0.55 |  |  | Completed 08/04/2004
John St/Bury St Blackfriars | 0.145 |  |  | Completed 09/09/04
Land at Salford University | 0.175 |  | June/July | completed 29/10/04
Greenwood School | 1 | December | November/December | 2005-03-01
Land at Oakley St | 0.4 |  |  | will be achieived in tranches between oct 04 and march 05
Area 11 Trinity | 0.25 | June-September | October-November | Auction Dec 04
Brentnall Primary School | 1.39 |  |  | 2005-03-01
Trinity Way/Urban splash | 0.25 |  |  | 2005-03-01
Quays Project Office | 1 | June-October | November-February | 2005-03-01
Moorfield House | 0.1 |  |  | 2005-03-01

## Appendix 4
Lead Member Corporate Services - 2004/05 Tender Approvals
Scheme Details |  | Costs |  | Source of
| 2004/05 | 2005/06 | Total | Funding
Onwards
| £m | £m | £m
Development Services
Block Improvements to Properties in Weaste Phase 3 | 0.224 | 0.505 | 0.729 | HMRF and Capital receipts
Block Improvements to Properties in the Arrowhead Charlestown | 0.29 | 0.306 | 0.596 | HMRF, New Deal and Capital receipts
Cadishead Way Stage 2 - Landscaping Works Phase 1 | 0.088 | 0.004 | 0.092 | Supported Borrowing
A5066 Adelphi Street/ Silk Street Primary Route Network Resurfacing | 0.347 | 0.038 | 0.385 | Supported Borrowing
Refurbishment of toilet and bathroom facilities, Alexandra House | 0.088 | 0.003 | 0.091 | Capital receipts and RCCO
| 1.037 | 0.856 | 1.893