## Appendix 1
|  | Capital Programme 2005/06 | [18 empty] | Resources 2005/06
| SAP |  | 2005/06 Estimate | Contract |  | Actual spend | Profiled spend | [11 empty] | Profiled spend | profiled spend received | Single capital pot | RING FENCED | Unsupported Borrowing |  | CAPITAL RECEIPTS
| REF |  |  | Start | Finish | August | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | August |  | SCE (R) | SCE (R) |  | RCCO |  | GRANT | OTHER | TOTAL | TSG | EP | NDS | Surestart | STANDARDS FUND | DFC | SEED | DFG | SRB | ERDF | NDC | Lottery | NWDA | HMRF | Home Office | Other | TOTAL | Notes
|  |  | £m |  |  | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m |  | £m | £m |  | £m | £m | £m | £m | £m | £m |  | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m
PRIVATE SECTOR HOUSING
| summary | Langwothy / Seedley | 7 |  |  | 1.394 | [12 empty] | 2.9167
| summary | NEW DEAL/ NORTH IRWELL | 5.577 |  |  | 2.037 | [12 empty] | 2.3237 | [25 empty] | 0
| summary | Higher Broughton | 10.433 |  |  | 3.807 | [12 empty] | 4.3471 | [25 empty] | 0
| summary | CLAREMONT / WEASTE | 1.957 |  |  | 0.94 | [12 empty] | 0.81542 | [25 empty] | 0
| summary | ENTERPRISE PARK | 1.248 |  |  | 0.116 | [12 empty] | 0.52 | [25 empty] | 0
| summary | ORDSALL | 0.64 |  |  | 0 | [12 empty] | 0.26667 | [25 empty] | 0
| summary | NON AREA BASED | 4.798 |  |  | 0.603 | [12 empty] | 1.9992 | [25 empty] | 0
| summary | OUTER AREA / CITYWIDE | 4.549 |  |  | 0.843 | [12 empty] | 1.8954 | [25 empty] | 0
| summary | Underprogramming ** | -2.38 | [15 empty] | -0.99167 |  | 3.481 |  |  |  | 7.129 | 23.212 |  | 33.822 |  | 0.514 | [5 empty] | 0.676 | 1.573 | 0.679 | 1.55 |  |  | 18.22 |  |  | 23.212
| 14.601 | PRIVATE SECTOR HOUSING -TOTAL | 33.822 |  |  | 9.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.0925 |  | 3.481 | 0 | 0 | 0 | 7.129 | 23.212 | 0 | 33.822 | 0 | 0.514 | 0 | 0 | 0 | 0 | 0 | 0.676 | 1.573 | 0.679 | 1.55 | 0 | 0 | 18.22 | 0 | 0 | 23.212
PUBLIC SECTOR HOUSING
Page 2 | summary | 2005/06 New Starts - Partners | 11.109 |  |  | 3.827 | 0 | 0 | 1.011 | 1.916 | 1.546 | 1.695 | 1.029 | 0.852 | 0.675 | 0.649 | 0.517 | 1.568 | 4.473 | [9 empty] | 0
|  | WATES | 0 |  |  | 0 | [12 empty] | 0
|  | SALFORD NORTH | 0 |  |  | 0 | [12 empty] | 0
| H50818 | ALBION STADIUM - Heating/Elec Upgrade/Kit/Bath | 1.108 |  |  | 0.714 |  |  | 0.21 | 0.207 | 0.224 | 0.266 | 0.083 | 0.027 | 0 | 0 | 0 | 0.102 | 0.641
| H50819 | RACECOURSE - Prior to Paint | 0.011 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.033 | 0.066 | 0 | 0 | 0.01 | 0
|  | ECCLES | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50969 | FAIRHILLS ROAD - Heating & Rewire | 0.143 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.092 | 0.038 | 0 | 0.013 | 0
| H50970 | FALMOUTH ROAD - Heating & Rewire | 0.025 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.023 | 0 | 0.002 | 0
| H50971 | SANDIWAY - Heating | 0.026 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.026 | 0
| H50972 | DE TRAFFORDS/MOORFIELD - Heating & Rewire | 0.532 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.244 | 0.229 | 0.098 | 0
| H50973 | THE DE TRAFFORDS - Heating & Rewire | 0.353 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.353 | 0
| H50974 | 1-12 St GEORGES COURT - Re-roof & Walkway | 0.051 |  |  | 0 |  |  | 0 | 0 | 0 | 0.046 | 0 | 0 | 0 | 0 | 0 | 0.005 | 0
|  | SWINTON |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50881 | MANCHESTER ROAD SOUTH - Re-roof & Balcony Resurface | 0.223 |  |  | 0 |  |  | 0 | 0 | 0 | 0.203 | 0 | 0 | 0 | 0 | 0 | 0.02 | 0
| H50882 | WATSON STREET - Elec Upgrade | 0.027 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.027 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | WHITES |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | SWINTON |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50883 | THE VALLEY - Kitchen & Elec Upgrade | 1.394 |  |  | 0.171 |  |  | 0.035 | 0.129 | 0.182 | 0.182 | 0.182 | 0.182 | 0.182 | 0 | 0.194 | 0.127 | 0.346
|  | SALFORD SOUTH |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50721 | SOUTH ORDSALL - Heating/Elec Upgrade/Kit/Bath | 1.709 |  |  | 0.607 |  |  | 0.087 | 0.151 | 0.206 | 0.212 | 0.246 | 0.246 | 0.19 | 0.178 | 0 | 0.152 | 0.444
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | BRAMALL |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | SWINTON |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50884 | CORONATION STREET - Elec Upgrade/Kit/Bath/Heating | 1.483 |  |  | 1.199 |  |  | 0.036 | 0.812 | 0.406 | 0.185 | 0 | 0 | 0.04 | 0 | 0 | 0.167 | 1.254
| H50885 | NEWTOWN - Heating/Elec Upgrade | 0.538 |  |  | 0.346 |  |  | 0.036 | 0.097 | 0.249 | 0.135 | 0.012 | 0 | 0.018 | 0 | 0 | 0.071 | 0.382
| H50886 | HAMILTON STREET - Elec Upgrade/Heating/Bath/Kit | 0.586 |  |  | 0.043 |  |  | 0.036 | 0 | 0 | 0.073 | 0.298 | 0.144 | 0 | 0 | 0 | 0.096 | 0.036
|  | SALFORD SOUTH |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50722 | PARK ROAD - Heating & Elec Upgrade | 0.202 |  |  | 0.202 |  |  | 0.183 | 0.014 | 0 | 0.002 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0.197 | [25 empty] | 0
| H50723 | St. GEORGES CRESCENT - Heating & Elec Upgrade | 0.148 |  |  | 0.137 |  |  | 0 | 0.063 | 0.028 | 0.04 | 0.011 | 0 | 0 | 0 | 0 | 0.044 | 0.091 | [25 empty] | 0
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | NEW PROSPECT |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ECCLES |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [25 empty] | 0
| H50975 | CANTERBURY GARDENS - Stairwell Refurb. | 0.025 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.025 | 0 | [25 empty] | 0
|  | WORSLEY |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [25 empty] | 0
| H50922 | HILLTOP/NINIAN GDNS - Prior to Paint | 0.341 |  |  | 0.036 |  |  | 0.102 | 0.208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.031 | 0.31 | [25 empty] | 0
| H50923 | GROSVENOR ROAD - Heating & Elec Upgrade | 0.68 |  |  | 0.372 |  |  | 0.286 | 0.208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.049 | 0.494 | [25 empty] | 0
| H50924 | WHARTON - Prior to Paint | 0.097 |  |  | 0 |  |  | 0 | 0.027 | 0.003 | 0.058 | 0 | 0 | 0 | 0 | 0 | 0.009 | 0.03 | [25 empty] | 0
|  | SWINTON |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50887 | SWINTON HALL ROAD - Heating/Elec Upgrade/Bath | 0.424 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.125 | 0.05 | 0.116 | 0.094 | 0.039 | 0 | [25 empty] | 0
|  | SALFORD SOUTH |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50724 | MEADOWGATE - Heating/Elec Upgrade/Re-roof | 0.983 |  |  | 0 |  |  | 0 | 0 | 0.248 | 0.293 | 0.197 | 0.095 | 0.037 | 0.05 | 0 | 0.092 | 0.248
|  | THORN COURT - Soil Stack Replacement | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Page 3 | summary | 2005/06 New Starts Citywide | 0.452 |  |  | 0.07 |  | 0 | 0.03 | 0.044 | 0.068 | 0.021 | 0.043 | 0.042 | 0.043 | 0.04 | 0.04 | 1.301 | 0.142
| H50667 | ENERGY EFFICIENCY SURVEYS | 0.11 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.01 | 0
|  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50968 | INSULATION - Eccles | 0.044 |  |  | 0.023 |  |  | 0.023 | 0.003 | 0.003 | 0.003 | 0.003 | 0.002 | 0.003 | 0 | 0 | 0.004 | 0.029
| H51206 | INSULATION - Salford Nth | 0.044 |  |  | 0.006 |  |  | 0.007 | 0 | 0 | 0.003 | 0.005 | 0.005 | 0.005 | 0.005 | 0.005 | 0.009 | 0.007
| H50574 | INSULATION - Salford Sth | 0.044 |  |  | 0 |  |  | 0 | 0 | 0.005 | 0.005 | 0.005 | 0.005 | 0.005 | 0.005 | 0.005 | 0.009 | 0.005
| H50880 | INSULATION - Swinton | 0.044 |  |  | 0 |  |  | 0 | 0 | 0.005 | 0.005 | 0.005 | 0.005 | 0.005 | 0.005 | 0.005 | 0.009 | 0.005
| H50921 | INSULATION - Worsley/LittleHulton | 0.044 |  |  | 0 |  |  | 0 | 0 | 0.005 | 0.005 | 0.005 | 0.005 | 0.005 | 0.005 | 0.005 | 0.009 | 0.005
|  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | HIGHRISE STRUCTURAL REPAIRS AND SURVEYS | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0
|  | AD HOC WORKS FROM SMALL SCALE STOCK OPTIONS | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0
|  | MARK AVENUE FLATS | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.02 | 0
|  | HIGHRISE/ADHOC MAINTENANCE | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.55 | 0
|  | BARONFOLD/THORNFIELD GROVE | 0.022 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.022 | 0
|  | POLLUTION/DRAINAGE CITYWIDE | 0.1 |  |  | 0.041 |  |  | 0 | 0.041 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0.009 | 0.091
0
Page 4 | summary | 2004/05 New Starts | 4.45 |  |  | 1.797 |  |  | 0.748 | 1.147 | 0.568 | 0.42 | 0.33 | 0.276 | 0.231 | 0.023 | 0.082 | 0.412 | 2.463
| H50707 | STRUCTURAL-SPRUCE | 1.129 |  |  | 0.457 |  |  | 0.284 | 0.15 | 0.15 | 0.15 | 0.15 | 0.133 | 0.1 | 0 | 0 | 0.112 | 0.584
| H50805 | LIFTS-NEWBANK / RIVERBANK | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50665 | SHELTERED HOMES -EXTRA CARE WORK (Funded) | 0.847 |  |  | 0.258 |  |  | 0.111 | 0.142 | 0.1 | 0.1 | 0.1 | 0.1 | 0.086 | 0 | 0.031 | 0.077 | 0.353
|  | SHELTERED HOMES -EXTRA CARE WORK (Additional Works) | 0.06 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.012 | 0 | 0.02 | 0.029 | 0
| H50664 | AREA OFFICE DISABLED ADAPTATIONS | 0.005 |  |  | 0.001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.006 | 0
| H50816 | MULTI STOREY SATELLITE TV | 0.009 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.008 | 0.001 | 0
| H50720 | COMMUNAL TV AERIALS - PRECINCT | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50967 | COMMUNAL TV AERIALS - ECCLES | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50662 | REFURB OF ACQUIREDS | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50663 | STRUCTURAL REPAIRS-AD HOC | 0.18 |  |  | 0.111 |  |  | 0.046 | 0.005 | 0.03 | 0 | 0.03 | 0 | 0.03 | 0 | 0.023 | 0.016 | 0.081
|  | SECURITY | 0.001 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.001 | 0 | 0 | 0 | 0 | 0
| H50660 | TURNPIKE OFFICE ALTERATIONS | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| h50870 | RIGHT TO BUY REAQUISITION | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50661 | CITYWIDE SURVEYS | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H51108 | SOLAR ELECTRICITY PLAN | 0.016 |  |  | 0.009 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PRE PARTNERING | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | WARDLEY PARTIAL REWIRE | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50871 | TEMPLE DRIVE ELECTRICAL UPGRADE | 0.002 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.002 | 0 | 0 | 0
| H51111 | DUDLEY RD HEATING | 0.008 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.008 | 0 | 0.001 | 0
| H51110 | MEADOWS HEATING | 0.004 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.003 | 0 | 0 | 0 | 0
| H51109 | BAINES AVE ROOFING | 0.002 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.002 | 0 | 0 | 0
|  | CROSSFIELDS ROOFING | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | WARREN ST ROOFING | 0.001 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.001 | 0 | 0 | 0
|  | MITCHELL ST REWIRE/KITCHENS | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PEEL GREEN RD REWIRE,KITCHEN/BATH | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PARTNERING | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50912 | WORSLEY PACKAGE 1 | 0.001 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.001 | 0 | 0 | 0
|  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50959 | ECCLES PACKAGE 1 | 0.002 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.002 | 0 | 0 | 0
| H50960 | ECCLES PACKAGE 2 | 0.002 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.002 | 0 | 0 | 0
| H50961 | ECCLES PACKAGE 3 | 0.303 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.003 | 0 | 0 | 0
| H50962 | ECCLES PACKAGE 4 | 0.002 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.002 | 0 | 0 | 0
|  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50872 | SWINTON PACKAGE 1 | 0.311 |  |  | 0.117 |  |  | 0.018 | 0.265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.028 | 0.283
| H50873 | SWINTON PACKAGE 2 | 0.189 |  |  | 0.189 |  |  | 0.032 | 0.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.017 | 0.172
| H50874 | SWINTON PACKAGE 3 | 0.419 |  |  | 0.144 |  |  | 0.042 | 0.098 | 0.121 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0.038 | 0.261
|  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50713 | SALFORD SOUTH PACKAGE 1 | 0.176 |  |  | 0.11 |  |  | 0.11 | 0 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0.016 | 0.16
| H50714 | SALFORD SOUTH PACKAGE 2 | 0.069 |  |  | 0.038 |  |  | 0.038 | 0 | 0.024 | 0 | 0 | 0 | 0 | 0 | 0 | 0.006 | 0.062
| H50715 | SALFORD SOUTH PACKAGE 3 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50817 | SALFORD NORTH PACKAGE 1 | 0.374 |  |  | 0.297 |  |  | 0 | 0.297 | 0.043 | 0 | 0 | 0 | 0 | 0 | 0 | 0.034 | 0.34
|  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H53223 | PPR PACKAGE 1 | 0.338 |  |  | 0.066 |  |  | 0.067 | 0.05 | 0.05 | 0.05 | 0.05 | 0.042 | 0 | 0 | 0 | 0.031 | 0.167
Page 5 | summary | 2004/05 Insulation Schemes | 0.049 |  |  | 0.048 | 0.036 | 0 | 0.012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.004 | 0.048
| H50963 | PACKAGE 1 | 0.007 |  |  | 0.007 | 0.007 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.001 | 0.007
| H50964 | PACKAGE 2 | 0.014 |  |  | 0.014 | 0.014 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.001 | 0.014
| H50965 | PACKAGE 3 | 0.014 |  |  | 0.014 | 0.014 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.001 | 0.014
| H50966 | PACKAGE 4 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50716 | PACKAGE 5 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50717 | PACKAGE 6 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50718 | PACKAGE 7 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50719 | PACKAGE 8 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H51203 | PACKAGE 9 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H51204 | PACKAGE 10 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H51205 | PACKAGE 11 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50875 | PACKAGE 12 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50876 | PACKAGE 13 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50877 | PACKAGE 14 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50878 | PACKAGE 15 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50879 | PACKAGE 16 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50916 | PACKAGE 17 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50917 | PACKAGE 18 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50913 | PACKAGE 19 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50914 | PACKAGE 20 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50915 | PACKAGE 21 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50918 | PACKAGE 22 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50919 | PACKAGE 23 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50659 | CITYWIDE INSULATION | 0.014 |  |  | 0.013 | 0.001 |  | 0.012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.001 | 0.013
Page 6 | summary | 2003/04 New Starts | 0.034 |  |  | 0.01 | 0.009 | 0 | 0 | 0.001 | 0 | 0.014 | 0 | 0 | 0 | 0 | 0 | 0.003 | 0.01
|  | DECENT HOMES PROGRAMME | 0 |  |  | 0 | [12 empty] | 0
|  |  | 0 |  |  | 0 | [12 empty] | 0
| h50710 | Thorn Court Partnering scheme | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| h50868 | Ash Drive | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| h50641 d |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| h50641 f | Jackson St | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| h50812 | Racecourse ph 1/2 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| h50954 | Fairhope | 0.01 |  |  | 0 | 0.009 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.001 | 0.009
| h51107 | Higher Irlam ph 4 | 0.001 |  |  | 0.001 |  |  | 0 | 0.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.001
| h50869 | Pendleway | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| h50711 | Kinder | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| h50957 | Hereford rd/Salisbury rd | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| h50908 | St Georges Ct/Peel Pk Cres | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| h50955 | De Traffords | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PROGRAMMED WORKS-BUILDINGS | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| h50652 | structural repairs | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| h50653 | concrete floors | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| h50654 | solid fuel heating | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| h51106 | Admiralty / LHDC | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| h50956 | Peel Green | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| h50910 | Eccles/L Hulton | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| h50867 | Green Avenue ,Swinton | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PROGRAMMED WORKS-SERVICES | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| h50814 | Greyfriars Court | 0.006 |  |  | 0 |  |  | 0 | 0 | 0 | 0.007 | 0 | 0 | 0 | 0 | 0 | 0.001 | 0
| h50815 | Black/Whitefriars | 0.001 |  |  | 0.001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| h50712 | Apple/Pear/Peach | 0.008 |  |  | 0 |  |  | 0 | 0 | 0 | 0.007 | 0 | 0 | 0 | 0 | 0 | 0.001 | 0
| h50709 | Lombardy Court | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PROGRAMMED WORKS-OTHER | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| h51105 | elderly adaptations | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| h50813 | salford north office improvements | 0.008 |  |  | 0.008 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Page 7 | summary | ROLLING PROGRAMMES | 2.946 |  |  | 0.59 | 0.014 | 0 | 0.213 | 0.234 | 0.244 | 0.232 | 0.232 | 0.248 | 0.233 | 0.22 | 0.245 | 1.153 | 0.705
|  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50001 | 2004/5 D.F.G.s | 1.898 |  |  | 0.478 |  |  | 0.197 | 0.186 | 0.178 | 0.178 | 0.178 | 0.178 | 0.178 | 0.178 | 0.178 | 0.371 | 0.561
| H50001A | D.F.G.s in future years | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50643A | CAPITALISED SALARIES (DPU/CT) | 0 |  |  | 0 | 0.005 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.105 | 0.005
| H50643 | ADVANCE FEES | 0.04 |  |  | 0.007 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.04 | 0
|  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H54001 | 2004/5 BURGLARY REDUCTION INITIATIVE | 0.5 |  |  | 0.076 |  |  | 0.016 | 0.028 | 0.054 | 0.054 | 0.054 | 0.054 | 0.054 | 0.054 | 0.054 | 0.081 | 0.098
|  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2005/6 NEW STARTS (DSD SCHEMES) | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50253 | PEEL PH 5 ENVIRONMENT | 0.392 |  |  | 0.006 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0
|  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2002/3 NEW STARTS (DSD SCHEMES) | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50250 | PEEL PH 4 ENVIRONMENT | 0.013 |  |  | 0.004 |  |  | 0 | 0 | 0 | 0 | 0 | 0.007 | 0 | 0 | 0 | 0.006 | 0
| H50270 | ARMITAGE PH 3 ENVIRONMENT | 0.016 |  |  | 0.009 | 0.005 |  | 0 | 0 | 0.012 | 0 | 0 | 0.009 | 0.001 | -0.012 | 0 | 0 | 0.017
| H50249 | MOUNT SKIP PH 2 ENVIRONMENT | 0.029 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.029 | 0
| H51202 | ROCKLEY GARDENS | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2001/2 NEW STARTS (DSD SCHEMES) | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50485 | FLORAL COURT CAR PARK | 0.001 |  |  | 0.001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.001 | 0
| H50625 | BIRCH RD / OLD CLOUGH ENV'T | 0.013 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.013 | 0 | 0
| H50610 | ADMIRALTY ENVIRONMENT | 0.002 |  |  | 0.001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.002 | 0
| H50519 | PHILIP ST PHASE 2 SECURITY | 0.001 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.001 | 0
| H50486 | GREENGATE CAR PARKING | 0.001 |  |  | 0.001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.001 | 0
| H50297 | JENNINGS / TAMWORTH / WESLEY | 0.002 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.002 | 0
| H50565 | TOOTAL DRIVE PH 3 ENVIRONMENT | 0.02 |  |  | 0.002 |  |  | 0 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.02
| H50593 | CASTLEWAY PH 1 ENVIRONMENT | 0.003 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.003 | 0
| H50595 | VALLEY PH 2 ENVIRONMENT | 0.002 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.002 | 0
| H50269 | ARMITAGE PH 2 ENVIRONMENT | 0.008 |  |  | 0.005 | 0.004 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.004 | 0.004
| H50246 | PEEL PH 3 ENVIRONMENT | 0.004 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.004 | 0
| H50804 | MELBOURNE ST ENVIRONMENT | 0.001 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.001 | 0
Page 8 | summary | New Deal - Kersal/Charlestown | 0.124 |  |  | 0.009 | 0.002 | 0 | 0.004 | 0.004 | 0.005 | 0.007 | 0.007 | 0.007 | 0.007 | 0.047 | 0.057 | 0.248 | 0.015
|  | 2002/3 NEW STARTS | 0 |  |  | 0 | [12 empty] | 0
|  |  | 0 |  |  | 0 | [12 empty] | 0
| H54101 | DISTRICT HEATING-LONDON ST / LISSADEL ST | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2003/4 NEW STARTS | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | WHIT LANE / LITTLETON RD | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| h50550 | LITTLETON RD WATER PIPES | 0.003 |  |  |  | 0.001 |  | 0.004 | 0.004 | 0.005 | 0.007 | 0.007 | 0.007 | 0.007 | 0.047 | 0.057 | 0.058 | 0.014
|  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H54104 | LITTLETON RD INTERNALS | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H54105 | WHIT LANE INTERNALS | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H54106 | LITTLETON RD EXTERNALS | 0.097 |  |  | 0.006 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.19 | 0
| H54107 | WHIT LANE EXTERNALS | 0.024 |  |  | 0.003 | 0.001 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.001
|  |  | 0 |  |  | 0 | [12 empty] | 0
Page 9 | summary | SRB/Estate Action/ CC Schemes 1 | 1.175 |  |  | 0.548 | 0.154 | 0 | 0.004 | 0.109 | 0.114 | 0.114 | 0.132 | 0.099 | 0.084 | 0.079 | 0.09 | 0.184 | 0.381
|  | S.R.B. 2 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50103 | LOWER BROUGHTON ENV'L PH 1 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50122 | LOWER BROUGHTON ENV'L PH 2 | 0.001 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.001 | 0
| H50124 | LOWER BROUGHTON ENV'L PH 3A/4A | 0.001 |  |  | 0.001 | 0.001 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.001
| H50123 | LOWER BROUGHTON ENV'L PH 3 | 0.004 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.004 | 0
| H50125 | LOWER BROUGHTON ENV'L PH 4 | 0.01 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0
| H50126 | LOWER BROUGHTON TEMP. TREATM'T PH 2 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | SPIKE ISLAND | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50183 | SPIKE ISLAND-PTP PH 1 | 0.01 |  |  | 0.01 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.005 | 0
| H50185 | DISTRICT HEATING PH 1/2 | 0.009 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.009 | 0
| H50186 | ENVIRONMENT PH 1 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50187 | ENVIRONMENT PH 2 | 0.018 |  |  | 0.002 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.018 | 0
| H50188 | ENVIRONMENT PH 3 | 0.003 |  |  | 0.003 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.003 | 0
| H50189 | ENVIRONMENT PH 4 | 0.023 |  |  | 0.005 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.023 | 0
| H50190 | ENVIRONMENT PH 5 | 0.019 |  |  | 0.001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.006 | 0.013 | 0
| H50191 | ENVIRONMENT PH 6 | 0.047 |  |  | 0.022 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.044 | 0
| H50192 | ENVIRONMENT PH 7 | 1.03 |  |  | 0.504 | 0.153 |  | 0.004 | 0.109 | 0.114 | 0.114 | 0.132 | 0.099 | 0.084 | 0.079 | 0.084 | 0.054 | 0.38
Page 10 | summary | PPR Programme | 0.223 |  |  | 0.118 | 0.017 | 0 | 0 | 0.018 | 0 | 0.013 | 0 | 0.003 | 0 | 0 | 0 | 0.154 | 0.035
| H53001 | COMMITMENTS | 0.004 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.004 | 0
| H53178 | ALDER PARK | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H53179 | FALCON CRES | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H53188 | LANCASTER RD | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H53189 | BROOKHOUSE PH 1 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H53192 | BROOKHOUSE PH 2 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H53193 | TOOTAL DR PH 1ACKWORTH RD/TEMPLE DR | 0.001 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.001 | 0
| H53194 | TOOTAL DR PH 2 / VICTORY RD | 0.013 |  |  | 0.001 |  |  | 0 | 0 | 0 | 0.013 | 0 | 0 | 0 | 0 | 0 | 0.001 | 0
| H53200 | ADVANCE FEES / SURVEYS | 0.045 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.045 | 0
| H53203 | CLOUGHFIELD | 0.007 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.007 | 0
| H53204 | HOSPITAL ROAD | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H53205 | NEW ISLINGTON | 0.016 |  |  | 0 |  |  | 0 | 0.015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.001 | 0.015
| H53206 | MOSSFIELD RD | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.001 | 0
| H53208 | WARDLEY | 0.003 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0.003 | 0 | 0 | 0 | 0 | 0
| H53209 | BROOKHOUSE PH 3 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H53210 | CASTLEWAY | 0.013 |  |  | 0.012 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.021 | 0
| H53212 | GROSVENOR ph 1 | 0.043 |  |  | 0.043 | 0.017 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.008 | 0.017
| H53214 | LANE END | 0.003 |  |  | 0 |  |  | 0 | 0.003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.003
| H53215 | CAWDOR ST | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H53216 | BRENTWOOD | 0.001 |  |  | 0.001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H53217 | DUCHY PH 1 | 0.011 |  |  | 0.001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.011 | 0
| H53218 | DUCHY PH 2 | 0.009 |  |  | 0.009 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H53219 | HILL TOP PH 1 | 0.001 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.001 | 0
| H53220 | HILL TOP PH 2/3 | 0.053 |  |  | 0.051 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.053 | 0
Page 11 | summary | Demolitions | 0.795 |  |  | 0.169 | 0 | 0 | 0.123 | 0 | 0.1 | 0 | 0.1 | 0 | 0.1 | 0 | 0.119 | 0.054 | 0.223
|  | 2004/5 new start allocation | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Mark Avenue Flats | 0.022
|  | TMO Kitchens - Albion, Appletree | 0.032
| h52001 a | Available for new starts | 0.2 |  |  | 0 |  |  | 0 | 0 | 0.1 | 0 | 0.1 | 0 | 0.1 | 0 | 0.119 | 0.054 | 0.1
| h52009 | Hanover Court | 0 |  |  | 0 |  |  | 0.035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.035
| h52024 | Florence St | 0.003 |  |  | 0.003 |  |  | 0.003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.003
| h52018 | Kestrel Avenue | 0.009 |  |  | 0.009 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| h52019 | Wheatersfield | 0.122 |  |  | 0.104 |  |  | 0.034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.034
| H52006 | Little Hulton Cottage Flats | 0.006 |  |  | 0.006 |  |  | 0.005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.005
| H52003 | Poets Corner | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| h52008 | Ladywell Avenue | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| h52028 | Cedar Place | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H52029 | Aspinall Drive | 0.013 |  |  | 0.013 |  |  | 0.011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.011
| H52011 | Kingsley/Granville | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H52012 | Wheaters/Jessamine | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H52030 | Plum Tree Court | 0.36 |  |  | 0.006 |  |  | 0.004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.004
|  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Schemes funded from previous | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | years allocations | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| h52023 | Lime Court | 0.003 |  |  | 0.003 |  |  | 0.003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.003
| h52025 | Meadowside | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| h52026 | Hulton Ave launderette | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| h52027 | Windsor Avenue | 0.025 |  |  | 0.025 |  |  | 0.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.001
| h52020 | Shakespeare Rd / Blantyre St | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H51002 | Birley Court | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H52010 | Duchy Bank | 0 |  |  | 0 |  |  | 0.027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.027
| H51001 | Ruthin Court | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Page 12 | summary | Retentions/Balances | 0.152 |  |  | 0.036 | 0.003 | 0 | 0 | 0.011 | 0 | 0.006 | 0 | 0 | 0.003 | 0.011 | 0 | 0.011 | 0.014
| Order Code | RETENTIONS / BALANCES | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | OLD SCHEMES | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50624 | ENERGY EFF.LEAD PIPES | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50482 | HIGH RISE PROG -CANON GREEN | 0.003 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.003 | 0 | 0 | 0 | 0
| H50504 | BEECH ST ENVIRONMENT PH 1 | 0.001 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50604 |  |  |  |  | 0.001
|  | 2000/1 NEW STARTS (DSD) | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50562 | TOOTAL DRIVE PHASE 2 | 0.001 |  |  | 0.001 | 0.001 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.001
| H50564 | MEADOWGATE | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.001 | 0 | 0 | 0
| H50584 | VALLEY ENVIRONMENT PH 1 | 0.013 |  |  | 0.001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0.003 | 0
| H50585 | CLIVELEY ENVIRONMENT PH 1 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50295 | GOODIERS DRIVE HIGHWAY WORKS | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2001/2 NEW STARTS (HPMS) | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50702 | STRUCTURAL REPAIRS-THORN COURT | 0.026 |  |  | 0.026 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50534 | SECURITY-ARGOSY/BEECH/MITCH/SCOTCH | 0.001 |  |  | 0 |  |  | 0 | 0 | 0 | 0.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50706 | SECURITY-WROTHAM CLOSE | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50705 | SECURITY-ALBION / SPRUCE | 0.002 |  |  | 0 |  |  | 0 | 0 | 0 | 0.002 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50636 | SOLID FUEL - WORSLEY | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2002/3 NEW STARTS (HPMS-SERVICES) | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50559 | SECURITY-HERALDIC | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50857 | HEATING/REWIRES-WYNDHAM | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50860 | HEATING/REWIRES-DEANS COURT | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H51104 | GAS HEATING-MOSS VALE PH 1 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50864 | GAS HEATING-BEEHIVE | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50572 | GAS HEATING-LANCASTER RD | 0.003 |  |  | 0 |  |  | 0 | 0 | 0 | 0.003 | 0 | 0 | 0 | 0 | 0 | 0.001 | 0
| H50810 | GAS HEATING-L BROUGHTON RD | 0.003 |  |  | 0.003 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50811 | HEATING BOILER-ALEX GARDENS | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| h50809 | SECURITY-STONEY KNOLL/GLOVERFIELD | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| h50540 | SECURITY-SOUTH KING STREET | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50288 | SECURITY OF OPEN SPACES | 0.001 |  |  | 0.001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.001 | 0
|  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2002/3 NEW STARTS (HPMS-BUILDING) | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50570 | WALKWAYS-SEEDLEY TERRACE/AILSA | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50807 | KITCHENS-L BROUGHTON PH 1/TOOTAL PH 1 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50620 | INTERNALS-ADMIRALTY | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50571 | INTERNALS-MEADOWGATE | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50859 | INTERNALS-CLIVELEY | 0.078 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50904 | INTERNALS-AMBLECOTE | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | EA SCHEMES | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50402 | AMERSHAM ST PHASE 1 | 0.001 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.001 | 0
| H50488 | ALBION TOWERS | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50422 | FITZWARREN COURT REFURBISHMENT | 0.001 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.001 | 0
| H50285 | ORDSALL-LINDEN GR PH 3(NWO PH 2) | 0.004 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.004 | 0
| H50287 | ORDSALL-BURNETT (NWO PH 3) | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | SRB /CC SCHEMES | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50083 | BROADWALK WEST PHASE 2 | 0.002 |  |  | 0.002 | 0.002 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.002
| H50222 | Kenyon Environment Phase 3 | 0.001 |  |  | 0.001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50223 | PEEL ENVIRONMENT PH 2 | 0.011 |  |  | 0 |  |  | 0 | 0.011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.011
| H50230 | AMBLECOTE ENVIRONMENT | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50228 | MT SKIP ENVIRONMENT | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50251 | PEEL HOMES FOR ALL | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H50263 | ARMITAGE ENVIRONMENT PH 1 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Page 13 | summary | Resources and underprogramming | -1.622 | [14 empty] | -1.622 | 0 |  | 2 |  |  | 1 |  | 16.887 |  | 19.887 | [10 empty] | 0.04 |  |  |  |  | 16.847 | 16.887 | 16m MRA, 0.300m extra care housing slipped at outturn
|  | PUBLIC SECTOR HOUSING - TOTAL | 19.887 |  |  | 7.222 | 0.235 | 0 | 2.145 | 3.484 | 2.645 | 2.522 | 1.873 | 1.527 | 1.376 | 1.069 | 1.15 | 3.47 | 8.509 |  | 2 | 0 | 0 | 1 | 0 | 16.887 | 0 | 19.887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.04 | 0 | 0 | 0 | 0 | 16.847 | 16.887
|  | HOUSING TOTAL | 53.709 |  |  | 16.962 | 0.235 | 0 | 2.145 | 3.484 | 2.645 | 2.522 | 1.873 | 1.527 | 1.376 | 1.069 | 1.15 | 3.47 | 22.6015 |  | 5.481 | 0 | 0 | 1 | 7.129 | 40.099 | 0 | 53.709 | 0 | 0.514 | 0 | 0 | 0 | 0 | 0 | 0.676 | 1.573 | 0.679 | 1.59 | 0 | 0 | 18.22 | 0 | 16.847 | 40.099
CHILDREN'S SERVICES
|  | NDS 4 | 0.022 | Apr 05 | Mar 06 |  | 0.004 | 0.004 | 0.005 | 0.005 | 0.004 | [7 empty] | 0.022 | [6 empty] | 0.022 |  | 0.022 |  |  | 0.022 | [13 empty] | 0.022
|  | Out of School Childcare | 0.028 | Apr 05 | Mar 06 | [12 empty] | 0.028 | 0 | [6 empty] | 0.028 |  | 0.028 |  |  |  | 0.028 | [12 empty] | 0.028
|  | Capitalised salaries | 0.181 | Apr 05 | Mar 06 | [12 empty] | 0.181 | 0 | [5 empty] | 0.181 | 0 |  | 0.181 | [16 empty] | 0
|  | Devolved Formual Capital | 2.128 | Apr 05 | Mar 06 | 0.656 | 0.177 | 0.178 | 0.177 | 0.178 | 0.177 | 0.177 | 0.177 | 0.177 | 0.177 | 0.177 | 0.178 | 0.178 | 0.887 | [6 empty] | 2.128 |  | 2.128 | [5 empty] | 2.128 | [10 empty] | 2.128
|  | NDS Condition/Modernisation | 3.25 | Apr 05 | Aug 06 | 1.117 | 0.02 | 0.02 | 0.02 | 0.023 | 1.008 | 0.381 | 0.381 | 0.381 | 0.381 | 0.381 | 0.381 | 0.381 | 1.091 | [5 empty] | 0.695 | 2.555 |  | 3.25 |  |  | 2.555 | [13 empty] | 2.555
|  | Class size reduction | 0.001 | Apr 05 | Mar 06 | [12 empty] | 0.001 | 0 | [5 empty] | 0.001 | 0 |  | 0.001 | [16 empty] | 0
|  | PFI 2 | 0.023 | [7 empty] | 0.023 | [7 empty] | 0.023 | [5 empty] | 0.018 | 0.005 |  | 0.023 | [5 empty] | 0.005 | [10 empty] | 0.005
|  | Playgroup Conversion | 0.097 | [7 empty] | 0.097 | [7 empty] | 0.097 | [6 empty] | 0.097 |  | 0.097 |  |  |  | 0.097 | [12 empty] | 0.097
|  | Primary Review | 3.798 | Feb 04 | Dec 05 | 1.065 | 0.02 | 0.02 | 0.02 | 0.02 | 0.023 | 0.527 | 0.527 | 0.527 | 0.527 | 0.527 | 0.527 | 0.533 | 0.103 |  | 0.499 |  |  |  | 2.294 | 0.982 | 0.023 | 3.798 |  |  | 0.406 |  |  | 0.473 | 0.103 | [9 empty] | 0.982 | 0.023 citywide contribution
| e02004 | Schools Access Initiative | 0.435 | Apr 05 | Mar 06 | 0.109 | 0.014 | 0.014 | 0.014 | 0.014 | 0.015 | 0.052 | 0.052 | 0.052 | 0.052 | 0.052 | 0.052 | 0.052 | 0.071 |  | 0.323 |  |  |  | 0.041 | 0.071 |  | 0.435 |  |  | 0.071 | [13 empty] | 0.071
| E00017 | Surplus Place Removal Radclyffe/St Clements | 0.161 | Feb 04 | Aug 07 | 0.062 | 0.014 | 0.014 | 0.014 | 0.014 | 0.012 | 0.013 | 0.013 | 0.013 | 0.013 | 0.013 | 0.013 | 0.015 | 0.068 | [5 empty] | 0.068 | 0.093 |  | 0.161 | [15 empty] | 0.093 | 0.093
| e00510 | The Albion | 0.306 | Apr 01 | Mar 06 | 0.029 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.026 | 0.026 | 0.026 | 0.026 | 0.026 | 0.026 | 0.025 | 0.125 | [5 empty] | 0.306 | 0 |  | 0.306 | [16 empty] | 0
| e04851 | Beacon Resource Centre | 0.322 | May 04 | Aug 05 | 0.2 | 0.026 | 0.026 | 0.026 | 0.026 | 0.026 | 0.027 | 0.027 | 0.027 | 0.027 | 0.027 | 0.027 | 0.03 | 0.13 |  | 0.001 |  |  |  | 0.321 | 0 |  | 0.322 | [16 empty] | 0
| E00514 | Wentworth High School | 0.036 | Apr 05 | Mar 06 | 0.005 | 0.003 | 0.003 | 0.003 | 0.003 | 0.003 | 0.003 | 0.003 | 0.003 | 0.003 | 0.003 | 0.003 | 0.003 | 0.015 | [5 empty] | 0.036 | 0 |  | 0.036 | [16 empty] | 0
|  | ACG minor works | 0.009 | Apr 05 | Mar 06 | 0.011 | [11 empty] | 0.009 | 0 | [5 empty] | 0.009 | 0 |  | 0.009 | [16 empty] | 0
| e01008 | VA minor works | 0.004 | Apr 05 | Mar 06 | 0.001 | [11 empty] | 0.004 | 0 | [5 empty] | 0.004 | 0 |  | 0.004 | [16 empty] | 0
|  | Little Hulton Childrens Centres | 1.506 | Apr 05 | Mar 06 | 0.075 | 0.01 | 0.01 | 0.02 | 0.1 | 0.1 | 0.25 | 0.25 | 0.25 | 0.15 | 0.15 | 0.05 | 0.166 | 0.24 | [6 empty] | 1.506 |  | 1.506 |  |  |  | 1.506 | [12 empty] | 1.506
|  | Larkhill Childrens Centres | 0.23 | Apr 05 | Mar 06 | 0.015 | [11 empty] | 0.23 | 0 | 2005-08-15 | [5 empty] | 0.23 |  | 0.23 |  |  |  | 0.23 | [12 empty] | 0.23
|  | Winton Nursery | 0.235 | Apr 05 | Mar 06 | 0.184 | [11 empty] | 0.235 | 0 | x | [5 empty] | 0.235 |  | 0.235 |  |  |  | 0.235 | [12 empty] | 0.235
|  | Barton Moss Neighbourhood Nursery | 0.129 | Apr 05 | Mar 06 | 0.017 | [11 empty] | 0.129 | 0 | [6 empty] | 0.129 |  | 0.129 |  |  |  | 0.129 | [12 empty] | 0.129
|  | Belvedere | 0.5 | Apr 05 | Mar 06 | 0.039 | [11 empty] | 0.5 | 0 | [6 empty] | 0.5 |  | 0.5 |  |  |  | 0.5 | [12 empty] | 0.5
|  | North Swinton Childrens Centres | 0.5 | Apr 05 | Mar 06 | [12 empty] | 0.5 | 0 | [6 empty] | 0.5 |  | 0.5 |  |  |  | 0.5 | [12 empty] | 0.5
|  | Irlam Childrens Centres | 0.5 | Apr 05 | Mar 06 | [12 empty] | 0.5 | 0 | [6 empty] | 0.5 |  | 0.5 |  |  |  | 0.5 | [12 empty] | 0.5
| E04852-3 | Specialist colleges | 0.129 | Apr 05 | Aug 05 | 0.128 | 0.025 | 0.025 | 0.025 | 0.025 | 0.029 | [7 empty] | 0.129 | [6 empty] | 0.129 |  | 0.129 | [15 empty] | 0.129 | 0.129
| e02027 | adult education grant | 0.01 | Apr 05 | June 05 | 0.029 | 0.002 | 0.002 | 0.002 | 0.002 | 0.002 | [7 empty] | 0.01 | [6 empty] | 0.01 |  | 0.01 | [15 empty] | 0.01 | 0.01
|  | Charlestown primary | 0.002 | [15 empty] | 0 |  |  |  |  | 0.002 |  | 0 |  | 0.002 | [16 empty] | 0
|  | School Travel Plans | 0.086 | Apr 05 | Mar 08 | 0.004 | [11 empty] | 0.091 | 0 | [6 empty] | 0.086 |  | 0.086 |  |  |  |  | 0.086 | [11 empty] | 0.086
|  | CHILDREN'S SERVICES - TOTAL | 14.628 |  |  | 3.746 | 0.34 | 0.341 | 0.351 | 0.435 | 1.544 | 1.456 | 1.456 | 1.456 | 1.356 | 1.356 | 1.257 | 3.7 | 3.011 |  | 0.823 | 0 | 0 | 0.002 | 3.974 | 9.806 | 0.023 | 14.628 | 0 | 0 | 3.054 | 3.725 | 0.086 | 2.606 | 0.103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.232 | 9.806
|  | HIGHWAYS | [42 empty] | 0
summary | D00003 | Cadishead Way Stage 1 | 0.075 | 1991-01-01 | 1992-03-01 | [12 empty] | 0.075 | 0 | [8 empty] | 0 | [16 empty] | 0
summary | D00004 | Cadishead Way Stage 2 | 6.966 | 2004-02-01 | 2005-09-01 | 1.892 | 0.7 |  | 0.93 | 0.93 | 0.93 | 0.93 | 0.93 | 0.93 |  |  |  | 2 | 3.49 |  | 0 | 1.732 |  |  |  | 6.482 |  | 8.214 | 6.482 | [15 empty] | 6.482
summary | D00005 | Manchester/Salford Inner Relief Route | 3.719 | 2001-02-01 | 2004-11-01 | 2.933 | [5 empty] | 2.549 | [6 empty] | 0 | [6 empty] | 2.527 |  | 2.527 | 2.527 | [15 empty] | 2.527
| D00101 | Anti-skid Surfacing Programme | 0.1 | 2005-04-01 | 2006-03-01 |  |  | 0.009 | 0.009 | 0.009 | 0.009 | 0.009 | 0.009 | 0.009 | 0.009 | 0.009 | 0.009 | 0.009 | 0.036 | [8 empty] | 0
| D00103 | Accident Investigation | 0.02 | 2005-04-01 | 2006-03-01 | 0.001 |  | 0.002 | 0.002 | 0.002 | 0.002 | 0.002 | 0.002 | 0.002 | 0.002 | 0.002 | 0.002 |  | 0.008 | [8 empty] | 0
| D00104 | White Lining Programme | 0.015 | 2005-04-01 | 2006-03-01 | 0.002 |  | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.004 | [8 empty] | 0
| D00105 | Road Safety Strategy | 0.005 | 2005-04-01 | 2006-03-01 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0
| D00107 | A6 Crescent/Irwell Place |  |  |  | 0.001 | [21 empty] | 0
| D00111 | 20mph Zone - Westwood Park Winton |  |  |  | 0.001 | [21 empty] | 0
| D00119 | Barton Lane Ped Improvements | 0.05 | 2005-05-05 | 2005-07-05 |  |  |  | 0.025 | 0.025 | [8 empty] | 0.05 | [8 empty] | 0
| D00121 | A6 High Street/ Campbell Way | 0.001 | - | - | [13 empty] | 0 | [8 empty] | 0
| D00125 | A580 East Lancs/Worsley Road |  |  |  | 0.007 | [21 empty] | 0
| D00141 | Moorside Rd/Wardley Ind Estate Area Sch | 0.08 | 2005-09-01 | 2005-11-01 | 0.002 | [7 empty] | 0.04 | 0.04 |  |  |  | 0 | [8 empty] | 0
| D00142 | B5229 Monton Centre Scheme | 0.01 | 2006-04-01 | 2006-07-01 | 0.003 | [11 empty] | 0.01 | 0 | [8 empty] | 0
| D00143 | Cadishead NW Area Safety Scheme | 0 | 2003-12-01 | 2004-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0
| D00148 | A6 Chorley Road Route Scheme | 0.002 | 2006-06-01 | 2006-09-01 | [12 empty] | 0.002 | 0 | [8 empty] | 0
| D00161 | Trafford Road, Eccles, Speed Management | 0.005 | 2004-10-04 | 2004-12-04 | 0.005 | 0.002 | 0.002 | [10 empty] | 0.004 | [8 empty] | 0
| D00166 | Newearth Rd - Traffic Calming |  |  |  | 0.001 | [21 empty] | 0
| D00172 | Kersal Area Traffic Calming | 0 | 2003-03-01 | 2004-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0
| D00173 | New Lane, Winton | 0.07 | 2005-02-05 | 2005-04-05 | 0.006 |  | 0.019 | 0.019 | [9 empty] | 0.038 | [8 empty] | 0
| D00174 | City wide Speed Management Policy |  |  |  | 0.002 | [21 empty] | 0
| D00175 | Amendments to Early T Calming Schemes | 0.008 | 2004-04-01 | 2005-03-01 | 0.008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.004 | 0 | [8 empty] | 0
| D00176 | Dealing with Disadvantage Initiative | 0.18 | 2005-09-01 | 2005-12-01 | 0.004 | [8 empty] | 0.09 | 0.09 |  |  | 0 | [8 empty] | 0
| D00177 | Liverpool Rd, Cad, Speed Management | 0 | [15 empty] | 0 | [8 empty] | 0
| D00178 | Greenleach Lane, Worsley | 0.03 | 2005-09-01 | 2005-10-01 | 0.018 | [6 empty] | 0.03 | [5 empty] | 0 | [8 empty] | 0
| D00179 | Oxford Road Remedial Traffic Calming | 0.01 | 2005-02-05 | 2005-04-05 |  |  | 0.005 | 0.005 | [9 empty] | 0.01 | [8 empty] | 0
| D00180 | Langley Rd Speed Reduction Measures | 0.05 | 2005-01-01 | 2005-02-01 | 0.002 | [11 empty] | 0.05 | 0 | [8 empty] | 0
| D00181 | Light Oaks Primary Safer Routes | 0.02 | 2006-01-01 | 2006-04-01 | [10 empty] | 0.02 | 0.02 | 0.02 | 0 | [8 empty] | 0
| D00182 | St Georges High School Safer Routes | 0.01 | 2006-01-01 | 2006-04-01 | [10 empty] | 0.02 | 0.02 | 0.02 | 0 | [8 empty] | 0
| D00183 | Station Rd/Bolton Rd Ped'n Facilities | 0.005 | 2006-03-01 | 2006-08-01 | 0.003 | 0.02 | [10 empty] | 0.02 | 0.02 | 2005-04-04 | [7 empty] | 0
| D00184 | Gerald Road Area Traffic Calming | 0.075 | 2005-11-01 | 2006-02-01 | 0.001 | [8 empty] | 0.025 | 0.025 | 0.025 |  | 0 | [8 empty] | 0
| D00185 | Partington Ln/Worsley Rd Junction | 0.01 | 2006-02-01 | 2006-04-01 | 0.001 | [11 empty] | 0.03 | 0 | [8 empty] | 0
| D00186 | A666 / M60 J'n Cyclist Awareness | 0.035 | 2006-02-01 | 2006-04-01 | [12 empty] | 0.035 | 0 | [8 empty] | 0
| D00187 | Parrin Lane/Monton Fields St Lighting | 0.025 | 2006-03-01 | 2006-04-01 | [12 empty] | 0.025 | 0 | [8 empty] | 0
| summary | Local Safety schemes | 0.816 | 2004-04-01 | 2005-03-01 | 0.068 | 0.022 | 0.038 | 0.061 | 0.037 | 0.012 | 0.012 | 0.042 | 0.052 | 0.167 | 0.167 | 0.077 | 0.226 | 0.17 | [8 empty] | 0
| D00500 | Bridge Inspections and Assessments | 0 | 2005-04-01 | 2006-03-01 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0
| D00501 | Bridges general | 0.01 | 2005-04-01 | 2006-03-01 | 0.001 |  |  | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.003 | [8 empty] | 0
| D00503 | Subways | 0.005 | 2005-04-01 | 2006-03-01 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.005 | 0 | [8 empty] | 0
| D00510 | Network Rail Bridges | 0.09 | [24 empty] | 0
| D00512 | Eccles Old Road Underpass | 0.005 | 2004-01-01 | 2004-04-04 |  | 0.002 | 0.002 | 0.001 | [9 empty] | 0.005 | [8 empty] | 0
| D00524 | Pendleton Roundabout Parapets Ph1 | 0.013 | 2003-12-01 | 2004-05-01 | 0.013 | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | [6 empty] | 0.005 | [8 empty] | 0
| D00525 | Railtrack Incursion Works | 0.075 | 2005-06-01 | 2005-06-01 | 0.001 |  | 0.001 | 0.02 | 0.001 |  | 0.015 |  | 0.015 |  |  |  | 0.015 | 0.022 | 2005-05-23 | [7 empty] | 0
| D00527 | Culvert Safety Improvement Programme | 0.02 | 2004-09-01 | 2006-03-01 | [6 empty] | 0.002 | 0.003 | 0.003 | 0.003 | 0.003 | 0.003 | 0.003 | 0 | [8 empty] | 0
| D00528 | Wallness Bridge | 0.002 | 2004-05-01 | 2004-06-01 | 0.001 |  |  |  | 0.002 | [8 empty] | 0.002 | [8 empty] | 0
| D00529 | West Egerton Street Bridge | 0 | 2004-02-01 | 2004-07-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0
| D00530 | Woden Street Footbridge | 0 | 2004-07-04 | 2004-10-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0
| D00531 | Eccles Road Footbridge Painting | 0.002 | 2004-07-04 | 2004-10-04 | [6 empty] | 0.001 | 0.001 | [5 empty] | 0 | [8 empty] | 0
| D00532 | Hough Lane Footbridge | 0.005 | 2004-08-04 | 2004-10-04 | 0.004 | [5 empty] | 0.002 | 0.003 | [5 empty] | 0 | [8 empty] | 0
| D00533 | Stott Lane Railway Bridge | 0 | 2005-04-05 | 2005-08-05 |  |  | 0.019 | 0.019 | 0.019 | 0.019 | [7 empty] | 0.076 | [8 empty] | 0
| D00534 | Heywood Way Subway Infill | 0.003 | - | - | [12 empty] | 0.003 | 0 | [8 empty] | 0
| D00535 | Pendleton Roundabout Parapets Ph2 | 0.009 | 2005-01-05 | 2005-03-05 | 0.009 | [10 empty] | 0.003 | 0.003 | 0 | [8 empty] | 0
| D00536 | East Ordsall Lane Canal Bridge | 0.1 | 2005-10-01 | 2006-10-01 | 0.014 | [6 empty] | 0.016 | 0.016 | 0.016 | 0.016 | 0.016 | 0.02 | 0 | [8 empty] | 0
| D00537 | Eccles Old Road Subway Drainage | 0.025 | 2005-12-01 | 2005-12-01 | [11 empty] | 0.025 |  | 0 | [8 empty] | 0
| D00538 | Swinton Subway (Moorside Ramp) | 0.055 | 2006-01-01 | 2006-02-01 | [12 empty] | 0.055 | 0 | [8 empty] | 0
| D00539 | Little Hulton Station Bridge | 0.115 | 2006-01-01 | 2006-03-01 | [11 empty] | 0.058 | 0.058 | 0 | [8 empty] | 0
| D00540 | West/East Bridges, Pendleton Roundabout | 0 | 2005-08-01 | 2005-09-01 | [12 empty] | 0.05 | 0 | [8 empty] | 0
| D00541 | Monton Canal Bridge | 0.1 | 2005-07-01 | 2005-09-01 | 0.006 | [10 empty] | 0.05 | 0.05 | 0 | [8 empty] | 0
| D00542 | Mariners Canal Central Footbridge | 0.03 | 2005-05-01 | 2005-07-01 | 0.025 |  | 0.012 | 0.012 | 0.003 | [8 empty] | 0.027 | 2005-05-16 | [7 empty] | 0
| D00543 | Pendleton Roundabout Retaining Walls | 0.15 | 2005-10-01 | 2005-11-01 | 0.002 | [7 empty] | 0.048 | 0.047 |  |  |  | 0 | [8 empty] | 0
| D00544 | Centenary Bridge Abutments | 0.026 | 2005-03-01 | 2005-03-01 | 0.007 | [11 empty] | 0.026 | 0 | [8 empty] | 0
| summary | Bridge Assessment and Strengthening Schemes | 0.84 | 2004-04-01 | 2005-03-01 | 0.083 | 0.003 | 0.035 | 0.054 | 0.027 | 0.021 | 0.022 | 0.024 | 0.083 | 0.067 | 0.02 | 0.156 | 0.289 | 0.14 | [8 empty] | 0
| D00601 | A57 Liverpool Road, Cadishead (New Moss Road - Fir Street) | 0.001 |  |  | 0.001 | [12 empty] | 0 | [8 empty] | 0
| D00603 | A576 Great Cheetham St |  |  |  | 0.001
| D00604 | A572 Worsley Road (Greenleach - Ringlow) |  |  |  | 0.001
| D00600 | A666 Bolton Rd (Hospital Rd - Bridge St) |  |  |  | 0.001
| D00605 | BVPI Surveys | 0.06 | 2003-08-01 | 2003-12-01 | 0.036 | [10 empty] | 0.03 | 0.03 | 0 | [8 empty] | 0
| D00606 | A57 Liverpool Rd (Boysnope - Barton Moss Road) | 0 | [15 empty] | 0 | [8 empty] | 0
| D00608 | Principal Road Maintenance - General | 0.02 | 2004-04-01 | 2005-03-01 |  |  |  | 0.002 | 0.002 | 0.002 | 0.002 | 0.002 | 0.002 | 0.002 | 0.002 | 0.002 | 0.002 | 0.006 | [8 empty] | 0
| D00610 | A575 Walkden Road (Manchester Road - Park Road) | 0.008 | 2004-01-01 | 2004-06-01 |  | 0.002 | 0.002 | 0.002 | 0.002 | [8 empty] | 0.008 | [8 empty] | 0
| D00611 | A576 Cromwell Rd (Lissadel St - Lwr Broughton) |  |  |  | 0.002
| D00613 | A5082 Armitage Av (M/cr Rd - Boundary) |  |  |  | 0.002
| D00614 | Structural Maintenance of Minor Roads | 0.009 | 2003-10-01 | 2005-03-01 | 0.004 | 0.001 | 0.001 | 0.001 | 0.001 | [7 empty] | 0.005 | 0.004 | [8 empty] | 0
| D00617 | A5066 Adelphi Street & Silk Street | 0.005 | 2004-11-01 | 2005-03-05 | 0.005 | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | [7 empty] | 0.005 | [8 empty] | 0
| D00618 | A5066 Oldfield Road(Ordsall Lane - Regent Road) | 0.025 | 2005-01-05 | 2005-03-01 | 0.025 | 0.004 | 0.004 | [10 empty] | 0.008 | [8 empty] | 0
| D00619 | A5066 Oldfield Road (Regent Road - Crescent) | 0.01 | 2005-01-01 | 2205-03-01 | 0.01 | 0.005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.005 | [8 empty] | 0
| D00620 | A575 Cleggs Lane (A6 - Bolton Boundary) | 0.59 | 2005-03-05 | 2005-06-05 | 0.004 |  |  |  | 0.003 | 0.079 | 0.079 | 0.079 | 0.079 | 0.079 | 0.079 | 0.079 | 0.032 | 0.082 | 2005-08-01 | [7 empty] | 0
| D00624 | S/l Westbourne Ave |  |  |  | 0.004
| D00625 | S/lL Langley Road |  |  |  | 0.003
| D00629 | Street Lighting Inventory Work | 0.06 | - | - | 0 | [11 empty] | 0.06 | 0 | [8 empty] | 0
| D00630 | Langworthy Road (Liverpool Street - Eccles New Road) | 0.275 | 2005-10-01 | 2006-01-01 | 0.011 | [8 empty] | 0.08 | 0.08 | 0.08 |  | 0 | [8 empty] | 0
| D00631 | Albion Way (Broad St - Regent Rd) | 0.005 | 2006-11-01 | 2007-02-01 | 0.001 | [11 empty] | 0.005 | 0 | [8 empty] | 0
| D00632 | Worsley Road (East Lancs Rd - Ringlow Park Rd) | 0.47 | 2005-12-01 | 2006-03-01 | 0.005 | [9 empty] | 0.157 | 0.157 | 0.157 | 0 | [8 empty] | 0
| D00633 | A666 Manchester Road (Clifton House Road - Manley Avenue) | 0.34 | 2005-11-01 | 2006-02-01 | 0.002 | [9 empty] | 0.033 | 0.033 | 0.033 | 0 | [8 empty] | 0
| D00634 | Cadishead Way Stage 1 Repairs | 0.242 | 2005-08-01 | 2005-09-01 | 0.009 | [5 empty] | 0.1 | 0.1 | [5 empty] | 0 | [8 empty] | 0
| D00635 | Street Lighting in support of HI prog | 0.1 | 2005-09-01 | 2006-03-01 | [22 empty] | 0
| summary | Principal Roads Structural Maintenance | 2.22 | 2004-04-01 | 2005-03-01 | 0.127 | 0.013 | 0.008 | 0.006 | 0.009 | 0.082 | 0.181 | 0.181 | 0.081 | 0.161 | 0.351 | 0.381 | 0.324 | 0.118 | [8 empty] | 0
| D00703 | A56 Quality Bus Corridor | 0.021 | 2003-11-01 | 2005-01-05 | 0.02 | [9 empty] | 0.01 | 0.011 |  | 0 | [8 empty] | 0
| D00709 | A57 Irlam Bus Stop Improvements | 0.06 | 2006-01-01 | 2007-04-01 | [12 empty] | 0.06 | [9 empty] | 0
| D00708 | Central Station Study | 0.008 | - | - | 0.008 | [12 empty] | 0 | [8 empty] | 0
| summary | Public Transport Schemes | 0.089 |  |  | 0.028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0.011 | 0.06 | [9 empty] | 0
| D00803 | Barton Cycling Facilities | 0.28 | 2005-03-05 | 2005-05-05 | 0.27 | [11 empty] | 0.28 | 0 | [8 empty] | 0
| D00805 | Cycle Parking Facilities | 0.01 | 2004-09-01 | 2005-03-01 | 0.001 | [11 empty] | 0.02 | 0 | [8 empty] | 0
| D00806 | Sustrans Routes | 0.072 | 2005-07-01 | 2005-09-01 | 0.019 | [11 empty] | 0.2 | 0 | [8 empty] | 0
| D00807 | Cycling Projects Grant Fund | 0.025 | 2005-02-05 | 2005-03-01 |  | 0.025 | 0.025 | [10 empty] | 0.05 | [8 empty] | 0
add on 40 for sustrants cont | D00808 | Tyldesley Loopline Surfacing Improv'ts | 0.06 | 2005-03-05 | 2005-05-05 |  | 0.015 | 0.02 | 0.02 | 0.013 | [8 empty] | 0.068 | 2005-04-18 | [6 empty] | 0.04 | 0.04 | [17 empty] | sustrans contribution
| D00809 | Cycle Parking Facilities at Schools | 0.075 | - | - |  | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.03 | [8 empty] | 0
| D00810 | Irwell Walk, Charlestown, New Deal Cont' | 0.015 | - | - |  | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.005 | [8 empty] | 0
| D00811 | A580 East Lancs Rd (To Wigan Boundary) | 0.01 | 2005-10-01 | 2005-11-01 | 0.002 | [8 empty] | 0.01 |  |  |  | 0 | [8 empty] | 0
| summary | Schemes to Assist Cycling | 0.547 | 2004-04-01 | 2005-03-01 | 0.292 | 0.047 | 0.052 | 0.027 | 0.02 | 0.007 | 0.007 | 0.007 | 0.007 | 0.017 | 0.007 | 0.007 | 0.507 | 0.153 | [8 empty] | 0
| D00901 | GM Local Transport Plan | 0.04 | 1999-04-01 | 2005-03-01 | 0.004 |  |  | 0.004 | 0.004 | 0.004 | 0.004 | 0.004 | 0.004 | 0.004 | 0.004 | 0.004 | 0.004 | 0.012 | [8 empty] | 0
| D00902 | Salford's Green Transport Plan | 0.01 | 2005-01-01 | 2005-03-01 | [11 empty] | 0.013 | 0.013 | 0 | [8 empty] | 0
| D00903 | M60/ PRN Signing | 0.001 | 1998-04-01 | 2005-03-01 | 0.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0
| D00909 | AGMA Countywide Advertising | 0.005 | 2000-04-01 | 2005-03-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.005 | 0 | [8 empty] | 0
| D00912 | Disabled Facilities at Pedestrian Crossings | 0.15 | 2003-04-01 | 2005-03-01 | 0.055 |  |  | 0.014 | 0.014 | 0.014 | 0.014 | 0.014 | 0.014 | 0.014 | 0.014 | 0.014 | 0.024 | 0.042 | [8 empty] | 0
| D00918 | Chapel St Pedestrian Route Improve'ts | 0 | 2004-08-01 | 2004-10-01 | -0.008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0
| D00920 | Barton Rd/Barton Ln/Peel Rd UTC wk |  |  |  | 0.029
| D00923 | Little Moss Lane Works | 0.05 | 2003-11-01 | 2004-07-01 | 0.001 |  |  |  |  | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.008 | 0.006 | [8 empty] | 0
| D00924 | Miscellaneous SRTS Works | 0 | 2003-08-01 | 2005-03-01 | [5 empty] | 0.002 | 0.002 | 0.002 | 0.002 | 0.002 | 0.002 | 0.002 | 0.002 | 0.002 | [8 empty] | 0
| D00925 | GMTU Non-core Modelling Work | 0.01 | 2003-06-01 | 2005-03-01 |  | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.001 | 0.005 | [8 empty] | 0
| D00926 | Public Rights of Way Signing | 0.03 | 2005-01-01 | 2006-03-01 | [11 empty] | 0.015 | 0.015 | 0 | [8 empty] | 0
| D00927 | Public Rights of Way Improvements | 0.007 | 2004-12-01 | 2005-03-01 | 0.008 | [9 empty] | 0.083 | 0.083 | 0.083 | 0 | [8 empty] | 0
| D00928 | Barton Rd/Barton Ln J'n Improvement | 0.029 | 2005-01-05 | 2005-03-05 | [11 empty] | 0.008 | 0.008 | 0 | [8 empty] | 0
| D00929 | Liverpool Rd, Cadishead, Town Centre | 0.01 | 2005-11-05 | 2006-05-06 | [9 empty] | 0.002 | 0.002 | 0.002 | 0.002 | 0 | [8 empty] | 0
| D00930 | Oaklands Road | 0.001 | 2004-10-04 | 2004-12-04 | 0.001 | [9 empty] | 0.001 |  |  | 0 | [8 empty] | 0
| D00931 | Chapel St/New Bailey St Ped Facilities | 0.04 | 2005-02-05 | 2005-04-05 | 0.038 | [10 empty] | 0.02 | 0.02 | 0 | [8 empty] | 0
| D00932 | Station Road Puffin Crossing | 0.04 | 2005-02-05 | 2005-03-05 | 0.003 | [11 empty] | 0.025 | 0 | [8 empty] | 0
| D00933 | Langworthy Road Parking Layby | 0 | 2005-01-05 | 2005-03-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0
| D00934 | Dropped Kerbs & Tactile Paving Programme | 0.1 | 2005-07-01 | 2006-03-01 | 0.001 |  |  |  |  | 0.009 | 0.013 | 0.013 | 0.013 | 0.013 | 0.013 | 0.013 | 0.013 | 0.009 | [8 empty] | 0
| D00935 | A6 Chorley Rd / Moorside Rd Ped' Facilities | 0.05 | [14 empty] | 0.05 | 0 | [8 empty] | 0
| D00936 | Chapel Street Traffic Management |  | 2006-01-01 | 2006-12-01 | [11 empty] | 0.05 | 0.05 | 0 | [8 empty] | 0
| D00938 | Roe Green Loopline | 0.245 | [24 empty] | 0
| D00939 | Fairhills Rd Puffin Crossing Contribution | 0.055 | [23 empty] | 0.03 | 0.03 | [17 empty] | contribution from Tesco as part of Section 278 agreement, other half of scheme funded from block 3
| D00937 | Major Scheme Feasibility Studies | 0 | - | - | [13 empty] | 0 | [8 empty] | 0
| summary | Other Minor Schemes | 0.873 | 2004-04-01 | 2005-03-01 | 0.133 | 0.001 | 0.001 | 0.019 | 0.019 | 0.036 | 0.04 | 0.04 | 0.04 | 0.042 | 0.126 | 0.231 | 0.323 | 0.076 | [8 empty] | 0
0
| 0.028 | Block 3 overprogramming less cfwd receipts | -1.235 | [24 empty] | 0
| 0.019 | carryforward cont to salford central | 0.019 | [24 empty] | 0
|  | Major schemes anticipated overspend | 0.055 | [22 empty] | 0 |  | 0 | [16 empty] | 0
summary | D07230-d07259 | [24 empty] | 0 |  | 0 | [16 empty] | 0
| summary | Improvement s to the highway network | 0.25 |  |  |  | 0.021 | 0.021 | 0.021 | 0.021 | 0.021 | 0.021 | 0.021 | 0.021 | 0.021 | 0.021 | 0.021 | 0.021 | 0.105 | [8 empty] | 0
D99999 7015 contains , 0.250 highways improvement less overprogramming of 0.115 | [20 empty] | 4.126 |  |  |  | 0.297 | 0 |  | 4.423 | [16 empty] | 0
|  | HIGHWAYS - TOTAL | 15.234 |  |  | 5.556 | 0.807 | 0.155 | 1.118 | 1.063 | 1.109 | 3.762 | 1.245 | 1.214 | 0.475 | 0.702 | 0.884 | 3.825 | 4.252 |  | 4.126 | 1.732 | 0 | 0 | 0.297 | 9.009 | 0.07 | 15.234 | 9.009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.009
COMMUNITY, HEALTH AND SOCIAL CARE
| S05106 | The Limes - Fire Safety | 0.026 | [9 empty] | 0.007 | 0.007 | 0.007 | 0.007 |  |  | 0 | [5 empty] | 0.026 | 0 |  | 0.026 | [16 empty] | 0
| S05052 | Barton Moss Expansion |  |  |  | 0.005
| S05107 | White Meadows - Fire Safety | 0.025 |  |  | 0.005 |  |  | 0.005 |  |  | 0.005 | 0.005 | 0.005 | 0.005 |  |  |  | 0.005 | [5 empty] | 0.025 | 0 |  | 0.025 | [16 empty] | 0
| S09008 | Day Services Modernisation Unallocated | 0.002 | [14 empty] | 0.002 | 0 |  | 0.002 |  |  |  |  | 0 |  | 0.002 | [16 empty] | 0
| S05109 | The Limes - Bathroom/laundry/anc space impr | 0.05 | [9 empty] | 0.008 | 0.008 | 0.008 | 0.008 | 0.008 | 0.008 | 0 | [5 empty] | 0.05 | 0 |  | 0.05 | [16 empty] | 0
| S05151 | Modernising Intermediate Care | 0.009 |  |  | 0.001 |  |  |  |  | 0.003 | 0.003 | 0.003 | [5 empty] | 0.003 |  | 0.005 |  |  |  | 0.004 | 0 |  | 0.009
| S05112 | Day Services Modernisation | 0.024 | [7 empty] | 0.008 | 0.008 | 0.008 | [5 empty] | 0.008 | [5 empty] | 0.024 | 0 |  | 0.024
| S05113 | Homes to Trust |  |  |  | 0.56 | [12 empty] | 0 | [6 empty] | 0 |  | 0
| S06054 | Alexandra House - Bathroom & Toilets | 0.003 | [8 empty] | 0.003 | [6 empty] | 0 | [5 empty] | 0.003 | 0 |  | 0.003 | [16 empty] | 0
| S06152 | Craig Hall Re-roofing | 0.003 |  |  | 0.003 | 0.003 | [11 empty] | 0.003 |  | 0.003 |  |  |  |  | 0 |  | 0.003
| S06155 | Waterside - Replacement boiler | 0.016 | [8 empty] | 0.016 | [6 empty] | 0 | [5 empty] | 0.016 | 0 |  | 0.016 | [16 empty] | 0
| S06157 | Waterside 05/06 car parking |  |  |  | 0.001 | [19 empty] | 0
| S08061 | Crompton House - remodelling of garage | 0.1 | [9 empty] | 0.017 | 0.017 | 0.017 | 0.017 | 0.017 | 0.017 | 0 |  | 0.1 |  |  |  |  | 0 |  | 0.1 | [16 empty] | 0
| S09010 | Brierley CC - Demolition stables/gym | 0.008 |  |  | 0.001 |  |  |  |  | 0.003 | 0.003 | 0.003 | [5 empty] | 0.003 | [5 empty] | 0.008 | 0 |  | 0.008 | [16 empty] | 0
| S09011 | Wardley CC - Car park/paved areas resurface | 0.008 | [8 empty] | 0.004 | 0.004 | [5 empty] | 0 |  | 0.008 |  |  |  |  | 0 |  | 0.008 | [16 empty] | 0
| S09012 | Wardley CC - Replacement boiler | 0.02 | [9 empty] | 0.003 | 0.003 | 0.003 | 0.003 | 0.003 | 0.003 | 0 | [5 empty] | 0.02 | 0 |  | 0.02 | [16 empty] | 0
| S09013 | Boothstown CC - Replacement boiler | 0.033 | [9 empty] | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0 |  | 0.033 |  |  |  |  | 0 |  | 0.033 | [16 empty] | 0
| S08056 | Improving Information Management 2004/2005 | 0.137 |  |  | 0.015 |  |  | 0.014 | 0.014 | 0.014 | 0.014 | 0.014 | 0.014 | 0.014 | 0.014 | 0.014 | 0.014 | 0.042 | [5 empty] | 0.1 | 0.037 |  | 0.137 | [15 empty] | 0.037 | 0.037
| S08058 | Improving Information Management 2005/2006 | 0.248 |  |  | 0.007 |  |  |  |  | 0.031 | 0.031 | 0.031 | 0.031 | 0.031 | 0.031 | 0.031 | 0.031 | 0.031 | [5 empty] | 0.1 | 0.148 |  | 0.248 | [15 empty] | 0.148 | 0.148
| S04006 | Mental Health - S C E (2004/2005) | 0.11 |  |  | 0.006 |  |  |  | 0.005 |  | 0.03 | 0.025 | 0.021 | 0.029 |  |  |  | 0.005 |  |  | 0.09 |  |  |  | 0 | 0.02 | 0.11 | [16 empty] | 0 | .020 mental health contribution
| S09003 | Boothstown / Worsley C C Refurb - Retention | 0.002 | [6 empty] | 0.002 | [8 empty] | 0.002 | [6 empty] | 0 | 0.002 | 0.002 | [16 empty] | 0 | .002 community contribution
| S09005 | Wardley Community Centre - Retention | 0.002 | [6 empty] | 0.002 | [8 empty] | 0.002 | [6 empty] | 0 | 0.002 | 0.002 | [16 empty] | 0 | .002 community contribution
| S09007 | Womens Centre | 0.006 | [5 empty] | 0.003 | 0.003 | [8 empty] | 0.006 | [6 empty] | 0 | 0.006 | 0.006 | [16 empty] | 0 | .006 community contribution
| S00001 | Alterations to Properties - Foster Carers | 0.036 |  |  | 0.02 |  |  |  | 0.004 | 0.004 | 0.004 | 0.004 | 0.004 | 0.004 | 0.004 | 0.004 | 0.004 | 0.008 |  |  |  |  | 0.036 |  | 0 |  | 0.036 | [16 empty] | 0
| S08057 | Integrated Children's Services 2004/5 | 0.057 | [7 empty] | 0.007 | 0.007 | 0.007 | 0.007 | 0.007 | 0.007 | 0.007 | 0.007 | 0.007 | [6 empty] | 0.057 |  | 0.057 | [15 empty] | 0.057 | 0.057 | child service grant
| S08059 | Integrated Children's Services 2005/6 | 0.086 | [7 empty] | 0.011 | 0.011 | 0.011 | 0.011 | 0.011 | 0.011 | 0.011 | 0.011 | 0.011 | [6 empty] | 0.086 |  | 0.086 | [15 empty] | 0.086 | 0.086
| S06051 | Humphrey Booth L B - Booth's Charity Funded | 0.019 |  |  | 0.021 | 0.003 | 0.003 | 0.003 | 0.003 | 0.003 | 0.003 | [6 empty] | 0.015 | [6 empty] | 0 | 0.019 | 0.019 | [16 empty] | 0 | .019 humphrey booth
| S06052 | Humphrey Booth Ordsall - Booth's Charity Funded | 0.031 |  |  | 0.01 | 0.005 | 0.005 | 0.005 | 0.005 | 0.005 | 0.005 | [6 empty] | 0.025 | [6 empty] | 0 | 0.031 | 0.031 | [16 empty] | 0 | .031 humphrey booth
| S09101 | STASH Day Centre | 0.165 |  |  | 0.112 |  |  |  | 0.033 | 0.033 | 0.033 | 0.033 | 0.033 |  |  |  |  | 0.066 | [6 empty] | 0.05 | 0.115 | 0.165 | [15 empty] | 0.05 | 0.05
| S01003 | Sutherland House Refurbishment | 0.079 |  |  | 0.015 |  |  |  |  | 0.015 | 0.04 | 0.022 |  |  |  |  | 0.002 | 0.015 | 2005-07-04 | [5 empty] | 0 | 0.079 | 0.079
| S06151 | Waterside Resource Centre |  |  |  | 0.002 | [12 empty] | 0 | [6 empty] | 0 |  | 0
|  | COMMUNITY, HEALTH AND SOCIAL CARE -TOTAL | 1.305 |  |  | 0.784 | 0.011 | 0.008 | 0.03 | 0.071 | 0.137 | 0.22 | 0.211 | 0.167 | 0.142 | 0.108 | 0.101 | 0.105 | 0.242 |  | 0.151 | 0.09 | 0 | 0.036 | 0.376 | 0.378 | 0.274 | 1.305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.378 | 0.378
ENVIRONMENTAL SERVICES
| F00022 | Parks Infrastructure Improvements | 0.111 |  |  | 0.002 | [12 empty] | 0.04625 | [5 empty] | 0.097 | 0 | 0.014 | 0.111 | [16 empty] | 0 | 0.014 boundary road irlam s106 use as capital receipts this year,
| F00032 | Lightoaks Park | 0.026 |  |  | 0.011 | [12 empty] | 0.010833 | 2005-05-09 |  |  |  |  | 0.02 | 0.006 |  | 0.026 | [15 empty] | 0.006 | 0.006 | greening greater manchester
| F00033 | Princes Park Tennis Court | 0.017 |  |  | 0.014 | [12 empty] | 0.0070833 | [5 empty] | 0.017 | 0 |  | 0.017 | [16 empty] | 0
| F10001 | Parr Fold Pavillion | 0.272 | [15 empty] | 0.11333 | [5 empty] | 0.134 | 0 | 0.138 | 0.272 | [16 empty] | 0 | 0.138 insurance money
| F00010 | Mandley Park | 0.101 | [15 empty] | 0.042083 | 2005-01-27 |  |  |  | 0.003 |  | 0.098 |  | 0.101 | [11 empty] | 0.098 |  |  |  |  | 0.098
| F00011 | Lightoaks Park NOF | 0.066 |  |  | 0.16 | [12 empty] | 0.0275 | [6 empty] | 0.066 |  | 0.066 | [11 empty] | 0.066 |  |  |  |  | 0.066
| F00011 | Eccles Recreation Grd/ Albert Park MUGA | 0.098 | [15 empty] | 0.040833 | [6 empty] | 0.098 |  | 0.098 | [11 empty] | 0.098 |  |  |  |  | 0.098
| F00011 | Albert Park | 0.047 | [15 empty] | 0.019583 | [6 empty] | 0.047 |  | 0.047 | [11 empty] | 0.047 |  |  |  |  | 0.047
| F00011 | Winton park | 0.129 | [15 empty] | 0.05375 | [6 empty] | 0.129 |  | 0.129 |  |  |  | 0.085 | [7 empty] | 0.044 |  |  |  |  | 0.129
| F00013 | Beechfarm Lottery | 0.104 |  |  | 0.094 | [12 empty] | 0.043333 | [6 empty] | 0.104 |  | 0.104 | [11 empty] | 0.104 |  |  |  |  | 0.104
| F00014 | Princes Park | 0.093 |  |  | 0.076 | [12 empty] | 0.03875 | [6 empty] | 0.077 | 0.016 | 0.093 | [11 empty] | 0.077 |  |  |  |  | 0.077 | 0.016 bmx bandits community contribution
| F00017 | Croal Irwell Access/Fencing section 106 | 0.024 | [15 empty] | 0.01 | [6 empty] | 0 | 0.024 | 0.024 | [16 empty] | 0 | section 106
| F00018 | Sharp Street, Walkden section 106 | 0.04 |  |  | 0.04 | [12 empty] | 0.016667 | [6 empty] | 0 | 0.04 | 0.04 | [16 empty] | 0 | section 106
| F00025 | Peel Park section 106 | 0.024 |  |  | 0.024 | [12 empty] | 0.01 | [6 empty] | 0 | 0.024 | 0.024 | [16 empty] | 0 | section 106
| F00004 | Cemetery Roadways | 0.059 | [15 empty] | 0.024583 | [5 empty] | 0.059 | 0 |  | 0.059 | [16 empty] | 0
| F00007 | Buille Hill Park Restoration | 0.184 |  |  | 0.008 | [12 empty] | 0.076667 | [5 empty] | 0.184 | 0 |  | 0.184 | [16 empty] | 0
| F00008 | Cemetery Headstones | 0.055 |  |  | 0.002 | [12 empty] | 0.022917 | [5 empty] | 0.055 | 0 |  | 0.055 | [16 empty] | 0
| F00023 | Recycling Bring Sites | 0.025 |  |  | 0.021 | [12 empty] | 0.010417 | [5 empty] | 0.025 | 0 |  | 0.025 | [16 empty] | 0
| F00024 | SCE Crofters Heights | 0.005 | [15 empty] | 0.0020833 |  |  | 0.005 |  |  |  | 0 |  | 0.005 | [16 empty] | 0
| F000 | Waste Performance Efficiency Grant | 0.095 | [15 empty] | 0.039583 | [6 empty] | 0.095 |  | 0.095 | [15 empty] | 0.095 | 0.095
| F00021 | Chesnut Ave Depot |  |  |  | 0.002 | [12 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
| f00034 | Hancocks Tip Site Investigation |  |  |  | 0.013 | [12 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
| F00035 | Wheeled Bins | 0.03 | [15 empty] | 0.0125 |  |  |  | 0.03 |  |  | 0 |  | 0.03 | [16 empty] | 0
| F00037 | Beechfarm playing fields drainage | 0.269 |  |  | 0.006 | [12 empty] | 0.11208 |  |  |  |  | 0.017 |  | 0.122 | 0.13 | 0.269 | [11 empty] | 0.122 |  |  |  |  | 0.122 | 0.122 football foundation
[26 empty] | 0 |  | 0 | [16 empty] | 0
|  | ENVIRONMENTAL SERVICES - TOTAL | 1.874 |  |  | 0.473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.78083 |  | 0 | 0.005 | 0.03 | 0.02 | 0.591 | 0.842 | 0.386 | 1.874 | 0 | 0 | 0 | 0.085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.656 | 0 | 0 | 0 | 0.101 | 0.842
ARTS & LEISURE
partially adjusted via control 04/05 | w00001 | City wide investment | 0.258 |  |  | 0.032 | [12 empty] | 0.1075 |  |  |  | 0.258 |  |  | 0 |  | 0.258 | [16 empty] | 0
| E05703 | Winton Community Library | 0.004 | [15 empty] | 0.0016667 | [5 empty] | 0.004 | 0 |  | 0.004 | [16 empty] | 0
| E05007 | SPACE Dukesgate Primary |  |  |  | 0.001 | [12 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
| e05030 | Cleavley Athletic Track | 0.101 |  |  | 0.025 | [12 empty] | 0.042083 | [5 empty] | 0.091 | 0.01 |  | 0.101 | [11 empty] | 0.01 |  |  |  |  | 0.01
| e05031 | DDA arts and leisure | 0.044 |  |  | 0.012 | [12 empty] | 0.018333 | [5 empty] | 0.044 | 0 |  | 0.044 | [16 empty] | 0
| E05032 | Efficiency Improvements | 0.003 | [15 empty] | 0.00125 | [5 empty] | 0.003 | 0 |  | 0.003 | [16 empty] | 0
| e05033 | Sports Village | 2.022 |  |  | 0.287 | [12 empty] | 0.8425 | [5 empty] | 0.5 | 1.522 | 0 | 2.022 | [10 empty] | 0.639 |  |  |  |  | 0.883 | 1.522
| e05037 | Ordsall Recreation Centre | 0.017 |  |  | 0.008 | [12 empty] | 0.0070833 |  |  |  |  | 0.017 |  | 0 |  | 0.017 | [16 empty] | 0
| e05038 | Broughton Pool ICT suite |  |  |  | 0.008 | [12 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
| E05041 | Roller Hockey Relocation |  |  |  | 0.012 | [12 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
|  | Lledr Hall Outdoor Education Centre | 0.126 | [15 empty] | 0 | 2005-08-15 |  |  | 0.095 |  |  | 0.031 |  | 0.126 | [11 empty] | 0.031 |  |  |  |  | 0.031
|  | Arts and Leisure - Broughton Pool additional scheme | 0.017 | [15 empty] | 0.0070833 | [6 empty] | 0 | 0.017 | 0.017 | [16 empty] | 0 | 0.017 cont from SCL
|  | Arts and Leisure - Irlam Pool additional scheme | 0.03 | [15 empty] | 0.0125 | [6 empty] | 0 | 0.03 | 0.03 | [16 empty] | 0 | 0.030 cont from SCL
|  | Eccles Youth Centre | 0.01 | [15 empty] | 0.0041667 | [5 empty] | 0.01 | 0 |  | 0.01 | [16 empty] | 0
|  | Hope Library | 0.005 | [15 empty] | 0.0020833 | [6 empty] | 0 | 0.005 | 0.005 | [16 empty] | 0 | NHS contribution
|  | Library service computerisation | 0.014 | [15 empty] | 0.0058333 | [5 empty] | 0.014 | 0 |  | 0.014 | [16 empty] | 0
|  | SPACE | [16 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
| E05036 | Orthodox Jewish school | 0.116 | [15 empty] | 0.048333 | [6 empty] | 0.116 |  | 0.116 | [11 empty] | 0.1 |  |  |  | 0.016 | 0.116
| E05015 | Clarendon | 0.241 |  |  | 0.242 | [12 empty] | 0.10042 | [6 empty] | 0.235 | 0.006 | 0.241 | [11 empty] | 0.235 |  |  |  |  | 0.235
|  | CSD officers | 0.081 | [15 empty] | 0.03375 | [6 empty] | 0.081 |  | 0.081 | [11 empty] | 0.081 |  |  |  |  | 0.081
|  | Irlam bulkead | 0.2 | [15 empty] | 0.083333 | [6 empty] | 0.2 |  | 0.2 | [11 empty] | 0.2 |  |  |  |  | 0.2
|  | Irlam changing rooms | 0.107 |  |  | 0.002 | [12 empty] | 0.044583 | [6 empty] | 0.107 |  | 0.107 | [11 empty] | 0.107 |  |  |  |  | 0.107
| E05011 | Lledr Hall | 0.894 |  |  | 0.277 | [12 empty] | 0.3725 |  |  |  |  | 0.114 |  | 0.757 | 0.023 | 0.894 | [11 empty] | 0.757 |  |  |  |  | 0.757
|  | Portfolio manager | 0.037 | [15 empty] | 0.015417 | [6 empty] | 0.037 |  | 0.037 | [11 empty] | 0.037 |  |  |  |  | 0.037
| E05027 | Fit City Worsley | 0.302 |  |  | 0.067 | [12 empty] | 0.12583 | [5 empty] | 0.294 | 0.008 |  | 0.302 | [11 empty] | 0.008 |  |  |  |  | 0.008
| E05019 | St Ambrose Barlow | 0.015 | [15 empty] | 0.00625 | [6 empty] | 0.015 |  | 0.015 | [11 empty] | 0.015 |  |  |  |  | 0.015
| E05021 | St Patricks | 0.075 | [15 empty] | 0.03125 | [6 empty] | 0.075 |  | 0.075 | [11 empty] | 0.075 |  |  |  |  | 0.075
| E05043 | Bridgewater FC faclity | 0.022 |  |  | 0.03 | [12 empty] | 0.0091667 | [6 empty] | 0.022 |  | 0.022 | [15 empty] | 0.022 | 0.022
| E05034 | Talmud Torah | 0.014 | [22 empty] | 0.014 |  | 0.014 | [11 empty] | 0.012 |  |  |  | 0.002 | 0.014
| E05040 | Clarendon Fitness centre |  |  |  | 0.017 | [12 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0
|  | ARTS & LEISURE - TOTAL | 4.755 |  |  | 1.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9229 |  | 0 | 0 | 0.353 | 0.131 | 0.96 | 3.23 | 0.081 | 4.755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.639 | 1.668 | 0 | 0 | 0 | 0.923 | 3.23
CUSTOMER AND SUPPORT SERVICES
| C00059 7015 | Office Refurbishments | 0.516 |  |  |  | 0.041 | 0.041 | 0.041 | 0.041 | 0.042 | 0.042 | 0.042 | 0.042 | 0.042 | 0.042 | 0.042 | 0.042 | 0.206 | [5 empty] | 0.516 | 0 |  | 0.516 | [16 empty] | 0
| C00059 7027 | Capitalisation of Revenue | 2.225 | [14 empty] | 2.225 | 0 | [5 empty] | 2.225 | 0 |  | 2.225 | [16 empty] | 0
adjusted via control 04/05 | c00063 | Data Centre | 0.164 |  |  | 0.143 | [12 empty] | 0.068333 |  |  |  | 0.164 |  |  | 0 | 0 | 0.164 | [16 empty] | 0
| C99999 7015 | Swinton Library temporary relocation | 0.186 | [15 empty] | 0.0775 | [6 empty] | 0 | 0.186 | 0.186 | [16 empty] | 0 | lift enabling fund
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
| C00070 | Network and SANs upgrade | 0.145 | [15 empty] | 0.060417 |  |  |  | 0.145 |  |  | 0 |  | 0.145
| C99999 7027 | Security Civic Centre Main Reception | 0.045 | [15 empty] | 0.01875 | [5 empty] | 0.045 | 0 |  | 0.045
adjusted via control 04/05 | C00064 | Replacement Council Tax system | 0.123 | [15 empty] | 0.05125 |  |  |  | 0.123 |  |  | 0 |  | 0.123 | [16 empty] | 0
| C00068 | Call Centre - relocation | 0.03 | [15 empty] | 0.0125 | [5 empty] | 0.03 | 0 |  | 0.03
| C00069 | Upgrading IT training rooms | 0.1 | [15 empty] | 0.041667 | [5 empty] | 0.1 | 0 |  | 0.1
on revenue journalled at year end | C99999 7017 | Highways depot | 0.039 | [14 empty] | 0.039 | 0 | [5 empty] | 0.039 | 0 |  | 0.039
| C00054 | Schools networking lease |  |  |  | 0.002 | [12 empty] | 0 | [6 empty] | 0 |  | 0
| C00067 | Implementing e government | 0.15 | [15 empty] | 0.0625 | [6 empty] | 0.15 |  | 0.15 | [15 empty] | 0.15 | 0.15 | e governmnent grant 05/06
|  | CUSTOMER AND SUPPORT SERVICES - TOTAL | 3.723 |  |  | 0.145 | 0.041 | 0.041 | 0.041 | 0.041 | 0.042 | 0.042 | 0.042 | 0.042 | 0.042 | 0.042 | 0.042 | 2.306 | 0.59892 |  | 0 | 0 | 0.432 | 0 | 2.955 | 0.15 | 0.186 | 3.723 | [15 empty] | 0.15 | 0.15
CHIEF EXECUTIVE
|  | Community Envrionment Programme | 0.363 |  |  | 0.044 | [12 empty] | 0.15125 | [6 empty] | 0.363 |  | 0.363 | [9 empty] | 0.163 | 0.2 | [5 empty] | 0.363
|  | Salford Innovation Park | 8.126 |  |  | 0.023 | [12 empty] | 3.3858 |  |  |  | 6 |  |  | 2.126 |  | 8.126 | [9 empty] | 1.962 | 0.164 | [5 empty] | 2.126
|  | Site Assembly | 0.8 | [15 empty] | 0.33333 | [6 empty] | 0.8 |  | 0.8 | [10 empty] | 0.8 | [5 empty] | 0.8
|  | Central Salford | 0.05 |  |  | 0.021 | [12 empty] | 0.020833 | [5 empty] | 0.05 | 0 |  | 0.05 | [16 empty] | 0 | chapel st receipts slipped from 0405
|  | Expanding Boundaries |  |  |  | 0.063 | [12 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
|  | Gateway | 0.64 | [15 empty] | 0.26667 | [6 empty] | 0.64 |  | 0.64 | [10 empty] | 0.61 |  |  |  |  | 0.03 | 0.64
|  | Environmental/Shop Parade Improvements | 0.1 | [15 empty] | 0.041667 | [6 empty] | 0.05 | 0.05 | 0.1 | [10 empty] | 0.05 | [5 empty] | 0.05
|  | Charlestown and Lower Kersal in Bloom | 0.026 | [15 empty] | 0.010833 | [6 empty] | 0.026 |  | 0.026 | [10 empty] | 0.026 | [5 empty] | 0.026
|  | Alleygating | 0.078 |  |  | 0.007 | [12 empty] | 0.0325 | [6 empty] | 0.078 |  | 0.078 | [10 empty] | 0.078 | [5 empty] | 0.078
|  | Chapel st receipts | [16 empty] | 0 | [6 empty] | 0 | [18 empty] | 0
|  | Economic Development | 0.15 | [15 empty] | 0.0625 | [5 empty] | 0.15 | 0 |  | 0.15
|  | Cultural Quarter | 0.07 | [15 empty] | 0.029167 | [5 empty] | 0.07 | 0 |  | 0.07
|  | Public Realm Improvements | 0.05 | [15 empty] | 0.020833 | [5 empty] | 0.05 | 0 |  | 0.05
|  | Chapel Street Walking Plan | 0.05 | [15 empty] | 0.020833 | [5 empty] | 0.05 | 0 |  | 0.05
|  | Contribution to URC Business Plan | 0.18 | [15 empty] | 0.075 | [5 empty] | 0.18 | 0 |  | 0.18
| D01425&D01450 | Chapel Street/URC (04/05 Slippage) | 0.179 |  |  | 0.003 | [12 empty] | 0.074583 | [5 empty] | 0.179 | 0 |  | 0.179
|  | Liverpool Road Eccles | 0.244 |  |  | 0.001 | [12 empty] | 0.10167 | [5 empty] | 0.08 | 0.164 |  | 0.244 | [8 empty] | 0.064 | [6 empty] | 0.1 | 0.164 | 0.064 srb, 0.1 NRF,
|  | Riverside Bowling and Leisure Activity Centre | 0.165 | [15 empty] | 0.06875 | [6 empty] | 0.165 |  | 0.165 | [10 empty] | 0.165 | [5 empty] | 0.165
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
|  | CHIEF EXECUTIVE - TOTAL | 11.271 |  |  | 0.162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.6962 |  | 0 | 0 | 6 | 0 | 0.809 | 4.412 | 0.05 | 11.271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.064 | 2.125 | 2.093 | 0 | 0 | 0 | 0 | 0.13 | 4.412
PLANNING SERVICES
| D07016 | Manchester Bolton Bury Canal | 0.705 |  |  | 0.062 | [12 empty] | 0.29375 |  |  |  | 0.667 |  | 0.038 | 0 |  | 0.705 | [16 empty] | 0
|  | Purchase of Meadow Road Campus | 0 | [16 empty] | 2005-07-04 |  |  |  |  | 0 | 0 |  | 0 | [17 empty] | 2.8m purchase and receipt not shown on programme or receipts forecast
|  | Purchase of Hulme St Nursery | 0.3 | [21 empty] | 0.3 | 0 |  | 0.3
| D02151 | Detroit Bridge | 0.595 |  |  | 0.275 |  |  | 0.074 | 0.074 | 0.075 | 0.113 | 0.113 | 0.113 |  |  |  | 0.013 | 0.223 | 2005-04-18 |  |  |  |  | 0.345 | 0 | 0.25 | 0.595 | [16 empty] | 0
| D07024 | City Academy Access Road | 0.8 |  |  | 0.006 | [12 empty] | 0.33333 | [5 empty] | 0.7 | 0 | 0.1 | 0.8 | [16 empty] | 0
| D00050 | Investment in the Highways | 5 |  |  | 0.38 | [12 empty] | 2.0833 |  |  |  | 5 |  |  | 0 |  | 5 | [16 empty] | 0
|  | Eccles Town Centre Slipped from 04/05 | 0.589 |  |  | 0.007 | [12 empty] | 0.24542 | [5 empty] | 0.589 | 0 |  | 0.589 | [16 empty] | 0
|  | Red City Developments | 0.03 | [7 empty] | 0.03 | [7 empty] | 0.0125 | 2005-06-27 |  |  |  |  | 0.03 | 0 |  | 0.03
| C00060 and | Ordsall Neighbourhood office | 0.395 |  |  | 0.224 | 0.023 | 0.065 | 0.085 | 0.085 | 0.08 | 0.032 | 0.012 | 0.005 | 0.025 |  |  |  | 0.338 |  |  |  |  | 0.034 | 0.172 | 0.174 | 0.015 | 0.395 |  |  |  | 0.174 | [12 empty] | 0.174 | .118 office moves budget
| D06071 | LIVIA Community Engagement Programme | 0.103 |  |  | 0.017 | [12 empty] | 0.042917 | [6 empty] | 0.103 |  | 0.103 | [12 empty] | 0.1 |  |  | 0.003 | 0.103 | CEP grant
| D01958 | Newlands (LIVIA) | 0.1 |  |  | 0.001 | [12 empty] | 0.041667 | [5 empty] | 0.1 | 0 |  | 0.1 | [16 empty] | 0
| D07200-d07229 | Disabled Access Improvements | 0.339 |  |  | 0.071 | [12 empty] | 0.14125 | [5 empty] | 0.339 | 0 |  | 0.339 | [16 empty] | 0
| D07401 | Frederick Road/Camp Street | 0.052 | 2005-08-01 | 2005-12-01 | [7 empty] | 0.02 | 0.025 | 0.007 |  |  |  | 0.017333 | 2005-08-08 | [5 empty] | 0.052 |  | 0.052 | [15 empty] | 0.052 | 0.052 | Dealing with the Disadvantaged DoT Neighbourhood Road Safety Initiative grant
| D07400 | Langworthy Area - Traffic Calming Scheme | 0.237 | 2005-08-01 | 2005-12-01 | [6 empty] | 0.037 | 0.05 | 0.05 | 0.05 | 0.05 |  |  | 0.079 | 2005-08-08 |  |  |  |  | 0 | 0.237 |  | 0.237 | [15 empty] | 0.237 | 0.237 | Dealing with the Disadvantaged DoT Neighbourhood Road Safety Initiative grant
| d08000 | [17 empty] | 0 | [6 empty] | 0 |  | 0
| D08006 |  |  |  |  | 0.001
| d08024 |  |  |  |  | 0.006 | [12 empty] | 0 | [6 empty] | 0 |  | 0
| d08026 |  |  |  |  | 0.02 | [12 empty] | 0 | [6 empty] | 0 | 0 | 0
| d08030 | [17 empty] | 0 | [6 empty] | 0 |  | 0
| d08034 |  |  |  |  | 0.006 | [12 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
| d08035 |  |  |  |  | 0.003 | [12 empty] | 0 | [6 empty] | 0 |  | 0
| d08036 |  |  |  |  | 0.011 | [12 empty] | 0 | [6 empty] | 0 |  | 0
| d08040 |  |  |  |  | 0 | [12 empty] | 0 | [6 empty] | 0 |  | 0
| d08041 | [17 empty] | 0 | [5 empty] | 0 | 0 |  | 0
| D08044 |  |  |  |  | 0.001
| d08045 |  |  |  |  | 0.005 | [12 empty] | 0 | [6 empty] | 0 |  | 0
| d08048 | [17 empty] | 0 | [6 empty] | 0 |  | 0
| d08051 |  |  |  |  | 0.001 | [12 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
| d08052 |  |  |  |  | 0.002 | [12 empty] | 0 | [6 empty] | 0 |  | 0
| d08055 |  |  |  |  | 0.002 | [12 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
| d08059 |  |  |  |  | 0.001 | [12 empty] | 0 | [6 empty] | 0 |  | 0
| d08060 |  |  |  |  | 0.009 | [12 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
| d08064 |  |  |  |  | 0.006 | [12 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
| d08066 |  |  |  |  | 0.013 | [12 empty] | 0 | [6 empty] | 0 |  | 0
| d08067 |  |  |  |  | 0.004 | [12 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0
[19 empty] | 0 | [6 empty] | 0
on sap d99999 7027 |  | Advance Fees | 0.1 |  |  | 0.091 | 0.091 | [11 empty] | 0.041667 | [5 empty] | 0.1 | 0 |  | 0.1 | [16 empty] | 0
| D07013 | emerson house dev servs | 0.1 |  |  | 0.013 | [12 empty] | 0.041667 | [5 empty] | 0.02 | 0.08 |  | 0.1 | [15 empty] | 0.08 | 0.08 | lift enabling fund
|  | Improvement Works Swinton Civic Centre | 0.062 | [15 empty] | 0.025833 |  |  |  |  | 0.007 | 0.01 | 0.045 |  | 0.062 | [15 empty] | 0.045 | 0.045 | 0.013 planning delivery grant, 0.010 DDA,
|  | Ordsall Rec drainage | 0.058 | [15 empty] | 0.024167 |  |  |  |  | 0.058 |  | 0 |  | 0.058 | [16 empty] | 0
|  | disp starts here | [16 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
| D06108 | Demolition Windsor School |  |  |  | 0.009
| D06110 | Disposal Buille Hill |  |  |  | 0.003 | [12 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
| D06116 | Disposal PCL/Chapel Street |  |  |  | 0.002 | [12 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
| D06117 | Salford Shopping City |  |  |  | 0.006 | [12 empty] | 0
| D06118 | Demolition New Croft |  |  |  | 0.057 | [12 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
| D06121 | Land at Sovereign Street |  |  |  | 0.002 | [12 empty] | 0
| D06122 | Demolition Ordsall District Centre |  |  |  | 0.028 | [12 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
| D06123 | Disposal Chapel Wharf |  |  |  | 0.005 | [12 empty] | 0 | [6 empty] | 0
| D06126 | Land Adjacent to Duchy Inn |  |  |  | 0.001 | [12 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
| D06127 | Adelphi St and Meadow Road |  |  |  | 0.008 | [12 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0
0 | [18 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0 |  | 0 | [16 empty] | 0
[19 empty] | 0 | [6 empty] | 0
[19 empty] | 0 | [6 empty] | 0
on sap d99999 7027 |  | Disposal Costs | 0.121 |  |  | 0.121 | 0.121 | [11 empty] | 0.050417 | [5 empty] | 0.121 | 0 |  | 0.121 | [16 empty] | 0
|  | Former Police Station, Stanwell Road ** | 0.735 | [6 empty] | 0.685 |  | 0.05 | [6 empty] | 0.30625 | 2005-06-06 |  |  |  |  | 0.735 | 0 |  | 0.735
|  | Higher Broughton Community Hub ** | 0.445 | [15 empty] | 0.18542 | [5 empty] | 0.445 | 0 |  | 0.445
|  | Demolition Newcroft High School | 0.058 | [15 empty] | 0.024167 | [5 empty] | 0.058 | 0 |  | 0.058
|  | NWDA Headroom projects |  |  |  | 0.008 | [12 empty] | 0 | [6 empty] | 0 |  | 0
|  | LIVIA | 0.069 | [15 empty] | 0.02875 | [5 empty] | 0.006 | 0.063 |  | 0.069 | [15 empty] | 0.063 | 0.063
|  | NWDA Tatton Park | 0.026 | [15 empty] | 0.010833 | [5 empty] | 0 | 0.026 |  | 0.026 | [12 empty] | 0.026 |  |  |  | 0.026
|  | Trinity Park Chapel section 106 | 0.07 | [15 empty] | 0.029167 | [5 empty] | 0.038 | 0.02 | 0.012 | 0.07 | [13 empty] | 0.02 |  |  | 0.02 | section 106, 38 chapel st receipts 0405
|  | Oakwood Section 106 | 0.009 | [15 empty] | 0.00375 | [5 empty] | 0 | 0 | 0.009 | 0.009 | [16 empty] | 0 | section 106
|  | Eccles Town hall auditorium | 0.004 | [15 empty] | 0.0016667 | [5 empty] | 0.004 | 0 |  | 0.004 | [16 empty] | 0
|  | Countryside Programme | 0.01 | [15 empty] | 0.0041667 | [5 empty] | 0.01 | 0 |  | 0.01 | [16 empty] | 0
|  | Barton SES | 0.075 | [15 empty] | 0.03125 | [5 empty] | 0.075 | 0 |  | 0.075 | [16 empty] | 0
| D03600 | conserving and developing Ordsall Hall | 0.148 |  |  | 0.037 | [12 empty] | 0.061667 |  |  |  |  | 0.009 | 0.139 | 0 |  | 0.148 | [16 empty] | 0 | .005 e&L rcco, 0.004 arts and leisure RCCO, see sept mon depts
|  | SRB | 0.001 |  |  | 0.001 | [12 empty] | 0.00041667 | [5 empty] | 0.001 | 0 |  | 0.001 | [16 empty] | 0
| D07014 | Quays Maintenance Office Move | 0.003 |  |  | 0.003 | [12 empty] | 0.00125 | [5 empty] | 0.003 | 0 |  | 0.003 | [16 empty] | 0
| D07260-D07299 | Footpath works | 0.184 |  |  | 0.001 | [12 empty] | 0.076667 | [5 empty] | 0.184 | 0 |  | 0.184 | [16 empty] | 0
|  | relocation Tourist Inofrmation Centre | 0.001 | [15 empty] | 0.00041667 | [5 empty] | 0.001 | 0 |  | 0.001 | [16 empty] | 0
| D03501 | Pendleton Church Area Study |  |  |  | 0.119 | [12 empty] | 0 | [6 empty] | 0 |  | 0
| D03502 | Highway and Community Safety | 0.03 |  |  | 0.004 | [12 empty] | 0.0125 | [6 empty] | 0.03 |  | 0.03 | [10 empty] | 0.03 | [5 empty] | 0.03
| D03503 | Minor Works Fund | 0.01 |  |  | 0.001 | [12 empty] | 0.0041667 | [6 empty] | 0.01 |  | 0.01 | [10 empty] | 0.01 | [5 empty] | 0.01
| D03505 | Physical Design Strategy |  |  |  | 0.001 | [19 empty] | 0 |  | 0
| D03506 | Mini Bus | 0.006 | [15 empty] | 0.0025 | [6 empty] | 0.006 |  | 0.006 | [10 empty] | 0.006 | [5 empty] | 0.006
| D08018 D08053 | Salford Shopping Food Retail Development |  |  |  | 0.096 | [12 empty] | 0 | [6 empty] | 0 |  | 0
empty c00060 | [23 empty] | 0 |  | 0 | 0 | 0 |  |  |  | 0 | [12 empty] | 0
|  | PLANNING SERVICES - TOTAL | 11.57 |  |  | 1.539 | 0.235 | 0.065 | 0.159 | 0.844 | 0.185 | 0.232 | 0.195 | 0.193 | 0.082 | 0.05 | 0 | 0.013 | 4.8203 |  | 0 | 0 | 5.667 | 0.108 | 4.563 | 0.846 | 0.386 | 11.57 | 0 | 0 | 0 | 0.174 | 0 | 0 | 0 | 0 | 0 | 0 | 0.046 | 0 | 0.126 | 0.02 | 0 | 0.48 | 0.846
|  | 05/06 PROGRAMME TOTAL | 118.069 |  |  | 30.387 | 1.669 | 0.61 | 3.844 | 5.938 | 5.662 | 8.234 | 5.022 | 4.599 | 3.473 | 3.327 | 3.434 | 13.419 | 42.9257 |  | 10.581 | 1.827 | 12.482 | 1.297 | 21.654 | 68.772 | 1.456 | 118.069 | 9.009 | 0.514 | 3.054 | 3.984 | 0.086 | 2.606 | 0.103 | 0.676 | 1.637 | 2.804 | 4.368 | 2.324 | 0.126 | 18.24 | 0 | 19.241 | 68.772
|  | Education contribution to cap'n of revenue | [18 empty] | 0.2 |  |  |  | -0.2 |  |  | 0
|  | Education SB adjustment | [18 empty] | 6.8 |  |  |  | -6.8 |  |  | 0
|  | EFFECT OF 04/05 OUTTURN | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PROGRAMME TOTAL | 118.069 |  |  | 30.387 | 1.669 | 0.61 | 3.844 | 5.938 | 5.662 | 8.234 | 5.022 | 4.599 | 3.473 | 3.327 | 3.434 | 13.419 | 42.9257 |  | 17.581 | 1.827 | 12.482 | 1.297 | 14.654 | 68.772 | 1.456 | 118.069 | 9.009 | 0.514 | 3.054 | 3.984 | 0.086 | 2.606 | 0.103 | 0.676 | 1.637 | 2.804 | 4.368 | 2.324 | 0.126 | 18.24 | 0 | 19.241 | 68.772
** Shown as funded by capital receipts, if receipts are unavailable unsupported borrowing will be used
Private sector housing loan to partnership £0.466m Unsupported borrowing or capital receipts, if private sector housing underspends may be able to fund it within existing resource
Private sector housing land at elton st £0.300m Unsupported borrowing or capital receipts, if private sector housing underspends may be able to fund it within existing resource
Private sector housing premises at Great Clowes St £0.690m Unsupported borrowing or capital receipts, if private sector housing underspends may be able to fund it within existing resource
Timing adjustments
[26 empty] | 0 |  | 0 | [16 empty] | 0
[26 empty] | 0 |  | 0 | [16 empty] | 0
[26 empty] | 0 |  | 0 | [16 empty] | 0
[26 empty] | 0 |  | 0 | [16 empty] | 0
[26 empty] | 0 |  | 0 | [16 empty] | 0
[26 empty] | 0 |  | 0 | [16 empty] | 0
[26 empty] | 0 |  | 0 | [16 empty] | 0
[26 empty] | 0 |  | 0 | [16 empty] | 0
[26 empty] | 0 |  | 0 | [16 empty] | 0
[26 empty] | 0 |  | 0 | [16 empty] | 0
[26 empty] | 0 |  | 0 | [16 empty] | 0
|  | Red Rose Scheme | [23 empty] | 0 |  | 0 | [16 empty] | 0
|  | Total | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Resources total (includes receipts required) | 118.069 | [17 empty] | 10.581 | 1.827 | 12.482 | 1.297 | 21.654 | 68.772 | 1.456 | 118.069 | 9.009 | 0.514 | 3.054 | 3.984 | 0.086 | 2.606 | 0.103 | 0.676 | 1.637 | 2.804 | 4.368 | 2.324 | 0.126 | 18.24 | 0 | 19.241 | 68.772
|  | adjust for actual reciepts | #REF! | [21 empty] | #REF!
|  | Resources adjusted for forecast receipts | #REF! | [17 empty] | 10.581 | 1.827 | 12.482 | 1.297 | #REF! | 68.772 | 1.456 | #REF!
|  | programme including unfunded from 03/04 | 118.069
|  | Sufplus/(shortfall) in resources over programme | #REF!
Finacc 04 timing differences
[9 empty] | 0506 | 04/05 | 03/04 | 02/03
HMRF
NWDA
|  | surestart | [8 empty] | 19785
ERDF
|  | School Contributions | [9 empty] | 175989
|  | Insurance Clifton Primary / Broadwalk | [9 empty] | 261581
Dept of Health Barton Moss Expansion
Sure Start (Winton linrary)
|  | Beesley Green NOF |  |  |  | shaded area is 534 timing difference in
|  | NOF/PE Sports |  |  |  | resources due
SPACE
Central salford
|  | Chapel Wharf | [9 empty] | 146000
|  | Fire insurance Moorside CP fire damage claim not finalised | [6 empty] | 126071.52
|  | RCCO due E00037, from budget on D(or E??)6110 agreed with Dave mac to correct in new year | [6 empty] | 1500
|  | Winton Community Library RCCO from dev services | [6 empty] | 8000
-5.934
-5.934
Note on W2: City of Salford: single capital pot 9001
Note on X2: City of Salford: ringfenced 9003
Note on AA2: City of Salford: 9007 COLUMN SHOWS CAP RECEIPTS REQUIRED NOT THOSE AVAILABLE
Note on AH2: City of Salford: 9027
Note on AQ2: City of Salford: 9029
Note on AP2: City of Salford: 9057
Note on AI2: City of Salford: 9055
Note on AK2: City of Salford: 9045
Note on AL2: City of Salford: 9043
Note on AE2: City of Salford: 9035 other govt grants 9037 other grants 9039 privat sector cont 9041 other cont
Note on Z2: City of Salford: 9011
Note on AU2: City of Salford: 9037
Note on C705: City of Salford: slipped from 04/05
Note on D396: City of Salford: slipped from 05/06 as part of 04/05 monitoring not at outturn
Note on D642: City of Salford: slipped from 05/06 as part of 04/05 monitoring not at outturn
Note on D643: City of Salford: slipped from 05/06 as part of 04/05 monitoring not at outturn
Note on D653: City of Salford: slipped from 05/06 as part of 04/05 monitoring not at outturn
Note on D658: City of Salford: slipped from 05/06 as part of 04/05 monitoring not at outturn
Note on D759: City of Salford: slipped from 05/06 as part of 04/05 monitoring not at outturn
Note on D761: City of Salford: slipped from 05/06 as part of 04/05 monitoring not at outturn
Note on D617: City of Salford:
Note on D618: City of Salford: slipped from 05/06 as part of 04/05 monitoring not at outturn
Note on D610: City of Salford: slipped from 05/06 as part of 04/05 monitoring not at outturn
Note on Y2: City of Salford: 9001 unsupported borrowing
Note on AF2: City of Salford: 9035
Note on AG2: City of Salford: 9037
Note on AM2: City of Salford: 9035
Note on AN2: City of Salford: 9037
Note on AO2: City of Salford: 9037
Note on AR2: City of Salford: 9037
Note on AS2: City of Salford: 9035
Note on D654: City of Salford: 04/05 office moves budget unallocated at end of year, reduces carry forward of office moves spend
Note on D655: City of Salford: 04/05 office moves budget unallocated at end of year, reduces carry forward of office moves spend
Note on H15: this line represents HMRF monthly cash flow estimate it is used to cash flow all private sector programme pro rata
Note on H846: City of Salford: winton and belvedere
Note on Z566: Barton moss contribution 0.036 goes through at year end as an appropriation, not as a contribution
Note on C15: Loan to the Higher Broughton Partnership £0.466m capital receipts of unsupported borrowing if no receipts available
Note on AA705: 90k cap receipts from windfall footpath repairs pot
Note on AA795: 90k to detroit bridge

## Appendix 2
2005/06 ESTIMATED CAPITAL RECEIPTS
| CAPITAL |  | USABLE
| RECEIPT | Prop'n | Amount
| £000s | % | £000s
COMPLETED DISPOSALS
Housing Right-to-Buy | 9285 | 25 | 2321.25
Housing Land
Land at Lane End | 60 | 50 | 30
General Fund - Properties and Land
Moorfield House | 100 | 100 | 100
Land adjacent to Hope Hospital | 14 | 100 | 14
Community Centre Kenyon Way | 85 | 100 | 85
St Johns playing field, Walkden | 206 | 100 | 206
Sale of Shares Modesole | 715 | 100 | 715
Land at Ravenscraig Road | 50 | 100 | 50
TOTAL COMPLETED | 10515 |  | 3521.25
APPROVED DISPOSALS
Housing Right-to-Buy | 8715 | 25 | 2178.75
Housing Land & Property | 244 | 50 | 122
General Fund - Properties and Land | 5297 | 100 | 5297
TOTAL ESTIMATED DISPOSALS | 14256 |  | 7597.75
TOTAL ESTIMATED RECEIPTS | 24771 |  | 11119
Less - Costs to be set against capital receipts |  |  | 500
NET ESTIMATED RECEIPTS 05/06 |  |  | 10619
RECEIPTS BROUGHT FORWARD |  |  | 14082
ESTIMATED RECEIPTS FOR 2005/06 |  |  | 24701
RECEIPTS REQUIRED FOR 2005/06 CAPITAL PROGRAMME |  |  | 14654
SURPLUS/(SHORTFALL) IN CAPITAL RECEIPTS |  |  | 10047
Note on C34: City of Salford: CAPITAL RECEIPTS LINE 5
Note on C13: City of Salford: CAPITAL RECEIPTS Line 1
Note on C26: City of Salford: SHOULD EQUAL LINE 2
Note on C30: City of Salford: CAPITAL RECEIPTS LINE 3
Note on C32: City of Salford: CAPITAL RECEIPTS LINE 4
Note on C38: City of Salford: SHOULD EQUAL LINE 6
Note on F26: City of Salford: SHOULD EQUAL LINE 2

## Appendix 3
CAPITAL RECEIPTS 2005/06
TIMESCALES-RECEIPTS IN EXCESS OF £100,000
Disposal | Estimated Receipt | Preliminaries/Marketing | Legal/Planning | Completion
£m
Stay Inn, Trinity Way | 0.25 |  |  | December
Duchy Road Public House | 0.1 |  |  | March
St Simon St | 0.3 |  |  | November
265/273 & 281,Chapel Street | 0.35 |  |  | December
Willowbank/Mere drive Site, Clifton. | 0.75 |  |  | November
Wilburn Street Basin | 0.75 |  |  | December
Ontario Basin | 2 |  |  | December
Land at Egerton St/ East Ordsall Lane | 0.15 |  |  | March
Legendary Properties | 0.12 |  |  | March

## Appendix 4
Lead Member Corporate Services - 2005/06 Tender Approvals
Scheme Details |  | Costs |  | Source of
| 2005/06 | 2006/07 | Total | Funding
Onwards
| £m | £m | £m
Land and Premises at Great Clowes St/Clarence St | 0.303 | 0 | 0.303 | Capital receipts or unsupported borrowing
A5082 Cleggs Lane, A6 Bolton Boundary PRN re-surfacing | 0.588 | 0.017 | 0.605 | Block 3
Fairhills Road, Irlam - proposed puffin crossing | 0.051 | 0.002 | 0.053 | Block 3 and contribution from Tesco section 278
Monton Canal Bridge Repainting | 0.07 | 0.002 | 0.072 | Block 3
Pedestrian Crossing Facilities - Station Road Swinton | 0.032 | 0.002 | 0.034 | Block 3
Belvedere Early Years Centre - Childrens Centre | 0.456 | 0.012 | 0.468 | Early Years Development Children's Partnership Grant
Commercial Premises off Fitzwarren St | 0.217 | 0 | 0.217 | SRB 5
Block Improvements Seedley West Phase 3 | 0.18 | 0.497 | 0.677 | HMRF
Block Improvements Langworthy Road Shops phase 2 | 0.085 | 0.424 | 0.509 | Capital receipts/supported borrowing
| 1.982 | 0.956 | 2.938