| Part One | ITEM NO.10 |
| --- | --- |

REPORT OF THE STRATEGIC DIRECTOR OF CUSTOMER & SUPPORT SERVICES

TO THE: BUDGET & AUDIT SCRUTINY – AUDIT SUB-COMMITTEE

ON Monday, 17 January, 2005

TITLE: REVISION TO CORPORATE GOVERNANCE TEAM PLAN, AUDIT & RISK MANAGEMENT UNIT

RECOMMENDATIONS: That members approve the proposed revision to the Corporate Governance Team Plan

EXECUTIVE SUMMARY: The purpose of this report is to seek approval for the revision to the annual operational plan for the Corporate Governance Team in the Audit & Risk Management Unit.

BACKGROUND DOCUMENTS: Internal Audit Outturn Report

(Available for public inspection)

ASSESSMENT OF RISK: The work of the team is primarily to support the council in its Corporate Governance arrangements and the plan is compiled to ensure that risk management can be supported throughout the council. In addition, special investigations are managed within the unit’s risk-based audit protocols.

SOURCE OF FUNDING: Existing revenue budget.

COMMENTS OF THE STRATEGIC DIRECTOR OF CUSTOMER AND SUPPORT SERVICES (or his representative):

- LEGAL IMPLICATIONS				Provided by: Head of Law & Admin

- FINANCIAL IMPLICATIONS			Provided by: Head of Finance

PROPERTY (if applicable):

HUMAN RESOURCES (if applicable):

CONTACT OFFICER: Julie Flanagan – Audit Manager 0161 793 3239

Email – julie.flanagan@salford.gov.uk

WARD(S) TO WHICH REPORT RELATE(S): N/A

KEY COUNCIL POLICIES: Anti-Fraud and Anti-Corruption Strategy, Salford City Council Risk Management Toolkit

DETAILS (Continued Overleaf)

#### Corporate Governance Team Plan – 2004/05

The Corporate Governance Team within the Audit & Risk Management Unit is responsible for supporting corporate governance for the council, insurance, special investigations and special projects.

The team has had significant vacancies during the year due to internal promotions and staff moving to other disciplines within the Audit & Risk Management Unit. The team is now fully established.

The original plan for 1450 chargeable days equated to approximately 8 members of staff, based on the average number of 179 available days. Vacancies on the team to the end of November, and projected to the end of the year, amount to 432 days. Agency staff have been utilised to meet part of this deficit leaving an estimated shortfall of 320 days on the year. The revised plan, therefore, represents a 22% reduction in original plan allocation.

A revised plan has been developed to reflect staff availability to the end of the year. Each of the disciplines of governance, insurance, special projects, and irregularities has been reduced to reflect staff skills available and projects already committed. Irregularity days for this year are inflated due to preparation and anticipated participation in the Audit Commission’s National Fraud Initiative data matching exercise.

Days allocated for irregularity referrals have been reassessed to take account of the revised strategic directorate structure, taking into account historical data on referral levels.

Corporate Governance Team Plan 2004/05

#### Original Plan

|  | Planned Days | Proportion of Plan |
| --- | --- | --- |
| Governance | 190 | 13% |
| Insurance | 592 | 41% |
| Special Projects | 267 | 18% |
| Investigations | 401 | 27% |
| Total | 1450 |  |

#### Investigations Planned and Actual

| Directorate | Planned Days | Actual Days to end Nov 04 |
| --- | --- | --- |
| General | 140 | 80 |
| Chief Executive’s | 30 | 15 |
| Community & Social Services | 30 | 6 |
| Corporate Services | 30 | 19 |
| Development Services | 30 | 0 |
| Education & Leisure Services | 45 | 36 |
| Environmental Services | 30 | 32 |
| Housing Services | 20 | 1 |
| NPHL | 46 | 11 |

#### Corporate Governance Team Plan 2004/05

#### Revised Plan

|  | Planned Days | Proportion of Plan |
| --- | --- | --- |
| Governance | 110 | 7% |
| Insurance | 497 | 44% |
| Special Projects | 200 | 18% |
| Investigations | 323 | 31% |
| Total | 1130 |  |

#### Investigations Planned and Actual

| Directorate | Planned Days | Actual Days to end Nov 04 |
| --- | --- | --- |
| General | 132 | 80 |
| Community & Social Services | 10 | 6 |
| Customer & Support Services | 25 | 19 |
| Education & Leisure | 45 | 36 |
| Environment | 40 | 32 |
| Housing & Planning | 5 | 1 |
| Policy, Strategy & Research | 20 | 15 |
| NPHL | 46 | 11 |