| Part One | ITEM NO.9 |
| --- | --- |

REPORT OF THE STRATEGIC DIRECTOR OF

CUSTOMER & SUPPORT SERVICES

TO THE: BUDGET & AUDIT SCRUTINY - AUDIT SUB COMMITTEE

ON Monday, 17 January, 2005

TITLE: INTERNAL AUDIT PLAN – OUTTURN REPORT 2004/2005

RECOMMENDATIONS:

Members are asked to note the contents of the report.

EXECUTIVE SUMMARY:

The purpose of this report is to inform members of progress against the 2004/2005 Internal Audit Plan.

BACKGROUND DOCUMENTS:

(Available for public inspection)

Quarterly Committee reports, Audit Management Information System.

ASSESSMENT OF RISK:

Internal Audit projects are managed within the Unit’s risk based audit protocols aimed at giving assurance regarding the management of the City Council’s key business risks.

SOURCE OF FUNDING:

Existing revenue budget.

COMMENTS OF THE STRATEGIC DIRECTOR OF CUSTOMER AND SUPPORT SERVICES (or his representative):

- LEGAL IMPLICATIONS			Provided by: Head of Law & Admin

- FINANCIAL IMPLICATIONS		Provided by: Head of Finance

PROPERTY (if applicable): N/A

HUMAN RESOURCES (if applicable): N/A

CONTACT OFFICER:

Andrew Waine Audit Manager

Tel: 0161 793 3357

Email: andrew.waine@salford.gov.uk

WARD(S) TO WHICH REPORT RELATE(S): N/A

KEY COUNCIL POLICIES: N/A

DETAILS: See report attached.

INTRODUCTION

This report provides details of the progress relating to delivery of the Internal Audit Plan for 2004/2005. Members should note that this is the final year of a four-year Strategic Plan approved by the Audit Committee in 2001.

This report provides Members with information regarding the performance of the Unit in achieving its commitment to the delivery of an efficient and effective internal audit service.

Plan Delivery

Details of the days that are available if the Unit is fully staffed (10076) are analysed in the table below.

These are broken down into the days that can be directly charged to a client, and those that are non-chargeable which relate to the day-to-day operation of the Unit.

In the period 31st July 2004 to 30th November 2004, 55% of the mainstream Salford Internal Audit element of the plan had been delivered, and 67% of the overall Unit plan for Salford had been delivered, relative to the chargeable days element.

Members will note that the total plan figure has changed since the previous Committee as a result of a reorganisation of the Corporate Governance Team, see the separate report submitted to this Committee.

# Chargeable days

|  |  | Actual Days | Annual Plan | % Achieved |
| --- | --- | --- | --- | --- |
| Organisation | Reporting Unit |  |  |  |
| Salford | Chief Executive | 7 | 69 | 10 |
|  | Community & Social Services | 111 | 180 | 61 |
|  | Corporate Management | 139 | 338 | 41 |
|  | Corporate Services | 198 | 450 | 44 |
|  | Development Services | 20 | 77 | 25 |
|  | Education & Leisure | 313 | 326 | 96 |
|  | Environmental Services | 28 | 45 | 61 |
|  | Personnel | 15 | 23 | 63 |
| Total |  | 831 | 1508 | 55 |
| Specialist Groups | Computer Audit | 703 | 718 | 98 |
|  | Energy | 639 | 1037 | 62 |
|  | Corp Governance inc Risk mgt, Insurance | 845 | 1130 | 75 |
|  | Contracts | 3 | 80 | 4 |
| Salford Totals |  | 3021 | 4473 | 67 |
| External Contracts | GMPA/NPHL/SCLL/NWLG | 901 | 1490 | 60 |
|  | Computer – GMPA and AGMA related contracts | 342 | 495 | 68 |
| External Contracts Totals |  | 1243 | 1985 | 63 |
| Total Chargeable |  | 4264 | 6458 | 66 |

# Non-Chargeable Days

|  | Administration | 338 | 334 | 101 |
| --- | --- | --- | --- | --- |
|  | Internal Management | 40 | 100 | 40 |
|  | Leave | 897 | 1732 | 52 |
|  | Reduced Hours | 0 | 281 | 0 |
|  | Secondments | 134 | 161 | 83 |
|  | Sickness | 88 | 357 | 25 |
|  | Staffing & Appraisals | 81 | 104 | 78 |
|  | Training | 275 | 549 | 50 |
|  | Vacancies | 551 | 0 | 0 |
| Unit Total Non-Chargeable |  | 2404 | 3618 | 66 |
| Grand Total |  | 6668 | 10076 | 66 |

The table shows that planned activity for non-chargeable time is on target for achievement during the year.

Within this reporting period, the Salford Team has had to utilise agency staff to cover for vacancies. A recruitment drive during September failed to attract suitable candidates and it was decided not to utilise agency staff further to cover for this shortage. However, it is pleasing to note that the Salford Team has been successful in attracting three permanent senior auditors as a result of a further recruitment drive in November. All three appointments are due to commence work with the Unit early in the new year.

#### Summary

The report has identified that after eight months of the plan year, the Unit has achieved 67% of its planned activity relative to Salford City Council disciplines. It is therefore, anticipated that the Unit will achieve full delivery of its commitments by the year end.