BROUGHTON BLACKFRIARS

COMMUNITY COMMITTEE

Community Action Plan

2002/04

Presented to Community Committee 23 July 2002

Introduction

The Community Action Plan which is set out on the following pages is being put for approval to the July meeting of the Broughton / Blackfriars Community Committee. The proposals contained in the Plan have been agreed by the Task Groups of the Community Committee. The groups which have done this work are made up of community representatives, partner agencies working in the area and council officers. This is the sixth year in which an Action Plan has been developed for the Community Committee area and it will provide the basis for action until the end of the current financial year in March 2003. Key projects or events which are foreseen for the following 2 years are also shown in the comments column so as to help with budgeting and planning future work.

Priorities

The Task Groups have prioritised key projects for the coming year.

Young Persons

- Support development of community-based play initiatives, (for example TIG and RITA Youth Leisure, ZSARA, TETRA)

- Continue to provide safe transport to youth facilities and activities

- Develop  outreach and detached youth work for the Chapel St. programme area

- Improve support for children with learning and behavioural difficulties in schools

- Ensure full time educational provision for all excluded pupils

- Explore feasibility of a mobile resource vehicle to support outreach work across the whole of the Community Committee area

Community Safety:

- Continue to support and develop Broughton/Blackfriars Play Development Project

- Ensure support, advice and assistance to community groups organising activities with young people

- Develop mobile outreach youth work service

- Provide community policing with continued liaison with community groups

- Improve Business Security

- Ensure the removal of all abandoned cars to a safe and secure location within 24 hours

Economic Development

- Co-ordinate resources to link local people with local jobs opportunities particularly those arising from the Chapel Street Regeneration Programme

- Develop the work of Careers Partnership/the Connexions service in the area
																	(continued…

- Identify ways to improve transport links to areas of job opportunity

- Support the work of the Broughton Trust

- Identify ways to improve transport links to areas of job opportunity

- Support the work of the Broughton Trust

Environment

- Design and implement improvements to open spaces and parks throughout the area

- Progress implementation of housing and environmental works

- Tackle vacant sites and buildings, particularly retail premises and the Wiltshire Street area

- Improve lighting, particularly for pedestrians

- Continue the improvements to the environmental maintenance regime

- Improve education and communication on environmental maintenance issues

- Develop improved mechanisms for tackling fly tipping

- Develop community-based projects to be supported by the key funding sources

Supporting Community Groups

- Ensure community development support for new & existing community groups & projects, in particular help with funding

- Support the Broughton Trust and secure funding for its work

- Develop Broughton Community Resource Centre and secure continuation funding

- Develop Blackfriars and Broughton Community Committee, in particular involving under-represented groups and developing its Task Groups

- Ensure that future regeneration projects in the area are designed and operated in partnership with local people

- Develop local Information & Communication Technology Centres at Broughton Library, Community Resource Centre, D@tabase and the Angel and coordinate their work

- Encourage and enable individuals to be active in community groups and projects

Health

- Secure funding for Broughton Health Project to continue beyond March 2002

- Support establishment of ‘self help’ group for Asian women

- Support Women Working Together’s proposed projects

- To support work with older people in the Broughton area and develop the Broughton Older peoples project.

Contents

Page 1-2			Summary of Priorities Recommended to the Community Committee

Page 3			Introduction - the Preparation of the Action Plan

Page 4 onwards	Action Plan proposals from Task Groups for 2000/01

The Task Groups’ work relate to the 7 themes of the Salford Partnership’s Community Plan for the city as follows:

Salford Partnership’s Themes					Blackfriars Broughton Community Action Plan

A HEALTHY CITY							Health Action Plan

A SAFE CITY								Crime & Disorder Reduction Action Plan

A CITY WHERE CHILDREN AND YOUNG PEOPLE ARE VALUED 	Youth Action Plan

AN INCLUSIVE CITY WITH STRONGER COMMUNITIES		Supporting Community Groups Action Plan

AN ECONOMICALLY PROSPEROUS CITY				Economic Development Action Plan

A LEARNING AND CREATIVE CITY

A CITY THAT'S GOOD TO LIVE IN					Environment Action Plan

BLACKFRIARS BROUGHTON ENVIRONMENT ACTION PLAN 1

| Ref. | Action in 2002/2003 | Performance Indicator and Target | Funding (source & amount if known) | Local or Central Decision needed for Action | Partners (Lead agency & officer responsible in bold) | KEY DEVELOPMENTS IN 2003/2004 AND 2004/2005 |
| --- | --- | --- | --- | --- | --- | --- |
| Objective 1: To improve and encourage the use of land and buildings |
| 1.1 | Design and implement improvements to open spaces and parks throughout the area | Implement the Hill Street Play Area Design a scheme for Grosvenor Park Complete refurbishment of Trinity Park, Mount Street Park and St Stephens Gardens Design/refurbishment schemes for Islington Park and Greengate Park Design a scheme for the community use of the open space adjacent to St. Philip’s Church Design a new public square at East Ordsall Lane Design improvement proposals for Mandley park Design schemes for Heath Avenue and Tulip Walk | City Council City Council; Police sector City Council; Private sector City Council NWDA; City Council NWDA; City Council | Local Central Central Central Central Central Central Central | Groundwork; Hill Street Residents Association ALMA; Police Chapel Street Project Team; Local residents forum Chapel Street Project Team; Local residents forum Chapel Street Project Team; Local residents forum; St. Philip’s Church Chapel Street Project Team City Council City Council | Refurbish Grosvenor Park Refurbish Islington Play Area and Grosvenor Park Commence the reintroduction of play areas and refurbishment of open spaces within Lower Broughton Commence implementation of the Albert Park masterplan, securing quality play facilities Encourage the use of the Greengate multisports pitch Design a new public square at East Ordsall Lane |

BLACKFRIARS BROUGHTON ENVIRONMENT ACTION PLAN 2

| Ref. | Action in 2002/2003 | Performance Indicator and Target | Funding (source & amount if known) | Local or Central Decision needed for Action | Partners (Lead agency & officer responsible in bold) | KEY DEVELOPMENTS IN 2003/2004 AND 2004/2005 |
| --- | --- | --- | --- | --- | --- | --- |
| 1.2 | Progress implementation of housing and environmental works | Continue remodelling and enhancement of Spike Island Continue redevelopment of Zebra Street area Complete a Housing Renewal Assessment for Higher Broughton ? Declare a clearance area at 1-17 Hamilton Street ? Implement clearance area at 2-20 Lucy Street and 1-21 Muriel Street Renovate 271-299 Great Clowes Street and associate environmental works | SRB2; HIP City Council Housing capital programme Housing capital programme Housing capital programme | Central Central Central | City Council (Development Services; Housing Services) City Council (Housing Services) City Council (Housing Services) City Council (Housing Services) City Council (Housing Services) | Complete the remodelling of Spike Island, incorporating the Lower Broughton masterplan Complete the redevelopment of Zebra Street Commence work to stabilise and sustain the private housing areas of Higher Broughton following the Housing Renewal Assessment Commence new housing development in Higher Broughton |
| 1.3 | Design and implement other site-specific environmental improvement schemes | Commence clearance of redundant housing in Wiltshire Street area. Enhance the railway arches at Deal Street Design pedestrians scheme estates end of Chapel Street. | City Council Railtrack NWDA: City Council | Central Central Central | City Council (Housing Services) Railtrack City Council (Development Services) | Refurbish Blackfriars Street |
| 1.4 | Adopt and commence implementation of masterplans for key areas | Lower Broughton Wiltshire Street area Marlborough Road and St. Thomas’ Schools Crescent area Adelphi Quarter Greengate South River Irwell/City Centre Corridor Middlewood | City Council; NWDA | All Central | All City Council | All projects roll through to 2003/04 and 2004/05 |

BLACKFRIARS BROUGHTON ENVIRONMENT ACTION PLAN 3

| Ref. | Action in 2002/2003 | Performance Indicator and Target | Funding (source & amount if known) | Local or Central Decision needed for Action | Partners (Lead agency & officer responsible in bold) | KEY DEVELOPMENTS IN 2003/2004 AND 2004/2005 |
| --- | --- | --- | --- | --- | --- | --- |
| 1.5 | Progress the redevelopment of key sites, producing development briefs where appropriate | Land at Trafalgar Street Bowker Street for Broughton Trust scheme Exchange Station Chapel Wharf land at Springfield Lane/Trinity Way Land at Bloom Street/Trinity Way Land at Gore Street/Trinity Way Land at Chapel Street/Park Street Education Offices/Vulcan House Salford Royal Hospital Farmer Norton Land at Adelphi Street riverside | Existing resources | All Central | City Council; Manchester City Council Broughton Trust Railtrack Chapel Street Project Team Chapel Street Project Team Chapel Street Project Team Chapel Street Project Team Chapel Street Project Team; NWDA City Council (Development Services) Chapel Street Project Team Chapel Street Project Team Chapel Street Project Team | All projects roll through to 2003/2004 and 2004/2005 |
| 1.6 | Consolidate retail areas | Demolish derelict buildings and promote development sites within Broughton Village Consolidate retail facilities and broaden community facilities at Broughton Village Manage changing retail trends by acquiring and demolishing redundant shops Establish a local centre on Chapel Street | NWDA; Existing resources |  | City Council (Development Services) | All projects roll through to 2003/04 and 2004/05 RECOMMEND AS PRIORITY |
| 1.7 | Improvement of sites and buildings | Encourage the appropriate use of privately owned vacant site, and their protection in the meantime Provide Environmental Improvement Grants for the Chapel Street area | Existing resources City Council |  | City Council (Development Services; Housing Services) Chapel Street Project Team |  |
| 1.8 | Support the improvement of housing | Preparation of the Area Housing Plan Continue the work of the Higher Broughton Housing Group Support landscaping schemes nominated by residents | Existing resources Existing resources Area Housing Minor Works Budget |  | City Council (Housing Services) Higher Broughton Housing Group City Council (Housing Services) | The Area Housing Plan will be agreed locally in partnership with tenants, residents and other partners, and will provide both a vision for the area and address local operational and strategic issues, including environmental improvements. |

BLACKFRIARS BROUGHTON ENVIRONMENT ACTION PLAN 4

| Objective 2: To improve community security and safety through environmental improvements |
| --- |
| Ref. | Action in 2002/2003 | Performance Indicator and Target | Funding (source & amount if known) | Local or Central Decision | Partners (Lead agency & officer responsible in bold) | KEY DEVELOPMENTS IN 2002/2004 AND 2004/2005 |
| 2.1 | Improve lighting, particularly for pedestrians | Key routes in the Chapel Street Walking Plan Spike Island | Existing resources; Private sector SRB | Central | City Council (Dev. Services) Chapel Street Project Team City Council (Dev. Services) | All projects roll through to 2003/04 and 2004/05 |
| 2.2 | ‘Secure by Design’ principles to be incorporated in all comprehensive regeneration projects, and encouraged in other new development and public realm schemes | Secure by design advice provided on all major projects | Existing resources | Local | GM Police; City Council (Development Services) | Ongoing |
| 2.3 | Tackle vacant sites and buildings | Ensure the proper protection of vacant properties and sites Secure the Lowry High School site from crime, vandalism and stolen cars until redevelopment commences | Existing resources | Local | City Council (Development & Housing Services); GM Police | Ongoing |
| 2.4 | Seek to improve security of sites and buildings in active use | Continue working with Residents’ Groups and businesses to identify vulnerable areas and buildings where security problems are most acute Continue to investigate ‘best practice’ for environmental security Liase with the Cheetham and Broughton Business Network and the Chapel Street Corridor Business Group Encourage security improvements to permanent car parks Develop and implement strategies for dealing with crime and fear and crime at Salford Central and Salford Crescent Stations Support schemes nominated by residents | Existing resources Railtrack; NWDA | Local | All residents groups; City Council (Development Services); GM Police GM Police Railtrack | Ongoing |

BLACKFRIARS BROUGHTON ENVIRONMENT ACTION PLAN 5

| Objective3: To improve traffic safety and access to transport |
| --- |
| Ref. | Action in 2002/2003 | Performance Indicator and Target | Funding (source & amount if known) | Local or Central Decision | Partners (Lead agency & officer responsible in bold) | KEY DEVELOPMENTS IN 2003/2004 AND 2004/2005 |
| 3.1 | Commence state 2 of the construction of the final section of the Inner Relief Route | Irwell Street to Gore Street | DETR | Central | City Council (Development Services) |  |
| 3.2 | Improve traffic safety | Continue to work with Residents’ Groups and businesses to identify the most dangerous areas and priorities for action Implement road traffic management/highway safety schemes as funding allows | Local transport plan; private sector | Central | All residents groups; City Council (Development Services) | Ongoing |
| 3.3 | Improve facilities for pedestrians | Design a pedestrian priority scheme for Chapel Street between New Bailey Street and Blackfriars Street Commence implementation of schemes in the Chapel Street Walking Plan Complete traffic study of Chapel Street, between Oldfield Road and Trinity Way, and the Crescent | Existing resources; NWDA Local transport plan; private sector Existing resources | Central | City Council (Development Services) Chapel Street Project Team City Council (Development Services) | Implement the pedestrian priority scheme for Chapel Street between New Bailey Street and Blackfriars Street, following completion of the Inner Relief Route Expand the coverage of the Walking Plan into Lower Broughton |
| 3.4 | Complete the review of car parking within the Chapel Street area | On Street Parking Locations | Existing resources | Central | Chapel Street Project Team; GM Police | Continue to renew and undertake environmental and security improvements to key car parks |
| 3.5 | Develop Green Travel Plans | University of Salford Proposed Albion High School | University; Health Authority City Council | Central | University; Health Authority; City Council City Council (Development Services; Education/Leisure) | Implement the Green Travel Plans |
| 4.6 | Tackle dog-related and abandoned vehicle problems | Develop the dog warden service Consider other ways to tackle dogs and open spaces Monitor new procedures for dealing with abandoned vehicles | Existing resources |  |  | Ongoing |
| 4.7 | Develop improved mechanisms for tackling fly tipping | Secure and publicise prosecutions against flytippers Introduce CCTV at regularly flytipped sites Continue the service to dispose of large bulky items for residents |  | Central | Environment Agency | Ongoing |
| 4.8 | Continue to secure and properly maintain vacant private sites and empty residential properties | Continue to work with private landlords, housing associations and private landowners | Existing resources | Central | City Council (Housing Services; Development Services) | Ongoing |

BLACKFRIARS BROUGHTON ENVIRONMENT ACTION PLAN 6

| Ref. | Action in 2002/2003 | Performance Indicator and Target | Funding (source & amount if known) | Local or Central Decision | Partners (Lead agency & officer responsible in bold) | KEY DEVELOPMENTS IN 2003/2004 AND 2004/2005 |
| --- | --- | --- | --- | --- | --- | --- |

| 4.9 | Monitor noise, air and land pollution within Broughton and Blackfriars | Monitoring report by March 2003 | Existing resources | Central | City Council (Environmental Services) | Ongoing |
| --- | --- | --- | --- | --- | --- | --- |
| Objective 5: To encourage the development of local initiatives and community-based projects |
| 5.1 | Encourage recycling | Implement the Greening Greater Broughton scheme, providing composting bins | Greening Greater Manchester | Local | Groundwork | Develop other projects for local recycling and composting |
| 5.2 | Develop community-based projects to be supported by the key funding sources | Number of schemes developed | Community Committee Devolved Budget Greening Greater Manchester New Opportunities Fund | Local | Groundwork: City Council | Ongoing |
| 5.3 | Develop projects for energy saving in the local residential and business communities | Business Environment Association – number of events held and businesses helped Incorporate energy efficiency measures into housing improvements | SRB; ERDF; Private sector Existing resources |  | Groundwork City Council (Housing Services; Development Services) | Continue in 2003/04 Ongoing |

City of Salford Community and Social Services Department

Broughton/Blackfriars Community Committee:

Health and Wellbeing Task Group:  Action Plan 2002/2003

| Action in 2002/03 | Performance Indicator/target | Funding (source) and Amount (if known) | Local/Central Decision for Action | Partner/Lead Agency/Officer Responsible | Priorities for 2003/2004 |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Action | Funding |
| Objective (A): Involving the Local Community |
| Work with Older People Mocha Community Centre | To continue to support work with older people in the Broughton area and develop the Broughton Older Peoples project (BOPS) The Centre is fully used and the groups well established 1. Youth Leisure 2. Salford Family Link Project 3. Broughton Health & Well Being Group 4. Mocha Community Art Project | The Centre is funded by Salford Community & Social Services £2000 funding acquired from Community Initiative Fund for (BOPS) Not Known at present Groups are funded individually | Central Carol Morris - CDW B.O.P.S Community Social Services Carol Morris – CDW Family Link Worker Youth Service | Carol Morris Carol Morris Carol Morris - CDW | Launch Event Increase usage of the Centre Maintain joint working at the centre |  |

C:\LJ\Rpt\HTGACTPLAN.A.doc

City of Salford Community and Social Services Department

Broughton/Blackfriars Community Committee:

Health and Wellbeing Task Group:  Action Plan 2002/2003

| Action in 2001/2 | Performance Indicator/target | Funding (source) and Amount (if known) | Local/Central Decision for Action | Partner/Lead Agency/Officer Responsible | Priorities for 2003/2004 |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Action | Funding |
| Objective (A): Involving the Local Community |
| Broughton Older People’s Scheme | Work towards funding for designated worker & part time admin support worker for B.O.Ps Set up a registration scheme for individuals in the community Apply for lottery bid Link B.O.Ps into city wide network for older people Negotiate with course provides for wide ranging course provision Produce B.O.Ps Bulletin 2 Put on both large and small scale events/activities in various location in Broughton | £2000 Community Imitative Fund Not Known Funding received | B.O.Ps Manager Comm. Carol Morris – Community & Social Services Eccles College, Salford College & Angel healthy Living Centre etc. Wardens, S. H Projects, Group Leaders, & Volunteers | Carol Morris Provide 12 courses 2 Holidays 1 Health Day Carol Morris | Access funding for workers Lottery Application Link in isolated people |  |

C:\LJ\Rpt\HTGACTPLAN.A.doc

City of Salford Community and Social Services Department

Broughton/Blackfriars Community Committee:

Health and Wellbeing Task Group:  Action Plan 2002/2003

| Action in 2001/2 | Performance Indicator/target | Funding (source) and Amount (if known) | Local/Central Decision for Action | Partner/Lead Agency/Officer Responsible | Priorities for 2003/2004 |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Action | Funding |
| Objective (A): Involving the Local Community |
| Continue to involve local people into various group, projects and events particularly around health issues. Support individuals to establish community networks, self-help groups and build self advocacy capacities with their community. Support to build new communities into the indigenous population Continue to send information regarding community issues to a wide mailing list,. Continue to support groups and individuals that are underrepresented, support representation on mainstream. Ongoing evaluation and assessment of changing needs | Women Working Together Group constituted and launched. Broughton Health Interest Group supported to independent status Supported the setting up of Food and Nutrition Group and the M.O.T to health workshops. Ongoing support to Research project –Higher Broughton Health Centre. Broughton Blackfriars healthy Salford Network set up initially for Salford fair. Needs assessment done to support S.R.B. bid to work with refugee and asylum seekers in Salford. Ongoing representation sought from underrepresented groups on various networks. Healthy Salford Network, RAPAR, Community Committee, health Task Group, SMARHF Developmental, continuous flexible and inductive. | Community Health Development Project. (P.C.T) Workers time, Time base resources, Local Community, Volunteers time. | Local and Central Local Central | Community Health development project. (Nilofer Shaikh) Work closely with local community activists. C.H.P project and volunteers to support Researcher Community H. Project with local groups and workers. Involvement of various organisations. R.A.P.A.R Refugee and asylum seekers, Heath and Advocacy Project, Community health Development Project & Broughton Men’s Health Club. Community Health Development Project, Projects with various groups and agencies. Community | Support Women working Together Group to gain independent status. Continue to support Broughton Health Interest Group as and when necessary. Ongoing support to research Continue and build on existing Network. Full time S.R.B. Project to develop work around Refugee and Asylum Seeking Communities. Ongoing and continuous support of groups onto mainstream. Ongoing evaluation | Community Health Project (P.C.T) Possibility of S.R.B. funding. Community Initiatives fund and P.C.T. S.R.B. and various agencies. |

C:\LJ\Rpt\HTGACTPLAN.A.doc

City of Salford Community and Social Services Department

Broughton/Blackfriars Community Committee:

Health and Wellbeing Task Group:  Action Plan 2002/2003

| Action in 2001/2 | Performance Indicator/target | Funding (source) and Amount (if known) | Local/Central Decision for Action | Partner/Lead Agency/Officer Responsible | Priorities for 2003/2004 |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Action | Funding |
| Objective (A): Involving the Local Community |
| Within the Community. Recruitment of support worker Project Advisory Group Production of information flyer Training needs of groups Chapel Street Residents Forum Greengate Drop Inn Centre Canon Green Court Tenants Group T.I.G. Festival Chapel Street Small Grants Scheme | Evaluation Currently on hold due to set up of P.C.T. On hold, as currently no development support worker. Support the involvement of residents in the strategy and wider community activity. Support for T.I.G Group to use Greengate Community Centre as a drop in facility Increased usage of Canon Green Court Community Flat Build up a steering group to put on festival at end of August in Mount Street Park. Provide Grants to support Community Projects | Development Services Group to be self funding through Community Committee etc. Small bids for I.T. provision Community Committee, Education & Leisure £5k Development Services | Local Local | Health Development Project Community Health Development Project Chris Furse - C.D.W Chapel Street Chris Furse - C.D.W Chapel Street Chris Furse, Leanne Feasy, Jacqui Griggs, Community Art Workers. Chris Furse - C.D.W | Possible recruitment of support and trainee workers Publicity and increased attendance Publicity support for training Maintain usage of the centre Build on last years events Build on last years events |  |

C:\LJ\Rpt\HTGACTPLAN.A.doc

City of Salford Community and Social Services Department

Broughton/Blackfriars Community Committee:

Health and Wellbeing Task Group:  Action Plan 2002/2003

| Action in 2001/2 | Performance Indicator/target | Funding (source) and Amount (if known) | Local/Central Decision for Action | Partner/Lead Agency/Officer Responsible | Priorities for 2003/2004 |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Action | Funding |
| Objective (B): Drugs |
| Develop a supported housing scheme Residents Action Group | To engage and support 15 people in their own tenancies who have drug misuse problems To support and develop a range of activities in deprived areas. | S.R.B - £19,500 Becoming self financing via T.H.B and after March 2003 via Supporting People | Local Local | Salford Drug Service Local Authority/Neighbourhood Co-ordinator. |  |  |

C:\LJ\Rpt\HTGACTPLAN.A.doc

# FORM 1

City of Salford Community and Social Services Department

Broughton/Blackfriars Community Committee:

Health and Wellbeing Task Group:  Action Plan 2002/2003

| Action in 2001/2 | Performance Indicator/target | Funding (source) and Amount (if known) | Local/Central Decision for Action | Partner/Lead Agency/Officer Responsible | Priorities for 2003/2004 |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Action | Funding |
| Objective (C): Healthy Living |
| Support groups on various initiatives Chapel Street Walking and Cycling Group Princess Royal Trust - Salford Centre | Therapies Courses M.O.T. to Health Workshops Food and Nutrition Group Health Research Higher Broughton Health Centre Healthy Salford Fair International Women’s Health Day Begin implementing the walking forum scheme in Blackfriars and Broughton Integrated Physical Activity Strategy aimed at children, young people, adults Continue partnership project with local GP to identify cares and provide services to meet the needs of cares. | W,E,A, Community Health Project Women Working Together Group Joint Finance Women Working Together Group £1905 from Community Initiative Fund allocated to support the scheme Funding bid submitted to Community Committee Salford Primary Care Trust | Local Local Central and Local Local Local Local Local | Women Working Together Group Researcher, Health Centre users and staff Community Health Development Team with various groups an agencies Women Working together Group The Angel Steering Group Education & Leisure Directorate Services, The Angel Alistair Fisher & Chris Furse Education leisure Directorate Alistair Fisher Salford Primary Care Trust, community Social Services Directorate | Continue to support individuals on various initiatives Action research project Support communities and agencies to hold health fair annually Hold annual International Women’s Health Day Implement the Chapel Street Walking and Cycling plan through supporting local projects | Community Development Health Project and Community Committee P.C.T Possible S.R.B Community Health Project and Community Committee Local |

C:\LJ\Rpt\HTGACTPLAN.C.doc

City of Salford Community and Social Services Department

Broughton/Blackfriars Community Committee:

Health and Wellbeing Task Group:  Action Plan 2002/2003

| Action in 2001/2 | Performance Indicator/target | Funding (source) and Amount (if known) | Local/Central Decision for Action | Partner/Lead Agency/Officer Responsible | Priorities for 2003/2004 |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Action | Funding |
| Objective (C): Healthy Living |
| The Angel Healthy Living Initiative Princess Royal Trust Salford Carers Centre Plan 2nd MAYFEST Music Festival In collaboration with St Phillips Church & Local Residents Community Playschemes Community Arts activities in Chapel Street Area Sure Start | Identify continued revenue funding from 1st April 2003 Complete Business Plan to ensure sustainability toward independent management Appoint Business Manager Continuing complementary therapy service Start phase I and 2of the Community Cafe Project within The Angel Summer Playschemes using Greengate Multi Sport Pitch. Training for T.I.G. volunteers. Provide Art Projects linked to Community events and festivals Activities for 0-4 years old and their parents in Chapel Street Area. | £200,000 pa £30,000 pa £54,000 £1,000 approximately form Community Committee N.W Arts Board, Education & Leisure, Chapel Street Strategy Sure Start Co-ordinator by chief execs. | Local Local Local Local Local | Salford Primary Care Trust With The Angel Shadow Board Salford Primary Care Trust MAYFEST Committee Dave Fraser S.U.M Chris Furse Chapel Street C.D.W Leanne Fealy, jacqui Griggs & Community Art Workers Sure Start | Complete The Angel Business Plan and clarify ongoing revenue funding Volunteers to be trained in play work skills. | Salford Primary Care Trust |

C:\LJ\Rpt\HTGACTPLAN.C.doc-

City of Salford Community and Social Services Department

Broughton/Blackfriars Community Committee:

Health and Wellbeing Task Group:  Action Plan 2002/2003

| Action in 2001/2 | Performance Indicator/target | Funding (source) and Amount (if known) | Local/Central Decision for Action | Partner/Lead Agency/Officer Responsible | Priorities for 2003/2004 |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Action | Funding |
| Objective (E): Mental Health/Wellbeing |
| Secure long term funding beyond June 2002. Initial `bridging’ funding gained from Community Committee Devolved Budget. To continue project operation from April – June 2002-07-15 Existing projects self sufficient and able to bring in own funding Supported by other agencies/key figures therefore all are capable of continuing existence in community. | Broughton Men’s Health Club staged Broughton Champions Group, Broughton Health Week, Outdoor Activities Weeks and Team Building Events and increased club membership positively. Broughton Knights (skills x change completed 12 weeks scheme) Gears Motor Vehicle Project C.H.I.P.S. trained members in food hygiene and community café course & staged 2 community awareness events. Mental health & Wellbeing Directory launched successfully 14th March. Included local artwork, creative writing, photography and full community involvement. Broughton Health & Wellbeing Group celebrated World Mental health Day 2001 Broughton Health & Wellbeing Projects to continue to run weekly sessions after 3 years of offering local, practical support and events all aimed at increasing well being. Lowry High School & ACE Project – Due to loss of funding for school based youth worker project closed down. Youth Leisure continues to run positive events throughout the year with minimal support form Broughton Health & Wellbeing Project. Work with Men – on going new contacts | Global Grants - £6,000 £500.00 P.C.T Funding Awards for All - £5000 £1,500 – P.CP.T Funding Devolved Budget £73500 – Devolved Budget | Local & Central Local & Central Local & Central Local & Central Local Local | Broughton health & Wellbeing Group, Safer Salford, Salford Leisure Services Dave Fraser –Broughton Trust Community Health Broughton Health & Wellbeing Project & Salford Venture. Broughton Health & Wellbeing Project & Salford Venture. Broughton Health & Wellbeing Project, Transitional Employment Project & Pathfinder Project. Broughton Health & Wellbeing Project, Safer Salford, Community Development Workers, B.O.Ps & Leisure Services. Salford Family Link & Broughton Health & Wellbeing Project | Club continues to run independently and successfully in the community. Young Men’s Group continues to meet weekly. Continue to consult with community, stage events & produce business plan. Launch directory and distribute in the community. Commit to staging yearly event. Continue to plan and deliver quarterly programmes | Funding gained until September 2002 Funding needed for short-term projects and to cover cost of hire for football session. Awards for all funding in operation Seek out funding to update directory yearly. Seek Local Funding Money needed for ongoing running costs |

C:\LJ\Rpt\HTGACTPLAN.C.doc-

City of Salford Community and Social Services Department

Broughton/Blackfriars Community Committee:

Health and Wellbeing Task Group:  Action Plan 2002/2003

| Action in 2001/2 | Performance Indicator/target | Funding (source) and Amount (if known) | Local/Central Decision for Action | Partner/Lead Agency/Officer Responsible | Priorities for 2003/2004 |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Action | Funding |
| Objective (E): Mental Health/Wellbeing |
| Broughton Health and Wellbeing Project – Long Term funding issue Community Health Project Needs identified to set up Asian Women’s including carers self help group | Evaluated/disseminated 3 ½ years of positive project running. Produced evaluation report and proposal paper to present to potential funders – P.C.T main target Development worker applied for communities Against Drugs for 3 years funding Research identified and focus group discussions assessment. Currently on hold as no support worker available. | £40,000 Not Known | Local & Central Local & Central Local & Central | Alan Cooper Community Development Worker. Jane Birch Co-ordinator Communities Against Drugs. Community Health Project with other agencies | Presentation given to L.I.T Application bid submitted Support the development of Self Help Projects | Not a priority for funding by P.C>T Awaiting response Not Know |

City of Salford Community and Social Services Department

Broughton/Blackfriars Community Committee:

Health and Wellbeing Task Group:  Action Plan 2002/2003

| Action in 2001/2 | Performance Indicator/target | Funding (source) and Amount (if known) | Local/Central Decision for Action | Partner/Lead Agency/Officer Responsible | Priorities for 2003/2004 |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Action | Funding |
| Objective (F): Poverty and Health |
| HP 1 Broughton Health Project Weekly advise sessions conducted at: Higher Broughton Health Centre (WRO – Health; CAB Advisor) x2 Lower Broughton Health Centre (WRO – Health; CAB Advisor) x2 Take-up work Training Evaluation Secure funding post March 2003 | Numbers of people assisted Target (quarterly): new rpt. total HBHC 30 30 50 LBHC 20 30 50 Other 15 15 30 130 Number of issues dealt with Target (quarterly): 125 Profile of people assisted in target groups. Target:- to exceed the % in the community as a whole Generate additional income. Target (quarterly):- £60,000 Mailshots to > 60s. Target (monthly): - TBA Target:- achieved/not achieved Target conduct regular customer satisfaction survey health staff evaluation of project Target: feedback findings of the Health Research Project Target:- successfully negotiate continuing funding from Salford PCT by Autumn 2002. | Salford Primary Care Trust - £60,000 | N/A | Lead Agency - City of Salford Community & Social Services Partners - Salford CAB - Lower Broughton GP Practices - Higher Broughton GP Practices - Mocha Parade GP Practice - Salford PCT - HAZ | Continue/ develop work in existing sites Co-ordinate with similar work in other parts of the City Consider links with the developments i.e. LIFT | Salford PCT - £60,000 pa Will need to be reviewed to take account of salary increases |

City of Salford Community and Social Services Department

Broughton/Blackfriars Community Committee:

Health and Wellbeing Task Group:  Action Plan 2002/2003

| Action in 2002/3 | Performance Indicator/target | Funding (source) and Amount (if known) | Local/Central Decision for Action | Partner/Lead Agency/Officer Responsible | Priorities for 2003/2004 |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Action | Funding |
| Objective (F): Poverty and Health |
| HP 2Linkworker Project Recruit & induct staff Weekly advice session conducted at North Salford Youth Centre Telephone advice session Take-up work Benefit & services awareness amongst Asian communities | Target: Achieve by June 2002. Target: 90% of sessions conducted Target: weekly session – conducted @ 90% Numbers of people assisted Target : 100 with 300 contacts Number of issues dealt with Target: 250 Profile of people assisted in target groups especially ethnic minority communities. Target:- to exceed the % in the community as a whole Generate additional income. Target :- £100,000 Regular mailshots and leaflet drops to the Asian communities. Target:- achieved/not achieved Produce & distribute leaflets and posters about the service and appropriate benefit issues. Conduct talks to appropriate groups within the Asian communities. Target:- achieved/not achieved | Funding - SRB 5 £33,000 until March 2005 | N/A | Lead Agency City of Salford Community & Social Services Partners Salford CAB Salford Community Health Project Salford PCT AWAAZ Asian Advocacy & Information Project Salford Link Project | Establish appropriate methods of delivering the service to other Urdu/Paunjabi communities in the City. | £33,000 Per annum Source beyond March 2005 to be identified |

City of Salford Community and Social Services Department

Broughton/Blackfriars Community Committee:

Health and Wellbeing Task Group:  Action Plan 2002/2003

| Action in 2002/3 | Performance Indicator/target | Funding (source) and Amount (if known) | Local/Central Decision for Action | Partner/Lead Agency/Officer Responsible | Priorities for 2003/2004 |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Action | Funding |
| Objective (F): Poverty and Health |
| Community Health Projects Support groups training and capacity building in relation to employment. | Food and nutrition workshops identified. Volunteers capacity building make trainee community development post available. Link with Salford Wide P.A. network and support local training and work. | Community Health Development Project Primary Care Trust | Local and Central | Community Health Development Project, Women Working Together Community Health Development Project with various groups and agencies. | Continue to support groups training and capacity building in relation to employment. Support development of training and support group for volunteers. Continue link with Salford Wide P.A. network to support locally. |  |

BLACKFRIARS BROUGHTON ECONOMIC DEVELOPMENT ACTION PLAN 2002/047

| Ref | Action in 2002/03 | Performance Indicator and Target | Funding (Source & Amount) | Local or Central Decision | Partners (Lead agency & officer responsible in bold) | KEY DEVELOPMENTS IN 2002/3 AND 2003/4 |
| --- | --- | --- | --- | --- | --- | --- |

| Objective 1: Reduce Unemployment &Barriers to employment and raise standards and attainment levels in education and training and provide access to education, training and advice |
| --- |
| 1.1 | To develop the work of the Lower Broughton Job Shop Plus service | 175 residents accessing employment No of people entering training through the work of the job shop | SRB5 ERDF – applied for | Central | Salford City Council - Stuart Kitchen ERP - Ann Worsley SRB5 Partnership |  |
| 1.2 | Co-ordinate resources to link local people into local jobs with the help of:The Employment Charter; Job Shop Plus Service; Opportunities arising from Chapel Street Regeneration Strategy, and the Irwell Economic Development Zone 2002/3 To continue to develop the jobs shop plus service so that it tailors outreach work to the needs of the local community 2003/4 | The use of outreach venues to continue 2 outreach training/advice sessions held by The Job Shop Plus service Links with new developments to identify job opportunities for local people. Explore the potential of combining the Chapel Street Business Open Days with jobs and training events for local people. See 1.8 Ensure inter-agency working by cross reference of the Chapel Street and Broughton and Blackfriars Action Plan Continue to develop an employment database (employers, employment opportunities and skills requirements | SRB5 ERDF ESF LSC Money Existing Funding Salford City Council | Central | Job Shop Plus- ERP Ann Worsley. Chapel Street Regeneration Strategy, Peter Baker Chapel Street Business Group, Paul Wainwright Salford City Council – Economic Development Employment Charter Chris Edwards | Ensure that virtual access to the job shops is available through local computer suites 2003/4 Devise an exit strategy for SRB5 –funded projects Combine Chapel Street Business Open Days with information events for local people RECOMMEND AS PRIORITY |
| 1.3 | Deliver New Deal Programme in Cheetham and Broughton | 20 jobs created 10 residents obtaining qualifications | SRB2 Manchester Enterprises | Central | Manchester Enterprises – Neil Cheetham ERP – Mike Hayes | 2002/3 Research to maximise the number of young people taking up CEE places Targeted programmes and information events Devise and exit strategy for SRB2-funded projects |
| 1.4 | Develop the work of Careers Partnership/The new Connexions service in the area | Targeted approach to help young people gain access to the arts and media sector | None required | Central | Careers Partnership Salford City Council, Stuart Kitchen | 2003/4 Link the work of Careers Partnership into the work of other agencies in the area Links into the Chapel Street Programme with a long term approach to link young people into the arts/media sector through appropriate advice and training initiatives RECOMMEND AS PRIORITY |

BLACKFRIARS BROUGHTON ECONOMIC DEVELOPMENT ACTION PLAN 2002/048

| Ref | Action in 2002/03 | Performance Indicator and Target | Funding (Source & Amount) | Local or Central Decision | Partners (Lead agency & officer responsible in bold) | KEY DEVELOPMENTS IN 2002/3 AND 2003/4 |
| --- | --- | --- | --- | --- | --- | --- |

| 1.5 | Identify ways to improve transport links to areas of job opportunity | Develop an employment transport plan. Promotion of community bus services – new and existing | GMPTE Neighbourhood Renewal Fund | Central | GMPTE Salford City Council | 2003/4Development of sustainable transport plan RECOMMEND AS PRIORITY |
| --- | --- | --- | --- | --- | --- | --- |
| 1.6 | Develop the work of Salford College to meet the needs of job seekers in the area | Outreach work: Community consultation to identify demand for courses Continued attendance at the jobs and training fairs 100 Residents accessing non-vocational training. 30 Residents accessing vocational training | Existing Funding | Central | Salford College, Ian Thurman Job shop plus | 2003/4 Continue to develop outreach work of the college, |
| 1.7 | Ensure that basic skills and employability training is available to local people | Targeted bids Interagency working | ERDF ESF | Central | Higher Broughton Housing Group ERP | 2002/3 Work with the Youth service via Broughton Knights to develop the employability of young people in Broughton |
| 1.8 | Encourage local employers and training providers to become involved in Jobs and Training Fairs | Salford wide event 12/09/02 1 training event 1 employers event | Salford City Council | Central | Salford City Council, (Charter) Stuart Kitchen Job shop Plus, Ann Worsley | 2003/4 Further Jobs and Training Fairs to be held at regular intervals Themed Fairs/ Sector – Specific Fairs |
| 1.9 | ICT in the Community | To provide training for 100 residents Assist community groups and community businesses to develop Web sites | Salford City Council | Central | Salford City Council Mike Benjamin | 2003/4 a further residents 100 trained and continued support for community and voluntary businesses seeking a Web presence |

BLACKFRIARS BROUGHTON ECONOMIC DEVELOPMENT ACTION PLAN 2002/049

| Ref | Action in 2002/03 | Performance Indicator and Target | Funding (Source & Amount) | Local or Central Decision | Partners (Lead agency & officer responsible in bold) | KEY DEVELOPMENTS IN 2002/3 AND 2003/4 |
| --- | --- | --- | --- | --- | --- | --- |

| Objective: Provision of advice and support to businesses and self employment and support community economic development and community enterprise |
| --- |
| 2.1 | Continue to develop the Business Environmental Network to help local companies to reduce the impact of their business on the environment and to help them save money in doing so | 10 Businesses advised 5 new SME members 5 audits delivered 1 publication produced 4 seminars Information sharing between Groundwork and City Council’s Economic Development Team | ERDF Private Sector SRB6 | Central | Groundwork Salford & Trafford – Sam Nicholson | 2003/4 Link into the Business Support Package and the work of other agencies Devise an exit strategy for SRB2-funded projects |
| 2.2 | Implement City Pride Waste Minimisation Programme | 2% reduced volume of waste in at least 3 companies £3,000 per company cost savings in at least 3 companies 2% energy reduction in at least 3 companies Liaison with City Council’s Business Liaison Team to share business data | SRB2 | Central | Groundwork Salford & Trafford – Helen Taylor | 2002/3/4 Link into the Business Support Package and the work of other agencies Devise an exit t strategy for SRB2-funded projects |
| 2.3 | Continue to develop Cheetham/Broughton Business Network | 50 companies accessing support | SRB2 | Central | SRB2 Partnership – Economic Development officer Post vacant | 2003/4 Increase the amount of companies accessing support year on year |
| 2.4 | Chapel Street Grants for Businesses | 15 businesses receiving grants Wage subsidies | Salford City Council | Central | Salford City Council. – Business Liaison Team & Employment charter | 2002/3/4 Continue to provide grants Apply for additional funding |
| 2.5 | Develop the work of the Small Business Service (SBS) through CBE and Salford Hundred Venture | No of new starts | CBE | Central | Chamber Business Enterprises Salford Hundred Venture | 2002/3/4 Continue to develop work with the SBS |
| 2.6 | Support the work of the Broughton Trust | Develop support services & local point of contact for community enterprise initiatives Complete & submit funding applications for the Trust Appoint staff to new posts Continue consultation Produce newsletters Continue work to develop & promote premises for the Broughton Trust & linked activities (Community Campus) Work alongside Salford Community Venture to initiate community enterprise Give preliminary assistance to community enterprises in Broughton Assist community groups to develop & implement funding strategies, leading to employment of staff Support the Broughton Child Care Network | Existing Funding | Local | Broughton Trust (Joan Williams Community Groups & Residents Associations Salford City Council | 2003/4 Continue to support the work of the Broughton Trust RECOMMEND AS PRIORITY |

BLACKFRIARS BROUGHTON ECONOMIC DEVELOPMENT ACTION PLAN 2002/0410

| Ref. | Action in 2002/03 | Performance Indicator and Target | Funding (Source & Amount) | Local or Central Decision | Partners (Lead agency & officer responsible in bold) | KEY DEVELOPMENTS IN 2002/3 AND 2003/4 |
| --- | --- | --- | --- | --- | --- | --- |

| 2.7 | Continue to develop the work of Salford Community Venture and its work with partners such as the Broughton Trust | Continue partnership working with Broughton Trust in capacity building training community activists to facilitate the development of ideas in community enterprise/business. Facilitate community workshops to generate ideas/interest in the development of community businesses. First workshop 2.9.02 Further develop links with training capacity building organisations to deliver community enterprise start-up requirements Explore market imbalances in demand and supply for developing community enterprises in Blackfriars and Broughton Facilitate 2 new Community Enterprise/Business start – ups Provide business advice support and guidance to 5 community groups/businesses | Existing Funding |  | Salford Community Venture (Edith Knowles) | 2003/2004 Continue work with Broughton Trust & other agencies operating in the area Continue to stimulate community action on developing Community Businesses and networking with other community enterprises Further Develop a community strategy to fill gaps in provision of goods and services by the development of community businesses Provide business advice support and guidance to 7 community groups/businesses Facilitate 2 new community enterprise start – ups |
| --- | --- | --- | --- | --- | --- | --- |

BLACKFRIARS BROUGHTON ECONOMIC DEVELOPMENT ACTION PLAN 2002/0411

| Ref. | Action in 2002/03 | Performance Indicator and Target | Funding (Source & Amount) | Local or Central Decision | Partners (Lead agency & officer responsible in bold) | KEY DEVELOPMENTS IN 2002/3 AND 2003/4 |
| --- | --- | --- | --- | --- | --- | --- |

|  | Objective 3: Reduce impact of crime towards businesses and improve industrial/commercial premises and surrounding environment |
| --- | --- |
| 3.1 | Deliver Environmental Improvement Grants for Broughton/Chapel Street | 3 buildings improved | ERDF SRB2 | Central | SRB2 Partnership Salford City Council: Business Liaison – Joanne Hall Development Services – Barry Whitmarsh Chapel Street Regeneration Partnership | 2003/4 Review the benefits of the programme and if appropriate identify new resources |
| 3.2 | Dedicated mobile security patrol along the Chapel Street Corridor | Promote and expand membership of the Quaywatch service | Private sector NRF City Council | Central | Safer Salford | 2003/4 Continue to develop the project |
| 3.3 | Implement Security Grants Package | 25 grants awarded | SRB2 ERDF Private Sector Salford City Council | Central | SRB5 Partnership Private Sector Salford City Council Joanne Hall GMP Chapel Street Capital Receipts | 2003/4 Continue grants package Identify new resources |
| 3.4 | Continue to support retail and business centres | Ensure secure by design principles are used in new developments Offer support to retail sectors Pursue opportunities for new development | None required | Central | Chapel Street Regeneration Strategy Salford City Council : Development Services – Barry Whitmarsh | 2002/3/4 Continued Support |

BLACKFRIARS BROUGHTON YOUTH ACTION PLAN 2002-04

| Ref. | Action | Performance Indicator and Target | Funding (source & amount) | Local or Central Decision needed for Action | Partners (Lead agency/ officer responsible in bold) | Key Developments in 2002-4 |
| --- | --- | --- | --- | --- | --- | --- |

| Young people across all ages Objective: Ensure safe, supervised and affordable access to youth activities and facilities |
| --- |
| YP A1 | Continue to provide safe transport to youth facilities and activities | arrangements and budget in place | New | Central/local | Youth Service, all groups Community Transport | RECOMMEND AS PRIORITY |
| A2 | Plan & support funding bids for holiday activities incl. half term holidays | support work of Play Devel’t Project and the playschemes it supports summer activities at N. Salford Youth Centre summer activities at Zebra St. play area with 180 children participating Recreation Centre to provide summer holiday activities with Sports Development & Early Years Link recreation facilities to local groups | New existing | Local | Play Development Group, Broughton Trust Youth Service, Task Group members and partners. Education & Leisure |  |
| A3 | Continue to support uniformed youth activities | maintain the current number of local groups | New | Local | Uniformed youth organisations |  |
| A4 | Evaluation of support for children leaving care | review of current arrangements | existing resources | local | Community & Social Services, Education & Leisure, Housing, Health Authority, voluntary organisations (NCH, Barnardo’s) |  |
| A5 | Evaluation of the support available to young carers with responsibilities for siblings and adults in need | review of current arrangements | Existing | local | Community & Social Services Education & Leisure, Housing, Health Authority, voluntary organisations |  |
| A6 | Provide outreach and detached youth work for the Chapel St. programme area | 50 young people involved in social education activities | N’hood Renewal Fund, Angel |  | Salford Youth Service, Chapel St programme, TIG | RECOMMEND AS PRIORITY |
| A7 | Develop support for youth work by Police officers | joint activities held involving local groups and local police officers | Existing Local funds |  | GM Police |  |
| A8 | Support the work of the Broughton rust | information exchanged between Task Group and the Trust publicise developments in childcare provision explore opportunities for involvement in Youth project |  | Local | Task Group and Broughton Trust |  |
| A9 | Update leaflets on activities for Broughton and include Blackfriars. | leaflets produced & circulated report to Youth Task group |  |  | Arts & Leisure and Task Group Andy Harrison. |  |
| A10 | Develop use of the Information & Communication Tech Centres at Resource Centre, Angel & D@tabase | programmes underway at Resource C’tre D@tabase project launched | existing |  | Community Resource Centre, D@tabase & City Leisure Services |  |
| YP A11 | Review quantity and quality and accessibility of sports, arts and leisure facilities and activities. | review completed report to Task Group | Existing. | Central | Arts & Leisure Garry Bateman |  |

BLACKFRIARS BROUGHTON YOUTH ACTION PLAN 2002-04

| Ref. | Action | Performance Indicator and Target | Funding (source & amount) | Local or Central Decision needed for Action | Partners (Lead agency/ officer responsible in bold) | Key Developments in 2002-4 |
| --- | --- | --- | --- | --- | --- | --- |

| A12 | Explore different uses for changing facilities at Albert Park all-weather pitch | report produced links made with young people locally | to be identified |  | Arts & Leisure, Andy Harrison |  |
| --- | --- | --- | --- | --- | --- | --- |
| A13 | Promote and publicise existing youth provision. | 5 pieces on activities in local press | Existing. | Central | All agencies with Council’s Communications & Public Relations |  |
| A14 | Identify needs of black young people in Broughton | research work with Asian, African-caribbean and refugee communities 40 young people contacted Report to be completed and findings circulated Develop new provision for Black young people at North Salford Youth centre as a result | Existing | Local | Black Youth Work Development Project |  |
| A15 | Deliver music project – Dhol drumming | 15 young people involved Group to become self-constituted | New | local | Black Youth Work Development Project, Youth service |  |
| A16 | Extending work with young men from minority ethnic communities | 12 young men involved in residential 15 young men being more involved in community activities | existing | local | Black Youth Work Development Project |  |
| A17 | Establish black women only sessions at N. Salford Youth Centre | 10 women participating in sessions community celebration event for International women’s week | Existing | local | Black Youth Work Development Project, Women working Together |  |
| A18 | Provide a programme of activities over the summer | funding secured workers recruited programme advertised | To be identified | central | Youth Services |  |

BLACKFRIARS BROUGHTON YOUTH ACTION PLAN 2002-04

| Ref. | Action | Performance Indicator and Target | Funding (source & amount) | Local or Central Decision needed for Action | Partners (Lead agency/ officer responsible in bold) | Key Developments in 2002-4 |
| --- | --- | --- | --- | --- | --- | --- |

| Young people across all ages Objective: Programmes of Community Safety & opportunities for addressing anti-social behaviour including racial harassment |
| --- |
| B1 | Complete pilot project at Zebra St play area addressing bullying and racism issues. Research into what works with young people | Provide opportunities for young people to participate in programmes of education and activity 24 young people participating Monitor success of project i.e. people feeling safe to use the park | existing | local | Youth Services & ZSARA |  |
| B3 | Ensure black young people are involved in Salford Multi-Agency Racial Harassment Forum (SMARHF) | 3 black young people participating | existing | local | BYWDP, Police, Police Authority, Probation, Salford Link Project, Community Health Project |  |
| B4 | Involve young people in relevant decision-making structures | continued development of young people 13 – 25 years helping to develop representative voice in city-wide structures develop structures in schools | existing | local | Youth Service Police Authority |  |

| Children aged 0 - 11 Years Objective: Ensure provision of more safe opportunities for play. |
| --- |
| YP C1 | Continue to support and develop Broughton / Blackfriars Play Development Group, | retain 25 volunteers; recruit 5 new vols 2000 places offered on playdays & activity days; 200 children to benefit training programme for adults development of equipment store | Project budget; | Local | Play Development Group, Broughton Trust Salford City Council , community groups, Youth Task Group, Sports Development |  |
| C2 | Secure long term funding for the Play Dev’t Co-ordinator | successful funding bids to provide a sustainable project | New funding for 2002/3 | Local | Play Development Group, Broughton Trust City Council | Funding for Co-ordinator needed by 2002/3 |
| C3 | Develop plan of work for new Play worker | plan of work agreed and implemented | Project budget | Local | Play Development Group, Broughton Trust | Funding for Play Worker needed by 2003/4 |
| C4 | Promote out of school activities (including holidays and weekends) | further 40 children accessing new provision involve sports coaching in playschemes playscheme for 25 Asian young people at N. Salford Youth Centre | NOF (New Opportunities Fund) /existing Devolved budget to be identified |  | Early Years Team (Iris Kennedy); Play Development Project; N. Salford; Play Development Black Youth Work Devel’t Project Salford Link Project | total of 116 new places by 2004; current NOF fund ends in 2003 training programme in place by 2003 |

BLACKFRIARS BROUGHTON YOUTH ACTION PLAN 2002-04

| Ref. | Action | Performance Indicator and Target | Funding (source & amount) | Local or Central Decision needed for Action | Partners (Lead agency/ officer responsible in bold) | Key Developments in 2002-4 |
| --- | --- | --- | --- | --- | --- | --- |

| C5 | Support development of new community-based play initiatives, (for example TIG and RITA Youth Leisure) | support development of SIRRA Youth Leisure regular events held, funding in place offer support to the TIG group involve 7 volunteers at TIG 20 children attending regularly practical skills training for volunteers secure funding for sessions, equipment and activities | Devolved budget to be identified |  | Health & Well-being Project, Safer Salford, SUM, Play Development Project Chapel St. project; Youth Services; Angel; Play Development Project | RECOMMENDED AS PRIORITY |
| --- | --- | --- | --- | --- | --- | --- |
| C6 | Identify and support more play projects including pre-school groups | 2 new parent & toddler groups developed and supported 1 additional project set up | existing, Start-up grant, Devolved budget |  | Early Years Team, Play Development Project, SUM, , Tiny Tots, SIRRA Youth Leisure, Police, Youth Task Group, N Salford | total of 2 new play groups set up by 2004; |
| C7 | Develop toy library provision | training event on sustaining toy libraries to be convened involving local groups | In place |  | Early Years Partnership |  |
| C8 | Explore establishment of a Play Resource Unit in Salford | feasibility study on location and operation completed | £28,500 SRB5 | funding in place | Gtr. M’cr Play Resource Unit SRB5 Team |  |
| C10 | Widen knowledge of and access to sports, arts and leisure facilities and programmes. | joint work with Sports Development on holiday playschemes providing sport coaching and activities for 8-14 year olds weekly sessions held for local youth groups at Recreation Centre & Pool programme of publicity for holiday events | Devolved budget existing | Central | Education & Leisure, Sports Dev’t, City Leisure, Men’s Health Group City Leisure City Leisure Activities Development |  |
| C11 | Support the development of Saturday activities at the Oasis for 6-11 year olds by the TIG group | support for summer programme in place access to Oasis ensured | Devolved Budget, Arts & Culture |  | TIGGroup, Chris Furse (Chapel St.) Youth Service, Play Development Project, Community Arts Team | RECOMMEND AS PRIORITY |
| C12 | Develop summer playscheme for Chapel St programme area | involve 5 volunteers 30 children involved from area funding refurbish St Simon St all weather pitch develop programme of play & sports activities for the area | Chapel St. Arts & Culture budget; Devolved budget |  | TIG, Chris Furse (Chapel St.), Arts & Leisure Community Arts officer |  |
| C13 | Extend and develop accessible sporting facilities at N. Salford Youth Centre for a Junior Youth Club for 8-11 year olds | staff in place for outreach work around Higher Broughton on 6 month pilot explore outdoor facilities @ N.Salford | To be identified | Local/Central | Youth Service/North in Action Project; local community groups | Funding for North in Action Project expires 2003 |

BLACKFRIARS BROUGHTON YOUTH ACTION PLAN 2002-04

| Ref. | Action | Performance Indicator and Target | Funding (source & amount) | Local or Central Decision needed for Action | Partners (Lead agency/ officer responsible in bold) | Key Developments in 2002-4 |
| --- | --- | --- | --- | --- | --- | --- |

| Children aged 4 - 11 Years Objective: Address problem of school disaffection |
| --- |
| D1 | Provide intense support to children, schools and families. | Learning Mentors Family Link Project | to be identified | Local & Central | to be identified Family Link Project (Shelli Nelson) |  |
| D2 | Develop links with projects on school disaffection & encourage good practice | to be identified | to be identified | Local | to be identified |  |
| D3 | Support existing projects in area (e.g. Family Link Project, St Philips Project, Tiny Tots) | projects maintained | to be identified | Local | Family Link Project, Ascension Community Project | funding requirements identified |
| D4 | Improve support for children with learning and behavioural difficulties in schools | programmes put in place by schools monitoring by Education Welfare |  | Central | Education & Leisure | RECOMMEND AS PRIORITY |
| D5 | Provide full time educational provision for all excluded pupils | funding, accommodation and provision in place for full time educational provision for all excluded pupils support in place for all pupils at risk of exclusion develop work of the Grosvenor Centre | In place | Central/ Government | Education & Leisure | RECOMMEND AS PRIORITY |
| Young people aged 11-14 years Objective: Ensure provision of more safe opportunities for young people to meet. |
| YP E1 | Support development of a Intermediate Youth Club at North Salford Youth Centre | 30 juniors attending intermediate night 20 juniors becoming senior members 6 volunteers involved 1 volunteer training programme |  |  | Youth Service and Voluntary Sector. |  |
| E2 | Maintain accessible sporting facilities at N Salford Youth Centre | 1 additional session per month for community sporting activities |  |  | Youth Service, Education & Leisure, Sports Development. |  |
| E3 | Widen knowledge of and access to sports, arts and leisure facilities and programmes. | explore change of use for changing room facilities at Albert Park all weather funding for ICT Centre at Broughton Rec. in place | to be identified Lottery | central | Education & Leisure, Sports Dev’t, City Leisure |  |
| E4 | Establish regular contact & programmes in Chapel St programme area | regular contact established programmes agreed and under way | to be identified | central | Youth Service | RECOMMEND AS PRIORITY |
| E5 | Explore feasibility of a mobile resource vehicle to support outreach work across the whole of the Community C'tee area | research under way feasibility study prepared | to be identified | local/central | Youth Task Group; Safer Salford | RECOMMEND AS PRIORITY |
| Young people aged 11-14 years Objective: Address problem of school disaffection |
| F1 | Grosvenor Project for excluded pupils and the most disaffected young people to be opened | project to become fully operational delays in opening project to be overcome Encourage exchange of good practice | NCH Education | Local | NCH Action for Children, Education & Leisure | RECOMMEND AS PRIORITY |

BLACKFRIARS BROUGHTON YOUTH ACTION PLAN 2002-04

| Ref. | Action | Performance Indicator and Target | Funding (source & amount) | Local or Central Decision needed for Action | Partners (Lead agency/ officer responsible in bold) | Key Developments in 2002-4 |
| --- | --- | --- | --- | --- | --- | --- |

| F2 | Truancy Patrol to be in operation within the area | Take appropriate action for those with less than 80% attendance Implement first day response to absenteeism Arrange sweeps by Truancy Patrol when appropriate and take appropriate action | To be identified | Central | City Council Education Welfare Albion School |  |
| --- | --- | --- | --- | --- | --- | --- |
| D5 | Provide full time educational provision for all excluded pupils | funding, accommodation and provision in place for full time educational provision for all excluded pupils support in place for all pupils at risk of exclusion develop work of the Grosvenor Centre provide support to pupils on health & drug abuse | In place | Central/ Government | Education & Leisure | RECOMMEND AS PRIORITY |
| F3 | Pursue full time educational provision for all excluded pupils | funding and provision in place Pursue full time educational provision for all excluded pupils | To be identified | Central | Education & Leisure | RECOMMEND AS PRIORITY |
| Young people aged 14 -16 years Objective: Provide more safe opportunities for young people to meet (14-16 years age group) |
| G1 | Provide programmes targeted at young people at risk. | continued support for North in Action Time Out Group increased number of young people involved up to 12 in total | Existing and new. | Central and local | Youth Services, Education & Leisure, Community & Social Services, Community Sector Team, Safer Salford, Youth Task Group, Men’s Health Group/Broughton Knights. |  |
| G2 | Assess the impact of the proposed loss of the Charlestown Youth Centre for local young people | centre to be mothballed regular contact to be maintained in different locations | Existing | Local | Youth Service |  |
| G3 | Assess the impact of the reduction in detached and outreach youth work programmes | reassess existing services in the area and prioritise detached and outreach work pursue resources to expand outreach and detached youth work | Existing and New. | Local and central | Youth Service & Youth Task Group | RECOMMEND AS PRIORITY |
| G4 | Continue to develop N. Salford Youth Centre | minimum of 3 sessions per week 50 young people attending per week 2 open events | New and Existing. | Local | Youth Service |  |
| G5 | Development of personal and social education and health programmes. | programme of 2 sessions per week 20 young people involved each week quarterly reports to Youth Task Group | Existing and new. | Local | Youth Service, Drug Advisory Service, Schools. |  |
| G6 | Establish regular contact and relevant programmes in the Chapel St programme area | funding secured and staffing in place programmes agreed and in operation | N’hood Renewal Fund | Central | Youth Service |  |
| G7 | Continuation of specialist programmes at Oasis. | PHAB, TIG, Youth Affairs and training programmes to continue | Existing. | Local | Youth Service |  |
| G8 | Provide full time educational provision for all excluded pupils | funding, accommodation and provision in place for full time educational provision for all excluded pupils support in place for all pupils at risk of exclusion develop work of the Grosvenor Centre provide support to pupils on health & drug abuse | In place | Central/ Government | Education & Leisure |  |

BLACKFRIARS BROUGHTON YOUTH ACTION PLAN 2002-04

| Ref. | Action | Performance Indicator and Target | Funding (source & amount) | Local or Central Decision needed for Action | Partners (Lead agency/ officer responsible in bold) | Key Developments in 2002-4 |
| --- | --- | --- | --- | --- | --- | --- |

| Young people aged 16-25 years Objective: Provide more safe opportunities for young people to meet |
| --- |
| YP H1 | Assess the impact of the reduction in detached and outreach youth work programmes | reassess existing services in the area and prioritise detached and outreach work pursue resources to expand outreach and detached youth work | Existing and new. | Local and Central | Youth Service |  |
| H2 | Extend work at N. Salford Youth Centre | increase no. attending to 20 in total no. of weekly sessions increased to 2 | New and existing. | Local | Youth Service |  |
| H3 | Continue to provide secure transport to youth facilities. | transport provided to youth facilities min. of 5 times per week monitoring of the numbers benefiting | New. | Local | All partners | RECOMMEND AS PRIORITY |

| Young people aged 16-25 years Objective: Provide more opportunities for young people to learn about issues related to Health, Drugs and Parenting Skills |
| --- |
| I1 | Support and develop parenting projects. | projects involved in parenting work identified | New. | Local | All partners. |  |
| Young people aged 16-25 years Objective: Reduce criminal behaviour |
| J1 | Project to address disaffection | provide point of contact sessions for 20 young women at risk; activities to develop confidence & esteem pursue funding for contact sessions for young men at risk | Existing To be identified | Central & local | Youth Service, Safer Salford Community Police officers, Sports Devel’t. Education & Leisure |  |
| J2 | Provide advice, information and support to unemployed/disaffected young people | Work with other agencies to provide relevant up to date information and referral procedures 20 young people benefiting |  |  | Youth Service, all partners |  |
| Young people aged 16-25 years Objective: Enable greater community involvement with and ownership of play and youth activities |
| K1 | Deliver Music project. | A project. Numbers of young people involved development of the Dhol drumming project | Existing. | Local | Youth Service and other agencies. |  |
| K2 | Improve the availability of funds and resources for childcare to enable young parents to attend courses and events | funds obtained for crèche provision or other appropriate childcare provision | SureStart | local | Economic Devl’t, Education, SureStart, |  |
| K3 | Identify & recruit new Chair for Youth Task Group | new Chair for Task Group in place |  | local | Task Group membership |  |
| Young people aged 16-25 years Objective: Provide more safe opportunities for young people to meet |
| L1 | Continue to provide secure transport to youth facilities | provide safe transport at least 5 times per week to youth facilities, including black young people’s sessions no. of weekly sessions increased to 2 | New | central/local | Youth Service, Community Transport | RECOMMEND AS PRIORITY |
| L2 | Extend work at N. Salford Youth Centre | increase no. of young people attending to 20 in total increased no. of sessions to 2 in total set up sports sessions for Asian young men, linking to local sports facilities | existing | central | Youth Service, Salford Foyer |  |