Crime and Disorder Reduction Local Action Plan 2001/04

Strategic Objective 3:- Graffiti and flytipping

Local target – immediate service within 24 hours.

Proposed Outcomes – improve living environment * (See Environmental Action Plan targets)

Environmental Action Plan 2001/04

Objective 4:- To improve environmental maintenance and management.

4.1.  Continue the improvements to the environmental maintenance regime.

| Provide SRB – funded hit squad | Operational since 1999 , funded to 2003 |
| --- | --- |
| Provide an environmental hit squad for the Chapel Street area | No hit squad has been funded by the City Council, however £5,000 was allocated to the Directorate to resolve fly-tipping problems in the area |
| Commence the use of the two mini-sweepers | One SRB-funded mini-sweepers is used exclusively in this area and is supplemented by the normal street sweeping service. |
| Hold community clean up days | 17 Community clean up events have been held since 1st April 2002 |
| Collection of large bulky items | 238 Free removal of bulky items requests have been dealt with since 1st April 2002 |
| Graffiti removal service | 85 Incidents of graffiti removal have been dealt with since 1st April 2002. Consideration is being given to providing additional service paid for from Community Committee budget |
| Programme of spraying weeds in rear alleys | Funding is not currently designated purely for rear alley spraying. However, the Directorate will deal with specific problems as they arise. |
| Monitor new environmental systems and levels of service | Environmental surveys carried out by Encams (formerly Tidy Britain Group) have shown City-wide improvements in street cleanliness levels. |

  - Improve education and communication on environmental maintenance

| Public action taken with regular reports from the Environmental Services to the Environment Task Group | Environmental Co-ordinators from the Directorate, regularly attend Environmental Task Group meetings and provided reports when requested to. |
| --- | --- |

  - Tackle refuse and litter problems

| Develop the Tidy Business Standards Campaign within the Chapel Street Area | Some success within 2 businesses achieving the standard but overall poor response. There is an intention to introduce the scheme City-wide |
| --- | --- |
| Increase the number of litter bins in open spaces | An additional 14 litter bins have been sited in the area |
| Work with McDonalds to tackle take away litter. | McDonalds have taken responsibility for cleaning around their restaurant and a significant improvement has occurred |
| Tackle problems of litter in Cambridge Industrial Estate | Currently levels of cleansing appear to be dealing with street litter removal needs |

  - Introduce the Green Directory, enabling local communities to make decisions on the specification and frequency of maintenance of open spaces.

| Implementation of the Green Directory (a list of open spaces maintained by the City Council, along with the specification and frequency of their maintenance) | Although all Community Committees have received presentations from the Directorate on the Green Directory, there has been little feedback. A further meeting is to be held with Area Co-ordinators in January 2003. |
| --- | --- |

  - Tackle dog-related problems

| Introduce a dog warden service | The service has been contracted out and is now provided by Leigh Cats and Dogs Home |
| --- | --- |
| Consider other ways to tackle dogs and open spaces | The Dogs (Fouling of Land)Act 1996 has now been introduced which allows on the spot fines against dog owners who do not clean up dog faeces |

  - Develop improved mechanisms for tackling fly-tipping

| Continue the service to dispose of large bulky items for residents | Since April 2002, 201 requests have been dealt with and community clean up events have been carried out. |
| --- | --- |

  - Monitor noise, air and land pollution within Broughton and Blackfriars

| Monitoring report by March 2002 | Due to the constraints of the need for external validations of monitoring results acquired, the report for the year 2002 (Jan-Dec) cannot be provided until June 2003. The Directorate is currently undertaking discussions with the external validators to speed up the process. |
| --- | --- |