APPENDIX 4

CAPITAL RECEIPTS 2002/2003

ESTIMATED TIMESCALES FOR RECEIPTS IN EXCESS OF £100,000

| Disposal | Estimate | Planning/ Marketing | Negotiation | Approval | Legal | Completion | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Council House Right-to-Buy. | £6,000,000 |  |  |  |  | £500,000 per calendar month. | Progressing satisfactorily. |
| Alpine Soft Drinks | £200,000 |  | February – June 2002. | July 2002 | July- October 2002. | End of March 2003. | Terms now agreed for the disposal. Subject to the purchaser obtaining NWDA grant. |
| Chasely Fields | £250,000 | March – October 2002 |  | November 2002 | December 2002 | Completion slipped to 2003/04 | Offers and proposals currently being appraised. |
| Clifton House Farm | £163,000 |  | February – April 2002 | July2002 | July2002 | End of March 2003 | Progressing satisfactorily. |
| Greenwood School | £1,000,000 |  |  |  |  | Completion slipped to 2003/04 | Lead Member has approved the submission of an outline planning application. |
| Lancashire Mining Museum | £250,000 | February – March 2002 | May – October 2002 | November 2002 | December 2002 | Completion slipped to 2003/04 | Offers and proposals currently being appraised. |
| Quays Campus | £1,600,000 |  |  |  |  | Completed 21st March 2003 |  |
| Swinton Sauna Site | £200,000 | September-October 2002 |  | November 2002 | December 2002 | Completion slipped to 2003/04 | Offers and proposals currently being appraised |
| Trafford Road (Option) | £274,000 |  |  |  |  | Completed 22nd July 2002 |  |
| The Anchorage. | £2,400,000 |  |  |  | November 2002 | Completed 25th March 2003 |  |
| Education Offices Chapel Street | £500,000 |  |  |  | November 2002 | Completion slipped to 2003/04 | With Corporate Services for completion. |