## Savings Proposals 20012002
Ref | Description | Progress |  |  |  |  | £000
|  | Fully | Ahead of | On Target | Behind | Achieved | Not Yet | Total | Comments
|  | Implented | Schedule |  | Schedule |  | Achieved
ARTS & LEISURE
2000-2001
| Achieved |  |  |  |  | 600 | 0 | 600
AL10 | Review of Library Strategy |  |  |  |  | 27 | 27 | 54 | Balance under review
| Total 2000-2001 |  |  |  |  | 627 | 27 | 654
2001-2002
| Achieved |  |  |  |  | 41 | 0 | 41
| Total 2001-2002 |  |  |  |  | 41 | 0 | 41
| ARTS AND LEISURE TOTAL |  |  |  |  | 668 | 27 | 695
EDUCATION ( Non - Schools )
2000-2001
| Achieved |  |  |  |  | 660 | 0 | 660
ED2 | Reduce /release admin buildings |  |  |  |  | 0 | 240 | 240 | Delay in signing leases and move to Amec. £80,000 may not be achieved
| Total 2000-2001 |  |  |  |  | 660 | 240 | 900
2001-2002
| Achieved |  |  |  |  | 314 | 0 | 314
EDSO1 | SETAS - Consolidation into Job Shop Plus |  |  |  |  | 0 | 30 | 30 | Implementation July 2001- balance of saving to be met by EDSO1a.
| Total 2001-2002 |  |  |  |  | 314 | 30 | 344
| EDUCATION ( Non Schools ) TOTAL |  |  |  |  | 974 | 270 | 1244
CHIEF EXECUTIVE
2000-2001
| Achieved |  |  |  |  | 100 | 0 | 100
| Total 2000-2001 |  |  |  |  | 100 | 0 | 100
2001-2002
| Achieved |  |  |  |  | 51 | 0 | 51
| Total 2001-2002 |  |  |  |  | 51 | 0 | 51
| CHIEF EXECUTIVES TOTAL |  |  |  |  | 151 | 0 | 151
ENVIRONMENTAL SERVICES
2001-2002
| Achieved |  |  |  |  | 251 | 0 | 251
ES3 | Parks & Countryside |  |  |  |  | 14 | 17 | 31 | £14k ver accepted.Balance subject to detailed report.
ES5 | Dog Warden Service - tender |  |  |  |  | 0 | 5 | 5 | Alternative proposal to be identified
| ENVIRONMENTAL & CONSUMER SERVICES TOTAL |  |  |  |  | 265 | 22 | 287
COMMUNITY AND SOCIAL SERVICES
2000-2001
| Achieved |  |  |  |  | 1621 | 0 | 1621
| Total 2000-2001 |  |  |  |  | 1621 | 0 | 1621
2001-2002
| Achieved |  |  |  |  | 388 | 0 | 388
| Total 2001-2002 |  |  |  |  | 388 | 0 | 388
| COMMUNITY AND SOCIAL SERVICES TOTAL |  |  |  |  | 2009 | 0 | 2009
DEVELOPMENT SERVICES
2000-2001
| Achieved |  |  |  |  | 215 | 0 | 215
DE9 | Property Review |  |  |  |  | 0 | 50 | 50
DE10 | Vacate offices at The Parade, Swinton |  |  |  |  | 0 | 50 | 50
| Total 2000-2001 |  |  |  |  | 215 | 100 | 315
2001/2002
| Achieved |  |  |  |  | 195 | 0 | 195
DE5 | Rationalise Office Accommodation |  |  |  |  | 0 | 100 | 100 | Report requested
| Total 2001-2002 |  |  |  |  | 195 | 100 | 295
| DEVELOPMENT SERVICES TOTAL |  |  |  |  | 410 | 200 | 610
PERSONNEL
2000-2001
| Achieved |  |  |  |  | 1000 | 0 | 1000
| Total 2000-2001 |  |  |  |  | 1000 | 0 | 1000
2001/2002
| Achieved |  |  |  |  | 37 | 0 | 37
| Total 2001-2002 |  |  |  |  | 37 | 0 | 37
| PERSONNEL TOTAL |  |  |  |  | 1037 | 0 | 1037
CORPORATE SERVICES
2000-2001
| Achieved |  |  |  |  | 131 | 0 | 131
CS1 | Centralisation of financial support services |  |  |  |  | 482 | 218 | 700 | Savings on target,subject to finalisation of income from SLAs to HRA,
DSOs and schools.
CS2 | Energy Conservation |  |  |  |  | 340 | 60 | 400 | Savings are continuing to be identified.
CS3 | Improvement to Customer services |  |  |  |  | 430 | 450 | 880 | Compensating savings for the delays in changes to cash collection and
the introduction of the benefit verification framework have been identified.
| Total 2000-2001 |  |  |  |  | 1383 | 728 | 2111
2001/2002
| Achieved |  |  |  |  | 35 | 0 | 35
CS1 (IT) | Move to single node operation for mainframe |  |  |  |  | 0 | 65 | 65 | IT in negotiations to reduce costs
CS3 | Increase the level of casual vacancies and
| reduce supplies and other discretionary expenditure |  |  |  |  | 0 | 123 | 123 | To be managed as vacancies arise
CS4 | Accelerate savings from
| a) Customer services - £50,000 |  |  |  |  | 0 | 50 | 50 | Action plan in place to achieve target
| b) Energy conservation - £100,000 |  |  |  |  | 0 | 100 | 100 | Action plan in place to achieve target
| c) Financial support services - £100,000 |  |  |  |  | 0 | 100 | 100 | See comments CS1 2000/01 saving
| Total 2001-2002 |  |  |  |  | 35 | 438 | 473
| CORPORATE SERVICES TOTAL |  |  |  |  | 1418 | 1166 | 2584
HOUSING
2000-2001
| Achieved |  |  |  |  | 84 | 0 | 84
| HOUSING TOTAL |  |  |  |  | 84 | 0 | 84
SERVICE WIDE
2001/2002
SW1 | Review of services to the community |  |  |  |  | 0 | 43 | 43
SW2 | Income - new/increased charges/advertising
| cost saving |  |  |  |  | 150 | 150 | 300 | £150k shortfall likely from increasing existing fees and charges - to be
met proportionately by each directorate.
| SERVICE WIDE TOTAL |  |  |  |  | 150 | 193 | 343
CONTINGENCY / FINANANCING ADJUSTMENTS
2001/2002
| Achieved |  |  |  |  | 3500 | 0 | 3500
GC3 | Debt Rescheduling |  |  |  |  | 940 | 60 | 1000 | £940k already achieved
GC4 | Buy-out mainframe open hire agreement |  |  |  |  | 870 | 0 | 870 | Can be achieved by bringing forward final payment due in 2002/03 into
2001/02.
| CONTINGENCY / FINANANCING TOTAL |  |  |  |  | 5310 | 60 | 5370
| CUMULATIVE TOTAL |  |  |  |  | 12476 | 1938 | 14414
cksavingsmonitoring29/08/01

## Savings Summary 20012002
Appendix 1
REVENUE ESTIMATES 2001/2002
SAVINGS SUMMARY
DIRECTORATE | ACHIEVED | NOT ACHIEVED | TOTAL | ACHIEVED | NOT ACHIEVED | TOTAL | GRAND
| 2000-2001 | 2000-2001 | 2000-2001 | 2001-2002 | 2001-2002 | 2001-2002 | TOTAL
| £000 | £000 | £000 | £000 | £000 | £000 | £000
ARTS AND LEISURE | 627 | 27 | 654 | 41 | 0 | 41 | 695
EDUCATION | 660 | 240 | 900 | 314 | 30 | 344 | 1244
CHIEF EXECUTIVE | 100 | 0 | 100 | 51 | 0 | 51 | 151
ENVIRONMENTAL AND CONSUMER | 0 | 0 | 0 | 265 | 22 | 287 | 287
COMMUNITY AND SOCIAL SERVICES | 1621 | 0 | 1621 | 388 | 0 | 388 | 2009
DEVELOPMENT SERVICES | 215 | 100 | 315 | 195 | 100 | 295 | 610
PERSONNEL | 1000 | 0 | 1000 | 37 | 0 | 37 | 1037
CORPORATE SERVICES | 1383 | 728 | 2111 | 35 | 438 | 473 | 2584
HOUSING | 84 | 0 | 84 | 0 | 0 | 0 | 84
SERVICE WIDE | 0 | 0 | 0 | 150 | 193 | 343 | 343
CONTINGENCY / FINANCING | 0 | 0 | 0 | 5310 | 60 | 5370 | 5370
TOTAL | 5690 | 1095 | 6785 | 6786 | 843 | 7629 | 14414
[5 empty] | TOTAL ACHIEVED |  | 12476
[5 empty] | TOTAL NOT ACHIEVED |  | 1938
. |  |  |  |  | GRAND TOTAL |  | 14414
cksavingsmonitoring21/08/01