## Appendix 2a
SUMMARY OF 2003/04 APPROVED PROGRAMME
|  |  | Planning Level |  |  |  | Resource Level
COMMITTEE | Planning Level 04/06/03 | 2002/03 Provisional Outturn Adj's | 2003/04 Monitoring Adj's | Revised Planning Level | Funded Schemes 04/06/03 | 2002/03 Provisional Outturn Adj's | 2003/04 Monitoring Adj's | Revised Funded Schemes | Expenditure | Control Check
| £m | £m | £m | £m | £m | £m | £m | £m | £m
HOUSING | 37.118 | 2.279 | 0 | 39.397 | 37.118 | 2.279 | 0 | 39.397 | 4.229 | #REF!
EDUCATION | 11.04 | 2.086 | 0 | 13.126 | 11.04 | 2.086 | 0 | 13.126 | 2.041 | #REF!
HIGHWAYS | 20.049 | 1.314 | 0 | 21.363 | 20.049 | 1.314 | 0 | 21.363 | 0.34 | #REF!
SOCIAL SERVICES | 0.732 | 0.148 | 0 | 0.88 | 0.732 | 0.148 | 0 | 0.88 | 0.155 | #REF!
Sub-Total | 68.939 | 5.827 | 0 | 74.766 | 68.939 | 5.827 | 0 | 74.766 | 6.765 | #REF!
OTHER SERVICES BLOCK
ARTS & LEISURE | 2.006 | 0.053 | -0.078 | 1.981 | 2.006 | 0.053 | -0.078 | 1.981 | 0.92 | #REF!
DEVELOPMENT SERVICES | 0.345 | 1.21 | 0.071 | 1.626 | 0.345 | 1.21 | 0.071 | 1.626 | 0.148 | #REF!
|  |  | . |  |  |  | .
POLICY | 4.067 | 0.667 | 0 | 4.734 | 4.067 | 0.667 | 0 | 4.734 | 0.826 | #REF!
ENVIRONENTAL & CONSUMER SERVICES | 0.2 | 0.027 | 0 | 0.227 | 0.2 | 0.027 | 0 | 0.227 | 0.008
CHIEF EXECUTIVE | 2.397 | -0.075 | 0 | 2.322 | 2.397 | -0.075 | 0 | 2.322 | 0.177
Sub-Total (Other Services Block) | 9.015 | 1.882 | -0.007 | 10.89 | 9.015 | 1.882 | -0.007 | 10.89 | 2.079 | #REF!
TOTAL - CAPITAL PROGRAMME | 77.954 | 7.709 | -0.007 | 85.656 | 77.954 | 7.709 | -0.007 | 85.656 | 8.844 | #REF!

## Appendix 2b
Contract
| 2003/04 Estimate | Start | Finish | A | M | J | Est to Date | Actual to Date | Diff. | J | A | S | O | N | D | J | F | M | Total
| £m |  |  | £m | £m | £m | [12 empty] | £m | bar: J to M
HOUSING
Private Sector
Disabled Facilities Grants | 1 |  |  |  | 0.015 | 0.035 | 0.05 | 0.049 | 0.001 | 0.05 | 0.05 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.15 | 0.2 | 1
Houses in Multiple Occupation | 0.222 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.03 | 0.03 | 0.102 | 0.222
Citywide | 0.25 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.03 | 0.03 | 0.13 | 0.25
Home Improvement Agency | 0.5 |  |  |  | 0.015 | 0.025 | 0.04 | 0.015 | 0.025 | 0.025 | 0.025 | 0.04 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.12 | 0.5
Special Needs (Repairs Associated with DFG's) | 0.25 |  |  |  | 0.005 | 0.01 | 0.015 | 0.004 | 0.011 | 0.01 | 0.01 | 0.01 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.08 | 0.25
Local Authority SHG-Pendleway | 0.304 | [5 empty] | 0 | 0 | Diff.: 0; N: 0.304 | 0.304
Local Authority SHG-King Edward St | 0.565 | [5 empty] | 0 | 0 | Diff.: 0; S: 0.565 | 0.565
Local Authority SHG-2003/4new start | 0.131 | [5 empty] | 0 | 0 | Diff.: 0; M: 0.131 | 0.131
Broughton Inpartnership | 3.3 |  |  |  | 0.044 | 0.05 | 0.094 | 0.064 | 0.03 | 0.1 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.4 | 0.5 | 0.806 | 3.3
Broughton Grants(from 2/3) | 0.027 |  |  |  | 0.01 | 0 | 0.01 | 0.016 | Diff.: -0.006; A: 0.017 | 0.027
Broughton Capital Works | 0 | [5 empty] | 0 | 0 | Diff.: 0 | 0
Broughton Grants (Owner-occ's) | 0 | [5 empty] | 0 | 0 | Diff.: 0 | 0
Broughton Grants (Empty prop's) | 0 | [5 empty] | 0 | 0 | Diff.: 0 | 0
Broughton (Gt Clowes St Block Treatment Ph 2) | 0 | [5 empty] | 0 | 0 | Diff.: 0 | 0
Claremont & Weaste | 1.55 |  |  |  | 0.022 | 0.01 | 0.032 | 0.025 | 0.007 | 0.01 | 0.01 | 0.01 | 0.01 | 0.1 | 0.2 | 0.3 | 0.4 | 0.478 | 1.55
Charlestown & Kersal NDC - Grants | 0.029 |  |  |  | 0.013 |  | 0.013 | 0.017 | Diff.: -0.004; A: 0.016 | 0.029
Charlestown & Kersal NDC - Norfolk St | 0.066 |  |  |  | 0.047 | 0.019 | 0.066 | 0.048 | Diff.: 0.018 | 0.066
Charlestown & Kersal NDC - major scheme preparation | 1.655 | [5 empty] | 0 | 0 | 0 | 0.005 | 0.005 | 0.005 | 0.005 | 0.005 | 0.01 | 0.01 | 0.01 | 1.6 | 1.655
Advance Fees | 0.1 |  |  |  |  | 0.005 | 0.005 | 0.004 | 0.001 | 0.005 | 0.005 | 0.005 | 0.005 | 0.005 | 0.01 | 0.01 | 0.025 | 0.025 | 0.1
RBI Individual Grants | 0.5 |  |  |  |  | 0.02 | 0.02 | 0 | 0.02 | 0.02 | 0.02 | 0.02 | 0.04 | 0.04 | 0.04 | 0.06 | 0.1 | 0.14 | 0.5
Claremont/Weaste Grants (from 2/3) | 0.026 |  |  |  | 0.008 | 0.008 | 0.016 | 0.015 | Diff.: 0.001; J: 0.01 | 0.026
Eccles SDA - Grants | 0.101 |  |  |  | 0.001 | 0.009 | 0.01 | 0.001 | 0.009 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.011 | 0.101
Slippage from 2002/03 | 0.172 |  |  | 0.172 |  |  | 0.172 | 0.009 | Diff.: 0.163 | 0.172
| 10.748 |  |  | 0.172 | 0.18 | 0.191 | 0.543 | 0.267 | 0.276 | 0.265 | 0.388 | 1.085 | 0.565 | 0.959 | 0.765 | 1.025 | 1.33 | 3.823 | 10.748
Seedley & Langworthy
Acquisitions (04/05 Onwards Incl Homeswaps) | 1.3 |  |  |  | 0.15 | 0.1 | 0.25 | 0.215 | 0.035 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.25 | 1.3
DS Homeswaps in LN | 0.379 |  |  |  | 0.062 | 0.06 | 0.122 | 0.122 | 0 | 0.06 | 0.06 | 0.06 | 0.06 |  |  |  |  | 0.017 | 0.379
DS Phase 3 Homeswaps | 0 | [5 empty] | 0 | 0 | Diff.: 0 | 0
DS Seedley West Homeswaps | 0 | [5 empty] | 0 | 0 | Diff.: 0 | 0
Homeswaps | 0.45 |  |  |  | 0.042 |  | 0.042 | 0.078 | -0.036 | 0.002 | 0.03 | 0.04 | 0.04 | 0.04 | 0.06 | 0.06 | 0.06 | 0.076 | 0.45
Demolitions | 0.2 |  |  |  | 0.05 | 0.01 | 0.06 | 0.061 | -0.001 | 0.01 | 0.01 | 0.01 | 0.01 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.2
Environmental Works | 0.2 |  |  |  |  | 0.01 | 0.01 | 0.009 | 0.001 |  |  |  |  | 0.02 | 0.04 | 0.04 | 0.04 | 0.05 | 0.2
Shop Renovations Phase 1 | 0.95 |  |  |  | 0.002 |  | 0.002 | 0.017 | -0.015 | 0.028 | 0.03 | 0.05 | 0.07 | 0.1 | 0.1 | 0.12 | 0.2 | 0.25 | 0.95
Shop Renovations Phase 2 | 0 | [5 empty] | 0 | 0 | Diff.: 0 | 0
Buille Hill Area Group Scheme | 0.4 | [5 empty] | 0 | 0 | Diff.: 0; D: 0.03; J: 0.07; F: 0.1; M: 0.2 | 0.4
Langworthy North Phase 3 | 1.4 |  |  |  | 0.077 | 0.15 | 0.227 | 0.148 | 0.079 | 0.15 | 0.2 | 0.2 | 0.15 | 0.15 | 0.15 | 0.15 |  | 0.023 | 1.4
Langworthy North Retention | 0.052 |  |  |  | 0.003 |  | 0.003 | 0.003 | Diff.: 0; A: 0.049 | 0.052
Langworthy North Phase 4 | 0.791 |  |  |  |  | 0.011 | 0.011 | 0 | 0.011 | 0.02 | 0.05 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.11 | 0.791
Individual Improvement | 0.25 | [5 empty] | 0 | 0 | 0 |  |  |  |  | 0.02 | 0.03 | 0.05 | 0.05 | 0.1 | 0.25
West of Seedley Park Road | 0.3 | [5 empty] | 0 | 0 | 0 |  |  |  |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.1 | 0.3
Seedley West Remodelling | 0.598 | [5 empty] | 0 | 0 | 0 |  |  | 0.048 | 0.08 | 0.08 | 0.09 | 0.1 | 0.1 | 0.1 | 0.598
Seedley South Remodelling | 0.03 | [5 empty] | 0 | 0 | Diff.: 0; M: 0.03 | 0.03
Marketing / Developing Gap Funding | 0.1 | [5 empty] | 0 | 0 | Diff.: 0; M: 0.1 | 0.1
| 7.4 |  |  | 0 | 0.386 | 0.341 | 0.727 | 0.653 | 0.074 | 0.37 | 0.529 | 0.608 | 0.61 | 0.68 | 0.77 | 0.86 | 0.82 | 1.426 | 7.4
Total Private Sector | 18.148 |  |  | 0.172 | 0.566 | 0.532 | 1.27 | 0.92 | 0.35 | 0.635 | 0.917 | 1.693 | 1.175 | 1.639 | 1.535 | 1.885 | 2.15 | 5.249 | 18.148
Public Sector
MRA Funded
Support of SRB 2 | 3.157 |  |  |  | 0.181 | 0.25 | 0.431 | 0.353 | 0.078 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.3 | 0.3 | 0.626 | 3.157
Support of SRB 3 | 0 | [5 empty] | 0 | 0.045 | Diff.: -0.045 | 0
Retentions | 1.253 |  |  |  | 0.2 | 0.1 | 0.3 | 0.3 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.153 | 1.253
2002/03 Commitments | 2.091 |  |  |  | 0.491 | 0.2 | 0.691 | 0.691 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  |  | 2.091
Public Sector Residents - Specific Adaptations | 1 |  |  |  | 0.115 | 0.06 | 0.175 | 0.221 | -0.046 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.1 | 0.1 | 0.1 | 0.225 | 1
Programmed Works | 5.001 |  |  |  | 0.684 | 0.3 | 0.984 | 0.984 | 0 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.717 | 1.2 | 5.001
Demolitions | 1 |  |  |  |  | 0.05 | 0.05 | 0.095 | -0.045 | 0.05 | 0.05 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.15 | 0.2 | 1
Burglary Reduction | 0.5 |  |  |  |  | 0.05 | 0.05 | 0 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.5
New Deal for Communities | 3.508 |  |  |  | 0.005 | 0.05 | 0.055 | 0.005 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.2 | 0.2 | 0.5 | 0.75 | 1.603 | 3.508
Fees - Future Programme Preparation | 0.15 | [5 empty] | 0 | 0 | 0 | 0.015 | 0.015 | 0.015 | 0.015 | 0.015 | 0.015 | 0.015 | 0.015 | 0.03 | 0.15
Environmental Improvements | 1.25 |  |  |  | 0.1 | 0.1 | 0.2 | 0.2 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.25 | 1.25
Slippage from 2002/03 | 2.107 |  |  | 2.107 |  |  | 2.107 | 0.415 | Diff.: 1.692 | 2.107
ALMO Funded
Decent Homes | 0.232 | [5 empty] | 0 | 0 | Diff.: 0; F: 0.1; M: 0.132 | 0.232
Total Public Sector | 21.249 |  |  | 2.107 | 1.776 | 1.16 | 5.043 | 3.309 | 1.734 | 1.175 | 1.175 | 1.225 | 1.225 | 1.375 | 1.415 | 1.765 | 2.382 | 4.469 | 21.249
HOUSING TOTAL | 39.397 |  |  | 2.279 | 2.342 | 1.692 | 6.313 | 4.229 | 2.084 | 1.81 | 2.092 | 2.918 | 2.4 | 3.014 | 2.95 | 3.65 | 4.532 | 9.718 | 39.397
EDUCATION
Commitments
New Deal fpr Schools 4 | 0.12 |  |  | 0.12 |  |  | 0.12 | 0.043 | Diff.: 0.077 | 0.12
New Deal Condition / Modernisation | 4.713 |  |  |  | 0.039 | 0.384 | 0.423 | 0.041 | 0.382 | 0.66 | 0.66 | 0.659 | 0.384 | 0.384 | 0.384 | 0.384 | 0.384 | 0.391 | 4.713
Devolved Capital Formula | 2.268 |  |  |  | 0.094 | 0.216 | 0.31 | 0.188 | 0.122 | 0.216 | 0.216 | 0.216 | 0.216 | 0.216 | 0.216 | 0.216 | 0.216 | 0.23 | 2.268
Seed Challenge | 0.294 |  |  |  | 0.027 | 0.026 | 0.053 | 0.042 | 0.011 | 0.026 | 0.026 | 0.026 | 0.026 | 0.026 | 0.026 | 0.026 | 0.026 | 0.033 | 0.294
The Albion | 2.864 |  |  | 0.6 | 0.6 | 0.6 | 1.8 | 1.609 | Diff.: 0.191; J: 0.6; A: 0.278; M: 0.186 | 2.864
Schools Access Initiative | 0.346 |  |  |  | 0.005 | 0.036 | 0.041 | 0.005 | 0.036 | 0.034 | 0.034 | 0.034 | 0.034 | 0.034 | 0.034 | 0.034 | 0.034 | 0.033 | 0.346
Capitalised Salaries | 0.087 |  |  | 0.007 | 0.007 | 0.007 | 0.021 | 0.014 | 0.007 | 0.007 | 0.007 | 0.007 | 0.007 | 0.007 | 0.007 | 0.007 | 0.007 | 0.01 | 0.087
Beacon Resource Centre | 1.461 |  |  |  |  | 0.139 | 0.139 | 0 | 0.139 | 0.223 | 0.089 | 0.185 | 0.15 | 0.11 | 0.13 | 0.225 | 0.155 | 0.055 | 1.461
PFI Consultancy | 0.083 |  |  | 0.083 |  |  | 0.083 | 0.092 | Diff.: -0.009 | 0.083
Springwood | 0.071 |  |  | 0.071 |  |  | 0.071 | 0 | Diff.: 0.071 | 0.071
Proposals
Wentworth High School | 0.037 |  |  |  | 0.001 | 0.004 | 0.005 | 0.001 | 0.004 | 0.005 | 0.005 | 0.005 | 0.005 | 0.005 | 0.007 |  |  |  | 0.037
ACG Minor Works | 0.131 |  |  |  |  | 0.006 | 0.006 | 0.006 | 0 | 0.014 | 0.014 | 0.014 | 0.014 | 0.014 | 0.014 | 0.014 | 0.014 | 0.013 | 0.131
Staff Workspaces | 0.124 |  |  |  |  | 0.012 | 0.012 | 0 | 0.012 | 0.012 | 0.012 | 0.012 | 0.012 | 0.012 | 0.012 | 0.012 | 0.012 | 0.016 | 0.124
Nursery's In Disadvantaged Ares | 0.373 |  |  |  |  | 0.037 | 0.037 | 0 | 0.037 | 0.037 | 0.037 | 0.037 | 0.037 | 0.037 | 0.037 | 0.037 | 0.037 | 0.04 | 0.373
Review Surplus Places (Expansion Popular Schools) | 0.154 |  |  |  |  | 0.015 | 0.015 | 0 | 0.015 | 0.015 | 0.015 | 0.015 | 0.015 | 0.015 | 0.015 | 0.015 | 0.015 | 0.019 | 0.154
EDUCATION - TOTAL | 13.126 |  |  | 0.881 | 0.773 | 1.482 | 3.136 | 2.041 | 1.095 | 1.849 | 1.393 | 1.21 | 0.9 | 0.86 | 0.882 | 0.97 | 0.9 | 1.026 | 13.126
HIGHWAYS
Proposals
Cadishead Way Stage 1 | 0.075 |  |  |  |  | 0.075 | 0.075 | 0 | Diff.: 0.075 | 0.075
Cadishead Way | 9.05 |  |  |  | 0.058 | 0.9 | 0.958 | 0.129 | 0.829 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.892 | 9.05
Local Safety schemes | 0.718 |  |  |  |  | 0.072 | 0.072 | 0.01 | 0.062 | 0.072 | 0.072 | 0.072 | 0.072 | 0.072 | 0.072 | 0.072 | 0.072 | 0.07 | 0.718
Bridge Assessment and Strengthening Schemes | 0.661 |  |  |  | 0.005 | 0.066 | 0.071 | 0.014 | 0.057 | 0.066 | 0.066 | 0.066 | 0.066 | 0.066 | 0.066 | 0.066 | 0.066 | 0.062 | 0.661
Principal Roads Structural Maintenance | 1.79 |  |  |  | 0.02 | 0.177 | 0.197 | 0.088 | 0.109 | 0.177 | 0.177 | 0.177 | 0.177 | 0.177 | 0.177 | 0.177 | 0.177 | 0.177 | 1.79
Public Transport Schemes | 0.465 |  |  |  |  | 0.047 | 0.047 | 0.001 | 0.046 | 0.047 | 0.047 | 0.047 | 0.047 | 0.047 | 0.047 | 0.047 | 0.047 | 0.042 | 0.465
Schemes to Assist Cycling | 0.1 |  |  |  |  | 0.01 | 0.01 | 0 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.1
Other Minor Schemes | 0.344 |  |  |  | 0.02 | 0.031 | 0.051 | 0.039 | 0.012 | 0.031 | 0.031 | 0.031 | 0.031 | 0.031 | 0.031 | 0.031 | 0.031 | 0.045 | 0.344
Commitments
Manchester / Salford Inner relief Road | 8.16 |  |  |  | 0.055 | 0.68 | 0.735 | 0.059 | 0.676 | 0.824 | 0.824 | 0.824 | 0.824 | 0.824 | 0.824 | 0.824 | 0.824 | 0.833 | 8.16
HIGHWAYS - TOTAL | 21.363 |  |  | 0 | 0.158 | 2.058 | 2.216 | 0.34 | 1.876 | 2.127 | 2.127 | 2.127 | 2.127 | 2.127 | 2.127 | 2.127 | 2.127 | 2.131 | 21.363
SOCIAL SERVICES
Proposals
Modernising ICT Infrastructure | 0.22 |  |  | 0.013 | 0.013 | 0.013 | 0.039 | 0.033 | 0.006 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.021 | 0.22
Mental Health SCA 2002 / 2005 | 0.185 |  |  |  | 0.079 | 0.016 | 0.095 | 0.021 | Diff.: 0.074; M: 0.09 | 0.185
Children's Homes - Safety Issues | 0.075 | [5 empty] | 0 | 0 | Diff.: 0; J: 0.025; A: 0.025; S: 0.025 | 0.075
Replacement Lift at The Limes | 0.02 | [5 empty] | 0 | 0 | Diff.: 0; M: 0.02 | 0.02
Brierley House DC - Re-model Toilet/Bathroom Area | 0.037 | [5 empty] | 0 | 0 | Diff.: 0; M: 0.037 | 0.037
Alexandra House DC - Re-model Toilet/Bathroom Area | 0.047 | [5 empty] | 0 | 0 | Diff.: 0; M: 0.047 | 0.047
Craig Hall DC Re-roofing | 0.056 | [5 empty] | 0 | 0 | 0 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.008 | 0.056
Waterside Resource Centre Partial Re-roofing | 0.035 | [5 empty] | 0 | 0 | 0 | 0.004 | 0.004 | 0.004 | 0.004 | 0.004 | 0.004 | 0.004 | 0.004 | 0.003 | 0.035
Cleveland House - Dry Lining of Basement | 0.025 | [5 empty] | 0 | 0 | Diff.: 0; J: 0.013; A: 0.012 | 0.025
West Dene Partial Re-roofing | 0.008 | [5 empty] | 0 | 0 | Diff.: 0; A: 0.004; S: 0.004 | 0.008
Boothstown / Worsley Community Centres Refurbishment | 0.04 | [5 empty] | 0 | 0 | 0 |  |  |  | 0.007 | 0.007 | 0.007 | 0.007 | 0.007 | 0.005 | 0.04
I.T. for Looked After Children | 0.053 | [5 empty] | 0 | 0 | 0 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.005 | 0.053
White Moss House - extension | 0.005 |  |  | 0.005 |  |  | 0.005 | 0 | Diff.: 0.005 | 0.005
White Moss House - IT Equipment | 0.012 |  |  | 0.012 |  |  | 0.012 | 0 | Diff.: 0.012 | 0.012
Sahal Court | 0.004 |  |  | 0.004 |  |  | 0.004 | 0.016 | Diff.: -0.012 | 0.004
The Withies | 0.038 |  |  | 0.038 |  |  | 0.038 | 0.072 | Diff.: -0.034 | 0.038
Brynheys | 0.02 |  |  | 0.02 |  |  | 0.02 | 0.013 | Diff.: 0.007 | 0.02
SOCIAL SERVICES -TOTAL | 0.88 |  |  | 0.092 | 0.092 | 0.029 | 0.213 | 0.155 | 0.058 | 0.074 | 0.077 | 0.065 | 0.043 | 0.043 | 0.043 | 0.043 | 0.043 | 0.236 | 0.88
ENVIRONMENTAL SERVICES
Proposals
Headstones and Roadway Works - Cemeteries | 0.105 |  |  |  |  | 0.01 | 0.01 | 0 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.015 | 0.105
Buille Hill Park Restoration | 0.1 |  |  |  |  | 0.01 | 0.01 | 0 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.1
DEFRA Waste Minimisation | 0.016 |  |  | 0.016 |  |  | 0.016 | 0 | Diff.: 0.016 | 0.016
Outdoor Services - Plant Acquisition | 0.003 |  |  | 0.003 |  |  | 0.003 | 0 | Diff.: 0.003 | 0.003
Fuel Island | 0.003 |  |  | 0.003 |  |  | 0.003 | 0.008 | Diff.: -0.005 | 0.003
ENVIRONMENTAL SERVICES TOTAL | 0.227 |  |  | 0.022 | 0 | 0.02 | 0.042 | 0.008 | 0.034 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.025 | 0.227
CHIEF EXECUTIVE
Business Security Grants | 0.007 |  |  | 0.007 |  |  | 0.007 | 0.001 | Diff.: 0.006 | 0.007
CCTV in New Deal Area | 0.34 |  |  |  |  | 0.032 | 0.032 | 0 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 | 0.052 | 0.34
Site Assembly / Acquisition Temp Treatment Works | 0.28 |  |  |  |  | 0.07 | 0.07 | 0 | 0.07 | 0.023 | 0.023 | 0.023 | 0.023 | 0.023 | 0.023 | 0.023 | 0.023 | 0.026 | 0.28
Gateway | 0.105 |  |  |  |  | 0.01 | 0.01 | 0 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.015 | 0.105
Highway and Community Safety | 0.141 |  |  |  |  | 0.012 | 0.012 | 0 | 0.012 | 0.012 | 0.012 | 0.012 | 0.012 | 0.012 | 0.012 | 0.012 | 0.012 | 0.033 | 0.141
Play Facilities | 0.115 |  |  |  | 0.012 | 0.011 | 0.023 | 0.012 | 0.011 | 0.011 | 0.011 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.115
Environmental / Shop Front Improvements | 0.052 |  |  |  |  | 0.005 | 0.005 | 0 | 0.005 | 0.005 | 0.005 | 0.005 | 0.005 | 0.005 | 0.005 | 0.005 | 0.005 | 0.007 | 0.052
Community Mini-Bus | 0.006 |  |  |  |  | 0.006 | 0.006 | 0 | Diff.: 0.006 | 0.006
Minor Works Fund | 0.01 |  |  |  |  | 0.01 | 0.01 | 0 | Diff.: 0.01 | 0.01
Public Transport Measures | 0.1 |  |  |  |  | 0.01 | 0.01 | 0 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.1
Reclamation of Derelict Land | 0.292 |  |  |  |  | 0.029 | 0.029 | 0 | 0.029 | 0.029 | 0.029 | 0.029 | 0.029 | 0.029 | 0.029 | 0.029 | 0.029 | 0.031 | 0.292
Youth Shelters | 0.054 |  |  |  |  | 0.005 | 0.005 | 0 | 0.005 | 0.005 | 0.005 | 0.005 | 0.005 | 0.005 | 0.005 | 0.005 | 0.005 | 0.009 | 0.054
Expanding Boundaries | 0.518 |  |  |  |  | 0.052 | 0.052 | 0.02 | 0.032 | 0.052 | 0.052 | 0.052 | 0.052 | 0.052 | 0.052 | 0.052 | 0.052 | 0.05 | 0.518
Home Office CCTV | 0.302 |  |  | 0.302 |  |  | 0.302 | 0.144 | Diff.: 0.158 | 0.302
CHIEF EXECUTIVE TOTAL | 2.322 |  |  | 0.309 | 0.012 | 0.252 | 0.573 | 0.177 | 0.396 | 0.189 | 0.189 | 0.188 | 0.188 | 0.188 | 0.188 | 0.188 | 0.188 | 0.243 | 2.322
ARTS & LEISURE
Committed
Leisure Trust / PPP | 0.106 |  |  | 0.005 | 0.005 | 0.01 | 0.02 | 0.007 | Diff.: 0.013; J: 0.02; A: 0.02; S: 0.03; O: 0.016 | 0.106
Library Service - Computerisation | 0.045 |  |  | 0.037 | 0.003 | 0.003 | 0.043 | 0.038 | Diff.: 0.005; J: 0.002 | 0.045
Peoples Network | 0.042 |  |  | 0.042 |  |  | 0.042 | 0 | Diff.: 0.042 | 0.042
SPACE for Sports and Arts
Marlborough | 0.322 |  |  | 0.079 | 0.105 | 0.11 | 0.294 | 0.246 | Diff.: 0.048; S: 0.028 | 0.322
Moorfield | 0.462 |  |  | 0.082 | 0.083 | 0.083 | 0.248 | 0.221 | Diff.: 0.027; J: 0.083; A: 0.083; N: 0.048 | 0.462
St Peter's | 0.464 |  |  | 0.064 | 0.117 | 0.117 | 0.298 | 0.249 | Diff.: 0.049; J: 0.118; O: 0.048 | 0.464
Dukesgate | 0.462 |  |  | 0.048 | 0.1 | 0.1 | 0.248 | 0.159 | Diff.: 0.089; J: 0.06; A: 0.06; S: 0.064; D: 0.03 | 0.462
Fit City Signage | 0.005 | [5 empty] | 0 | 0 | Diff.: 0; A: 0.005 | 0.005
Cleavley Playing Fields | 0.073 | [5 empty] | 0 | 0 | Diff.: 0; A: 0.016; S: 0.035; O: 0.018; N: 0.004 | 0.073
ARTS & LEISURE - TOTAL | 1.981 |  |  | 0.357 | 0.413 | 0.423 | 1.193 | 0.92 | 0.273 | 0.283 | 0.184 | 0.157 | 0.082 | 0.052 | 0.03 | 0 | 0 | 0 | 1.981
DEVELOPMENT SERVICES
Committed
Eccles Town Centre | 0.868 |  |  | 0.868 |  |  | 0.868 | 0.028 | Diff.: 0.84 | 0.868
Chapel St | 0.055 |  |  | 0.055 |  |  | 0.055 | 0.011 | Diff.: 0.044 | 0.055
Countryside Programme | 0.01 |  |  | 0.01 |  |  | 0.01 | 0 | Diff.: 0.01 | 0.01
Barton SES | 0.004 |  |  | 0.004 |  |  | 0.004 | 0.001 | Diff.: 0.003 | 0.004
Eccles Town Hall Auditorium | 0.024 |  |  | 0.024 |  |  | 0.024 | 0 | Diff.: 0.024 | 0.024
NWDA Headroom schemes | 0.161 |  |  | 0.161 |  |  | 0.161 | 0.091 | Diff.: 0.07 | 0.161
SRB 2 | 0.008 |  |  | 0.008 |  |  | 0.008 | 0.004 | Diff.: 0.004 | 0.008
Slackbrook - Security Measures / Improvements | 0.063 | [5 empty] | 0 | 0 | Diff.: 0; J: 0.007; A: 0.024; S: 0.019; O: 0.013 | 0.063
Proposals
Ordsall Neighbourhood Office Phase 2 | 0.413 |  |  |  |  | 0.067 | 0.067 | 0.004 | 0.063 | 0.067 | 0.067 | 0.067 | 0.066 | 0.079 |  |  |  |  | 0.413
LIVIA Programme Year 3 - Match Funding | 0.02 | [5 empty] | 0 | 0.009 | Diff.: -0.009; O: 0.011; N: 0.009 | 0.02
DEVELOPMENT SERVICES - TOTAL | 1.626 |  |  | 1.13 | 0 | 0.067 | 1.197 | 0.148 | 1.049 | 0.074 | 0.091 | 0.086 | 0.09 | 0.088 | 0 | 0 | 0 | 0 | 1.626
CORPORATE SERVICES
Office refurbishment/relocations | 0.682 |  |  |  |  | 0.015 | 0.015 | 0.048 | Diff.: -0.033; J: 0.182; M: 0.485 | 0.682
Capitalisation of Revenue
VER / VS | 0.5 |  |  |  | 0.012 | 0.049 | 0.061 | 0.012 | 0.049 | 0.049 | 0.049 | 0.049 | 0.049 | 0.049 | 0.049 | 0.049 | 0.049 | 0.047 | 0.5
Planned Highway Maintenance | 1.629 |  |  | 0.136 | 0.136 | 0.136 | 0.408 | 0.408 | 0 | 0.136 | 0.136 | 0.136 | 0.136 | 0.136 | 0.136 | 0.136 | 0.136 | 0.133 | 1.629
Planned Building Maintenance | 0.1 |  |  | 0.008 | 0.008 | 0.008 | 0.024 | 0.024 | 0 | 0.008 | 0.008 | 0.008 | 0.008 | 0.008 | 0.008 | 0.008 | 0.008 | 0.012 | 0.1
Major Building Maintenance | 0.3 |  |  | 0.025 | 0.025 | 0.025 | 0.075 | 0.075 | 0 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.3
Advance Fees | 0.1 |  |  | 0.008 | 0.008 | 0.008 | 0.024 | 0.028 | -0.004 | 0.008 | 0.008 | 0.008 | 0.008 | 0.008 | 0.008 | 0.008 | 0.008 | 0.012 | 0.1
Software Development | 0.5 |  |  | 0.041 | 0.041 | 0.041 | 0.123 | 0.123 | 0 | 0.041 | 0.041 | 0.041 | 0.041 | 0.041 | 0.041 | 0.041 | 0.041 | 0.049 | 0.5
Risk Management | 0.1 |  |  | 0.008 | 0.008 | 0.008 | 0.024 | 0.024 | 0 | 0.008 | 0.008 | 0.008 | 0.008 | 0.008 | 0.008 | 0.008 | 0.008 | 0.012 | 0.1
Project E-merge | 0.238 |  |  | 0.02 | 0.02 | 0.02 | 0.06 | 0.06 | 0 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.018 | 0.238
Energy Conservation | 0.1 |  |  | 0.008 | 0.008 | 0.008 | 0.024 | 0.024 | 0 | 0.008 | 0.008 | 0.008 | 0.008 | 0.008 | 0.008 | 0.008 | 0.008 | 0.012 | 0.1
Highways Depot | 0.395 | [5 empty] | 0 | 0 | Diff.: 0; F: 0.395 | 0.395
Leisure Mgt Info System | 0.09 | [5 empty] | 0 | 0 | Diff.: 0; F: 0.09 | 0.09
CORPORATE SERVICES | 4.734 |  |  | 0.254 | 0.266 | 0.318 | 0.838 | 0.826 | 0.012 | 0.485 | 0.303 | 0.303 | 0.303 | 0.303 | 0.303 | 0.303 | 0.788 | 0.805 | 4.734
TOTAL | 85.656 |  |  | 5.324 | 4.056 | 6.341 | 15.721 | 8.844 | 6.877 | 6.911 | 6.476 | 7.074 | 6.153 | 6.695 | 6.543 | 7.301 | 8.598 | 14.184 | 85.656
Nb. Exact timetable of works for Highways, Chief Executives and Education not yet determined, therefore future periods profiled on a straight line basis.

## Appendix 3
SUMMARY OF 2003/04 ESTIMATED RESOURCES AVAILABLE
Estimate at 03/03/03
|  | Internal |  | External | Estimate | 2002/03 | 2003/04 | Revised
|  | Resource | Resource | Resource | at 04/06/03 | Prov Outturn | Monitoring | Estimate
[6 empty] | Adjustments | Adjustments
|  | £m | £m | £m | £m | £m | £m | £m
CREDIT APPROVALS
BCA |  | 9.731 | #REF! |  | 9.731 |  |  | 9.731
BCA transferred to Other Authorities |  | -1.699 | #REF! |  | -1.699 | -1.174 |  | -2.873
SCA - | Highways - Inner Relief Route |  | #REF! | 0.835 | 0.835 |  |  | 0.835
| Highways - Cadishead Way |  |  | 9.05 | 9.05 |  |  | 9.05
| Education - New Deal for Schools Modernisation |  |  | 1.55 | 1.55 | 0.827 |  | 2.377
| Education - Primary Schools - Surplus Place Removal |  |  | 1.5 | 0 |  |  | 0
| Social Services - Mental Health |  |  |  | 0.21 |  |  | 0.21
CREDIT APPROVALS |  | 8.032 | #REF! | 12.935 | 19.677 | -0.347 |  | 19.33
GRANTS/CONTRIBUTIONS RECEIVABLE
Housing - Market Renewal Fund |  |  | #REF! | 9.352 | 9.352 |  |  | 9.352
Housing - SRB 5 |  |  |  | 1 | 1 |  |  | 1
Housing - Disabled Facilities Grant |  |  |  | 0.6 | 0.6 |  |  | 0.6
Education - Devolved Formula Capital |  |  |  | 2.26 | 2.26 | 0.008 |  | 2.268
Education - New Deal for Schools 4 |  |  |  |  | 0 | 0.12 |  | 0.12
Education - Seed Challenge |  |  |  | 0.29 | 0.29 | 0.004 |  | 0.294
Education - Asset Mangaement Plan Condition |  |  |  | 2.336 | 2.336 |  |  | 2.336
Education - Standards Fund |  |  |  | 0.124 | 0.124 |  |  | 0.124
Education - Sure Start |  |  |  | 0.187 | 0.187 |  |  | 0.187
Highways - TSG |  |  | #REF! | 5.586 | 6.027 | 1.298 |  | 7.325
Social Services - Management Information Grant |  |  |  | 0.151 | 0.151 | 0.069 |  | 0.22
Social Services - Quality Protects |  |  |  |  | 0.053 |  |  | 0.053
NWRDA |  |  |  | 1.366 | 1.366 | 0.358 | 0.052 | 1.776
Lottery Grant - Arts & Leisure |  |  | #REF! | 1.73 | 1.73 |  | -0.074 | 1.656
- Social Services |  |  |  |  | 0.04 |  |  | 0.04
ERDF |  |  |  | 0.905 | 0.905 |  |  | 0.905
New Deal for Communities |  |  |  | 4.377 | 4.773 | -0.377 |  | 4.396
Development Services - Sure Start |  |  |  | 0.169 | 0.169 | 0.045 |  | 0.214
DEFRA - Waste Minmisation |  |  |  |  | 0 | 0.016 |  | 0.016
Home Office - CCTV |  |  |  |  | 0 | 0.297 |  | 0.297
Neighbourhood Renewal Fund |  |  |  | 0.1 | 0.1 |  |  | 0.1
GRANTS/CONTRIBUTIONS RECEIVABLE |  |  | #REF! | 30.533 | 31.463 | 1.838 | -0.022 | 33.279
USABLE CAPITAL RECEIPTS
Estimated usable 2003/04 receipts |  | 8.338 | #REF! |  | 8.338 |  | 0.56 | 8.898
Usable Receipts Brought Forward |  |  |  |  | 0 | 4.19 |  | 4.19
USABLE CAPITAL RECEIPTS |  | 8.338 | #REF! |  | 8.338 | 4.19 | 0.56 | 13.088
OTHER RESOURCES
Housing HRA Contribution |  |  |  | 2.255 | 2.255 | 1.875 |  | 4.13
Housing Major Repairs Allowance |  |  |  | 15.946 | 15.946 |  |  | 15.946
DSO Surplus |  |  |  |  | 0 | 0.003 |  | 0.003
Insurance Claim - Ordsall Nursery |  |  |  | 0.13 | 0.13 |  |  | 0.13
GMWDA |  |  |  |  | 0 |  | 0.008 | 0.008
Biffa |  |  |  |  | 0 |  | 0.003 | 0.003
Environmental Services - Revenue Contribution |  |  |  |  | 0 |  | 0.004 | 0.004
Development Services - Revenue Contribution |  |  |  | 0.014 | 0.014 |  |  | 0.014
Social Services - Revenue Contributions |  |  |  |  | 0.131 |  |  | 0.131
OTHER RESOURCES |  |  | #REF! | 18.345 | 18.476 | 1.878 | 0.015 | 20.369
TOTAL - ESTIMATED RESOURCES |  | 16.37 | #REF! | 61.813 | 77.954 | 7.559 | 0.553 | 86.066

## Appendix 4
2003/04 ESTIMATED CAPITAL RECEIPTS
ASSET | CAPITAL |  | USABLE
| RECEIPT | Prop'n | Amount
| £000s | % | £000s
COMPLETED DISPOSALS
Housing Right-to-Buy | 2773 | 25 | 693.25
Housing Land
Land at Swinton Hall Road | 33 |  | 33
General Fund - Properties and Land
Land at Ravenscraig Road | 195 |  | 195
G-Mex Commuted Sum | 65 |  | 65
Sale Of Shares Ringway Development (Balance) | 86 | 25 | 22
TOTAL COMPLETED | 3152 |  | 1008.25
APPROVED DISPOSALS
Housing Right-to-Buy | 5227 | 25 | 1306.75
Housing Land & Property | 470 |  | 470
General Fund - Properties and Land | 6113 | 100 | 6113
TOTAL ESTIMATED DISPOSALS | 11810 |  | 7889.75
TOTAL ESTIMATED RECEIPTS | 14962 |  | 8898

## Appendix 6
Lead Member Corporate Services - 2003/04 Tender Approvals to 23rd June 2003
Scheme Details |  | Costs |  | Source of
| 2003/04 | 2004/05 | Total | Funding
Onwards
| £m | £m | £m
Education
Construction of Infill Extension Clifton Primary | 0.031 | 0 | 0.031 | Seed Challenge / Devolved Formula Capital
Arts & Leisure
Drainage and Security Works - Cleavely Playing Fields | 0.073 | 0.026 | 0.099 | Sport England / RCCO
Development Services
Cadishead Way Stage 2 - Bridge Design Check | 0.024 | 0 | 0.024 | SCA
Slackbrook Country Park - Security & Improvements to | 0.063 | 0.005 | 0.068 | NWDA / GMWDA / BIFFA
City Walk
Eccles Town Centre - Compensation to Consignia | 0.133 | 0 | 0.133 | Capital Receipts
| 0.324 | 0.031 | 0.355