| . | PART 1 (OPEN TO THE PUBLIC) | ITEM NO. 9 |
| --- | --- | --- |
| REPORT OF THE CITY TREASURER |
| TO THE BUDGET SCRUTINY COMMITTEE ON TUESDAY 30th OCTOBER 2007 |
| TITLE : CAPITAL MONITORING 2007/08 |
| RECOMMENDATION : Members are requested to review the current position regarding the 2007/08 capital programme and recommend to Cabinet that the current position continues to be monitored. |
| EXECUTIVE SUMMARY : The report provides details of the funding of the 2007/08 capital programme and expenditure to date. |
| BACKGROUND DOCUMENTS : (Available for public inspection) 1. Report to Budget Scrutiny Committee Wednesday 3rd October 2. Various working papers within the Finance Division |
| CONTACT OFFICER : Tony Thompstone 793-2685 E-mail : tony.thompstone@salford.gov.uk |
| ASSESSMENT OF RISK : Any increase in the planned programme or reduction in resources included in this report will require action to be taken to ensure the capital programme for 2007/08 remains fully funded. |
| SOURCE OF FUNDING : This report identifies the sources of funding for the 2007/08 Capital Programme. |
| LEGAL ADVICE OBTAINED : Not Applicable |
| FINANCIAL ADVICE OBTAINED : This report concerns key aspects of Council’s capital finance and has been produced by the Finance Division of Customer and Support Services. |
| WARD(S) TO WHICH REPORT RELATE(S) : ALL WARDS |
| KEY COUNCIL POLICIES : : Budget Strategy |

REPORT DETAILS

- INTRODUCTION

  - At the meeting of the Budget Scrutiny Committee on the 3rd October 2007 members were informed that the current capital programme for 2007/08 was £120.773m with capital funding amounting to £106.614m, comprising assumed internal funding of £35.428m and estimated external funding of £71.186m, giving a shortfall in resources of £14.159m.

  - This report now advises members of recent developments regarding funding the 2007/08 capital programme.

2.  	2007/08 CAPITAL PROGRAMME

  - Members are asked to note the following adjustments to the capital programme and resources:-

###### Resources

|  | Last Month | This Month | Variation | Comments |
| --- | --- | --- | --- | --- |
|  | £m | £m | £m |  |
| Supported Borrowing | 6.388 | 6.431 | 0.043 | Contaminated land funding |
| Unsupported Borrowing | 6.587 | 6.664 | 0.077 | Rephasing Higher Broughton community hub offset by equal pay and enterprise xp adjustments |
| RCCO | 0.051 | 0.051 | 0.000 |  |
| Capital receipts | 22.402 | 22.872 | 0.470 | Better than expected auction results |
| Subtotal – Internal resources | 35.428 | 36.018 | 0.590 |  |
| Grants | 69.049 | 68.086 | (0.963) | Childrens Centre phase 2 surestart grant rephased to 2008/09. Additional SSCF funding for private sector housing and CHSC |
| Other Contributions | 2.137 | 1.284 | (0.853) | Rephasing of Higher Broughton Community Hub partially offset by additional contributions on the Highways programme |
| Subtotal – External resources | 71.186 | 69.370 | (1.816) |  |
| Total Resources | 106.614 | 105.388 | (1.226) |  |

Programme

|  | Last Month | This Month | Variation | Comments |
| --- | --- | --- | --- | --- |
| Programme | £m | £m | £m |  |
| Private Sector Housing | 38.087 | 38.330 | 0.243 | Additional SSCF funding |
| Public Sector Housing | 19.537 | 19.537 | 0.000 |  |
| Children's Services | 16.668 | 15.558 | (1.110) | Rephasing of Children’s centres phase 2 and Primary review to 2008/09 |
| Highways | 5.853 | 5.449 | (0.404) | Adjustment to resources for Inner Relief Road and Cadishead Way |
| Community, Health And Social Care | 5.133 | 5.300 | 0.167 | Additional SSCF funding |
| Environmental Services | 2.568 | 2.611 | 0.043 | Contaminated land schemes |
| Customer and Support Services | 3.174 | 5.132 | 1.958 | Equal pay capitalisation and revision to enterprise XP forecast |
| Chief Executives | 14.913 | 13.883 | (1.030) | Rephasing of City Academy site acquisition and Corporate Security Strategy |
| Planning | 14.840 | 9.237 | (5.603) | Rephasing of Higher Broughton Hub, Eccles Town centre, building maintenance, office moves and MBB canal phase 1 |
| Total Programme | 120.773 | 115.037 | (5.736) |  |
| Surplus/(Shortfall) of Resources in current year | (14.159) | (9.649) | 4.510 |  |

Overall Position

  - Based on the current forecasts for expenditure and resources there is a shortfall of resources of £9.649m, which is an improvement of £4.510m on last month, but will require the use of prudential borrowing at the year end to balance the capital programme if additional capital receipts or other funding cannot be found.  This will incur interest charges in 2008/09 until capital receipts become available to repay the borrowing.

Comments on Programme adjustments

  - The council has received a capitalisation directive from DCLG allowing £1.392m of equal pay costs to be accounted for as capital expenditure in 2007/08.

  - A proportion of the Corporate Security Strategy has been rephased to 2008/09 as the expenditure in 2007/08 will be limited to design work only.

  - The office moves programme has been rephased due to the delay in relocating NPHL to new accommodation and the replacement building for Summerfield House still being assessed.

  - British Waterways are unlikely to draw upon the temporary funding provided for in the programme for Manchester Bolton and Bury canal phase 1 as the works on the site are substantially complete.

  - The land purchases for the Inner Relief Road are now expected to be settled by March this year, with a shortfall in TSG resources of £0.341m.  This is currently provided for in the capital programme by assuming additional resources coming from GONW.  GONW have been sent the details of the shortfall in funding on the Inner Relief Road with a request for additional resources to cover the increased land purchase costs incurred.  If additional resources are not received the costs would fall to be met from the Council’s own resources.

Comments on Resources adjustment

  - Revisions to the Salford Shopping City receipt due in 2007/08 were offset by an increase in the forecast for land at Boysnope Wharf and a partial loan repayment by the Higher Broughton Partnership.  The overall Salford Shopping City receipt remains unchanged.

  - At the auction on the 18th October the bids received were £0.545m over the original forecast amounts for the disposals at Orchard Mount, Greenbank and Clifford Street.   The forecast has been revised upwards to reflect the actual bids received.

  - The 2007/08 capital programme requires the use of £32.521m capital receipts.  Progress to date is as follows :-

|  | £m |
| --- | --- |
| Brought forward from 2006/07 | 5.570 |
| Completed to date this year | 2.368 |
| Total | 7.938 |
| Grants due for 2006/07 to be paid in 2007/08 where capital receipts used temporarily instead | 1.415 |
| Total received to date | 9.353 |
| Minimum amount of capital receipts required to avoid use of prudential borrowing | 32.521 |
| Current forecast for further receipts this year | 13.519 |
| Shortfall on receipts | 9.649 |

  - The timing of the use of capital receipts earmarked for use by Children’s Services which are included in the capital receipts forecast or other expenditure funded by capital receipts slipped from the 2007/08 capital programme is as follows: -

| Timing of use of Earmarked Receipts | 2008/09 | 2009/10 | 2010/11 | Total |
| --- | --- | --- | --- | --- |
| Included in the capital receipts forecast | £m | £m | £m | £m |
| Supported borrowing timing differences |  |  |  |  |
| £8.673m |  |  |  |  |
| Upfront Unitary charge payment for PFI 2 | 3.625 | 0.000 | 0.000 | 3.625 |
| Modernisation | 0.896 | 0.000 | 0.000 | 0.896 |
| School Access 06-07 | 0.150 | 0.000 | 0.000 | 0.150 |
| Westwood Park Thunderbird building | 0.044 | 0.000 | 0.000 | 0.044 |
| Primary Review other | 0.405 | 0.000 | 0.000 | 0.405 |
| Radclyffe & St Clements | 0.302 | 0.000 | 0.000 | 0.302 |
| Hope/ Buile | 2.500 | 0.000 | 0.000 | 2.500 |
| Other | 0.000 | 0.751 | 0.000 | 0.751 |
| Portion of Greenwood playing field receipt |  |  |  |  |
| Dukesgate playing field (£0.500m in 2007/08) | 1.579 | 0.000 | 0.000 | 1.579 |
| Playing field Little Hulton Catholic Primary school | 1.429 | 0.000 | 0.000 | 1.429 |
| Kersal High School £6.345m |  |  |  |  |
| Albion playing field | 0.000 | 0.000 | 2.875 | 2.875 |
| Primary review phase 2- new Charlestown school | 3.295 | 0.000 | 0.150 | 3.445 |
| Walkden High School - acquisition of 2 residential properties | 0.025 | 0.000 | 0.000 | 0.025 |
| Oakwood High School |  |  |  |  |
| Contribution to St Lukes RC Primary school extension (£0.200m in 2007/08) |  |  |  |  |
| New school Seedley/Langworthy/Weaste | 0.000 | 0.300 | 0.000 | 0.300 |
| Radclyffe St Clements £2.3m |  |  |  |  |
| (£1.215m on 2007/08) | 1.085 | 0.000 | 0.000 | 1.085 |
| Other Slippage from the 2007/08 capital programme funded by capital receipts |  |  |  |  |
| Academy site assembly | 0.900 | 0.000 | 0.000 | 0.900 |
| Corporate Security Strategy | 0.300 | 0.000 | 0.000 | 0.300 |
| Eccles Town Centre | 0.488 | 0.000 | 0.000 | 0.488 |
| Building Maintenance | 0.270 | 0.000 | 0.000 | 0.270 |
| MBB canal phase 1 | 0.800 | 0.000 | 0.000 | 0.800 |
| Office Moves | 0.800 | 0.000 | 0.000 | 0.800 |
| Total committed capital receipts | 18.893 | 1.051 | 3.025 | 22.969 |

Capital funding plans for 2008/09 onwards will need to accommodate these commitments.

Capital receipts which were in the original capital programme plans for 2007/08 and which have slipped into 2008/09 total an estimated £23.7m.

Other Underlying Risks

  - There remain some potential cost increases from outstanding Lands Tribunal hearings.  The Council is currently involved with Lands Tribunal hearings yet to be held in respect of land acquisitions at Eccles Town Centre.

3	EXPENDITURE TO DATE

3.1	Members are asked to note the following summary of actual expenditure against expected expenditure as at the end of September.

###### Actual Spend Against Profile to 30th September 2007

|  |  |  | Expected spend to date |  | Variance against |
| --- | --- | --- | --- | --- | --- |
|  |  | Programme | 2006/07 Spend Profile | Monthly profile | Actual Spend to date | 2006/07 Spend Profile | Monthly profile |
|  |  | £m | £m | £m | £m | £m | £m |
|  | Private Sector Housing | 38.330 | 11.116 | 19.165 | 9.885 | -1.231 | -9.280 |
|  | Public Sector Housing | 19.537 | 5.666 | 9.769 | 5.007 | -0.659 | -4.762 |
|  | Children's Services | 15.558 | 4.318 | 7.779 | 5.691 | 1.373 | -2.088 |
|  | Highways | 5.449 | 1.580 | 2.725 | 1.178 | -0.402 | -1.547 |
|  | Community, Health And Social Care | 5.300 | 1.326 | 2.650 | 1.381 | 0.055 | -1.269 |
|  | Environmental Services | 2.611 | 0.737 | 1.306 | 0.267 | -0.470 | -1.039 |
|  | Customer and Support Services | 5.132 | 1.488 | 2.566 | 0.171 | -1.317 | -2.395 |
|  | Chief Executives | 13.883 | 3.542 | 6.942 | 2.196 | -1.346 | -4.746 |
|  | Planning | 9.237 | 2.769 | 4.619 | 3.348 | 0.579 | -1.271 |
|  | 07/08 Programme Total | 115.037 | 32.541 | 57.519 | 29.124 | -3.417 | -28.395 |

- RECOMMENDATION

  - Members are requested to review the current position regarding the 2007/08 capital programme and confirm recommends to Cabinet that the current position continues to be monitored.

JOHN SPINK

###### CITY TREASURER