| . | PART 1 (OPEN TO THE PUBLIC) | ITEM NO. 6 |
| --- | --- | --- |
| REPORT OF THE CITY TREASURER |
| TO THE BUDGET SCRUTINY COMMITTEE ON WEDNESDAY 2nd APRIL 2008 |
| TITLE : CAPITAL MONITORING 2007/08 |
| RECOMMENDATION : Members are requested to review the current position regarding the 2007/08 capital programme and recommend to Cabinet that the current position continues to be monitored. |
| EXECUTIVE SUMMARY : The report provides details of the funding of the 2007/08 capital programme and expenditure to date. |
| BACKGROUND DOCUMENTS : (Available for public inspection) 1. Report to Budget Scrutiny Committee Friday 8th February 2. Various working papers within the Finance Division |
| CONTACT OFFICER : Tony Thompstone 793-2685 E-mail : tony.thompstone@salford.gov.uk |
| ASSESSMENT OF RISK : Any increase in the planned programme or reduction in resources included in this report will require action to be taken to ensure the capital programme for 2007/08 remains fully funded. |
| SOURCE OF FUNDING : This report identifies the sources of funding for the 2007/08 Capital Programme. |
| LEGAL ADVICE OBTAINED : Not Applicable |
| FINANCIAL ADVICE OBTAINED : This report concerns key aspects of Council’s capital finance and has been produced by the Finance Division of Customer and Support Services. |
| WARD(S) TO WHICH REPORT RELATE(S) : ALL WARDS |
| KEY COUNCIL POLICIES : : Budget Strategy |

REPORT DETAILS

- INTRODUCTION

  - At the meeting of the Budget Scrutiny Committee on the 8th February 2008 members were informed that the current capital programme for 2007/08 was £112.809m with capital funding amounting to £105.929m, comprising assumed internal funding of £37.821m and estimated external funding of £68.108m, giving a shortfall in resources of £6.880m.

  - This report now advises members of recent developments regarding funding the 2007/08 capital programme.

2.  	2007/08 CAPITAL PROGRAMME

  - Members are asked to note the following adjustments to the capital programme and resources:-

###### Resources

|  | Last Month | This Month | Variation | Comments |
| --- | --- | --- | --- | --- |
|  | £m | £m | £m |  |
| Supported Borrowing | 6.431 | 6.361 | (0.070) | Part of Mental Health SCE to be used in 2008/09 |
| Unsupported Borrowing | 7.884 | 7.544 | (0.340) | Fit City Irlam, Higher Broughton Hub rephased to 2008/09 |
| RCCO | 0.051 | 0.000 | (0.051) | St George’s and Granville re-modelling rephased to 2008/09 |
| Capital receipts | 23.455 | 17.797 | (5.658) | Changes to the capital receipts forecast |
| Subtotal – Internal resources | 37.821 | 31.702 | (6.119) |  |
| Grants | 66.660 | 65.070 | (1.590) | DFC, Surestart and PCT grant to be used in 2008/09 |
| Other Contributions | 1.448 | 1.546 | 0.098 | Monitoring adjustments |
| Subtotal – External resources | 68.108 | 66.616 | (1.492) |  |
| Total Resources | 105.929 | 98.318 | (7.611) |  |

Programme

|  | Last Month | This Month | Variation | Comments |
| --- | --- | --- | --- | --- |
| Programme | £m | £m | £m |  |
| Private Sector Housing | 37.915 | 34.233 | (3.682) | Adjust 07/08 resource levels to agree with forecast underprogramming |
| Public Sector Housing | 20.037 | 20.787 | 0.750 | Resources from Private Sector Housing |
| Children's Services | 15.768 | 12.826 | (2.942) | Devolved Formula Capital, residential purchases at Walkden High School and new school at Seedley/Langworthy/Weate rephased to 2008/09 |
| Highways | 5.063 | 5.063 | 0.000 |  |
| Community, Health And Social Care | 4.440 | 3.285 | (1.155) | Monitoring adjustments with expenditure and resources rephased to 2008/09 |
| Environmental Services | 3.090 | 2.801 | (0.289) | Rephase Parks infrastructure expenditure to 2008/09 |
| Customer and Support Services | 4.256 | 4.256 | 0.000 |  |
| Chief Executives | 12.168 | 12.168 | 0.000 |  |
| Planning | 10.072 | 8.898 | (1.174) | Rephasing of expenditure on crane repainting, Higher Broughton Community Hub, Agecroft Commerce Park Phase |
| Total Programme | 112.809 | 104.317 | (8.492) |  |
| Surplus/(Shortfall) of Resources in current year | (6.880) | (5.999) | 0.881 |  |

Overall Position

  - Based on the current forecasts for expenditure and resources there is a shortfall of resources of £5.999m.  This reduction in the forecast shortfall of resources is because of expenditure funded by internal resources slipping into 2008/09.  Whilst there is now a smaller shortfall in 2007/08, there is an increased shortfall on the 2008/09 programme, as the slipped expenditure will require funding.

Comments on Programme adjustments

  - The Private sector housing programme is under-programmed at present by £3m this has arisen not because of any individual action but fundamental changes to the original approved programme and HMRF appraised schemes. This has been around the requirement to re-assess future strategies in relation to CPO and market prices.

  - It should be noted that as a result of these changes there are commitments and pressures now occurring in future years and as such the only way that the level of under-programming can be addressed in the current year is by bringing forward schemes that are HMRF funded and not new or additional projects. However there is nothing currently identified that can address this again due to the market circumstances.

  - Expenditure for 2 residential properties needed for Walkden High School is now likely to be in 2008/09, similarly expenditure at the new school for Seedley/Langworthy/Weate will not now be until 2008/09.

  - A number of monitoring adjustments have been made to the Community, Health and Social Care programme, with expenditure slipping to 2008/09 for a number of schemes.

  - The expenditure on crane repainting, Higher Broughton Community Hub, Agecroft Commerce Park Phase has been moved to 2008/09

Comments on Resources adjustment

  - The capital receipts forecast for 2007/08 has been reduced by £5.658m.  It is expected that no money will be received from Tesco for Salford Shopping City in 2007/08.  However, every effort is being made to try and receive an interim payment before 31st March.

  - The forecast for Right to Buy receipts has been reduced by £1.0m which means a reduction in usable receipts of £0.250m.  The forecast disposal dates for land at St Marks Lane, Yew St and Slough Industrial Estate have been revised to 2008/09.  This has been partially offset by an increase in the forecast receipt for the land at Boysnope Wharf.

  - The 2007/08 capital programme requires the use of £23.796m capital receipts.  Progress to date is as follows :-

|  | £m |
| --- | --- |
| Brought forward from 2006/07 | 5.570 |
| Completed to date this year | 6.211 |
| Total | 11.781 |
| Grants due for 2006/07 to be paid in 2007/08 where capital receipts used temporarily instead | 1.415 |
| Total received to date | 13.196 |
| Minimum amount of capital receipts required to avoid use of prudential borrowing | 23.796 |
| Current forecast for further receipts this year | 4.601 |
| Shortfall on receipts | 5.999 |

  - The timing of the use of capital receipts earmarked for use by Children’s Services which are included in the capital receipts forecast or other expenditure funded by capital receipts slipped from the 2007/08 capital programme is as follows: -

| Timing of use of Earmarked Receipts | 2008/09 | 2009/10 | 2010/11 | Total |
| --- | --- | --- | --- | --- |
| Included in the capital receipts forecast | £m | £m | £m | £m |
| PFI 2 (slipped form 2007/08) | 0.023 | 0.000 | 0.000 | 0.023 |
| Westwood park thunderbird building (slipped form 2007/08) | 0.044 | 0.000 | 0.000 | 0.044 |
| School access (slipped form 2007/08) | 0.150 | 0.000 | 0.000 | 0.150 |
| Upfront Unitary charge payment for PFI 2 (funded by supported borrowing timing difference) | 6.354 | 0.000 | 0.000 | 6.354 |
| Weaste/Seedley/Langworthy 2 form entry school (3 into 1) (from SB slippage 0708) | 0.000 | 0.778 | 0.000 | 0.778 |
| Radclyffe & St Clements (funded by supported borrowing timing difference) | 0.285 | 0.000 | 0.000 | 0.285 |
| Modernisation Programme (reduce back-log of condition) | 1.022 | 0.000 | 0.000 | 1.022 |
| Weaste/Seedley/Langworthy 2 form entry school (3 into 1) (from Greenwood receipt) | 0.000 | 0.000 | 0.189 | 0.189 |
| Playing field provision to new Catholic Primary School in Little Hulton Greenwood receipt | 0.500 | 0.080 | 0.000 | 0.580 |
| School to replace Charlestown & North Grecian St (Wheatersfield site) (Greenwood receipt) | 0.000 | 0.229 | 0.000 | 0.229 |
| Dukesgate playing field (funded by Greenwood receipt) | 1.781 | 0.000 | 0.000 | 1.781 |
| Albion Playing Fields (Kersal receipt) | 0.000 | 0.000 | 0.380 | 0.380 |
| Weaste/Seedley/Langworthy 2 form entry school (3 into 1) (from Kersal receipt) | 0.000 | 0.839 | 1.161 | 2.000 |
| School to replace Charlestown & North Grecian St (Wheatersfield site) Kersal receipt | 0.057 | 1.800 | 1.045 | 2.902 |
| Other Slippage from the 2007/08 capital programme funded by capital receipts | 8.381 | 0.000 | 0.000 | 8.381 |
|  | 18.597 | 3.726 | 2.775 | 25.098 |

2.12	Capital funding plans for 2008/09 onwards will need to accommodate these commitments.

2.13	With a shortfall in resources for 2007/08 of £5.999m and a commitment to return £18.597m of resources already received/used, the 2008/09 capital programme will require £24.596m just to meet these obligations.

2.14	Capital receipts which were in the original capital programme plans for 2007/08 and which have slipped into 2008/09 total an estimated £28.9m.

Other Underlying Risks

2.15	There remain some potential cost increases from outstanding Lands Tribunal hearings.  The Council is currently involved with Lands Tribunal hearings yet to be held in respect of land acquisitions at Eccles Town Centre.

3	EXPENDITURE TO DATE

3.1	Members are asked to note the following summary of actual expenditure against expected expenditure as at the end of February.

###### Actual Spend Against Profile to 29th February 2008

|  |  |  | Expected spend to date |  | Variance against |
| --- | --- | --- | --- | --- | --- |
|  |  | Programme | 2006/07 Spend Profile | Monthly profile | Actual Spend to date | 2006/07 Spend Profile | Monthly profile |
|  |  | £m | £m | £m | £m | £m | £m |
|  | Private Sector Housing | 34.233 | 23.278 | 28.528 | 21.505 | -1.773 | -7.023 |
|  | Public Sector Housing | 20.787 | 14.135 | 17.323 | 16.046 | 1.911 | -1.277 |
|  | Children's Services | 12.826 | 8.077 | 10.688 | 11.232 | 3.155 | 0.544 |
|  | Highways | 5.063 | 3.443 | 4.219 | 2.790 | -0.653 | -1.429 |
|  | Community, Health And Social Care | 3.285 | 1.521 | 2.738 | 2.405 | 0.884 | -0.333 |
|  | Environmental Services | 2.801 | 1.514 | 2.334 | 0.668 | -0.846 | -1.666 |
|  | Customer and Support Services | 4.256 | 2.894 | 3.547 | 0.420 | -2.474 | -3.127 |
|  | Chief Executives | 12.168 | 8.274 | 10.140 | 5.837 | -2.437 | -4.303 |
|  | Planning | 8.898 | 6.175 | 7.415 | 6.923 | 0.748 | -0.492 |
|  | 07/08 Programme Total | 104.317 | 69.312 | 86.931 | 67.826 | -1.486 | -19.105 |

- RECOMMENDATION

  - Members are requested to review the current position regarding the 2007/08 capital programme and confirm recommends to Cabinet that the current position continues to be monitored.

JOHN SPINK

###### CITY TREASURER