| . | PART 1 (OPEN TO THE PUBLIC) | ITEM NO.9 |
| --- | --- | --- |
| REPORT OF THE CITY TREASURER |
| TO THE BUDGET SCRUTINY COMMITTEE ON WEDNESDAY 2 September 2009 |
| TITLE: CAPITAL MONITORING 2009/10 |
| RECOMMENDATION : Members are requested to review the current position regarding the 2009/10 capital programme and recommend to Cabinet that the current position continues to be monitored. |
| EXECUTIVE SUMMARY : The report provides details of the funding of the 2009/10 capital programme and expenditure to date. |
| BACKGROUND DOCUMENTS : (Available for public inspection) 1. Report to Budget Scrutiny Committee Wednesday 1 July 2009 2. Various working papers within the Finance Division |
| CONTACT OFFICER : Marion Rigg 793-2685 E-mail: marion.rigg@salford.gov.uk |
| ASSESSMENT OF RISK : Any increase in the planned programme or reduction in resources included in this report will require action to be taken to ensure the capital programme for 2009/10 remains fully funded. |
| SOURCE OF FUNDING : This report identifies the sources of funding for the 2009/10 Capital Programme. |
| LEGAL ADVICE OBTAINED : Not Applicable |
| FINANCIAL ADVICE OBTAINED : This report concerns key aspects of Council’s capital finance and has been produced by the Finance Division of Customer and Support Services. |
| WARD(S) TO WHICH REPORT RELATE(S) : ALL WARDS |
| KEY COUNCIL POLICIES : Budget Strategy |

Report Details

- Introduction

At the meeting of the Budget Scrutiny Committee on the 1 July 2009, members were informed that the current capital programme for 2009/10 was £137.834m, funded by estimated internal funding of £14.847m, estimated external funding of £88.731m and unsupported borrowing of £34.256m.

This report now advises members of recent developments regarding the 2009/10 capital programme

2.  	2009/10 Capital Programme

Review of Capital Programme

Members are asked to note the following adjustments to the capital programme and resources in August 2009:-

Programme

|  | June 2009 | This Month | Variation | Comments |
| --- | --- | --- | --- | --- |
|  | £m | £m | £m |  |
| Private Sector Housing | 27.443 | 27.443 | 0.000 |  |
| Public Sector Housing | 14.687 | 14.687 | 0.000 |  |
| Highways | 9.250 | 6.831 | (2.419) | Note 1 |
| Sustainable Regeneration | 36.477 | 33.564 | (2.913) | Note 2 |
| Children's Services | 25.908 | 24.287 | (1.621) | Note 3 |
| Environmental services | 2.627 | 2.790 | 0.163 | Note 4 |
| Community, Health And Social Care | 10.571 | 11.405 | 0.834 | Note 5 |
| Property | 1.800 | 1.800 | 0.000 |  |
| Crime and Disorder | 2.870 | 2.870 | 0.000 |  |
| Customer and Support Services | 6.201 | 6.201 | 0.000 |  |
| Total Programme | 137.834 | 131.878 | (5.956) |  |

###### Resources

|  | June 2009 | This Month | Variation | Comments |
| --- | --- | --- | --- | --- |
|  | £m | £m | £m |  |
| Supported Borrowing | 6.436 | 3.560 | (2.876) | Note 6 |
| Invest to save | 8.411 | 5.160 | (3.251) | Higher Broughton Hub moved to unsupported borrowing |
| Unsupported Borrowing | 34.256 | 33.891 | (0.365) | Note 7 |
| Revenue Contribution to Capital | 0.000 | 0.012 | 0.012 |  |
| Subtotal - Internal resources | 49.103 | 42.623 | (6.480) |  |
| Grants | 85.641 | 86.646 | 1.005 | Increase in grant funding for Children’s Services and Environment. |
| Other Contributions | 3.090 | 2.609 | (0.481) | Funding for SCL schemes amended from Other to Unsupported borrowing |
| Subtotal - External resources | 88.731 | 89.255 | 0.524 |  |
| Total Resources | 137.834 | 131.878 | (5.956) |  |

Comments on Programme adjustments

Overview

There have been the following adjustments to the capital programme

Note 1 – Highways

- Two major grant funded schemes, Trinity Way and Cadishead Way are nearing completion and the budget has been reduced to reflect the forecast of final expenditure.

Note 2 – Sustainable Regeneration

- Building work on Higher Broughton Community Hub is not expected to start until April 2010 and the budget has now slipped to 2010/11.

Note 3 – Children’s Services

- Slippage of spend from 2009/10 to 2010/11, totalling £1.925m relating to Children’s Centres, Holy Family School and ICT Projects. A £274k grant has been received to refurbish the kitchen at Light Oaks School.

Note 4 – Environment

- Playbuilder grant awarded for Cadishead Park and increase in budget for the visitor centre at Buile Hill Park.

Note 5 – Community Health & Social Care

- Increase in the grants received for White Meadows and St Georges.  Refurbishment of Worsley Area Housing Office to facilitate Salford Community Leisure’s move from Minerva House.  Spend on Eccles Library slipped from 2008/09.

Comments on Resources adjustments

Note 6 – Supported Borrowing

- Highways – Funding for Trinity Way (Inner Relief Road) no longer required in 2009/10.

- Children’s Services – Funding for VA school and modernisation programme changed from supported borrowing to grant funding.

Note 7 – Unsupported Borrowing

- Higher Broughton Community Hub – the start of the build has now slipped to 2010/11.

- A proportion of the spend on Holy Family School has slipped to 2010/11.

Capital Receipts

It is estimated that capital receipts of £6.052m will be received in 2009/10 and these will be used to repay unsupported borrowing taken out to finance the capital programme.

3	Expenditure to Date

Members are asked to note the following summary of actual expenditure against expected expenditure as at the end of July.

###### Actual Spend Against Profile to 31 July 2009

|  |  | Expected spend to date |  | Variance against |
| --- | --- | --- | --- | --- |
|  | Programme | 2009/10 Spend Profile | Monthly profile | Actual Spend to date | 2009/10 Spend Profile | Monthly profile |
|  | £m | £m | £m | £m | £m | £m |
| Private sector housing | 27.443 | 4.391 | 9.148 | 5.633 | 1.242 | -3.515 |
| Public sector housing | 14.687 | 0.734 | 4.896 | 1.996 | 1.262 | -2.900 |
| Highways | 6.831 | 1.093 | 2.277 | 1.167 | 0.074 | -1.110 |
| Sustainable Regeneration | 33.564 | 5.370 | 11.188 | 2.169 | -3.201 | -9.019 |
| Children's Services | 24.287 | 3.886 | 8.096 | 2.809 | -1.077 | -5.287 |
| Environmental Services | 2.790 | 0.446 | 0.930 | 0.355 | -0.091 | -0.575 |
| CH & SC | 11.405 | 1.825 | 3.802 | 1.634 | -0.191 | -2.168 |
| Crime and Disorder | 1.800 | 0.288 | 0.600 | 0.051 | -0.237 | -0.549 |
| Property | 2.870 | 0.459 | 0.957 | 0.494 | 0.035 | -0.463 |
| Customer & Support Services | 6.201 | 0.992 | 2.067 | 0.050 | -0.942 | -2.017 |
| 09/10 Programme Total | 131.878 | 19.484 | 43.961 | 16.358 | -3.126 | -27.603 |

4    Recommendation

Members are requested to review the current position regarding the 2009/10 capital programme and confirm recommendations to Cabinet that the current position continues to be monitored.

JOHN SPINK

###### CITY TREASURER