| . | PART 1 (OPEN TO THE PUBLIC) | ITEM NO.11 |
| --- | --- | --- |
| REPORT OF THE CITY TREASURER |
| TO THE BUDGET SCRUTINY COMMITTEE ON WEDNESDAY 5th SEPTEMBER 2007 |
| TITLE : CAPITAL MONITORING 2007/08 |
| RECOMMENDATION : Members are requested to review the current position regarding the 2007/08 capital programme and recommend to Cabinet that, in the light of certain outstanding issues yet to be resolved, that the current position continues to be monitored. |
| EXECUTIVE SUMMARY : The report provides details of the funding of the 2007/08 capital programme and expenditure to date. |
| BACKGROUND DOCUMENTS : (Available for public inspection) 1. Report to Budget Scrutiny Committee Wednesday 4th July 2. Various working papers within the Finance Division |
| CONTACT OFFICER : Tony Thompstone 793-2685 E-mail : tony.thompstone@salford.gov.uk |
| ASSESSMENT OF RISK : Any increase in the planned programme or reduction in resources included in this report will require action to be taken to ensure the capital programme for 2007/08 remains fully funded. |
| SOURCE OF FUNDING : This report identifies the sources of funding for the 2007/08 Capital Programme. |
| LEGAL ADVICE OBTAINED : Not Applicable |
| FINANCIAL ADVICE OBTAINED : This report concerns key aspects of Council’s capital finance and has been produced by the Finance Division of Customer and Support Services. |
| WARD(S) TO WHICH REPORT RELATE(S) : ALL WARDS |
| KEY COUNCIL POLICIES : : Budget Strategy |

REPORT DETAILS

- INTRODUCTION

  - At the meeting of the Budget Scrutiny Committee on the 4th July 2007 members were informed that the current capital programme for 2007/08 was £123.462m with capital funding amounting to £119.518m, comprising assumed internal funding of £52.015m and estimated external funding of £67.503m, giving a shortfall in resources of £3.944m.

  - This report now advises members of recent developments regarding funding the 2007/08 capital programme.

2.  	2007/08 CAPITAL PROGRAMME

  - Members are asked to note the following adjustments to the capital programme and resources:-

###### Resources

|  | Last Month | This Month | Variation | Comments |
| --- | --- | --- | --- | --- |
|  | £m | £m | £m |  |
| Supported Borrowing | 6.368 | 6.368 | 0.000 |  |
| Unsupported Borrowing | 6.565 | 6.587 | 0.022 |  |
| RCCO | 0.000 | 0.051 | 0.051 | CHSC Painting programme |
| Capital receipts | 39.082 | 34.867 | (4.215) | Reduction in forecast capital receipts (see para 2.8 to 2.11) |
| Subtotal – Internal resources | 52.015 | 47.873 | (4.142) |  |
| Grants | 64.102 | 69.966 | 5.864 | URC external funding (matched by an increase in programme) |
| Other Contributions | 3.401 | 2.318 | (1.083) | Broughton Pool and Fit City Broughton programmed works rather than feasibility study |
| Subtotal – External resources | 67.503 | 72.284 | 4.781 |  |
| Total Resources | 119.518 | 120.157 | 0.639 |  |

Programme

|  | Last Month | This Month | Variation | Comments |
| --- | --- | --- | --- | --- |
| Programme | £m | £m | £m |  |
| Private Sector Housing | 42.141 | 38.087 | (4.054) | Adjust resources and spend for the Ordsall Infrastructure account. Movement of resources within the Housing programme |
| Public Sector Housing | 18.537 | 19.537 | 1.000 | Movement of resources within the Housing programme |
| Children's Services | 17.429 | 18.087 | 0.658 | Acquisition cost at Walkden High school, Integrated Children’s Services grant |
| Highways | 7.928 | 7.688 | (0.240) | Quality bus corridor to be progressed by GMPTE |
| Community, Health And Social Care | 5.879 | 5.113 | (0.766) | PCT capital grant, painting programme |
| Environmental Services | 2.721 | 2.808 | 0.087 | Greenspace improvements - Clifton Green and Queensmere reservoir Clifton |
| Customer and Support Services | 1.551 | 2.898 | 1.347 | BSF/PFI development costs |
| Chief Executives | 7.663 | 13.413 | 5.750 | URC externally funded capital programme (see resources adjustment) |
| Planning | 19.613 | 19.709 | 0.096 |  |
| Total Programme | 123.462 | 127.340 | 3.878 |  |
| Surplus/(Shortfall) of Resources in current year | (3.944) | (7.183) | (3.239) |  |

Overall Position

Based on the current forecasts for expenditure and resources there is a shortfall of resources of £7.183m, which will require the use of prudential borrowing at the year end to balance the capital programme if additional capital receipts or other funding cannot be found.  This will incur interest charges in 2008/09 until capital receipts become available to repay the borrowing.

Comments on Programme adjustments

  - The forecast for the Ordsall Infrastructure account expenditure in the year has been revised downward.  Overall the Ordsall Infrastructure account is forecast to breakeven with expenditure being offset by capital receipts.

  - In order to mitigate pressure on the HRA schemes have been identified mainly around gas works that can be classed as capital works rather than repairs leading to an increase in the public sector housing programme.  It should be noted that this is an adjustment to funding and there is no impact upon the decent homes programme as a consequence of this.  To resource this programme adjustment capital resources have been re-allocated within the Housing Programme.

  - Section 106 monies have been approved for the funding of improvements at Clifton Green and Queensmere Reservoir.

  - The estimate for the consultancy and staffing costs for BSF/PFI have been increased, although the scope to recover some of these from Wigan and the HRA (in respect of housing PFI) is currently being assessed.

  - The URC programme now includes the external funding provided by NWDA and English Partnerships for the regeneration activity in their business plan.  For this year that is Chapel Street and Crescent area, the River Irwell corridor, the M602 corridor and strategic connections.

  - The resources for the feasibility study for a replacement facility for Broughton Pool and Fit City Broughton are to be used to fund a number of programmed works at those two buildings

Comments on Resources adjustment

  - The forecast for right to buy receipts has been revised downwards from £20m to 12m for 2007/08.  As only 25% of these receipts are retained by the City Council this represents a decrease in forecast usable capital receipts of £2m.

  - The table below shows the number of right to buy applications received each quarter for the last 4 years.  The fall in applications for 2006/07 was offset by increased property values, however so far this year the fall has been even greater and requires the forecast to be revised downwards.

RTB application figures

|  | No of | No of | No of | No of | No of |
| --- | --- | --- | --- | --- | --- |
|  | Applications | Applications | Applications | Applications | Applications |
|  | 2003-2004 | 2004-2005 | 2005-2006 | 2006-2007 | 2007-2008 |
| Qtr 1 | 520 | 469 | 479 | 350 | 182 |
| Qtr 2 | 313 | 434 | 479 | 514 |  |
| Qtr3 | 318 | 452 | 382 | 291 |  |
| Qtr 4 | 497 | 494 | 365 | 306 |  |
|  | 1648 | 1849 | 1705 | 1461 | 182 |

  - There has been a reduction in the amount of the Shopping City receipt which is forecast to be received in 2007/08.

  - The 2007/08 capital programme requires the use of £42.027m capital receipts.  Progress to date is as follows :-

|  | £m |
| --- | --- |
| Brought forward from 2006/07 | 5.570 |
| Completed to date this year | 1.227 |
| Total received to date | 6.797 |
| Grants due for 2006/07 to be paid in 2007/08 where capital receipts used temporarily instead | 1.415 |
| Total | 8.212 |
| Minimum amount of capital receipts required to avoid use of prudential borrowing | 33.815 |
| of which :-High risk | 13.000 |
| Medium to low risk | 20.815 |

  - The timing of the use of capital receipts earmarked for use by Children’s Services which are included in the capital receipts forecast is as follows: -

| Timing of use of Earmarked Receipts | 2008/09 | 2009/10 | 2010/11 | Total |
| --- | --- | --- | --- | --- |
| Included in the capital receipts forecast | £m | £m | £m | £m |
| Supported borrowing timing differences |  |  |  |  |
| £7.178m |  |  |  |  |
| Upfront Unitary charge payment for PFI 2 | 3.625 | 0.000 | 0.000 | 3.625 |
| Radclyffe & St Clements | 0.302 | 0.000 | 0.000 | 0.302 |
| Hope/ Buile | 2.500 | 0.000 | 0.000 | 2.500 |
| Other | 0.000 | 0.751 | 0.000 | 0.751 |
| Portion of Greenwood playing field receipt |  |  |  |  |
| Dukesgate playing field (£0.500m in 2007/08) | 1.579 | 0.000 | 0.000 | 1.579 |
| Playing field Little Hulton Catholic Primary school | 1.429 | 0.000 | 0.000 | 1.429 |
| Kersal High School £6.345m |  |  |  |  |
| Albion playing field | 0.000 | 0.000 | 2.875 | 2.875 |
| Primary review phase 2- new Charlestown school | 3.295 | 0.000 | 0.150 | 3.445 |
| Walkden High School - acquisition of 2 residential properties | 0.025 | 0.000 | 0.000 | 0.025 |
| Oakwood High School |  |  |  |  |
| Contribution to St Lukes RC Primary school extension (£0.200m in 2007/08) |  |  |  |  |
| New school Seedley/Langworthy/Weaste | 0.000 | 0.300 | 0.000 | 0.300 |
| Radclyffe St Clements £2.3m |  |  |  |  |
| (£1.215m on 2007/08) | 1.085 | 0.000 | 0.000 | 1.085 |
| Total committed capital receipts | 13.840 | 1.051 | 3.025 | 17.916 |

Capital funding plans for 2008/09 onwards will need to accommodate these commitments.

Other Underlying Risks

  - There remain some potential cost increases from outstanding Lands Tribunal hearings.  The Council is currently involved with Lands Tribunal hearings yet to be held in respect of land acquisitions at Eccles Town Centre.  Outstanding negotiations for the Manchester/Salford Inner Relief Route should be concluded at a cost of around £0.3m, which is currently provided for in the capital programme by assuming additional resources coming from GONW.  GONW have been sent the details of the shortfall in funding on the Inner Relief Road with a request for additional resources to cover the increased land purchase costs incurred.  Any additional costs over and above what has been provided in the capital programme and available by way of additional Government grant would fall to be met from the Council’s own resources.

3	EXPENDITURE TO DATE

3.1	Members are asked to note the following summary of actual expenditure against expected expenditure as at the end of July.

###### Actual Spend Against Profile to 31st July 2007

|  |  |  | Expected spend to date |  | Variance against |
| --- | --- | --- | --- | --- | --- |
|  |  | Programme | 2006/07 Spend Profile | Monthly profile | Actual Spend to date | 2006/07 Spend Profile | Monthly profile |
|  |  | £m | £m | £m | £m | £m | £m |
|  | Private Sector Housing | 39.087 | 6.254 | 6.515 | 5.203 | -1.051 | -1.312 |
|  | Public Sector Housing | 18.537 | 2.966 | 3.090 | 2.620 | -0.346 | -0.470 |
|  | Children's Services | 18.087 | 2.798 | 3.015 | 2.729 | -0.069 | -0.286 |
|  | Highways | 7.688 | 1.230 | 1.281 | 0.738 | -0.492 | -0.543 |
|  | Community, Health And Social Care | 5.113 | 0.796 | 0.852 | 0.748 | -0.048 | -0.104 |
|  | Environmental Services | 2.808 | 0.449 | 0.468 | 0.143 | -0.306 | -0.325 |
|  | Customer and Support Services | 2.898 | 0.464 | 0.483 | 0.007 | -0.457 | -0.476 |
|  | Chief Executives | 13.413 | 2.146 | 2.236 | 2.436 | 0.290 | 0.201 |
|  | Planning | 19.709 | 3.244 | 3.285 | 2.590 | -0.654 | -0.695 |
|  | 07/08 Programme Total | 127.340 | 20.347 | 21.223 | 17.214 | -3.133 | -4.009 |

- RECOMMENDATION

  - Members are requested to review the current position regarding the 2007/08 capital programme and confirm that, in the light of certain outstanding issues yet to be resolved, recommends to Cabinet that the current position continues to be monitored.

JOHN SPINK

###### CITY TREASURER