| . | PART 1 (OPEN TO THE PUBLIC) | ITEM NO. 6 |
| --- | --- | --- |
| REPORT OF THE HEAD OF FINANCE |
| TO THE BUDGET SCRUTINY COMMITTEE ON WEDNESDAY 6th DECEMBER 2006 |
| TITLE : CAPITAL MONITORING 2006/07 |
| RECOMMENDATION : Members are requested to review the current position regarding the 2006/07 capital programme and recommend to Cabinet that, in the light of certain outstanding issues yet to be resolved, that the current position continues to be monitored. |
| EXECUTIVE SUMMARY : The report provides details of the funding of the 2006/07 capital programme and expenditure to date. |
| BACKGROUND DOCUMENTS : (Available for public inspection) 1. Report to Budget Scrutiny Committee Wednesday 1st November 2. Various working papers within the Finance Division |
| CONTACT OFFICER : Tony Thompstone 793-2685 E-mail : tony.thompstone@salford.gov.uk |
| ASSESSMENT OF RISK : Any increase in the planned programme or reduction in resources included in this report will require action to be taken to ensure the capital programme for 2006/07 remains fully funded. |
| SOURCE OF FUNDING : This report identifies the sources of funding for the 2006/07 Capital Programme. |
| LEGAL ADVICE OBTAINED : Not Applicable |
| FINANCIAL ADVICE OBTAINED : This report concerns key aspects of Council’s capital finance and has been produced by the Finance Division of Customer and Support Services. |
| WARD(S) TO WHICH REPORT RELATE(S) : ALL WARDS |
| KEY COUNCIL POLICIES : : Budget Strategy |

REPORT DETAILS

1.    	INTRODUCTION

  - At the meeting of the Budget Scrutiny Committee on the 1st November 2006 members were informed that the current capital programme for 2006/07 was £121.396m with capital funding amounting to £130.009m, comprising assumed internal funding of £62.300m and estimated external funding of £67.709m, giving a surplus in resources of £8.613m.

  - This report now advises members of recent developments regarding funding the 2006/07 capital programme.

2.  	2006/07 CAPITAL PROGRAMME

  - Members are asked to note the following adjustments to the capital programme and resources:-

###### Resources

|  | Last Month | This month | Variation | Comments |
| --- | --- | --- | --- | --- |
|  | £m | £m | £m |  |
| Supported Borrowing | 7.278 | 7.278 | 0.000 |  |
| Unsupported Borrowing | 21.084 | 15.662 | (5.422) | Revision of funding sources for Salford Innovation Forum and monitoring adjustment |
| RCCO | 0.733 | 0.629 | (0.104) | Resourcing adjustments for Irlam Pool and Cadishead Recreation Centre |
| Capital receipts | 33.205 | 32.201 | (1.004) | Slippage of receipts into 2007/08 |
| Subtotal – Internal resources | 62.300 | 55.770 | (6.530) |  |
| Grants | 49.389 | 52.546 | 3.157 | Revision of funding sources for Salford Innovation Forum and Bridgewater Sports Pavilion and addition of Safer, Stronger Communities funding |
| Other Contributions | 18.320 | 18.036 | (0.284) | Resourcing adjustment for Bridgewater Sports Pavilion |
| Subtotal – External resources | 67.709 | 70.582 | 2.873 |  |
| Total Resources | 130.009 | 126.352 | (3.657) |  |

|  | Last Month | This month | Variation | Comments |
| --- | --- | --- | --- | --- |
| Programme | £m | £m | £m |  |
| Private sector housing | 29.670 | 29.680 | 0.010 | Minor monitoring adjustment |
| Public sector housing | 19.129 | 19.129 | 0.000 |  |
| Children's services | 16.201 | 15.531 | (0.670) | Rephasing of Barton Moss refurbishment and addition of Specialist colleges scheme |
| Highways | 7.285 | 7.285 | 0.000 |  |
| Community, Health And Social Care | 11.010 | 10.902 | (0.108) | Monitoring adjustments |
| Environmental Services | 1.809 | 2.607 | 0.798 | Addition of Safer Stronger Communities funded schemes and NRSI funding at Langholme Place, Winton |
| Customer and Support Services | 2.971 | 2.971 | 0.000 |  |
| Chief Executives | 15.651 | 12.807 | (2.844) | Monitoring adjustment to Salford Innovation Forum |
| Planning services | 17.670 | 17.663 | (0.007) | Minor monitoring adjustment |
| Total Programme | 121.396 | 118.575 | (2.821) |  |
| Surplus/(Shortfall) of Resources in current year | 8.613 | 7.777 | (0.836) |  |

  - £20.605m of receipts are earmarked for use by Children’s Services from 2007/08 onwards, this includes £7.250m from the Kersal school site and £3.658m of the £4.736m received for the playing field element of the Greenwood receipt (the other £1.078m has already been used on Springwood) and £9.697m due to timing differences on supported borrowing.  A further £0.647m is earmarked for Ordsall Infrastructure .  The timing of the use of capital receipts earmarked for use by Children’s Services and the Ordsall Infrastructure account is as follows: -

| Timing of use of Earmarked Receipts | 2007/08 | 2008/09 | Total |
| --- | --- | --- | --- |
|  | £m | £m | £m |
| Supported borrowing timing differences £9.697m |  |  |  |
| Upfront Unitary charge payment for PFI 2 | 0.000 | 3.625 | 3.625 |
| Radclyffe & St Clements | 3.252 | 0.320 | 3.572 |
| Hope/ Buile | 2.500 | 0.000 | 2.500 |
| Portion of Greenwood Playing Field receipt £3.658m |  |  |  |
| Dukesgate playing field | 2.079 | 0.000 | 2.079 |
| Playing field Little Hulton Catholic Primary School | 1.579 | 0.000 | 1.579 |
| Kersal High School £7.250m |  |  |  |
| Albion playing field | 0.000 | 3.500 | 3.500 |
| Primary review phase 2 | 0.100 | 3.650 | 3.750 |
| Children’s services subtotal | 9.510 | 11.095 | 20.605 |
| Ordsall Infrastructure account | 0.647 | 0.000 | 0.647 |
| Total | 10.157 | 11.095 | 21.252 |

This therefore leaves a potential shortfall of resources of £13.475m.  Looking ahead to 2007/08 however, this can be managed over the next 2 years through a combination of new capital receipts and unsupported borrowing.

  - The refurbishment of Barton Moss has been rephased with spend and resources moving into 2007/08.  Schemes have been added for specialist colleges, NRSI funding at Langholme Place, Winton and safer stronger communities schemes for environmental services.  The previous profile for Salford Innovation Forum has been updated to align with that submitted for the Capital Investment Strategy.

Capital Receipts

  - The reduction in the forecast for capital receipts is because the disposal date for Oakwood School has been revised to 2007/08 and the Cleminson Street Works receipt will be subject to clawback of grant by NWDA.  These reductions in the forecast receipts for 2006/07 were partially offset by an increase of £2m in the forecast for Right to Buy sales, which will give £0.5m of usable receipts and additional receipts at Bridgewater School and increases to the receipts forecast for Albert Park and Police Street.

  - A total of £32.201m of usable capital receipts is expected in 2006/07, comprising £10.836m brought forward from 2005/06 and £21.365m of new receipts in 2006/07.

  - The 2006/07 capital programme requires the use of £24.424m of capital receipts.  A total of £16.497 m has been received to date, £10.836m brought forward plus £5.661m completed this year.  This leaves £7.927m remaining to be received this year to fully fund the programme.

  - If the full programme of receipts is achieved there will be a surplus of receipts at year-end of £7.777m.

Other Underlying Risks

  - Cost increases from outstanding Lands Tribunal hearings - The Council is currently involved with Lands Tribunal hearings yet to be held in respect of land acquisitions at Eccles Town Centre.  Outstanding negotiations for the Manchester/Salford Inner Relief Route should be concluded at a cost of around £300,000, which is currently provided for in the capital programme by assuming additional resources coming form GONW.  GONW have been sent the details of the shortfall in funding on the Inner Relief Road with a request for additional resources to cover the increased land purchase costs incurred.  Any additional costs over and above what has been provided in the capital programme and available by way of additional Government grant would fall to be met from the Council’s own resources.

3	EXPENDITURE TO DATE

3.1	Members are asked to note the following summary of actual expenditure against expected expenditure as at the end of October.

###### Actual Spend Against Profile to 31st October 2006

|  |  | Programme | Expected Spend to date | Actual Spend to date | Variance |
| --- | --- | --- | --- | --- | --- |
|  |  | £m | £m | £m | £m |
|  | Private sector housing | 29.680 | 17.313 | 9.868 | 7.445 |
|  | Public sector housing | 19.129 | 11.159 | 4.508 | 6.651 |
|  | Children's Services | 15.531 | 7.690 | 7.308 | 0.382 |
|  | Highways | 7.285 | 4.250 | 3.259 | 0.991 |
|  | Community, Health And Social Care | 10.902 | 6.157 | 7.174 | -1.017 |
|  | Environmental Services | 2.607 | 0.485 | 0.524 | -0.039 |
|  | Customer and Support Services | 2.971 | 0.340 | 0.094 | 0.246 |
|  | Chief Executives | 12.807 | 7.393 | 3.300 | 4.093 |
|  | Planning Services | 17.663 | 9.768 | 7.336 | 2.432 |
|  | 06/07 Programme Total | 118.575 | 64.554 | 43.371 | 21.183 |

  - The forecast for the year is based upon an even split of the programme over the year, except where more accurate forecasts have been developed.

  - Expenditure to the end of October last year was £46.817m, against an expected profile of £64.076m with outturn expenditure of £102.571m.

- RECOMMENDATION

  - Members are requested to review the current position regarding the 2006/07 capital programme and confirm that, in the light of certain outstanding issues yet to be resolved, recommends to Cabinet that the current position continues to be monitored.

J SPINK

###### HEAD OF FINANCE