## Appendix 1a
SUMMARY OF 2003/04 APPROVED PROGRAMME
|  | Planning Level |  |  | Resourced Schemes
COMMITTEE | Planning Level 01/10/03 | 2003/04 Monitoring Adj's | Revised Planning Level | Funded Schemes 01/10/03 | 2003/04 Monitoring Adj's | Revised Funded Schemes | Expenditure | Control Check
| £m | £m | £m | £m | £m | £m | £m
HOUSING | 39.637 | -0.11 | 39.527 | 39.637 | -0.11 | 39.527 | 14.383 | #REF!
EDUCATION | 14.058 | 0.169 | 14.227 | 14.058 | 0.169 | 14.227 | 6.487 | #REF!
HIGHWAYS | 21.363 |  | 21.363 | 21.363 |  | 21.363 | 3.457 | #REF!
SOCIAL SERVICES | 0.981 |  | 0.981 | 0.981 |  | 0.981 | 0.438 | #REF!
Sub-Total | 76.039 | 0.059 | 76.098 | 76.039 | 0.059 | 76.098 | 24.765 | #REF!
OTHER SERVICES BLOCK
ARTS & LEISURE | 1.981 | 0.046 | 2.027 | 1.981 | 0.046 | 2.027 | 1.755 | #REF!
DEVELOPMENT SERVICES | 2.963 |  | 2.963 | 2.963 |  | 2.963 | 1.435 | #REF!
POLICY | 4.839 |  | 4.839 | 4.839 |  | 4.839 | 3.189 | #REF!
ENVIRONENTAL & CONSUMER SERVICES | 0.25 |  | 0.25 | 0.25 |  | 0.25 | 0.044
CHIEF EXECUTIVE | 2.322 |  | 2.322 | 2.322 |  | 2.322 | 0.54
Sub-Total (Other Services Block) | 12.355 | 0.046 | 12.401 | 12.355 | 0.046 | 12.401 | 6.963 | #REF!
TOTAL - CAPITAL PROGRAMME | 88.394 | 0.105 | 88.499 | 88.394 |  | 88.499 | 31.728 | #REF!

## Appendix 1b
Contract
|  | 2003/04 Estimate | Start | Finish | A | M | J | J | A | S | O | N | Est to Date | Actual to Date | Diff. | D | J | F | M |  | Total
|  | £m |  |  | £m | £m | £m | £m | £m | £m | £m | £m |  |  |  | £m | £m | £m | £m |  | £m
HOUSING
Private Sector
Disabled Facilities Grants |  | 1 |  |  |  | 0.015 | 0.035 | 0.05 | 0.05 | 0.1 | 0.1 | 0.1 | 0.45 | 0.348 | 0.102 | 0.1 | 0.1 | 0.15 | 0.2 |  | 1
Houses in Multiple Occupation |  | 0.222 |  |  |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.05 | 0 | 0.05 | 0.01 | 0.03 | 0.03 | 0.102 |  | 0.222
Citywide |  | 0.25 |  |  |  | 0 | 0 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.05 | 0 | 0.05 | 0.01 | 0.03 | 0.03 | 0.13 |  | 0.25
Home Improvement Agency |  | 0.5 |  |  |  | 0.015 | 0.025 | 0.025 | 0.025 | 0.04 | 0.05 | 0.05 | 0.23 | 0.128 | 0.102 | 0.05 | 0.05 | 0.05 | 0.12 |  | 0.5
Special Needs (Repairs Associated with DFG's) |  | 0.25 |  |  |  | 0.005 | 0.01 | 0.01 | 0.01 | 0.01 | 0.025 | 0.025 | 0.095 | 0.025 | 0.07 | 0.025 | 0.025 | 0.025 | 0.08 |  | 0.25
Local Authority SHG-Pendleway |  | 0.304 | [9 empty] | 0.304 | 0.304 | 0.608 | -0.304 | [5 empty] | 0.304
Local Authority SHG-King Edward St |  | 0.565 | [7 empty] | 0.565 |  |  | 0.565 | 1.13 | -0.565 | [5 empty] | 0.565
Local Authority SHG-2003/4new start |  | 0.131 | [10 empty] | 0 | 0 | 0 |  |  |  | 0.131 |  | 0.131
Broughton Inpartnership |  | 3.3 |  |  |  | 0.044 | 0.05 | 0.1 | 0.2 | 0.3 | 0.3 | 0.3 | 1.294 | 0.307 | 0.987 | 0.3 | 0.4 | 0.5 | 0.806 |  | 3.3
Broughton Grants(from 2/3) |  | 0.027 |  |  |  | 0.01 | 0 |  | 0.017 |  |  |  | 0.027 | 0.016 | 0.011 | [5 empty] | 0.027
Broughton Capital Works |  | 0 | [10 empty] | 0 | 0 | 0 | [5 empty] | 0
Broughton Grants (Owner-occ's) |  | 0 | [10 empty] | 0 | 0 | 0 | [5 empty] | 0
Broughton Grants (Empty prop's) |  | 0 | [10 empty] | 0 | 0 | 0 | [5 empty] | 0
Broughton (Gt Clowes St Block Treatment Ph 2) |  | 0 | [10 empty] | 0 | 0 | 0 | [5 empty] | 0
Claremont & Weaste |  | 1.55 |  |  |  | 0.022 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.1 | 0.172 | 0.068 | 0.104 | 0.2 | 0.3 | 0.4 | 0.478 |  | 1.55
Charlestown & Kersal NDC - Grants |  | 0.029 |  |  |  | 0.013 |  |  | 0.016 |  |  |  | 0.029 | 0.091 | -0.062 | [5 empty] | 0.029
Charlestown & Kersal NDC - Norfolk St |  | 0.066 |  |  |  | 0.047 | 0.019 | [5 empty] | 0.066 | 0.105 | -0.039 | [5 empty] | 0.066
Charlestown & Kersal NDC - major scheme preparation |  | 1.655 | [5 empty] | 0.005 | 0.005 | 0.005 | 0.005 | 0.005 | 0.025 | 0 | 0.025 | 0.01 | 0.01 | 0.01 | 1.6 |  | 1.655
Advance Fees |  | 0.1 |  |  |  |  | 0.005 | 0.005 | 0.005 | 0.005 | 0.005 | 0.005 | 0.03 | 0.004 | 0.026 | 0.01 | 0.01 | 0.025 | 0.025 |  | 0.1
RBI Individual Grants |  | 0.5 |  |  |  |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.04 | 0.04 | 0.16 | 0 | 0.16 | 0.04 | 0.06 | 0.1 | 0.14 |  | 0.5
Claremont/Weaste Grants (from 2/3) |  | 0.026 |  |  |  | 0.008 | 0.008 | 0.01 |  |  |  |  | 0.026 | 0.036 | -0.01 | [5 empty] | 0.026
Eccles SDA - Grants |  | 0.101 |  |  |  | 0.001 | 0.009 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.06 | 0.045 | 0.015 | 0.01 | 0.01 | 0.01 | 0.011 |  | 0.101
Slippage from 2002/03 |  | 0.172 |  |  | 0.172 | [7 empty] | 0.172 | 0.102 | 0.07 | [5 empty] | 0.172
|  | 10.748 |  |  | 0.172 | 0.18 | 0.191 | 0.265 | 0.388 | 1.085 | 0.565 | 0.959 | 3.805 | 3.013 | 0.792 | 0.765 | 1.025 | 1.33 | 3.823 |  | 10.748
Seedley & Langworthy
Acquisitions (04/05 Onwards Incl Homeswaps) |  | 1.3 |  |  |  | 0.15 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.75 | 0.578 | 0.172 | 0.1 | 0.1 | 0.1 | 0.25 |  | 1.3
DS Homeswaps in LN |  | 0.379 |  |  |  | 0.062 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 |  | 0.362 | 0 | 0.362 |  |  |  | 0.017 |  | 0.379
DS Phase 3 Homeswaps |  | 0 | [10 empty] | 0 | 0 | 0 | [5 empty] | 0
DS Seedley West Homeswaps |  | 0 | [10 empty] | 0 | 0 | 0 | [5 empty] | 0
Homeswaps |  | 0.45 |  |  |  | 0.042 |  | 0.002 | 0.03 | 0.04 | 0.04 | 0.04 | 0.194 | 0.729 | -0.535 | 0.06 | 0.06 | 0.06 | 0.076 |  | 0.45
Demolitions |  | 0.2 |  |  |  | 0.05 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.02 | 0.12 | 0.141 | -0.021 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.2
Environmental Works |  | 0.2 |  |  |  |  | 0.01 |  |  |  |  | 0.02 | 0.03 | 0.447 | -0.417 | 0.04 | 0.04 | 0.04 | 0.05 |  | 0.2
Shop Renovations Phase 1 |  | 0.95 |  |  |  | 0.002 |  | 0.028 | 0.03 | 0.05 | 0.07 | 0.1 | 0.28 | 0.04 | 0.24 | 0.1 | 0.12 | 0.2 | 0.25 |  | 0.95
Shop Renovations Phase 2 |  | 0 | [10 empty] | 0 | 0.018 | -0.018 | [5 empty] | 0
Buille Hill Area Group Scheme |  | 0.4 | [10 empty] | 0 | 0 | 0 | 0.03 | 0.07 | 0.1 | 0.2 |  | 0.4
Langworthy North Phase 3 |  | 1.4 |  |  |  | 0.077 | 0.15 | 0.15 | 0.2 | 0.2 | 0.15 | 0.15 | 1.077 | 0.519 | 0.558 | 0.15 | 0.15 |  | 0.023 |  | 1.4
Langworthy North Retention |  | 0.052 |  |  |  | 0.003 |  |  | 0.049 |  |  |  | 0.052 | 0.003 | 0.049 | [5 empty] | 0.052
Langworthy North Phase 4 |  | 0.791 |  |  |  |  | 0.011 | 0.02 | 0.05 | 0.1 | 0.1 | 0.1 | 0.381 | 0.31 | 0.071 | 0.1 | 0.1 | 0.1 | 0.11 |  | 0.791
Individual Improvement |  | 0.25 | [9 empty] | 0.02 | 0.02 | 0.091 | -0.071 | 0.03 | 0.05 | 0.05 | 0.1 |  | 0.25
West of Seedley Park Road |  | 0.3 | [9 empty] | 0.05 | 0.05 | 0 | 0.05 | 0.05 | 0.05 | 0.05 | 0.1 |  | 0.3
Seedley West Remodelling |  | 0.598 | [7 empty] | 0.048 | 0.08 | 0.08 | 0.208 | 0.309 | -0.101 | 0.09 | 0.1 | 0.1 | 0.1 |  | 0.598
Seedley South Remodelling |  | 0.03 | [10 empty] | 0 | 0 | 0 |  |  |  | 0.03 |  | 0.03
Marketing / Developing Gap Funding |  | 0.1 | [10 empty] | 0 | 0 | 0 |  |  |  | 0.1 |  | 0.1
Slippage from 2002/03 |  | 0.054 | [10 empty] | 0 | 0 | 0 |  |  |  | 0.054 |  | 0.054
|  | -0.226 | [10 empty] | 0 | 0 | 0 | [5 empty] | -0.226
|  | 7.228 |  |  | 0 | 0.386 | 0.341 | 0.37 | 0.529 | 0.608 | 0.61 | 0.68 | 3.524 | 3.185 | 0.339 | 0.77 | 0.86 | 0.82 | 1.48 |  | 7.228
Total Private Sector |  | 17.976 |  |  | 0.172 | 0.566 | 0.532 | 0.635 | 0.917 | 1.693 | 1.175 | 1.639 | 5.69 | 6.198 | 1.131 | 1.535 | 1.885 | 2.15 | 5.303 |  | 17.976
Public Sector
MRA Funded
Support of SRB 2 |  | 3.157
Support of SRB 3 |  | 0
Retentions |  | 1.255
2002/03 Commitments |  | 2.091
Public Sector Residents - Specific Adaptations |  | 1
Programmed Works |  | 6.201
Demolitions |  | 0.989
Burglary Reduction |  | 0.5
New Deal for Communities |  | 2.965
Fees - Future Programme Preparation |  | 0.15
Environmental Improvements |  | 1.25
Slippage from 2002/03 |  | 3.005
ALMO Funded
Decent Homes |  | 0.232
-1.244
Total Public Sector |  | 21.551 |  |  | 3.059 | 1.776 | 1.16 | 1.175 | 1.175 | 1.225 | 1.225 | 1.375 | 10.795 | 8.185 | 2.61 | 1.415 | 1.765 | 2.382 | 5.194 |  | 21.551
HOUSING TOTAL |  | 39.527 |  |  | 3.231 | 2.342 | 1.692 | 1.81 | 2.092 | 2.918 | 2.4 | 3.014 | 16.485 | 14.383 | 3.741 | 2.95 | 3.65 | 4.532 | 10.497 |  | 39.527
EDUCATION
Commitments
New Deal fpr Schools 4 |  | 0.123 |  |  | 0.053 |  |  |  |  | 0.07 |  |  | 0.123 | 0.158 | -0.035 | [5 empty] | 0.123
New Deal Condition / Modernisation |  | 4.713 |  |  |  | 0.039 | 0.384 | 0.384 | 0.384 | 0.384 | 0.384 | 0.384 | 2.343 | 1.799 | 0.544 | 0.384 | 0.384 | 0.384 | 1.218 |  | 4.713
Devolved Capital Formula |  | 2.26 |  |  |  | 0.094 | 0.216 | 0.216 | 0.216 | 0.216 | 0.216 | 0.216 | 1.39 | 0.901 | 0.489 | 0.216 | 0.216 | 0.216 | 0.222 |  | 2.26
Seed Challenge |  | 0.494 |  |  |  | 0.027 | 0.026 | 0.026 | 0.086 | 0.047 | 0.047 | 0.047 | 0.306 | 0.208 | 0.098 | 0.047 | 0.047 | 0.047 | 0.047 |  | 0.494
The Albion |  | 3.033 |  |  | 0.6 | 0.6 | 0.6 | 0.6 | 0.278 |  |  |  | 2.678 | 2.533 | 0.145 |  |  |  | 0.355 |  | 3.033
Schools Access Initiative |  | 0.35 |  |  |  | 0.005 | 0.036 | 0.034 | 0.034 | 0.034 | 0.034 | 0.034 | 0.211 | 0.032 | 0.179 | 0.034 | 0.034 | 0.034 | 0.037 |  | 0.35
Capitalised Salaries |  | 0.087 |  |  | 0.007 | 0.007 | 0.007 | 0.007 | 0.007 | 0.007 | 0.007 | 0.007 | 0.056 | 0.049 | 0.007 | 0.007 | 0.007 | 0.007 | 0.01 |  | 0.087
Beacon Resource Centre |  | 1.461 |  |  |  |  | 0.139 | 0.223 | 0.089 | 0.185 | 0.15 | 0.11 | 0.896 | 0.526 | 0.37 | 0.13 | 0.225 | 0.155 | 0.055 |  | 1.461
PFI Consultancy |  | 0.083 |  |  | 0.083 | [7 empty] | 0.083 | 0.097 | -0.014 | [5 empty] | 0.083
Springwood |  | 0.071 |  |  | 0.071 | [7 empty] | 0.071 | 0.002 | 0.069 | [5 empty] | 0.071
Wentworth High School |  | 0.037 |  |  |  | 0.001 | 0.004 | 0.005 | 0.005 | 0.005 | 0.005 | 0.005 | 0.03 | 0.01 | 0.02 | 0.007 |  |  |  |  | 0.037
Class Size Reduction - St Andrews |  | 0.008 |  |  | 0.008 | [7 empty] | 0.008 | 0.001 | 0.007 | [5 empty] | 0.008
Broadwalk PRU |  | 0.01 | [7 empty] | 0.01 |  |  | 0.01 | 0.026 | -0.016 | [5 empty] | 0.01
VA Minor Works |  | 0.065 |  |  | 0.065 | [7 empty] | 0.065 | 0.06 | 0.005 | [5 empty] | 0.065
Proposals
ACG Minor Works |  | 0.091 |  |  |  |  | 0.006 | 0.014 | 0.014 | 0.008 | 0.008 | 0.008 | 0.058 | 0.019 | 0.039 | 0.008 | 0.008 | 0.008 | 0.009 |  | 0.091
Staff Workspaces |  | 0.124 |  |  |  |  | 0.012 | 0.012 | 0.012 | 0.012 | 0.012 | 0.012 | 0.072 | 0.001 | 0.071 | 0.012 | 0.012 | 0.012 | 0.016 |  | 0.124
Nursery's In Disadvantaged Ares |  | 0.373 |  |  |  |  | 0.037 | 0.037 | 0.037 | 0.037 | 0.037 | 0.037 | 0.222 | 0 | 0.222 | 0.037 | 0.037 | 0.037 | 0.04 |  | 0.373
Review Surplus Places (Expansion Popular Schools) |  | 0.154 |  |  |  |  | 0.015 | 0.015 | 0.015 | 0.015 | 0.015 | 0.015 | 0.09 | 0 | 0.09 | 0.015 | 0.015 | 0.015 | 0.019 |  | 0.154
Pathfinder Scheme - Standards Fund |  | 0.053 | [6 empty] | 0.051 |  |  |  | 0.051 | 0.051 | 0 |  |  |  | 0.002 |  | 0.053
Adult & Community Education |  | 0.137 | [6 empty] | 0.014 |  |  |  | 0.014 | 0.014 | 0 |  |  |  | 0.123 |  | 0.137
Hope/Buile/Harrop fold interrim works/pfi fees |  | 0.5 | [6 empty] | 0.256 | 0.008 | 0 | 0.034 | 0.298 |  | 0.298 | 0.034 | 0.034 | 0.034 | 0.1 |  | 0.5
EDUCATION - TOTAL |  | 14.227 |  |  | 0.887 | 0.773 | 1.482 | 1.573 | 1.498 | 1.038 | 0.915 | 0.909 | 9.075 | 6.487 | 2.588 | 0.931 | 1.019 | 0.949 | 2.253 |  | 14.227
HIGHWAYS
Proposals
Cadishead Way Stage 1 | D00003 | 0.075 | [7 empty] | 0.075 |  |  | 0.075 | 0 | 0.075 | [5 empty] | 0.075
Cadishead Way | D00004 | 9.05 | 2004-01-01 | 2005-10-01 |  |  |  | 0.13 | 0.225 |  |  |  | 0.355 | 0.506 | -0.151 |  | 1.5 | 1.5 | 5.695 |  | 9.05
Local Safety schemes |  | 0.84 |  |  | 0.105 | 0.04 | 0.04 | 0.015 | 0.016 | 0.028 | 0.028 | 0.077 | 0.349 | 0.221 | 0.139 | 0.104 | 0.104 | 0.137 | 0.146 |  | 0.84
Anti Skid Surfacing Programme | D00101 | 0.05 | 2003-04-01 | 2004-03-01 | [5 empty] | 0.007 | 0.007 | 0.007 | 0.021 | 0 | 0.021 | 0.007 | 0.007 | 0.007 | 0.008 |  | 0.05
Accident Investigation | D00103 | 0.014 | 2003-04-01 | 2004-03-01 | [5 empty] | 0.002 | 0.002 | 0.002 | 0.006 | 0 | 0.006 | 0.002 | 0.002 | 0.002 | 0.002 |  | 0.014
White Lining | D00104 | 0.008 | 2003-04-01 | 2004-03-01 | [5 empty] | 0.001 | 0.001 | 0.001 | 0.003 | 0 | 0.003 | 0.001 | 0.001 | 0.001 | 0.002 |  | 0.008
20mph Zone-Westwood Park, Winton | D00111 | 0.06 | 2002-03-01 | 2003-07-01 | 0.015 | 0.015 | 0.015 | 0.015 |  |  |  |  | 0.06 | 0.059 | 0.001 | [5 empty] | 0.06
A6 High St Pedestrian Facilities | D00121 | 0.11 | 2003-11-01 | 2004-03-01 | [8 empty] | 0 | 0 | 0 | 0.027 | 0.027 | 0.027 | 0.029 |  | 0.11
Broughton Park Area scheme | D00132 | 0.05 | 2001-12-01 | 2003-04-01 | 0.05 | [7 empty] | 0.05 | 0.041 | 0.009 | [5 empty] | 0.05
East Lancs Moorside Rd (Speed Cameras) | D00133 | 0.003 | 2002-12-01 | 2003-03-01 | 0.003 | [7 empty] | 0.003 | 0.001 | 0.002 | [5 empty] | 0.003
Pendleton Round-a-bout | D00135 | 0.023 | 2004-01-01 | 2004-03-01 | [8 empty] | 0 |  |  |  |  | 0.011 | 0.012 |  | 0.023
Hilton Lane Traffic Calming | D00139 | 0.001 | 2002-02-01 | 2002-04-01 | 0.001 | [7 empty] | 0.001 | 0 | 0.001 | [5 empty] | 0.001
Cadishead NW area safety scheme | D00143 | 0.245 | 2003-10-01 | 2004-03-01 |  |  |  |  | 0.01 |  |  | 0.049 | 0.059 | 0.014 | 0.045 | 0.049 | 0.049 | 0.049 | 0.039 |  | 0.245
A576 Cromwell Rd/Littleton Rd | D00144 | 0.02 | 2004-01-01 | 2004-03-01 | [8 empty] | 0 |  |  |  |  | 0.01 | 0.01 |  | 0.02
A5185 Lancaster Rd/Swinton Park Rd | D00145 | 0.001 | 2003-01-01 | 2003-03-01 | 0.001 | [7 empty] | 0.001 | 0 | 0.001 | [5 empty] | 0.001
A576 Eccles Old Rd/A5185 Lancaster Rd | D00146 | 0.025 | 2004-01-01 | 2004-03-01 | [8 empty] | 0 | 0 | 0 |  |  | 0.012 | 0.013 |  | 0.025
Littleton Rd pedestrian safety | D00149 | 0.01 | 2002-03-01 | 2003-03-01 | 0.01 | [7 empty] | 0.01 | 0 | 0.01 | [5 empty] | 0.01
A57 Peel Green Roundabout | D00151 | 0.005 | 2004-02-01 | 2005-03-01 | [8 empty] | 0 | 0.001 | -0.001 |  |  |  | 0.005 |  | 0.005
Cantebury Gardens - Traffic Calming | D00170 | 0.075 | 2003-01-01 | 2003-07-01 | 0.025 | 0.025 | 0.025 | [5 empty] | 0.075 | 0.088 | -0.013 | [5 empty] | 0.075
Camera Site Speed Surveys | D00171 | 0.08 | 2003-04-01 | 2004-03-01 |  |  |  |  | 0.006 | 0.01 | 0.01 | 0.01 | 0.036 | 0.006 | 0.03 | 0.01 | 0.01 | 0.01 | 0.014 |  | 0.08
Kersal Area Traffic Calming | D00172 | 0.06 | 2003-03-01 | 2004-03-01 | [5 empty] | 0.008 | 0.008 | 0.008 | 0.024 | 0 | 0.024 | 0.008 | 0.008 | 0.008 | 0.012 |  | 0.06
[13 empty] | 0 | [7 empty] | 0
[13 empty] | 0 | [7 empty] | 0
Bridge Assessment and Strengthening Schemes |  | 0.676 |  |  | 0.016 | 0 | 0 | 0 | 0.009 | 0.054 | 0.066 | 0.095 | 0.24 | 0.185 | 0.185 | 0.095 | 0.095 | 0.119 | 0.127 |  | 0.676
Bridge Inspections and Assessments | D00500 | 0.06 | 2003-04-01 | 2004-03-01 | [5 empty] | 0.008 | 0.008 | 0.008 | 0.024 | 0 | 0.024 | 0.008 | 0.008 | 0.008 | 0.012 |  | 0.06
Bridges General | D00501 | 0.01 | 2003-04-01 | 2004-03-01 |  |  |  |  | 0.006 | 0.004 |  |  | 0.01 | 0.041 | -0.031 | [5 empty] | 0.01
Subways | D00503 | 0.005 | 2003-04-01 | 2004-03-01 | [5 empty] | 0.001 | 0.001 | 0.001 | 0.003 | 0 | 0.003 | 0.001 | 0.001 |  |  |  | 0.005
Agecroft Road Railway Bridge | D00504 | 0.005 | 2002-03-01 | 2002-09-01 | 0.005 | [7 empty] | 0.005 | 0 | 0.005 | [5 empty] | 0.005
Eccles Old Rd Underpass | D00512 | 0.1 | 2004-01-01 | 2004-03-01 | [8 empty] | 0 | 0 | 0 |  |  | 0.05 | 0.05 |  | 0.1
East Lancs Rd/ Eccles Rd Footbridge | D00514 | 0.03 | 2003-08-01 | 2003-09-01 | [5 empty] | 0.015 | 0.015 |  | 0.03 | 0 | 0.03 | [5 empty] | 0.03
Palatine Bridge | D00517 | 0.005 | 2001-11-01 | 2002-02-01 | 0.005 | [7 empty] | 0.005 | 0.005 | 0 | [5 empty] | 0.005
Waterloo Bridge | D00518 | 0.006 | 2002-01-01 | 2002-05-01 | 0.006 | [7 empty] | 0.006 | 0.006 | 0 | [5 empty] | 0.006
Carlton Footbridge | D00520 | 0.125 | 2003-08-01 | 2003-12-01 | [5 empty] | 0.025 | 0.025 | 0.025 | 0.075 | 0 | 0.075 | 0.025 | 0.025 |  |  |  | 0.125
Pendleton Roundabout Parapets | D00524 | 0.1 | 2003-09-01 | 2004-02-01 |  |  |  |  | 0.003 |  | 0.016 | 0.016 | 0.035 | 0.003 | 0.032 | 0.016 | 0.016 | 0.016 | 0.017 |  | 0.1
Railway Incursion Works | D00525 | 0.12 | 2003-10-01 | 2005-03-01 | [7 empty] | 0.024 | 0.024 | 0 | 0.024 | 0.024 | 0.024 | 0.024 | 0.024 |  | 0.12
Culvert Safety Improvement Programme | D00527 | 0.01 | 2003-04-01 | 2005-03-01 | [5 empty] | 0.001 | 0.001 | 0.001 | 0.003 | 0 | 0.003 | 0.001 | 0.001 | 0.001 | 0.004 |  | 0.01
Wallness Bridge | D00528 | 0.1 | 2003-10-01 | 2004-03-01 | [7 empty] | 0.02 | 0.02 | 0 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | 0.1
[13 empty] | 0 | [7 empty] | 0
Principal Roads Structural Maintenance |  | 2.028 |  |  | 0.042 | 0 | 0.053 | 0.113 | 0.015 | 0.22 | 0.22 | 0.374 | 1.037 | 0.879 | 0.315 | 0.372 | 0.156 | 0.231 | 0.232 |  | 2.028
A6 Chapel Street (Adelpi St-Trinity Way) | D00602 | 0.022 | 2001-01-01 | 2002-04-01 | 0.022 | [7 empty] | 0.022 | 0.037 | -0.015 | [5 empty] | 0.022
Deflectograph Surveys | D00605 | 0.02 | 2003-08-01 | 2003-12-01 |  |  |  |  | 0.01 | 0.003 | 0.003 | 0.003 | 0.019 | 0.01 | 0.009 | 0.001 |  |  |  |  | 0.02
Principal Rd Structural Maintenance | D00608 | 0.015 | 2003-04-01 | 2004-03-01 | [5 empty] | 0.002 | 0.002 | 0.002 | 0.006 | 0 | 0.006 | 0.002 | 0.002 | 0.002 | 0.003 |  | 0.015
A575 Walkden Rd (M/cr Rd-Park Rd) | D00610 | 0.15 | 2004-01-01 | 2004-03-01 | [8 empty] | 0 |  |  |  |  | 0.075 | 0.075 |  | 0.15
A576 Cromwell Rd (Lissadel St-Lwr Broug) | D00611 | 0.02 | 2002-02-01 | 2002-06-01 | 0.02 | [7 empty] | 0.02 | 0.004 | 0.016 | [5 empty] | 0.02
A6 Manchester Rd (Bolton Rd -Smithfold) | D00612 | 0.605 | 2003-01-01 | 2003-08-01 |  |  | 0.053 | 0.113 | 0.002 | 0.109 | 0.109 | 0.109 | 0.495 | 0.363 | 0.132 | 0.11 |  |  |  |  | 0.605
A5082 Armitage Av (M/cr Rd-Boundary) | D00613 | 0.426 | 2003-01-01 | 2003-07-01 |  |  |  |  | 0.003 | 0.106 | 0.106 | 0.106 | 0.321 | 0.308 | 0.013 | 0.105 |  |  |  |  | 0.426
Structural Maintenance of Minor Rds | D00614 | 0.5 | 2003-10-01 | 2004-03-01 | [7 empty] | 0.1 | 0.1 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 |  | 0.5
A56 Bury New Rd Boundary to Moor Lane | D00616 | 0.27 | 2003-10-01 | 2004-03-01 | [7 empty] | 0.054 | 0.054 | 0 | 0.054 | 0.054 | 0.054 | 0.054 | 0.054 |  | 0.27
[13 empty] | 0 | [7 empty] | 0
Public Transport Schemes |  | 0.465 |  |  | 0 | 0 | 0 | 0 | 0.004 | 0.03 | 0.03 | 0.091 | 0.155 | 0.025 | 0.147 | 0.093 | 0.091 | 0.063 | 0.063 |  | 0.465
A56 Quality Bus Corridor | D00703 | 0.315 | 2003-11-01 | 2004-06-01 |  |  |  |  | 0.002 |  |  | 0.061 | 0.063 | 0.003 | 0.06 | 0.063 | 0.063 | 0.063 | 0.063 |  | 0.315
Blackfriars Street Improvements | D00707 | 0.15 | 2003-08-01 | 2003-12-01 |  |  |  |  | 0.002 | 0.03 | 0.03 | 0.03 | 0.092 | 0.005 | 0.087 | 0.03 | 0.028 |  |  |  | 0.15
[13 empty] | 0 | [7 empty] | 0
Schemes to Assist Cycling |  | 0.16 |  |  | 0 | 0 | 0 | 0 | 0.002 | 0 | 0 | 0.012 | 0.014 | 0.002 | 0.012 | 0.012 | 0.012 | 0.062 | 0.06 |  | 0.16
A666 Cycling Facilities | D00802 | 0.1 | 2004-01-01 | 2004-04-01 |  |  |  |  | 0.002 |  |  |  | 0.002 | 0.002 | 0 |  |  | 0.05 | 0.048 |  | 0.1
Cycle Parking Facilities | D00805 | 0.06 | 2003-11-01 | 2004-03-01 | [7 empty] | 0.012 | 0.012 | 0 | 0.012 | 0.012 | 0.012 | 0.012 | 0.012 |  | 0.06
[13 empty] | 0 | [7 empty] | 0
Other Minor Schemes |  | 0.313 |  |  | 0.014 | 0.005 | 0.005 | 0.005 | 0.016 | 0.037 | 0.037 | 0.037 | 0.156 | 0.094 | 0.098 | 0.032 | 0.041 | 0.042 | 0.042 |  | 0.313
GM Local Transport Plan | D00901 | 0.04 | 1999-04-01 | 2005-03-01 | 0.005 | 0.005 | 0.005 | 0.005 | 0.005 | 0.005 | 0.005 | 0.005 | 0.04 | 0.029 | 0.011 | [5 empty] | 0.13
Salford's Green transport Plan | D00902 | 0.025 | 1999-07-01 | 2005-03-01 | [5 empty] | 0.003 | 0.003 | 0.003 | 0.009 | 0 | 0.009 | 0.003 | 0.003 | 0.003 | 0.007 |  | 0.049
Demand Management Measures | D00905 | 0.004 | 2000-04-01 | 2002-03-01 | 0.004 | [7 empty] | 0.004 | 0.004 | 0 | [5 empty] | 0.012
AGMA Countywide Advertising | D00909 | 0.005 | 2000-04-01 | 2003-03-01 | 0.005 | [7 empty] | 0.005 | 0.005 | 0 | [5 empty] | 0.015
Disabled Facilities at Ped. Crossings | D00912 | 0.075 | 2003-04-01 | 2004-03-01 |  |  |  |  | 0.003 | 0.01 | 0.01 | 0.01 | 0.033 | 0.008 | 0.025 | 0.01 | 0.01 | 0.01 | 0.012 |  | 0.161
Chapel St Pedestrian Route Improvements | D00918 | 0.03 | 2004-01-01 | 2004-09-01 |  |  |  |  | 0.001 |  |  |  | 0.001 | 0.001 | 0 |  | 0.009 | 0.01 | 0.01 |  | 0.032
Little Moss Lane | D00923 | 0.134 | 2003-09-01 | 2004-01-01 |  |  |  |  | 0.007 | 0.019 | 0.019 | 0.019 | 0.064 | 0.011 | 0.053 | 0.019 | 0.019 | 0.019 | 0.013 |  | 0.3
[13 empty] | 0 | [7 empty] | 0
Over-programme |  | -0.406 | [10 empty] | 0 | 0 | 0 |  |  |  | -0.406 |  | -0.406
Commitments
Manchester / Salford Inner relief Road | D00005 | 8.16 | 2001-02-01 | 2004-08-01 |  | 0.055 | 0.68 | 0.435 | 0 | 1 | 1 | 1 | 4.17 | 1.542 | 2.628 | 1 | 1 | 1 | 0.99 |  | 8.16
Trafford Rd | D00002 | 0.002 | [6 empty] | 0.002 |  |  |  | 0.002 | 0.003 | -0.001 | [5 empty] | 0.002
HIGHWAYS - TOTAL |  | 21.363 |  |  | 0.177 | 0.1 | 0.778 | 0.698 | 0.289 | 1.444 | 1.381 | 1.686 | 6.553 | 3.457 | 3.447 | 1.708 | 2.999 | 3.154 | 6.949 |  | 21.363
SOCIAL SERVICES
Proposals
Improving Information Mgt 2002/03 |  | 0.072 |  |  | 0.005 | 0.005 | 0.005 | 0.005 | 0.005 | 0.007 | 0.007 | 0.007 | 0.046 | 0.036 | 0.01 | 0.007 | 0.007 | 0.007 | 0.005 |  | 0.072
Modernising ICT Infrastructure |  | 0.151 |  |  | 0.008 | 0.008 | 0.008 | 0.008 | 0.008 | 0.016 | 0.016 | 0.016 | 0.088 | 0.148 | -0.06 | 0.016 | 0.016 | 0.016 | 0.015 |  | 0.151
Mental Health SCA 2002 / 2005 |  | 0.179 |  |  |  | 0.079 | 0.016 | [5 empty] | 0.095 | 0.029 | 0.066 |  |  |  | 0.084 |  | 0.179
Children's Homes - Safety Issues |  | 0.075 | [5 empty] | 0.025 | 0.025 | 0.025 |  |  | 0.075 | 0.017 | 0.058 | [5 empty] | 0.075
Replacement Lift at The Limes |  | 0.04 | [10 empty] | 0 | 0 | 0 |  |  |  | 0.04 |  | 0.04
Brierley House DC - Re-model Toilet/Bathroom Area |  | 0.037 | [10 empty] | 0 | 0 | 0 |  |  |  | 0.037 |  | 0.037
Alexandra House DC - Re-model Toilet/Bathroom Area |  | 0.047 | [10 empty] | 0 | 0 | 0 |  |  |  | 0.047 |  | 0.047
Craig Hall DC Re-roofing |  | 0.056 | [5 empty] | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.03 | 0 | 0.03 | 0.006 | 0.006 | 0.006 | 0.008 |  | 0.056
Waterside Resource Centre Partial Re-roofing |  | 0.035 | [5 empty] | 0.004 | 0.004 | 0.004 | 0.004 | 0.004 | 0.02 | 0 | 0.02 | 0.004 | 0.004 | 0.004 | 0.003 |  | 0.035
Cleveland House - Dry Lining of Basement |  | 0.025 | [5 empty] | 0.013 | 0.012 |  |  |  | 0.025 | 0 | 0.025 | [5 empty] | 0.025
West Dene Partial Re-roofing |  | 0.008 | [6 empty] | 0.004 | 0.004 |  |  | 0.008 | 0 | 0.008 | [5 empty] | 0.008
Boothstown / Worsley Community Centres Refurbishment |  | 0.04 | [8 empty] | 0.007 | 0.007 | 0.014 | 0 | 0.014 | 0.007 | 0.007 | 0.007 | 0.005 |  | 0.04
I.T. for Looked After Children |  | 0.053 | [5 empty] | 0.006 | 0.006 | 0.006 | 0.006 | 0.006 | 0.03 | 0 | 0.03 | 0.006 | 0.006 | 0.006 | 0.005 |  | 0.053
Refurbishment of Unwin Court |  | 0.001 |  |  | 0.001 | [7 empty] | 0.001 | 0.002 | -0.001 | [5 empty] | 0.001
The Withies |  | 0.049 |  |  | 0.049 | [7 empty] | 0.049 | 0.096 | -0.047 | [5 empty] | 0.049
Brynheys |  | 0.013 |  |  | 0.013 | [7 empty] | 0.013 | 0.02 | -0.007 | [5 empty] | 0.013
Demolition of Homes |  | 0.075 | [6 empty] | 0.037 | 0.038 |  |  | 0.075 | 0.09 | -0.015 | [5 empty] | 0.075
Re-modelling of Crompton House Reception |  | 0.025 | [7 empty] | 0.025 |  |  | 0.025 | 0 | 0.025 | [5 empty] | 0.025
SOCIAL SERVICES -TOTAL |  | 0.981 |  |  | 0.076 | 0.092 | 0.029 | 0.067 | 0.107 | 0.131 | 0.046 | 0.046 | 0.594 | 0.438 | 0.156 | 0.046 | 0.046 | 0.046 | 0.249 |  | 0.981
ENVIRONMENTAL SERVICES
Proposals
Lord Street Acid Tar |  | 0.003 |  |  | 0.003 | [7 empty] | 0.003 | 0.003 | 0 | [5 empty] | 0.003
Air Pollution Monitoring |  | 0.02 |  |  | 0.004 | 0.004 | 0.004 | 0.004 | 0.004 |  |  |  | 0.02 | 0.014 | 0.006 | [5 empty] | 0.02
Headstones and Roadway Works - Cemeteries |  | 0.105 |  |  |  |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.06 | 0.014 | 0.046 | 0.01 | 0.01 | 0.01 | 0.015 |  | 0.105
Buille Hill Park Restoration |  | 0.1 |  |  |  |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.06 | 0.005 | 0.055 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.1
DEFRA Waste Minimisation |  | 0.016 |  |  | 0.016 | [7 empty] | 0.016 | 0 | 0.016 | [5 empty] | 0.016
Outdoor Services - Plant Acquisition |  | 0.003 |  |  | 0.003 | [7 empty] | 0.003 | 0 | 0.003 | [5 empty] | 0.003
Fuel Island |  | 0.003 |  |  | 0.003 | [7 empty] | 0.003 | 0.008 | -0.005 | [5 empty] | 0.003
ENVIRONMENTAL SERVICES TOTAL |  | 0.25 |  |  | 0.029 | 0.004 | 0.024 | 0.024 | 0.024 | 0.02 | 0.02 | 0.02 | 0.165 | 0.044 | 0.121 | 0.02 | 0.02 | 0.02 | 0.025 | 0 | 0.25
CHIEF EXECUTIVE
Business Security Grants |  | 0.007 |  |  | 0.007 | [7 empty] | 0.007 | 0.014 | -0.007 | [5 empty] | 0.007
CCTV in New Deal Area |  | 0.34 |  |  |  |  | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 | 0.192 | 0.014 | 0.178 | 0.032 | 0.032 | 0.032 | 0.052 |  | 0.34
Site Assembly / Acquisition Temp Treatment Works |  | 0.28 |  |  |  |  | 0.07 | 0.023 | 0.023 | 0.023 | 0.023 | 0.023 | 0.185 | 0.002 | 0.183 | 0.023 | 0.023 | 0.023 | 0.026 |  | 0.28
Gateway |  | 0.105 |  |  |  |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.06 | 0 | 0.06 | 0.01 | 0.01 | 0.01 | 0.015 |  | 0.105
Highway and Community Safety |  | 0.141 |  |  |  |  | 0.012 | 0.012 | 0.012 | 0.012 | 0.012 | 0.012 | 0.072 | 0.018 | 0.054 | 0.012 | 0.012 | 0.012 | 0.033 |  | 0.141
Play Facilities |  | 0.115 |  |  |  | 0.012 | 0.011 | 0.011 | 0.011 | 0.01 | 0.01 | 0.01 | 0.075 | 0 | 0.075 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.115
Environmental / Shop Front Improvements |  | 0.052 |  |  |  |  | 0.005 | 0.005 | 0.005 | 0.005 | 0.005 | 0.005 | 0.03 | 0 | 0.03 | 0.005 | 0.005 | 0.005 | 0.007 |  | 0.052
Community Mini-Bus |  | 0.006 |  |  |  |  | 0.006 | [5 empty] | 0.006 | 0 | 0.006 | [5 empty] | 0.006
Minor Works Fund |  | 0.01 |  |  |  |  | 0.01 | [5 empty] | 0.01 | 0 | 0.01 | [5 empty] | 0.01
Public Transport Measures |  | 0.1 |  |  |  |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.06 | 0 | 0.06 | 0.01 | 0.01 | 0.01 | 0.01 |  | 0.1
Reclamation of Derelict Land |  | 0.292 |  |  |  |  | 0.029 | 0.029 | 0.029 | 0.029 | 0.029 | 0.029 | 0.174 | 0 | 0.174 | 0.029 | 0.029 | 0.029 | 0.031 |  | 0.292
Youth Shelters |  | 0.054 |  |  |  |  | 0.005 | 0.005 | 0.005 | 0.005 | 0.005 | 0.005 | 0.03 | 0 | 0.03 | 0.005 | 0.005 | 0.005 | 0.009 |  | 0.054
Expanding Boundaries |  | 0.518 |  |  |  |  | 0.052 | 0.052 | 0.052 | 0.052 | 0.052 | 0.052 | 0.312 | 0.109 | 0.203 | 0.052 | 0.052 | 0.052 | 0.05 |  | 0.518
Home Office CCTV |  | 0.302 |  |  | 0.302 | [7 empty] | 0.302 | 0.383 | -0.081 | [5 empty] | 0.302
CHIEF EXECUTIVE TOTAL |  | 2.322 |  |  | 0.309 | 0.012 | 0.252 | 0.189 | 0.189 | 0.188 | 0.188 | 0.188 | 1.515 | 0.54 | 0.975 | 0.188 | 0.188 | 0.188 | 0.243 |  | 2.322
ARTS & LEISURE
Committed
Leisure Trust / PPP |  | 0.106 |  |  | 0.005 | 0.005 | 0.01 | 0.02 | 0.02 | 0.03 | 0.016 |  | 0.106 | 0.109 | -0.003 | [5 empty] | 0.106
Library Service - Computerisation |  | 0.045 |  |  | 0.037 | 0.003 | 0.003 | 0.002 |  |  |  |  | 0.045 | 0.055 | -0.01 | [5 empty] | 0.045
Peoples Network |  | 0.042 |  |  | 0.042 | [7 empty] | 0.042 | 0 | 0.042 | [5 empty] | 0.042
SPACE for Sports and Arts
Marlborough |  | 0.304 |  |  | 0.079 | 0.105 | 0.11 |  |  | 0.01 |  |  | 0.304 | 0.292 | 0.012 | [5 empty] | 0.304
Moorfield |  | 0.437 |  |  | 0.082 | 0.083 | 0.083 | 0.083 | 0.081 |  |  |  | 0.412 | 0.408 | 0.004 | 0.025 |  |  |  |  | 0.437
St Peter's |  | 0.438 |  |  | 0.064 | 0.117 | 0.117 | 0.118 |  |  | 0.022 |  | 0.438 | 0.378 | 0.06 | [5 empty] | 0.438
Dukesgate |  | 0.577 |  |  | 0.048 | 0.1 | 0.1 | 0.06 | 0.06 | 0.064 |  |  | 0.432 | 0.464 | -0.032 | 0.145 |  |  |  |  | 0.577
Fit City Signage |  | 0.005 | [6 empty] | 0.005 |  |  |  | 0.005 | 0 | 0.005 | [5 empty] | 0.005
Cleavley Playing Fields |  | 0.073 | [7 empty] | 0.016 | 0.035 | 0.018 | 0.069 | 0.049 | 0.02 | 0.004 |  |  |  |  | 0.073
ARTS & LEISURE - TOTAL |  | 2.027 |  |  | 0.357 | 0.413 | 0.423 | 0.283 | 0.166 | 0.12 | 0.073 | 0.018 | 1.853 | 1.755 | 0.098 | 0.174 | 0 | 0 | 0 |  | 2.027
DEVELOPMENT SERVICES
Committed
Eccles Town Centre |  | 0.868 |  |  | 0.868 | [7 empty] | 0.868 | 0.222 | 0.646 | [5 empty] | 0.868
Chapel St |  | 0.057 |  |  | 0.057 | [7 empty] | 0.057 | 0.017 | 0.04 | [5 empty] | 0.057
Countryside Programme |  | 0.01 |  |  | 0.01 | [7 empty] | 0.01 | 0 | 0.01 | [5 empty] | 0.01
Barton SES |  | 0.004 |  |  | 0.004 | [7 empty] | 0.004 | 0.004 | 0 | [5 empty] | 0.004
Eccles Town Hall Auditorium |  | 0.024 |  |  | 0.024 | [7 empty] | 0.024 | 0 | 0.024 | [5 empty] | 0.024
NWDA Headroom schemes |  | 0.161 |  |  | 0.161 | [7 empty] | 0.161 | 0.154 | 0.007 | [5 empty] | 0.161
SRB 2 |  | 0.008 |  |  | 0.008 | [7 empty] | 0.008 | 0.004 | 0.004 | [5 empty] | 0.008
Slackbrook - Security Measures / Improvements |  | 0.063 | [5 empty] | 0.007 | 0.024 | 0.019 | 0.013 |  | 0.063 | 0 | 0.063 | [5 empty] | 0.063
Digital World |  | 1.3 | [6 empty] | 0.334 |  | 0.5 |  | 0.834 | 1.022 | -0.188 |  |  |  | 0.466 |  | 1.3
Proposals
Ordsall Neighbourhood Office Phase 1 |  | 0.082 | [7 empty] | 0.082 |  |  | 0.082 | 0 | 0.082 | [5 empty] | 0.082
Ordsall Neighbourhood Office Phase 2 |  | 0.366 |  |  |  |  | 0.067 | 0.067 | 0.067 | 0.067 | 0.066 | 0.032 | 0.366 | 0.005 | 0.361 | [5 empty] | 0.366
LIVIA Programme Year 3 - Match Funding |  | 0.02 | [8 empty] | 0.011 | 0.009 | 0.02 | 0.007 | 0.013 | [5 empty] | 0.02
DEVELOPMENT SERVICES - TOTAL |  | 2.963 |  |  | 1.132 | 0 | 0.067 | 0.074 | 0.425 | 0.168 | 0.59 | 0.041 | 2.497 | 1.435 | 1.062 | 0 | 0 | 0 | 0.466 |  | 2.963
CORPORATE SERVICES
Office refurbishment/relocations |  | 0.667 |  |  |  |  | 0.015 | 0.182 |  |  |  |  | 0.197 | 0.099 | 0.098 |  |  |  | 0.47 |  | 0.667
Capitalisation of Revenue
VER / VS |  | 0.5 |  |  |  | 0.012 | 0.102 | 0.102 | 0.102 | 0.102 | 0.08 |  | 0.5 | 0.5 | 0 | [5 empty] | 0.5
Planned Highway Maintenance |  | 1.629 |  |  | 0.136 | 0.136 | 0.136 | 0.136 | 0.136 | 0.136 | 0.136 | 0.136 | 1.088 | 1.088 | 0 | 0.136 | 0.136 | 0.136 | 0.133 |  | 1.629
Planned Building Maintenance |  | 0.1 |  |  | 0.008 | 0.008 | 0.008 | 0.008 | 0.008 | 0.008 | 0.008 | 0.008 | 0.064 | 0.064 | 0 | 0.008 | 0.008 | 0.008 | 0.012 |  | 0.1
Major Building Maintenance |  | 0.3 |  |  | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.2 | 0.2 | 0 | 0.025 | 0.025 | 0.025 | 0.025 |  | 0.3
Advance Fees |  | 0.239 |  |  | 0.008 | 0.008 | 0.008 | 0.008 | 0.008 | 0.008 | 0.147 | 0.008 | 0.203 | 0.246 | -0.043 | 0.008 | 0.008 | 0.008 | 0.012 |  | 0.239
Software Development |  | 0.5 |  |  | 0.041 | 0.041 | 0.041 | 0.041 | 0.041 | 0.041 | 0.041 | 0.041 | 0.328 | 0.328 | 0 | 0.041 | 0.041 | 0.041 | 0.049 |  | 0.5
Risk Management |  | 0.1 |  |  | 0.008 | 0.008 | 0.008 | 0.008 | 0.008 | 0.008 | 0.008 | 0.008 | 0.064 | 0.064 | 0 | 0.008 | 0.008 | 0.008 | 0.012 |  | 0.1
Project E-merge |  | 0.238 |  |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.16 | 0.16 | 0 | 0.02 | 0.02 | 0.02 | 0.018 |  | 0.238
Energy Conservation |  | 0.1 |  |  | 0.008 | 0.008 | 0.008 | 0.008 | 0.008 | 0.008 | 0.008 | 0.008 | 0.064 | 0.064 | 0 | 0.008 | 0.008 | 0.008 | 0.012 |  | 0.1
Highways Depot |  | 0.376 | [6 empty] | 0.287 | 0.03 | 0.03 | 0.029 | 0.376 | 0.376 | 0 | [5 empty] | 0.376
Leisure Mgt Info System |  | 0.09 | [10 empty] | 0 | 0 | 0 |  |  | 0.09 |  |  | 0.09
CORPORATE SERVICES |  | 4.839 |  |  | 0.254 | 0.266 | 0.371 | 0.538 | 0.643 | 0.386 | 0.503 | 0.283 | 3.244 | 3.189 | 0.055 | 0.254 | 0.254 | 0.344 | 0.743 |  | 4.839
TOTAL |  | 88.499 |  |  | 6.452 | 4.002 | 5.118 | 5.256 | 5.433 | 6.413 | 6.116 | 6.205 | 41.981 | 31.728 | 12.243 | 6.271 | 8.176 | 9.233 | 21.425 |  | 88.499

## Appendix 2
SUMMARY OF 2003/04 ESTIMATED RESOURCES AVAILABLE
Estimate at 03/03/03
|  | Internal |  | External | Estimate | 2003/04 | Revised
|  | Resource | Resource | Resource | at 01/10/03 | Monitoring | Estimate
Adjustments
|  | £m | £m | £m | £m | £m | £m
CREDIT APPROVALS
BCA |  | 9.731 | #REF! |  | 9.731 |  | 9.731
BCA transferred to Other Authorities |  | -1.699 | #REF! |  | -2.873 |  | -2.873
SCA - | Highways - Inner Relief Route |  | #REF! | 0.835 | 0.835 |  | 0.835
| Highways - Cadishead Way |  |  | 9.05 | 9.05 |  | 9.05
| Education - New Deal for Schools Modernisation |  |  | 1.55 | 2.377 |  | 2.377
| Education - Primary Schools - Surplus Place Removal |  |  | 1.5 | 0.5 |  | 0.5
| Social Services - Mental Health |  |  |  | 0.204 |  | 0.204
| Environmental services |  |  |  | 0.012 |  | 0.012
CREDIT APPROVALS |  | 8.032 | #REF! | 12.935 | 19.836 | 0 | 19.836
GRANTS/CONTRIBUTIONS RECEIVABLE
Housing - Market Renewal Fund |  |  | #REF! | 9.352 | 8.14 | -0.05 | 8.09
Housing - SRB 5 |  |  |  | 1 | 1.296 |  | 1.296
Housing - Disabled Facilities Grant |  |  |  | 0.6 | 0.6 |  | 0.6
Housing - Lottery Grant |  |  |  |  | 0.002 |  | 0.002
Education - Devolved Formula Capital |  |  |  | 2.26 | 2.268 |  | 2.268
Education - New Deal for Schools 4 |  |  |  |  | 0.123 | 0.169 | 0.292
Education - Seed Challenge |  |  |  | 0.29 | 0.304 |  | 0.304
Education - Asset Mangaement Plan Condition |  |  |  | 2.336 | 2.336 |  | 2.336
Education - Standards Fund |  |  |  | 0.124 | 0.177 |  | 0.177
Education - Sure Start |  |  |  | 0.187 | 0.278 |  | 0.278
Education - Learning Skills Council |  |  |  |  | 0.137 |  | 0.137
Highways - TSG |  |  | #REF! | 5.586 | 7.325 |  | 7.325
Social Services - Management Information Grant |  |  |  | 0.151 | 0.223 |  | 0.223
Social Services - Quality Protects |  |  |  |  | 0.053 |  | 0.053
NWRDA |  |  |  | 1.366 | 3.038 |  | 3.038
English Heritage |  |  |  |  | 0.016 |  | 0.016
Lottery Grant - Arts & Leisure |  |  | #REF! | 1.73 | 1.862 | 0.046 | 1.908
- Social Services |  |  |  |  | 0.04 |  | 0.04
SPACE |  |  |  |  | 0.064 |  | 0.064
ERDF |  |  |  | 0.905 | 2.66 |  | 2.66
SRB 2 - Non Housing |  |  |  |  | 0.052 |  | 0.052
SRB 5 - Non Housing |  |  |  |  | 0.002 |  | 0.002
New Deal for Communities |  |  |  | 4.377 | 3.228 |  | 3.228
Development Services - Sure Start |  |  |  | 0.169 | 0.214 |  | 0.214
DEFRA - Waste Minmisation |  |  |  |  | 0.096 |  | 0.096
Home Office - CCTV |  |  |  |  | 0.387 |  | 0.387
Neighbourhood Renewal Fund |  |  |  | 0.1 | 0.1 |  | 0.1
Capital Modernisation Fund |  |  |  |  | 0.7 |  | 0.7
Specified capital grant |  |  |  |  | 0.15 |  | 0.15
GRANTS/CONTRIBUTIONS RECEIVABLE |  |  | #REF! | 30.533 | 35.871 | 0.165 | 36.036
USABLE CAPITAL RECEIPTS
Estimated usable 2003/04 receipts |  | 8.338 | #REF! |  | 7.936 | -0.02 | 7.916
Usable Receipts Brought Forward |  |  |  |  | 1.148 |  | 1.148
USABLE CAPITAL RECEIPTS |  | 8.338 | #REF! |  | 9.084 | -0.02 | 9.064
OTHER RESOURCES
Housing HRA Contribution |  |  |  | 2.255 | 5.37 | -0.075 | 5.295
Housing Major Repairs Allowance |  |  |  | 15.946 | 15.946 |  | 15.946
DSO Surplus |  |  |  |  | 0.003 |  | 0.003
Insurance Claim - Ordsall Nursery |  |  |  | 0.13 | 0.13 |  | 0.13
Insurance Claims - Education |  |  |  |  | 0.436 |  | 0.436
Health Authority Contribution |  |  |  |  | 0.02 |  | 0.02
GMWDA |  |  |  |  | 0.008 |  | 0.008
Biffa |  |  |  |  | 0.003 |  | 0.003
Environmental Services - Revenue Contribution |  |  |  |  | 0.004 |  | 0.004
Development Services - Revenue Contribution |  |  |  | 0.014 | 0.014 |  | 0.014
Social Services - Revenue Contributions |  |  |  |  | 0.215 |  | 0.215
Education - Revenue Contribution |  |  |  |  | 0.02 |  | 0.02
Education - School Contributions |  |  |  |  | 0.433 |  | 0.433
Community Safety |  |  |  |  | 0.006 |  | 0.006
Private Sector Contributions |  |  |  |  | 0.209 | 0.015 | 0.224
Other Local Authority Contributions |  |  |  |  | 0.019 |  | 0.019
OTHER RESOURCES |  |  | #REF! | 18.345 | 22.836 | -0.06 | 22.776
TOTAL - ESTIMATED RESOURCES |  | 16.37 | #REF! | 61.813 | 87.627 | 0.085 | 87.712

## Appendix 3
2003/04 ESTIMATED CAPITAL RECEIPTS
ASSET | CAPITAL |  | USABLE
| RECEIPT | Prop'n | Amount
| £000s | % | £000s
COMPLETED DISPOSALS
Housing Right-to-Buy | 11188 | 25 | 2797
Housing Land
Land at Swinton Hall Road | 34 |  | 34
General Fund - Properties and Land
Upper Camp St | 252 |  | 252
Land at Ravenscraig Road | 195 |  | 195
Beechfield House | 138 |  | 138
G-Mex Commuted Sum | 65 |  | 65
Sale Of Shares Ringway Development (Balance) | 86 | 25 | 22
Peel Green wc's | 8 |  | 8
Highfield Road | 48 |  | 48
Taylorson Street Industrial Estate | 1485 |  | 1485
TOTAL COMPLETED | 13499 |  | 5044
APPROVED DISPOSALS
Housing Right-to-Buy | 3812 | 25 | 953
Housing Land & Property | 260 |  | 260
General Fund - Properties and Land | 1859 | 100 | 1859
TOTAL ESTIMATED DISPOSALS | 5931 |  | 3072
TOTAL ESTIMATED RECEIPTS | 19430 |  | 8116
Less - Costs to be set against capital receipts |  |  | 200
NET ESTIMATED RECEIPTS |  |  | 7916

## Appendix 4
Disposal | Estimated Receipt | Preliminaries/ Marketing | Legal/Planning | Completion
Alpine Soft Drinks | 200000 |  | April/May 2003 | Completed 6th June 2003
Beechfield House | 138000 |  | April/May 2003 | Completed 18th July 2003
628 Eccles New Road (Land adj) | 187000 |  | April /July 2003 | Completed August 2003
Land at Upper Camp Street | 252000 |  | April /May 2003 | Completed 1st July 2003
Tayloson Street Industrial Estate | 1485000 |  |  | Completed 13/11/03
Homes To Trust-Birchfold | 250000 |  | May/September 2003 | Lead member decision required on acceptability of disposal price
Chapel Street Ed. Offices (balance) | 450000 |  | April/Sept 2003 | 2003-12-01
Land @ Higher Croft, Eccles. | 205000 |  | Aug/Sept 2003 | Negotiating terms of sale due to need for road closures
Swinton Sauna Site | 225000 |  | May/Sept 2003 | 2003-11-01
Chaseley Fields | 550000 |  | July/Dec 2003 | 2004-02-01
Mining Museum, Buille Hill Park | 250000 |  |  | 2004-03-01
CAPITAL RECEIPTS 2003/4
TIMESCALES-RECEIPTS IN EXCESS OF £100,000

## Appendix 5
Lead Member Corporate Services - 2003/04 Tender Approvals to 19th September 2003
Scheme Details |  | Costs |  | Source of
| 2003/04 | 2004/05 | Total | Funding
Onwards
| £m | £m | £m
Development Services
Manchester-Salford Inner Releif Route Stage 3 | 0.234 | 0.77 | 1.004 | Borrowing (ACG)
Purchase of Bethany Church, Liverpool Street | 0.129 | 0 | 0.129 | HMR
Land Tribunal | 0 | 4.7 | 4.7 | Grant DETR
Footway reconstruction Programme | 0.367 | 0.025 | 0.392 | Block 3 Highways Capital Programme
Reconstruction of West Egerton Street Bridge | 0.05 | 0.025 | 0.075 | On existing programme
Cadishead Way Stage 2 | 0.255 | 0.084 | 0.339 | SCA
| 1.035 | 5.604 | 6.639