“Positive about young people and their potential”

Working together to improve Sexual Health and Wellbeing for young people in Salford action plan 2010-2013

After consultation with partner organisations the following action plan has been written to deliver the aim of Salford’s Young Peoples Sexual Health Strategy, which is:

“Reduce the conception rate in those under-18 and reduce the impact of this on social exclusion, educational attainment, social aspiration and the health and wellbeing of the mothers and children”.

Sections:

- Strategic Priority: Develop Contraception and Sexual Health Services

- Strategic Priority: Supporting young peoples sexual health and wellbeing through Primary Care

- Strategic Priority: Support for pregnant young women, young parents and their children

## Strategic Priority: Prevention and supportive environments

- Strategic Priority: Establish multi-agency service model

- Strategic Priority: Media and communications

- Strategic Priority: Relationship and Sex Education

- Strategic Priority: Early Years Environment

Strategic Priority: Develop Contraception and Sexual Health Services

| Strategic Objective | Action | Lead | Supporting Partner | Measure of Success | Start Date | Completion Date | Financial Resources Required | Financial Resources Committed |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Develop Tier 2 sexual health services in five schools with the highest conception rates. | Brook | Public Health, Youth Service, Salford Community Health | 5 school services up and running | January 2010 | Sept 2010 | Budget Identified | NHS Salford YPSH tender |
| 2 | All high schools to establish a drop in contraception and sexual health session. | School Health | Public Health, Youth Service, Brook | Drop in services up and running in all high schools | Sept 2010 | Sept 2011 | School Health additional hours + training | NHS Salford Additional hours – to be identified Training – YPSH business case |
| 3 | All Salford City College sites to deliver tier 3 contraception and sexual health services | Brook | Public Health, Salford City College | 5 college site services up and running | January 2010 | September 2010 | To be confirmed (Training and supplies) | NHS Salford YPSH tender |
| 4 | All providers of work-based training for young people, commissioned through the city council and the PCT, to provide tier one sexual health interventions. | Training Providers | NHS Salford, Youth Service, Brook, Children’s Services | Tier one sexual health interventions provided by all work based training providers | April 2010 | December 2011 | To be confirmed (Training and supplies) | NHS Salford YPSH business case Teenage Pregnancy Area Based Grant |

Strategic Priority: Supporting young peoples sexual health and wellbeing through Primary Care

| Strategic Objective | Action | Lead | Supporting Partner | Measure of Success | Start Date | Completion Date | Financial Resources Required | Financial Resources Committed |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 5 | Recruitment of a GP champion for young people’s sexual health to lead in primary care development and implementation. | NHS Salford Public Health | Primary Care Commissioning | GP Champion in post Increased uptake of LARCs/NCSP/ participation in C-Card condom distribution scheme | April 2010 | March 2012 | Budget Identified | NHS Salford YPSH business case |
| 6 | Implement the Local Enhanced Service contract with GPs for Chlamydia screening and young people’s sexual health services. | NHS Salford Public Health | Primary Care Commissioning | Local Enhanced Service in place. Increased uptake of LARCs/NCSP/ participation in C-Card condom distribution scheme | January 2010 | March 2011 | Budget Identified | NHS Salford YPSH business case |
| 7 | Complete a sexual health skills audit across Primary Care and make recommendations for training and development to PBC. | NHS Salford Public Health | Primary Care Commissioning, Public Health, Organon | Sexual health skills audit across Primary Care completed and training action plan developed | January 2010 | March 2010 | Cost Neutral | N/a |
| 8 | Include Tier one sexual health interventions into all frontline staff job descriptions. | Children’s Services, Salford City Council | NHS Salford Public Health | All frontline staff job descriptions include tier one sexual health interventions | April 2010 | March 2012 | (training and development costs) | Teenage Pregnancy Area Based Grant |

Strategic Priority: Support for pregnant young women, young parents and their children

| Strategic Objective | Action | Lead | Supporting Partner | Measure of Success | Start Date | Completion Date | Financial Resources Required | Financial Resources Committed |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 9 | Establish a post in Maternity Services to support Teenage parents and to develop the skills of the maternity services. | Salford Royal Foundation Trust | NHS Salford Public Health, Children’s Services, Salford City Council | Posts created and recruited. Maternity services skills base increased from baseline established by Clinical Quality Academy. Increased uptake in breastfeeding, post natal contraception take up and reduced smoking in pregnancy | January 2010 | March 2012 | £30,000 | NHS Salford YPSH business case |
| 10 | Develop personalised education programmes for all individual school age parents | Surestart Children’s Services, Salford City Council | Targeted Youth Support, Children’s Services, Salford City Council | Personalised education programmes for all individual school age parents implemented | January 2010 | September 2010 | Cost Neutral | n/a |

## Strategic Priority: Prevention and supportive environments

| Strategic Objective | Action | Lead | Supporting Partner | Measure of Success | Start Date | Completion Date | Financial Resources Required | Financial Resources Committed |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 11 | All services to achieve the standards for You’re Welcome and Getting it Right. | NHS Salford Children’s Commissioning | NHS Salford Public Health, Children’s Services, Salford City Council, Salford Community Health, Brook | 50% all young people’s services achieve You’re Welcome by 2011, 100% by 2012. | January 2010 | March 2012 | (training and development costs) | NHS Salford YPSH business case (for GPs) |
| 12 | Deliver courses in the community for parents to develop their skills and confidence around sexual health and relationships. | Children’s Services, Salford City Council | Salford Community Health, Brook | 2 courses per annum delivered in each Neighbourhood by 2011 | January 2010 | March 2011 | £40,000 | Teenage Pregnancy Area Based Grant |
| 13 | Complete a skills audit across frontline staff (PCT and SCC) to assess development needs. Develop a training plan for frontline staff. | Children’s Services, Salford City Council, NHS Salford | Brook, Salford Community Health Human Resources, Children’s Services Organisational Development, Salford City Council, | Skills audit and training plan completed | April 2010 | March 2012 | (training and development costs) | Teenage Pregnancy Area Based Grant NHS Salford YPSH business case |
| 14 | Evaluate the targeted youth support scheme around the school to assess the impact on young people’s sexual health. | Targeted Youth Support Children’s Services, Salford City Council, | NHS Salford Public Health | Evaluation of the targeted youth support scheme completed. | April 2010 | March 2011 | To be confirmed | Area Based Grant |
| 15 | All public buildings will be breast feeding friendly in line with UNICEF breast feeding requirements | Children’s Services, Salford City Council, NHS Salford | NHS Salford Public Health | Number of building with UNICEF breast feeding status | April 2010 | March 2011 | To be confirmed | To be confirmed |
| 16 | Develop an appropriate breastfeeding education package to be delivered as part of PSHE to Year 10 secondary pupils. | Public Health, NHS Salford | Children’s Services Directorate | Number of pupils taking part in sessions. | April 2010 | March 2011 | To be confirmed | To be confirmed |

Strategic Priority: Establish multi-agency service model

| Strategic Objective | Action | Lead | Supporting Partner | Measure of Success | Start Date | Completion Date | Financial Resources Required | Financial Resources Committed |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 17 | Set up a task and finish group to develop a young people’s healthy lifestyle model. | NHS Salford Public Health | Health Improvement Team, NHS Salford, Children’s Services Directorate, SCC | Young people’s healthy lifestyle model developed | April 2010 | March 2011 | Cost Neutral | n/a |
| 18 | Pilot in one of the hot spot area, the integrated youth development model through an identified team. | Children’s Services Directorate, SCC NHS Salford Public Health | Ordsall and Langworthy Neighbourhood Team, Langworthy Teenage Pregnancy Spotlighting Task Group | Complete Langworthy Teenage Pregnancy Spotlight process by April 2010 Pilot Youth development team proposal developed by Sept 2010 | January 2010 | March 2011 | To be developed at time of proposal | n/a |

Strategic Priority: Media and communications

| Strategic Objective | Action | Lead | Supporting Partner | Measure of Success | Start Date | Completion Date | Financial Resources Required | Financial Resources Committed |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 19 | Develop and implement a media communications strategy | Children’s Services Directorate, SCC NHS Salford Public Health | Media communications departments (SCC, NHS Salford and Salford Royal Foundation Trust) | Teenage Pregnancy media communications strategy developed | January 2010 | March 2010 | £2000 | NHS Salford YPSH business case |
| 20 | Develop and implement a Social Marketing campaign that targets those most at risk of early pregnancy | NHS Salford Public Health | Children’s Services Directorate, SCC Media communications departments (SCC, NHS Salford) | Social marketing campaign developed | April 2010 | March 2011 | To be confirmed | To be confirmed |

Strategic Priority: Relationship and Sex Education

| Strategic Objective | Action | Lead | Supporting Partner | Measure of Success | Start Date | Completion Date | Financial Resources Required | Financial Resources Committed |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 21 | All schools and Pupil Referral Units to achieve the Healthy Schools Status | Children’s Services Directorate, SCC NHS Salford Public Health | High schools | Enhanced Healthy School status | April 2010 | March 2012 | Identified | Within mainstream resources |
| 22 | All schools to have an accredited PSHE teacher. | Children’s Services Directorate, SCC | High schools | All schools have an accredited PSHE teacher. | April 2010 | September 2012 | To be confirmed | National PSHE CPD training programme |
| 23 | Implement RSE leadership scheme for all school governors and all Head Teachers. | Children’s Services Directorate, SCC | Regional/National Teenage Pregnancy Unit | All schools have trained RSE leadership | April 2010 | September 2012 | To be confirmed | To be confirmed |
| 24 | All schools to include RSE as part of the School Improvement Assessment. | RSE consultant, Children’s Services Directorate, SCC | School Improvement, Children’s Services Directorate, SCC NHS Salford Public Health | School Improvement Assessment for all schools include RSE. | April 2010 | September 2011 | Cost Neutral | n/a |
| 25 | Recruit 2 additional staff into the School Improvement Team. | School Improvement, Children’s Services Directorate, SCC | RSE consultant, Children’s Services Directorate, SCC NHS Salford Public Health | 2 additional staff recruited into the School Improvement Team. | April 2010 | September 2011 | £80,000 | To be confirmed |

Strategic Priority: Early Years Environment

| Strategic Objective | Action | Lead | Supporting Partner | Measure of Success | Start Date | Completion Date | Financial Resources Required | Financial Resources Committed |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 26 | Develop young parents support service in all Children’s Centres | Surestart Children’s Services, Salford City Council | Targeted Youth Support, Children’s Services, Salford City Council | Support services in 50% Childrens Centres by 2011, 100% by 2012 | January 2010 | March 2012 | £120,000 | Surestart Grant to SCC |

Glossary

CPD		Continuing Professional Development scheme (for teachers of PSHE see below)

LARC		Long Acting Reversible Contraception

NCSP		National Chlamydia Screening Programme

PBC		Practice Based Commissioning

PSHE		Personal Social and Health Education

RSE		Relationships and Sex Education

SCC 		Salford City Council

UNICEF	United Nations Children’s Fund Organisation

YPSH 		Young People’s Sexual Health