## Cover
SALFORD CITY COUNCIL
CORPORATE IMPROVEMENT PLAN AND MONITORING STATEMENT
SEPTEMBER 2004 (POST PILOT CORPORATE ASSESSMENT)
MONITORING STATEMENT 8th September 2005

## Intro
SALFORD CITY COUNCIL
CORPORATE IMPROVEMENT PLAN AND MONITORING STATEMENT
SEPTEMBER 2004 (POST PILOT CORPORATE ASSESSMENT)
This improvement plan is the Council's overall corporate improvement plan and embraces those activities applicable from the 2002 corporate assessment, activities
in response to the pilot assessment in September 2004, and corporate improvements identified via other routes (e.g. cabinet workplan, directors team). The plan identifies 5
corporate improvement areas, along with a sixth area, key service improvements:
1 | Scrutiny
2 | Performance management/planning
3 | Citizen focus (consultation, diversity and engagement)
4 | Organisational development (people and learning/development/culture)
5 | Strategic plans and finance
6 | Key service improvements
Actions/activities under each main improvement area will collectively lead to the improvement identified in the main area.
Weaknesses identified in the 2004 pilot are referenced to the improvement activities - See appendix for key.
Additionally the pilot assessment in September 2004 identified development areas in the achievement section which largely
apply to services. Corporate issues are addressed in this improvement plan, but service issues are largely covered in service plans.
Particularly corporately significant service developments are included in section 6.
The weaknesses table appendix links the weaknesses to the above improvement areas, and activities below are also cross
referenced to weaknesses, as appropriate.
A traffic light column appears to the right of each activity through the following pages, as follows: -
Not on target/not achieved
behind target (for various reasons), or some concern about achieving target
On target/achieved

## Scrutiny
Improvement area 1 - SCRUTINY | [5 empty] | 8th September 2005
Salford has shown a commitment to the modernisation agenda, and has made great strides in implementing the Cabinet and scrutiny system.
Members and officers work well together, providing effective joint leadership in strengthening and developing the council's vision.
It is acknowledged that there have been improvements in overview and scrutiny within the city council since the 2002 CPA corporate assessment. To progress this further
the Audit Commission has highlighted some additional development areas which we are keen to address. These areas are identified in the pilot CA report under the Prioritisation,
Capacity and Performance Management themes. The actions needed to make overview and scrutiny more effective are included in the strategic review of governance and the
scrutiny development action plan.
Item | Action/Activity | Responsible Member/Officer(s) | Milestones/Targets | Resources | Improvement area identified in: | Current position | On target?
1.1 | Implement the strategic review of governance to align scrutiny workplans more clearly to pledges, key improvement plans and key business risks | Leader/JCW/RB | See timetable in report to council dated 15th September 2004 |  | Pilot CA report (5 (Para 35)) | Scrutiny committees revised, Terms of Reference in place, Work programmes operating and being regularly monitored
| Align overview and scrutiny committees with the new governance arrangements |  | by 1st October 2004 | SST/O&SC |  | Achieved
| Revised ToR's for O&SC to reflect new arrangements |  | by 15th December 2004 | CG/RB/O&SC chairs |  | Achieved
| Agree/monitor work programmes for all O&SC's |  | Ongoing | O&SC's |  | Work programmes in place and are being regularly monitored
| Agree/design performance management arrangements for O&SC's |  | by 31st January 2005 | Cabinet/O&SC's |  | Achieved
1.2 | Implement the scrutiny development action plan (arising from the S. Leech report) | Leader/JCW/RB | See detailed improvement plan |  | Pilot CA report (9 (Para 42)) (14 (Para 56)) | All agreed recommendations implemented
Prepare improved and ongoing evidence to demonstrate effectiveness of scrutiny
| Agree protocols for evidence providers, chairs, member of O&SC, Lead Members, officers and partners |  | Protocols produced and consulted with identified groups | SST/O&SC chairs, members, officers |  | Achieved
Item | Action/Activity | Responsible Member/Officer(s) | Milestones/Targets | Resources | Improvement area identified in: | Current position | On target?
| Develop training and development programme reflecting needs of members and officers |  | Ongoing | SST |  | Programme in place which is monitored/reviewed at regular intervals
| Role of O&S in relation to the budget to be strengthened and linked directly to public consultation |  | Consultation strategy agreed by Nov 2004 and revisited for 2005 budget consultation | Budget & audit O&SC/ Lead Member |  | Achieved

## Perf Man
Improvement area 2 - PERFORMANCE MANAGEMENT/PLANNING | [5 empty] | 8th September 2005
We have a clear performance management framework in place at the council, with strong leadership committed to driving the issue forward. The 7 pledges give our priorities
and these are detailed in various documentation, providing greater clarity across the council as to what we are trying to achieve.
Whilst we have made improvements in performance management since the 2002 CPA, the progress has not been consistent throughout the entire council.
For performance management to be fully effective, we need to further develop our performance management systems and culture, and concentrate more on top-level
outcomes linked to our priorities. Action planning should be tied to achieving better quality of life outcomes and the 'bigger picture' rather than service based PI's.
The actions needed to ensure Salford’s performance management system is progressed further are detailed below.
Item | Action/Activity | Responsible Member/Officer(s) | Milestones/Targets | Resources | Improvement area identified in: | Current position | On target?
2.1 | Implement proposals to develop a council wide performance management system, as an ODPM pathfinder | Leader/JCW/RF/ALL DIRECTORS | See Performance Management system development project plan |  | Pilot CA report (2 (Para 22)) (3 (Para 28)) (13 (Para 55)) (15 (Para 58)) (16 (Para 57))
| PHASE 1 Approval of PID |  | January 2005 |  |  | Achieved
| Understand Framework architecture and map onto some of Salford's current plans |  | Dec 2004/Jan 2005 |  |  | Achieved but development work ongoing
| Install software |  | Jan 2005 |  |  | Achieved end Jan but enhancements required
| Design and write service plans |  | Feb/March 2005 |  |  | Uploading of service plans delayed pending development of corporate/directorate balanced scorecards
| Write and test interface with SPIN system |  | 20th June 2005. |  |  | Interface developed and testing underway. Target completion date revised to 20 june
| Hold awareness raising events |  | January - March 2005 |  |  | Several held but ongoing. Further events to be scheduled into developing perf man communication plan.
Item | Action/Activity | Responsible Member/Officer(s) | Milestones/Targets | Resources | Weaknesses in 2004 pilot | Current position | On target?
| Training sessions |  | Jun/Sept 2005. |  |  | Commenced - 1st phase completed early April. Phase 2 in development. Scheduled to take place from end june over rest of summer.
PHASE 2 Implementation of PMF
| Directorate Balanced Sorecards prepared | David Horsler / Paul McKenna | 31st August 2005 |  |  | Workshops held, draft scorecards prepared, formal typing up ongoing
| Input pilot directorate balanced scorecards onto PMF | Allison Lobley / Neil Watts | 30th September 2005
| Pilot directorate business level balanced scorecards roll-out and input onto PMF in Children's Services and Environmental Services | Paul McKenna / David Horsler / Allison Lobley / Neil Watts | Oct/Nov 2005
2.2 | Develop a performance management culture by ensuring staff in directorates have access to, understanding of, and apply/use performance data to improve service delivery | ALL LEAD MEMBERS/ ALL DIRECTORS | See project plan for Performance Management Review Project |  | 2003 imp't plan
| Annual performance appraisal for all staff | DH | New appraisal format and competencies agreed by Jun. 2005. All appropriate staff to have annual appraisal |  |  | Appraisal to be integrated into SAP by Sept 2005. All staff to be appraised March -Sept 2005. Fully computerised system by March 2006.
Item | Action/Activity | Responsible Member/Officer(s) | Milestones/Targets | Resources | Weaknesses in 2004 pilot | Current position | On target?
| Annual training plans for all directorates | DH | Training plan format agreed by Aug. 2005. 2006 training plan published by Dec. 2005. |  |  | Corporate Workforce Development Plan by Aug 2005.
| Performance management newsletter | AL/NW | Issue 1 distributed to all staff during Jan/Feb. 2005 |  |  | Achieved. Issue 2 to be disseminated 19th Sept. 05.
| Continued rollout of use of PMF across non-pilot directorates |  | April 2005 - March 2006 |  |  | ongoing
2.3 | Review targets in community plan, BVPP and service plans to ensure they are SMART | Leader/JCW/RF |  |  | Pilot CA report (3 (Para 28)) | BVPP targets for 2005/06 plan reviewed.
2.4 | Review pledge targets to ensure these link to outcomes for service users | Leader/ALL LEAD MEMBERS/ JCW/RF/ ALL DIRECTORS |  |  | Pilot CA report (3 (Para 29)) | Currently being undertaken
2.5 | Review the approach to allocating resources, at all levels, to ensure we have a robust and transparent approach to resource allocation | Lead Member customer and support services/ Alan W | Draft 3 year budget strategy by October 2005 |  | Pilot CA report (6 (Para 36)) (7(Para 37)) | Awaiting balanced score card and VFM assessments and Gov't proposals. Report on initial prospects presented to Budget and Efficiency Group. Draft agreed by Lead Member.
| Develop a balanced scorecard approach |  | Commencing 2005/06 |  |  | Balanced scorecard launched June 2005 with introductory seminars for directorates. Ongoing.
| Develop a VFM proforma approach and identify appropriate areas for review to be included in future years efficiency plans |  | By April 2006 |  |  | Initial VFM self assessments largely completed; some being revised. Final self assessments by end June 2005 for consideration at budget and efficiency group. Ongoing.
Item | Action/Activity | Responsible Member/Officer(s) | Milestones/Targets | Resources | Weaknesses in 2004 pilot | Current position at: Date: | On target?
| Align budget strategy in accordance with balanced scorecard principles |  | By 2006/07 financial year |  |  | On target - 2005/06 budget report demonstrated alignment of financial and service planning. Alignment with balanced scorecard approach to be developed during 2005/06. Ongoing.
2.6 | Develop the risk management approach (currently mainly corporate) at the operational level in all directorates | Lead Member customer and support services/ALL LEAD MEMBERS/Alan W/DS/ALL DIRECTORS | Included in 2005/06 service plans. Developed as part of PMF project |  | Pilot CA report (10 (Para 44)) | Strategic, directorate and operational risk registers have been developed and are reviewed on a quarterly basis. CRMG receive information on key issues. All information has been reviewed to ensure efficient transfer to the PMF system for risk management
2.7 | Develop a methodology to facilitate the production of business continuity plans to minimise the impact of loss to the Council, GMPA, NPHL and Salford Community Leisure following an incident | Lead Member customer and support services/ALL LEAD MEMBERS/ Alan W/ALL DIRECTORS | Develop business resumption plans Customer and Support Services by 31.01.05 and for remainder of council and NPHL by 31.03.05 |  | Pilot CA report (22 (Para 96)) | BCM work is being rolled out across the council and major partners. Business impact analysis has been undertaken and response and recovery plans are being developed and drafted. Development ongoing.
Item | Action/Activity | Responsible Member/Officer(s) | Milestones/Targets | Resources | Weaknesses in 2004 pilot | Current position at: Date: | On target?
2.8 | Develop the council's approach to risk management | Lead Member customer services and finance/ALL LEAD MEMBERS/ Alan W/DS/ALL DIRECTORS | Completion linked to PMF development |  | Pilot CA report (22 (Para 96)) | CRMG in operation and reviewing risk registers. Directorate responsibilities have been determined and the Corporate Risk Management Framework has been reviewed. Registers have been aligned to pledges as part of PMF implementation. Registers are also being reviewed to align to new strategic directorates. Assess staff awareness and utilise risk champions to embed risk management. To develop a risk management toolkit to raise awareness.
| Develop integration of business planning and risk management/ownership via the performance management framework (PMF) |  | Timescales all driven by PMF timescales |  |  | Risk element will be populated to be used by directorates when compiling business plans. Completed by PMF go live date
| Develop and embed risk management and production of business risk registers at the operational level via the PMF |  | Timescales all driven by PMF timescales |  |  | Preparatory work has been completed to ensure this information is available for PMF go live. Business units will be able to manage risks from start of PMF system
2.9 | Develop a robust approach to exit strategies in areas where short term funding has been achieved | Lead Member customer and support services/Alan W | Collect evidence to demonstrate exit strategies for areas of short term funding |  | Directors paper - 29th July 04 | An officer working group has been set up to address this issue and report to Budget Strategy Group. Ongoing

## Citizen focus
Improvement area 3 - Citizen focus (consultation, diversity and engagement) | [5 empty] | 8th September 2005
Salford is fully dedicated to the principles of diversity and has worked hard to ensure all citizens are consulted and engaged in the work that the council is doing. There is
a strong commitment to community engagement in developing ambitions. We recognise the need for further work to ensure that all Salford’s diverse communities are
consulted and engaged and able to inform our ambitions, as there have been some inconsistencies in our approach. The actions that we believe are necessary to develop
further the council’s work in these areas is covered below.
Item | Action/Activity | Responsible Member/Officer(s) | Milestones/Targets | Resources | Improvement area identified in: | Current position | On target?
3.1 | Implement the Community Engagement Improvement Plan to ensure true consultation and engagement with wide cross section of groups and communities across the city | Lead Member for neighbourhood management/ Anne W/BW | Establish Diversity Leadership Forum to engage with BME communities by 31/12/04 |  | Pilot CA report (1 (Para 23)) Community engagement review | Achieved
| Establish citizen's panel | Lead Member for neighbourhood | Circa 1000 citizens recruited by April 2005 |  |  | Consultant (MORI North) appointed
|  | management/ SH | First wave of research complete by April 2005 |  |  | Achieved
| Implement Neighbourhood Management model in Salford | Lead Member for neighbourhood management/ BW | Appoint Neighbourhood Managers & Establish N/Hood Teams by 31/12/04 | Resources already established |  | Achieved
| Review membership of Community Committees to take account of diversity | Lead Member for neighbourhood management/ BW | Review membership by 30/09/05 | Neighbourhood manager |  | Partners in Change consultacy engaged and will report prior to end September 2005. On schedule.
3.2 | Collect evidence to demonstrate how our delivery of services responds to the needs of our customers | ALL lead Members/ALL Directors | ongoing
Item | Action/Activity | Responsible Member/Officer(s) | Milestones/Targets | Resources | Improvement area identified in: | Current position | On target?
3.3 | Consult, review and develop performance information so that it is easy to access and appropriate to the needs of our users. | Leader/JCW/RF |  |  | Pilot CA report (17(Para 61)) | This will be covered by PMF installation.
3.4 | Review results of LSP research regarding community cohesion, and develop and implement recommendations | Lead Member for service development/ neighbourhood management/ Anne W/BW |  |  | Pilot CA report (21(Para 92))
| Establish BME-led Diversity Leadership Forum |  | by 30/9/05. |  |  | Consultant appt'd by GONW, work ongoing, consultation and launch event planned for late 2005.
| Establish Multi Agency Forum to address Asylum Seeker / Refugee Issues |  | by 31/3/05 |  |  | Achieved - First Meeting of Multi Agency Forum 12/1/05, regular meetings thereafter
| Maintain Strategic Leads Forum for Senior Leaders to address Community Cohesion issues |  | by 31/12/04 |  |  | Achieved - Strategic Leads continue to meet on quarterly basis with all key partners represented at senior level.
3.5 | Leader and Chief Exec to continue a dialogue with key partners to refine and develop a collective vision for the city | Leader/JCW | Ongoing |  | 2003 imp't plan | Ongoing
3.6 | Continue to consult partners and other partnerships on best practice and implement proposals for change in the light of experience gained | Leader/JCW/RF | Ongoing |  | 2003 imp't plan | Ongoing

## Org Develop
Improvement area 4 - Organisational development (people and learning/development/culture) | [6 empty] | 8th September 2005
Salford has a positive approach regarding the importance of a strong organisational culture. We believe in the value of learning from experience, and where possible try to
ensure that our knowledge is shared with partners and across the authority. We need to make this learning systematic across the council, as some areas are better at
sharing knowledge than others.
We have some work to do to increase internal capacity, through work in HR, appraisal and risk management- areas which we intend to advance through actions in this
improvement plan.
Item |  | Action/Activity | Responsible Member/Officer(s) | Milestones/Targets | Resources | Improvement area identified in: | Current position | On target?
4.1 | Implement the HR strategy delivery plan and embed the improvements to ensure capacity development: |  | Lead Member customer and support services/MB | See report to leader briefing 1st Nov. | 2004/05 £155,500 2005/06 £265,500 2006/07 £270,000 2007/08 £255,000 | CPA 2002 Leech report Pilot CA report | See report to Leader Briefing 1st Nov 2004
Key improvement programmes:
|  | Diversity and inclusion |  | Launch diversity leaders by April 2005 |  |  | Briefing for senior managers 23-24 Feb 2005, delivery of training from 4 April - 1500 places already booked. Ongoing.
|  | Customer care |  | Deliver training to 1000 staff by September 2006 |  |  | ODPM bid accepted - [pilots commenced in Citywide and Transport from Feb 05. Further areas to commence after review of pilots.
Leadership development
|  | First line |  | 6 programmes to be delivered by April 2005 |  |  | Programmes 1&2 completed. Programmes 3, 4 started Jan 05. Programmes 5,6 April . Further courses starting Sept 05
|  | Senior and middle managers |  | 100 senior/middle managers per year involved in programme |  |  | Assessment for development centre and 360 degree appraisal in April. Training commenced May.
Item |  | Action/Activity | Responsible Member/Officer(s) | Milestones/Targets | Resources | Improvement area identified in: | Current position | On target?
|  | Top team |  |  |  |  | Cabinet Sub group for HR Strategy and Members' Training set-up June 2006
Capacity building programmes:
|  | Change management (Audit Commission) |  | Establish/undertake programme in 5 areas |  |  | Action plans in place for 5 areas. A 2nd phase will commence in March involving a review of the earlier programmes and the development of coaching and mentoring skills
|  | AGMA capacity building |  | Undertake programme facilitated by Manchester Business School |  |  | The programme is facilitated by MBS and is based on an action-centred learning approach and each participant is required to identify a work based project for implementation as part of their commitment to service improvement. 12 participacts in 2004/05. Ongoing.
Salford capacity building
|  | Neighbourhood management |  | Undertake first 3 phases of programme by Nov. 2005 |  |  | Contract let April 2005. Provisional commencement September 2005
|  | Service transformation |  |  |  |  | Service areas identified as heritage and adult/ older people social work. Contract let April 2005to tender in March.
4.2 | Develop and implement corporate IT based complaints system to ensure a joined up approach to reviewing and monitoring of complaints |  | Lead Member customer and support services/AE | Implement IT system by 01.04.05 |  | Pilot CA report (8 (Para 39)) | Project has been scoped and specification of requirements produced. Work being undertaken by CRM team. System operative from October 2005.

## Strategic plans and finance
Improvement area 5 - STRATEGIC PLANS AND FINANCE | [5 empty] | 8th September 2005
At Salford, we are fully aware of the importance of value for money. We have a healthy culture around achieving more for less in delivering our pledges, whilst working hard
to recover financial health. Progress in the area of procurement is necessary however, to ensure we are working at our most efficient.
Item | Action/Activity | Responsible Member/Officer(s) | Milestones/Targets | Resources | Improvement area identified in: | Current position | On target?
5.1 | Develop clear strategic approach to meeting the needs of older people through a corporate and multi-agency strategy, | Lead Member adult social services/ Anne W/TM |  | City Council, PCT and Police input. | Pilot CA report (Para 111)
| Submit plan for development of strategy to Older People Partnership Board |  | 2005-03-01 |  |  | Submitted in May
| Establish multi agency steering group |  |  |  |  | Established
| Undertake stakeholder and older people workshops |  | 2005-07-01 |  |  | Stakeholder events with older citzens and service providers took place in July.
| Prepare first draft of strategy |  | 2005-10-01 |  |  | On schedule
5.2 | Development and review of strategic approach to adults with mental health needs | Lead Member adult social services/ Anne W/HW | Presentation of revised strategy to Mental Health Partnership Board in June 05 | Joint City Council, PCT and Bolton, Salford and Trafford Mental Health Trust | Pilot CA report (Para 116) | On target for strategy to be completed by end June. Will be presented to next partnership board in August or September. On schedule
5.3 | Review current services provision to meet the mental health needs of older people | Lead Member adult social services/ Anne W/TM | Present review to older people’s Partnership Board in June 05 | Joint City Council, PCT and Bolton, Salford and Trafford Mental Health Trust | Pilot CA report (Para 116) | Review presented to partnership board April 2005. Detailed action plan, arisinf from the review, being worked on. To be presented to partnership board by October 2005. On schedule.
Item | Action/Activity | Responsible Member/Officer(s) | Milestones/Targets | Resources | Improvement area identified in: | Current position | On target?
5.4 | Develop a coherent corporate preventative strategy for children and young people | Lead Member children's services/JB/ PW |  | Principally City Council and PCT | Pilot CA report (Para 131)
| Produce draft strategy for consideration by the Children's Services Planning Forum, indicating scope, outcomes, links to Pledges and resource implications |  | By April 2005 |  |  | To be presented to full Children's Services Planning Forum mid-June
| Seek approval by Council, PCT board and other partners |  | By end June 2005 |  |  | Cabinet date set for late June
5.5 | Continue to develop a corporate procurement strategy and procedure to improve VFM and ensure a consistent approach to procurement in all Directorates | Lead Member customer and support services/ Alan W/GA | Procurement strategy approved by Cabinet January 2005 |  | Pilot CA report (11 (Para 50)) | Procurement strategy approved as target. Procurement Officers' group meet monthly to progress action plan. Initial tasks underway: spend analysis, contract register, procurement plan and directorate procurement strategies. Core information to be uploaded to intranet Procurement progress to be monitored as part of Think Customer project. New Procurement Co-ordination Team structure agreed.
| Initial tasks - spend analysis, contract register, procurement plan, directorate procurement plans |  | Contract register and procurement plan by end June 2005, remainder by end July |  |  | Contract register and procurement plan complete, directorate procurement plans in progress and almost complete
| upload core information to intranet |  | By end June 2005 |  |  | complete
| monitor progress as part of think customer and think efficiency and finance Cabinet working group |  | on-going
| Implement new procurement coordination team structure |  | Begin mid June 2005, complete by end Sept (subject to level of external recruitment) |  |  | commenced and should be complete by end October
Item | Action/Activity | Responsible Member/Officer(s) | Milestones/Targets | Resources | Improvement area identified in: | Current position | On target?
5.6 | Elderly Persons Contact Centre Pilot locality model proposed for single point of contact to facilitate service/ information provision | Lead Member service development/ neighbourhood management/ Alan W/AP | CPA.Think Customer Theme 1/ Strategy to be in place by September. Projects initiated from September. |  |  | BPR work ongoing to identify re-engineering proposals to deliver single point of contact for services to elderly people.
5.7 | My Home: This project will provide all customers one point of contact to facilitate access and exercise choice of housing and related services to meet their needs | Lead Member service development/ neighbourhood management/ Alan W/AP | Leadership priorities (profile of city) Think Customer/Cabinet workplan/regeneration: Target date; 100 days mid June 2005. Choice based lettings system to be implemented by end March 2006 |  |  | BPR work ongoing to identify re-engineering proposals to deliver single point of contact for services for cross cutting housing issues.
5.8 | Welcome to Salford: This will enable customers to take a more active role in finding and single point of contact to new resident/improve access to information through all channels/ phase 1 council services resolved and reconciled around information pack and information sharing as per bereavement information hub/ phase 2 model launched across LSP | Lead Member service development/ neighbourhood management/ Alan W/JT | Leadership priorities (profile of city) Think Customer/Cabinet workplan/regeneration : Target date; 100 days mid June 2005. Complete September 2005 |  |  | Work in progress. On target

## Key service improvements
Improvement area 6 - KEY SERVICE IMPROVEMENTS | [5 empty] | 8th September 2005
The council's strategic and corporate approach has developed significantly since 2002, in many areas, as evidence by the CPA pilot inspection.
The report did however identify a small number of improvement areas, which are detailed below
Item | Action/Activity | Responsible Member/Officer(s) | Milestones/Targets | Resources | Improvement area identified in: | Current position | On target?
6.1 | Complete the review of stock options whilst continuing to support NPHL in achieving a 2* status so as to release decent homes funding | Lead Member housing/RO | Complete review of stock options by end April 2005 |  | Pilot CA report (18 (Para 74)) | Complete
| Report to Cabinet |  | by end May 2005 |  |  | Complete
| Government office sign off |  | June 2005 |  |  | On target
| Prepare 2* status delivery plan for 2005/06 |  |  |  |  | Delivery plan in place (July 2005). Progress is monitored at the SCC/NPHL monthly business meetings.
| Inspection |  | Date for re-inspection to be determined following Gov't announcement of timetable for round 6 bids. Gov't announcement anticipated September 2005.
6.2 | Implement a JVC in Development Services to generate, amongst other things, investment towards highway improvement | Lead Member planning/MS |  |  | Pilot CA report (19 (Para 78))
| Establish JVC (Urban Vision) |  | to commence 01.02.05 | Existing |  | Urban Vision commenced 01.02.05
| Complete formal highways pilot |  | April 05 | Existing |  | On schedule
| Commence first tranche of highway improvement funding (£6m) |  | from June 05 | Prudential borrowing |  | On schedule
| Further 4 tranches of £6m per annum |  | from April 06 | Prudential borrowing |  | On schedule
Item | Action/Activity | Responsible Member/Officer(s) | Milestones/Targets | Resources | Improvement area identified in: | Current position | On target?
6.3 | Improvements in key educational attainment | Lead Member children's services/JB |  |  | Pilot CA report (26 (Para 125))
| Implement in full the improvements in the Education Development Plan and subsequent revisions for children's services |  | % of 5A*-C GCSE's or equivalent to improve greater than the national average in 2005 |  |  | Provisional data for 2005 shows an increase of 8 percentage point to 46.3% (this equates to aan pproximately 22% improvement). This is the highest increase in Greater Manchester and likely to be one of the highest nationally
|  |  | All schools in OFSTED categories to be removed from the designation within stated timescales |  |  | Primary Partnership Centre removed from Special Measures Spring Term 2005. Other 4 schools still in special measures and one of these has been in special measures for 2 years.
|  |  | Overall performance in English and Maths at KS2 to be above the average of statistical neighbours and continue to show year on year improvement |  |  | 2005 KS2 performance in English was the second most improved nationally, in Science third most improved and Mathematics twenty sixth most improved. Salford is now at the national average in all three areas. We have the top performance of statistical neighbours in English and third in Maths and Science.
6.4 | Improvements in children's social services | Lead Member children's services/JB/ Anne W | Aim to improve educational performance of children looked after, reduce offending and absence from school rates for children looked after | Existing |  | Action plans in place for all these areas. New project with YOT on offending by LAC. Staff being designated to tackle attendance problems.
Item | Action/Activity | Responsible Member/Officer(s) | Milestones/Targets | Resources | Improvement area identified in: | Current position | On target?
|  |  | Improve assessment times | Existing, plus additional resources for data cleansing |  | Performance significantly improved (21.7% to 86% core assessments on time). However severe shortage of social workers is likely to impact on future performance
6.5 | Improvements in the environment
| Comply with statutory recycling targets through a range of activities including increasing kerbside collection and increasing/improving recycling sites | Lead Member environment/ BJ | Improve recycling rate to 20% by March 2006 | Bid into DEFRA funding to obtain finance |  | Recycling rate for 2004/05 is 12.15%. Action plan being developed and implemented in order to achieve 2005/06 20% target. In addition, developing action plan for further increases beyond 2005/06. Currently chasing the very challenging 20% target which needs to be achieved by March 2006. 1st qtr 2005/06 performance was 16.1%.
| Establish an effective education and enforcement regime regards environmental crime and prevention, in partnership with LSP and police | Lead Member environment/ BJ | Establish post of environmental crime co-ordinator | Financial resources identified |  | Apopointment to post of Environental Crime Co-ordinator achieved. Educational and enforcement action being undertaken. PCSO's and other Council Officers serving FPN's in relation to littering and dog fouling offences.
Item | Action/Activity | Responsible Member/Officer(s) | Milestones/Targets | Resources | Improvement area identified in: | Current position | On target?
|  |  | Develop programme of enforcement/education by September 2005 |  |  | Draft Environmental Crime Reduction Strategy written and being discussed with relevant partners. Environmental crime incorporated into the CDRP Strategy - 2005/08. On target to develop action plan by Sept. 2005. Environmental Crime Co-ordinator likely to be appointed late June 2005
6.6 | Reducing crime and perception of crime through the council's community safety strategy | Leader/JCW/DB | See details in community safety strategy |  |  | At September 2005, the position is: Burglary and vehicle crime public service agreements targets were achieved at the end of financial year 2004/05. New public service agreement targets are being negotiated around reducing crime and anti-social behaviour. Of the 16 targets in the 2005-08 community safety strategy 8 are on target and 2 are not on target (assaults and wounding and hate crime reduction). The remainder are either not yet due for reporting or are within timeframes for setting baseline targets.
Item | Action/Activity | Responsible Member/Officer(s) | Milestones/Targets | Resources | Improvement area identified in: | Current position | On target?
6.7 | Develop Council's response to the Gershon efficiency review | Lead Member customer and support services/Alan W / JS |  |  | Review of Gershon requirements August 2004
| Establish think efficiency team |  | 2004-08-01 |  |  | Achieved - meeting fortnightly
| Establish cabinet sub-group |  | Inaugural meeting April 2005 |  |  | Achieved
| Prepare efficency plan for 2005/06 |  | By 31 March 2005 |  |  | Plan submitted backward look for 2004/05 to be prepared by 15 June 2005
| Submit 2005/06 ODPM efficiency return |  | By 15 April 2005 |  |  | Achieved
| Submit 2005/06 backward looking efficiency return |  | By 15 June 2005 |  |  | Achieved
| Develop efficiency plans for future years |  | Ongoing during 2005/06 |  |  | Ongoing

## Appendix
APPENDIX
Table of Weaknesses
Pilot Corporate Assessment - Sept 2004
Ref | Theme | Weakness | Report Para | Imp area
1 | Ambition | Not yet fully effective in consulting and engaging with all of Salford's diverse communities | 23 | 3
2 |  | Quality of plans is mixed | 22 | 2
3 | Prioritisation | Targets are not consistently specific and measurable and linked to outcomes | 28 | 2
4 |  | Targeted consultation undertaken to build knowledge base but this is not yet driving design, delivery and evaluation of services | 31 | 2
5 |  | Tools to ensure focus are not consistently effective | 35 | 1
6 |  | Processes and criteria for allocation of resources lack clarity | 36 | 2
7 |  | No systematic impact analysis of resource shifting | 37 | 2
8 |  | Learning is not systematic and effective across the council | 39 | 4
9 | Capacity | Scrutiny is not fully effective | 42 | 1
10 |  | Risk management not fully embedded at operational level | 44 | 2
11 |  | No corporate procurement strategy | 50 | 5
12 |  | HR strategy has been revised but is not yet embedded | 45 | 4
13 | Performance | Not yet built a culture of performance management | 55 | 2
14 | Management | Members not effectively involved in performance management outside of cabinet | 56 | 1
15 |  | Track record in meeting targets is poor | 58 | 2
16 |  | Performance monitoring inconsistent and weak information systems in some areas inhibit effective performance management | 57 | 2
17 |  | Limited performance information for users and stakeholders | 61 | 3
18 | Sustainable communities | Yet to identify how it will meet DHS standard in relation to council housing stock | 74 | 2
19 | and Transport | Mixed performance on transport BVPI's | 78 | 2
20 | Safer and | Crime levels remain high | 80 | S
21 | stronger communities | Community cohesion is not strong although the council is working to address this | 92 | 3
22 |  | Emergency planning is not effectively integrated with business continuity planning and risk management | 96 | 2
23 | Healthier communities | Some success in meeting needs of all sections of the community but no real coherence to the approach to making services available to marginalised groups | 98 | S
24 | Older people | Development of integrated services for older people with health needs has been slow |  | *
25 |  | Plans for this area are under-developed and lack clear targets | 110 | S
26 | Children and young people | Progress in improving outcomes for young people in many key areas has been slow and majority of PI's failed to meet targets | 125 | 2,S
27 |  | High numbers of looked after children and rising costs | 126 | S
28 |  | Lack of overall preventative strategy | 131 | S
* Not really in keeping with revised text of report
S = Service area comment, rather than corporate.

## Abbreviations
Abbreviations
Initials | Name | Designation
AE | Alan Eastwood | Head of law and administration
Alan W | Alan Westwood | Strategic Director - Customer services and finance
Anne W | Anne Williams | Strategic Director - Community, health and social care
BJ | Bruce Jassi | Strategic Director - Environment
BW | Brian Wroe | Assistant Director - Community services
DB | Don Brown | Community safety manager
DH | David Horsler | Assistant Director - Human resources
DS | Don Simpson | Assistant Director - Audit and risk management
GA | Gary Amos | Assistant Director - Procurement
HW | Hilary Wensley | Joint head of mental health commissioning - Salford PCT
JB | Jill Baker | Strategic Director - Children's services
JCW | John Willis | Chief Executive
MB | Mike Bleese | Head of personnel services
MS | Malcolm Sykes | Strategic Director - Housing and planning
PT | Peter Towey | Emergency planning officer
PW | Paul Woltman | Assistant Director - Children commissioning
RB | Russell Bernstein | Assistant Director - Police and scrutiny support
RF | Ruth Fairhurst | Head of regeneration and improvement
RO | Bob Osborne | Head of housing
SH | Sue Hill | Corporate marketing manager
TM | Tom McDonald | Deputy Director - Community, health and social care