APPENDIX B – SALFORD DAT TREATMENT PLAN 2002/03

Section 6

###### DAT Reporting and Planning Grids

Please complete one of these tables for each of the DAT’s 2001/02 priorities and any new priorities for 2002/03

| What is / was the DAT priority: | Increase new referrals into treatment |
| --- | --- |
| What is / was the baseline position in relation to this priority? | From 301 1999/2000 to 410 2000/01 (Drug Misuse Database) |
| What is / was the target position in relation to this priority? | 458 by April 2002 (NDTMS source), achieve restricted practice, review community services |
| To which area of the national drugs strategy does / did this priority relate? | Adult Treatment |

| Action | Timetable | Outputs | Outcomes | Planned spend 2001 / 2002 | Actual spend 2001 / 2002 | Planned spend 2002 / 2003 | Lead agency | Monitoring arrangements | Comments on progress |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Expand Shared Care | March 2002 | Numbers of posts total = 8 Additional 2 funded via pooled budget | GP’s= 125 involved = 63 Full shared care programme= 28 | £280,000 | £280,000 | £436,000 | Salford Drug Service (SDS) – Richard Rodgers (RR) | Shared Care Monitoring Group (SCMG) – quarterly report Joint Commissioning Group: JCG | Posts agreed Further monitoring and information systems to be established |
| Appoint specialist generalist | By July 2002 | In post GP’s engaged at higher levels of shared care | Numbers of GP’s involved at higher levels of involvement | N/A | N/A | £50,000 - £65,000 | SDS (RR)– Salford PCT Alan Higgins (AH) | SCMG JCG | Post to be established during 2002/03 |
| Develop home detox service | Established | Numbers of service users involved 42 | Completed successfully - 23 | £15,000 | £15,000 | £27,500 | SDS (RR) | Via (JCG) | Very promising early results Requires formal evaluation |
| Enhance low threshold provision | Established | Service users involved - 20 | Developed a more stable profile for treatment - | £30,000 | £30,000 | £33,000 | SDS (RR) and Salford and Trafford Action on Street Health (STASH) Steve Simmons (SS) | Via JCG | Further possible extension of this programme to be considered |
| Improve access to services out of hours | Established | Late evenings Saturday | Numbers of service users User profiles | N/A | N/A | N/A | SDS (RR) | Via JCG | Monitored via new information systems |
| Review services for stimulant users | During 2002/03 | Review to be conducted | Report to be produced | £50,000 | £50,000 | £50,000 | DAT Colin Wisely (CW) | Via JCG And DAT | New recommendations due during 2002/03 |
| Develop Dual Diagnosis strategy | During 2002/03 | Review to be conducted | Report to be produced | N/A | N/A | N/A | SDS (RR) DAT (CW) | Via JCG and DAT | Recommendations due during 2002/03 |
| Acquire new premises | Established | N/A | N/A | £70,000 | £70,000 | £50,000 | SDS (RR) STASH (SS) and DAT Don Richards (DR) | Via JCG | Building work underway, new premises under review |
| Expand outreach | 2002/03 | Numbers of out of reach users contacted | Numbers of users 1.Vaccinated 2. Involved in research project 3. Entering treatment subsequently | N/A | N/A | £20,000 | STASH (SS) | Via JCG and CAD | Local reports produced during 2002/03 |
| Develop local responses to issues of diversity | 2002/02 | Development of local projects Formal review of needs | New activity commissioned | N/A | N/A | N/A | JCG (CW) / CAD Jane Birch (JB) | Via DAT | Project underway |

Please complete one of these tables for each of the DAT’s 2001/02 priorities and any new priorities for 2002/03

| What is / was the DAT priority: | Reduce Drug Related Deaths |
| --- | --- |
| What is / was the baseline position in relation to this priority? | Low level of information – 10 DRD’s reported during 2001 |
| What is / was the target position in relation to this priority? | Improved level of information – development of local confidential enquiry – develop retrospective studies into recent deaths – review local homicides |
| To which area of the national drugs strategy does / did this priority relate? | Adult Treatment |

| Action | Timetable | Outputs | Outcomes | Planned spend 2001 / 2002 | Actual spend 2001 / 2002 | Planned spend 2002 / 2003 | Lead agency | Monitoring arrangements | Comments on progress |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Develop observed consumption schemes | Established | Numbers of pharmacists involved in scheme | Numbers of new clients participating in scheme | £20,000 | £20,000 | £22,000 | SDS (RR) / JCG (CW) | Via DAT | Services developed |
| Improve dose induction | By April 2003 | Conduct review | Produce report | N/A | N/A | N/A | JCG (CW) | DAT |  |
| Introduce First Aid training | During 2002/03 | ? | ? | ? | ? | ? | ? | ? | Awaiting guidance from NTA |
| Develop A and E needs assessment | During 2002/03 | Conduct needs assessment | Produce report | N/A | N/A | £10,000 | JCG (CW) | DAT |  |
| Improve level of information | During 2002/03 | ? | ? | ? | ? | ? | ? | ? | Awaiting guidance from NTA |
| Develop local confidential enquiry | During 2002/03 | ? | ? | ? | ? | ? | ? | ? | Awaiting guidance from NTA |

###### DAT Reporting and Planning Grid

Please complete one of these tables for each of the DAT’s 2001/02 priorities and any new priorities for 2002/03.  Plans and reports may cover more than one financial year.

| What is / was the DAT priority: | Tackle Blood Borne Diseases |
| --- | --- |
| What is / was the baseline position in relation to this priority? | Local activity underway around Hep B-low level of Hep C activity |
| What is / was the target position in relation to this priority? | To increase level and range of activity with HIV/ hepatitis A,B and C |
| To which area of the national drugs strategy does / did this priority relate? | Adult Treatment |

| Action | Timetable | Outputs | Outcomes | Planned spend 2001 / 2002 | Actual spend 2001 / 2002 | Planned spend 2002 / 2003 | Lead agency | Monitoring arrangements | Comments on progress |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Increase Hep B vaccination programme | 2002/03 | Numbers of vaccinations in 2001=500 2002=1000 | Numbers of individuals completing programme | £20,000 | £20,000 | £35,000 | Salford drug service/ STASH | Via DAT/JCG | Project underway |
| Join anonymous testing programme | From April 2002 | Numbers of clients tested | Data available | N/A | N/A | N/A | SDS | Via DAT | Due to begin April 2002 |
| Review local Hep C strategy | By April 2003 | Report produced | New activity planned | N/A | N/A | N/A | JCG | Via DAT | underway |