PUBLIC LIBRARY POSITION STATEMENT 2003

Salford City Council

###### INTRODUCTION

I am delighted to introduce Salford City Council’s Public Library Position Statement for 2003.

It is produced at a really exciting time for our service as the plans developed in our Library Review of 2000 and subsequent Annual Library Plans begin to bear fruit in terms of

- rising visitor numbers

- completion of ICT services

- a new partnership between libraries and Salford Direct to develop corporate e-government initiatives

- the introduction of two new Special Needs Mobile Libraries

- The £200,000 increase in the materials fund which will support our Reader Development and community ICT policies.

Most exciting of all are the plans for new and redeveloped library buildings and the redesign of the services within them, currently,

- Salford’s four main town centre libraries will be rebuilt as part of the LIFT Private Finance Initiative in partnership with the Primary Care Trust

- we look forward to opening a new library in the new Albion High School in October

- Winton Library will be rebuilt as a Family Centre and Library in partnership with Sure Start

- there are also plans to develop libraries in multi-use sites [community hubs] in Broughton and Little Hulton

- Ordsall Library has already transferred to a community site, which includes Job Centre, Community Arts and other neighbourhood facilities.

The City Council fully supports the vision of the Department for Culture, Media and Sport as described in “Framework for the Future” and this is reflected in our actions and future plans.  We are also keen to reflect the ideas expressed in “Building Better Library Services” [Audit Commission] and “Better Public Libraries” [CABE] and we have ample opportunity to show this over the next few years as libraries are rebuilt, relocated and redesigned.

Cllr. Barry Warner

Lead Member for Arts & Leisure

Salford City Council

1.	CORPORATE VISION

1.1	VISION AND AMBITION FOR THE PUBLIC LIBRARY SERVICE

    - Vision - The City’s vision for the public library service is clearly stated in the Cabinet’s approval of the Library Review [2000] and subsequent Annual Library Plans.  The key elements being:-

- A wide branch network in shared/multi-use community spaces

- Investment in materials

- Developing the public libraries as a corporate asset in terms of modernising local government and e-government

- Investment in ICT for the public and as part of the corporate network

- Developing reading, lifelong learning and partnerships with schools and families.

The City’s Strategic and Best Value Performance Plan 2003/4 shows that these key elements reflect the objectives of the City and the Local Strategic Partnership [LSP], particularly in: -

| Mission | To create the best possible quality of life for the people of Salford |
| --- | --- |
| Council Pledges | Stronger communities; Supporting young People; Better education for all; Safer Salford |
| Community Plan [LSP] | A City that’s good to live in; A learning and creative City; A City where children and young people are valued; An inclusive and economically prosperous City. |
| Shared Government priorities | Creating safer and stronger communities; Raising standards across schools; Promoting healthier communities and independence for older people. |

[Strategic and Best Value Performance Plan 2003/4.  City of Salford. 2003]

    - Capacity – In spite of very difficult financial circumstances, the authority has managed to take financial and strategic steps towards realising the vision for public libraries [detailed below].  It is clearly acknowledged that the service can assist in achieving many corporate objectives from the focus on customer access and community cohesion to a major partnership with the local NHS Primary Care Trust.

Realistically, the key limits and barriers to the capacity of the authority to meet the vision are financial and are most often a result of external factors such as the level of standard spending assessment and major legislative demands.  These limits have already led to some delay in delivering the library strategy, although there has been no reduction in the basic momentum towards achieving the vision.

    - Evidence

- £100,000 addition to Materials Fund 2002/3

- Further £100,000 addition to Materials Fund 2003/4 [i.e. Total £200,000 new revenue]

- Development of Winton Library in partnership with Sure Start

- Four new main libraries as part of Primary Care Centres in four town centres.

- A new Community Library integrated into a new High School [October 2003]

- Financial support for regrading most front-line staff to work with Salford Direct on information, customer services and e-government

- Proposed further development of Little Hulton and Broughton Libraries into new ‘community hub’ buildings

- Relocation of Ordsall Library in a multi-use neighbourhood centre building

- Corporate partnership on developing the People’s Network and its continuing use for the modernisation of local government and lifelong learning

2.	RESPONSE TO “FRAMEWORK FOR THE FUTURE”

  - BOOKS, READING AND LEARNING

2.1.1	Key Strengths/Constraints/Challenges

Strengths – Underpinning the proactive development of reading and learning outlined in previous plans is the £200,000 increase in the materials fund for 2003/4 [£100,000 in 2002/3].  The City has therefore managed, in a difficult financial environment, to continue to fulfil its commitment to the Library Review, subsequent ALP Action Plans and to achieving the Public Library Standards.

The service is represented on the Salford Lifelong Learning Partnership and the Family Learning Steering Group

Reader Development

- Reader Development Officer appointed May 2002 and mainstream funded

- Reader Development Strategy published and approved

- Reader Development training for all staff – external (Book Communications Ltd) and on-going internal by Reader Development Officer

- Active promotional campaign – part of Greater Manchester group – Galaxy Radio jingle and bus campaign

## Children’s Services

- Specialist Children’s Team

- Salford Children’s Book Award

- Children’s Summer Reading Game (national)

- Summer reading game for under 4s (Sure Start areas)

- Partnerships with Sure Start

- Bookstart project, including the innovative Bookstart and Beyond for children between 10 months and 4 years

- Bookstart and Beyond Development Officers

- Annual Children’s Book Festival

- Homework Help Clubs

## ICT

- Free and assisted access to PCs, software and internet

- IT learning support – access to equipment and trained staff

- LearnDirect access points

- Locally based service, easily accessed by local community

- Partnerships with Community ICT/Adult and Community Learning

- Partnership with Heritage Service to use Wolfson and NOF Digitisation funds to develop community access to heritage materials

- Association with community–based learning organisations e.g. University of the Third Age, IAG Network, Adult learners’ Forum

Inclusion

- Books @ Home – radical reorganisation of the mobile services, leasing 2 new vehicles in 2004 to serve those with Special Needs

- Connexions Information Access Points in all libraries

- Special Interest collections – Jewish Collection, collections for under 5s, Working Class Movement Library, partnership with Community Heritage Team to develop access to local heritage

- Reduction in reservation fees to 10p

# Constraints

- Pressures on the City Council budget

- Lower than average professional staff numbers

- Long-term sustainability of grant -funded partnerships and projects –Sure Start, ICT in the community (SRB and ERDF funding)

- Delayed introduction of Sunday opening and extended hours generally

- Late start of Computerisation

- Library opening hours still do not reflect need

- Publishing world limited and short-term availability of some stock

- Socio-economic and cultural factors affecting audience responsiveness to reading and learning

# Challenges

- To meet increasing demand for library materials which reflect the reading and learning needs of our diverse community

- To continue to maximise opportunities for informal learning

- To track the progress of customers using the People’s Network

- Reaching non-users, particularly hard to reach groups

- Ensuring additional materials funds are spent effectively and results in increase in usage

- More coherent marketing strategy

- Rationalising opening hours to meet user and potential user need

- Developing informal and semi-formal learning opportunities and ensuring take-up

# Policies and Practices for adults and children

Policy is supported by agreed strategies related to Stock Management, Reader Development, Children & Young People, ICT and Marketing.  Key elements in all policy development relate to:-

- Ease of access - neutral, welcoming, non-institutional local environments are key to widening access in an area such as Salford

- Partnership working with, for example, Adult and Community Learning, colleges, Sure Start and others to ensure that opportunities for informal learning are maximised

- Non-users – developing strategies to attract non-users and lapsed users, ensuring that services meet their needs – e.g. opening hours, library environments, range of services

- Free services - where possible, charges are minimised

- Resource priority for children, young people and special needs

- Access to People’s Network to be simple and easy while maintaining monitoring regime

    - Develop and Evaluate practice

Throughout the service, evaluations of existing practice and ideas for new innovative practice are fed through appropriate groupings and forums, ultimately to the Library Management Team.  Service change and development arising from this is fed into the directorate and corporate planning process [January to March] and budgets allocated where required or where possible.

- All events and activities are evaluated statistically

- Some events and activities use feedback forms

- Specific target groups [teachers, parents, carers] are regularly asked to comment on specific practices or services in general

- Evaluations are used by a range of groups to determine development:-

  - Children’s Team

  - Staff Reader Development Group

  - Staff ICT Group

  - Salford Lifelong Learning Partnership

  - IAG Network Meeting [Greater Manchester]

  - Family Learning Partnership

    - Education Development Plan

The library service fits into the Education Development Plan [EDP] in terms of: -

- Assisting in raising achievement at all key stages

- Project based work, such as organised visits to libraries to undertake specific projects and curriculum based project packs to support school work and raise achievement

- Activities centred on Literacy and English

- Policy and action plans in the areas of lifelong learning and out-of-hours learning

The current EDP has limited specific reference to the service, however, discussions with the Assistant Director [School Improvement] are underway aimed at far closer involvement, especially specifying library service work that adds value to the 5 priorities, especially,

- Raising attainment at Early Years, Key Stage 1 and Key Stage 2

- Raising attainment at Key Stage 3

- Raising attainment at Key Stage 4

- Schools Causing Concern

- Inclusion – Narrowing the Gap and Tackling Under Achievement

    - Priorities and Targets

| PRIORITIES | ACTIONS | TARGETS & TIMESCALES |
| --- | --- | --- |
| 1. Widen and increase user base | Continue to develop the Bookstart and Bookstart and Beyond schemes | 3 new schemes in place |
|  |  | March 2004 |
|  | Continue non-user and lapsed user surveys | 1 non-user survey to be completed |
|  |  | March 2004 |
|  | Complete Opening Hours Strategy Complete Marketing Strategy | Completed Completed |
|  |  | March 2004 |
| 2. Maximise the value of additional Materials Fund. | Continue to implement Stock Management policy | Carry out stock audits at each library Develop stock profiles for each library Assess stock selection procedures |
|  |  | December 2005 |
|  | Continue outreach through Reader Development Strategy | Set up reading groups in 2 libraries |
|  |  | December 2003 |
|  |  | Continue staff training |
|  |  | Ongoing |
|  |  | Community learning programme – The Big Read at Little Hulton |
|  |  | September 2003 to June 2004 |
|  | Raise profile of Reader Development work throughout the region and develop best practice | Continue work with North West Time to Read Group |
|  |  | Ongoing |
| 3. Increase informal learning opportunities | People’s Network Marketing Strategy | Local promotion and marketing at each service point |
|  |  | March 2004 |
|  | Take opportunities through SRB and ERDF funding to continue links to adult and community learning | Minimum of 3 externally funded ICT support posts to March ‘05 |
|  |  | Bid by January 2004 for funding to March 2005 |

  - DIGITAL CITIZENSHIP

2.2.1	Key Strengths/Constraints/Challenges

Strengths

- Free unlimited access to ICT/Internet in 14 out of 16 libraries [2 libraries undergoing relocation]

- Partnership with Salford Direct to develop wider access to information and e-government transactions

- ICT development workers based in libraries offering one-to-one and group training in ICT skills, concentrating on basic ICT skills, in comfortable surroundings. Learners can then progress to accredited courses at colleges and LearnDirect centres. [350 sessions; 3560 hours from 9/02 to 9/03]

- ICT trained library staff to support use

- Computerised Community Information database, available via the Council’s web page

- DCMS/Wolfson joint digitisation project with Museums

- Relatively low computer ownership in the City, therefore potential to promote digital citizenship within libraries

Constraints

- Full computerisation not yet complete [due 2004]

- Sustainability of resources

- Limited ICT expertise of library staff beyond ECDL

Reliance on technical support at a corporate level

# Challenges

- Staff Training

- Promotion/marketing of People’s Network and ICT to non-library users

- Role of libraries within corporate e-government roll-out e.g. e-voting

- Adapting library role in ICT as more households become PC owners

# Policies and Practices

Policy and practice are determined by growing partnerships with

- Corporate Services’ Salford Advance Division, Community Telematics team and Customer Services Division.

- Salford Lifelong Learning Partnership

The Library Service fits into the web of e-government and digital citizenship developments as a key partner in the hub of each community, specialising in hard to reach groups, new users and those who are reluctant to use institutional settings.

- Most digital services must remain free –only printing is charged for

- Access to digital services should be easy and non-threatening –using trained staff and neutral welcoming environments, but encouraging a free, self-help culture.

- Staff assistance and support is vital, and this is enhanced by Outreach Workers funded by SRB/ERDF

# 2.2.3	Library Services users may access electronically in libraries and remotely

- Most libraries have OPACs, in fully computerised libraries customers can reserve stock

- Assisted or unassisted access to council payments facility in libraries

- Web access to library catalogue and user services 2005

- Access via web to library sites, opening hours and services details

- Book purchasing scheme via library or assistance with Amazon

- Access via web to community information database

# Library Service involvement in implementing e-government strategy

- As described elsewhere, Salford has a partnership with Salford Direct to assist the City to meet its e-government targets by providing local access to ICT facilities and encouraging citizens to use library ICT to conduct electronic transactions – by scanning forms, making payments on-line, etc.

- The library service maintains the Community Information A-Z for the web site and handles the general e-mail enquiry service received through the web site on behalf of the City Council

- The ICT in the community project, where one to one outreach work is being conducted in libraries.

- The promotion of the City Council web site through libraries providing access to information and on-line services

- The library service is one of the first services on the city’s new website [9/03]

    - Develop and Evaluate Practice

- People’s Network is closely monitored in terms of time, type of use, quality of use and details of user

- Customer feedback forms are used

- ICT outreach workers feedback the requirements and needs of their target clientele

- E-government team monitors citywide usage quarterly

- Regular reports are taken to the Salford Lifelong Learning Partnership and the Family Learning Partnership

- People’s Network Manager sits on the IAG Network Group [Greater Manchester], Adult learners’ Forum ICT Group, SRB5 development group

Evaluations are fed back to local staff and user groups and ultimately to the Library Management Team to develop policy and practice. [see also 2.1.2]

2.2.6	Priorities and Targets

| PRIORITIES | ACTIONS | TARGETS & TIMESCALES |
| --- | --- | --- |
| 1. Staff Training | Complete NOF funded training | All staff to ECDL level All staff to have completed NOF defined supplementary training Targeted advanced training |
|  |  | March 2004 |
|  | Develop targeted library management system training | All staff |
|  |  | December 2004 |
| 2. Promotion and marketing of People’s Network and ICT to non-library users | Maintain ERDF/SRB funded outreach posts | Minimum of 3 externally funded ICT support posts to March ‘05 |
|  |  | Bid by January 2004 for funding to March 2005 |
|  | People’s Network – local community launches | 8 launches |
|  |  | 3 in 2003/4 5 in 2004/5 |
| 3. Role of libraries within corporate e-government roll-out | Use of web cams and video conferencing for developing remote access to members and officers | Install and train staff |
|  |  | March 2004 |
|  |  | 4 pilots |
|  |  | September 2004 |
|  | Increase range of Salford Direct Services available from branches | Train all frontline staff |
|  |  | June 2004 |
|  | Pilot innovations – e-voting, broadcasting of meetings, community web sites | 4 exemplar projects |
|  |  | September 2004 |
| 4. Adapting library role in ICT as more households become PC owners | Research:- Percentage of home PC ownership Survey existing People’s Network users Research software which is not available or affordable for home use | Annual figures |
|  |  | Ongoing |

  - COMMUNITY AND CIVIC VALUES

2.3.1	Key Strengths/Constraints/Challenges

Strengths

- Partnerships – for example, Sure Start, Primary Care Trust [LIFT], Language Development Project, Family Support Team

- Close partnership with Heritage Services – Community Heritage Centres in 2 libraries; ‘LifeTimes’ activity in most libraries developing community cohesion; ‘Young Roots’ scheme.

- Use of libraries for Community Strategy development, Community Committees and Consultation events

- Locally based community libraries – often the only council service in an area and not regarded as ‘institutional’.

- Free community/meeting space

- 3 libraries established within community centres/neighbourhood centre

- 1 library established within a new High School

- Opportunity to re-locate libraries as part of LIFT

- Innovative library service to people in their own homes with two new vehicles and specially trained staff.

- ICT development workers based in libraries offering one-to-one and group training in ICT skills, concentrating on basic ICT skills, in comfortable surroundings. Learners can then progress to accredited courses at colleges and LearnDirect centres.

- ICT Development staff work with community groups to help them build websites. Once complete and ‘live’ the group members can use the People’s Network and PCs in other community access points to update the site

# Constraints

- Lack of knowledge of non-users needs

- Limited staff for outreach work

- Socio-economic conditions affect the acceptance of community and civic vales within many parts of the City.

Challenges

- Addressing gaps in the service within the City.

- Review of staff practices to enable more outreach work

- Engaging with hard to reach groups in the City.

Corporate working to provide improved services

# 2.3.2	Policies and Practices

The policy and practice on developing libraries in multi-use sites and acting as ‘hubs’ of the community are aimed at developing and assisting in community cohesion – plans are in place to locate all libraries in multiuse community sites [see 2.3.5 Priority 4]

- The radical developments around the LIFT PFI will ensure that the presence of the library, health facilities and One Stop Shop have mutual benefit and increase access and usage for all services.

- The opportunities to develop, ultimately, all Salford’s libraries in community sites, many of them new, allows the potential for user focussed services, both traditional and innovative, in every library.

- The Children’s and Young People’s Strategy is placing a clear priority on services for this group to develop long term community cohesion and civic value.

2.3.3	Actions which assist library users and non-users to develop citizenship and encourage a community identity

- ICT in the Community outreach work [in year to Sept 2003 – 42 courses; 272 people; 350 sessions; 3560 hours of training; at 9 libraries]

- Community web page development – using People’s Network sites

- Heritage links – using library sites and libraries with community heritage centres to develop the LifeTimes Community Heritage initiative

- Working with Community Committees to develop community use e.g. Worsley Library where the local Community Association has free and unassisted use of the library at all times.

- Use of libraries as drop-off points for ballot papers for postal vote

- Encouraging the setting up of self sustaining reading groups

- Encourage community to attend events that bring readers together e.g. author events

- Partnership working with other organisations – Sure Start, Age Concern, Action for Employment, local women and family centres

- New build sites will allow opportunities to design better community access,  for example “the living room in the city” .

2.3.4	Library service links into Authority’s plans to improve and develop customer service

- LIFT – [see above] – bringing One Stop Shop, primary health care and libraries together

- Salford Direct partnership – bringing the council closer to local communities through the libraries, and developing access to housebound and elderly through library mobile services

- Reviewing opening hours to better match local need

- Direct access to Council Services through the People’s Network

    - Development and Evaluation

As described in sections 2.1.3 and 2.2.5 evaluations and development initiatives are fed into the planning process via the Library Management Team. Evaluation specific to community cohesion and the development of civic values are:-

- Reading groups – using evaluation to work towards their self sustainability

- Work on website development in partnership with the ICT in the Community team

- Salford Direct and the formal feedback mechanisms associated with this

# Priorities and Targets

| PRIORITIES | ACTIONS | TARGETS & TIMESCALES |
| --- | --- | --- |
| 1. LIFT – taking the opportunity of new building to include retail entrances, café facilities, light, ‘domestic’ furniture, seminar rooms etc. | Ensure final plans have appropriate library layout and space for redesigned services. | Final plans |
|  |  | January 2004 |
|  | Plan service redesign – using staff forums, consultants, internal and external research | First library opens |
|  |  | Mid 2005 |
| 2. Filling service gaps in the City – new locations | Seek partnerships in order to develop library access sites in Blackfriars and Brookhouse areas | Identify partners and establish appropriate funding |
|  |  | Blackfriars by December 2004 Brookhouse by December 2005 |
| 3. Development of People’s Network | See 2.2.6 [above] | Ongoing |
| 4. Multi-use sites leading to local community hubs | Maintain momentum towards establishing al libraries in multi-use, community based sites | 4 multi use sites in 2003-4 8 multi-use sites in 2004-5 13 multi-use sites in 2005-6 All sites by 2008 |

  - BUILDING CAPACITY TO DELIVER TRANSFORMATION

2.4.1	Key Strengths/Constraints/Challenges

Strengths

- Partnerships to develop services – LIFT/Sure Start/Broughton Hub

- The Library Review [2000] and the commitment of the City Council to its recommendations

- ICT training and facilities paid for by the Opportunities Fund and the Bill and Melinda Gates Award

# Constraints

- Resource issues – limited opportunities for capital and revenue funded growth.

- Some staff resistance to change

# Challenges

- Developing services despite restricted budgets

- Building on partnership work – exploiting all opportunities

- Addressing staff resistance to change ( management of change)

- Reaching non-users

# 2.4.2	Improve Leadership/Staff Capacity and skills for service

- Two members of the library management team have taken part in e-learning pilot training programme for managers– once evaluated this will be extended to more staff

- Staff training in ICT skills/ reader development/work with Salford Direct

- Annual appraisal for all staff

- Race awareness training for all staff

- Disability awareness training

# 2.4.3	Develop and evaluate practice

As described in sections 2.1.3, 2.2.5 and 2.3.5 evaluations and development initiatives are fed into the planning process via the Library Management Team.  Transformation is being delivered at a rapid rate with new libraries opening and planned, and new ways of delivering services being integrated into service change.

Key elements in evaluating progress include,

- The formal appraisal system – annual, with six monthly review – where two way evaluation of change and training needs can be discussed and fed into training plans.

- Feedback from the growing number of staff groups, for example, joint staff forums for the development of services in the LIFT buildings, and library staff forums on service delivery and reader development.

2.4.4	Partnerships

| PARTNER | AREA OF WORK |
| --- | --- |
| Primary Care Trust | LIFT – four new town centre libraries |
| Sure Start | Bookstart; Bookstart and Beyond; capital investment in Winton Library |
| Connexions | Information Access Points in Libraries |
| Youth Service | Reader Development work, e.g. Rap Poet event |
| Salford Direct | Improving customer services |
| Community and Social Services | Review of use of community space |
| Schools | Schools Library Service; Children’s Services; New community library in new secondary school |
| Adult and Community Learning | Informal learning development; The Big Read; formal and accredited learning development |
| ICT in the Community | 3 Community ICT Development workers; piloting community web design |
| North West Time to Read | Developing best practice and continuing to raise the profile of reading development in the region |
| Heritage Service | Community based heritage |
| Education Welfare | Libraries host their outreach work |
| Community Associations and groups | Unique formal agreement at one library where Association has free unsupervised use of space; general meeting space |
| New Deal for Communities – Albion High | A new library in a new school which is now a pilot Extended School |

# 2.4.5	Priorities and Targets

| PRIORITIES | ACTIONS | TARGETS & TIMESCALES |
| --- | --- | --- |
| 1. Development of LIFT – | Taking the opportunity to carry out complete service re-design in four new libraries, using staff forums to deliver appropriate service redesign, | Pilot initiatives at LIFT sites |
|  |  | 2005/6 |
|  | Working with partner tenants to amalgamate reception, front of house and information delivery services | First site opens |
|  |  | 2005 |
| 2. Completion of Computerisation Project | All libraries have OPACs and computerised circulation | Completed |
|  |  | OPACs – March 2004 Circulation – December 2004 |
|  | Web access to computerised services, catalogue etc. | Catalogue and other services available on the Web |
|  |  | Estimated mid-2005 |
| 3. Review of working practices | Rollout from LIFT staff forums, see 1. [Above] |
| 4. Staff training | Key areas: Reader Development ECDL Advanced ICT | See 2.1.5; 2.2.6 [above] |

### Restructure [aimed at April 2004]

### Key aims: To better meet the new demands of service redesign, change and e-government, as well as the priorities including pre-school work, literacy and the development of informal learning opportunities

Key elements:-

- Matching skills to function

- Removing barriers to career development

- Service redesign and Business Process Re-Engineering in new town centre libraries

# 3	 PUBLIC LIBRARY STANDARDS – Standards not met

| STANDARD | MEET BY 2004? |
| --- | --- |
| PLS 3i Aggregate opening hours per 1,000 population for all libraries | YES |
| Once Ordsall and Charlestown libraries have relocated to permanent sites (by December ’03) opening hours will increase and standard will be met. |  |
| PLS 3ii Proportion of aggregate opening hours that fall outside 9am – 5pm on weekdays | NO |
| Local circumstances clearly show very low usage on dark evenings. Additional resources being sought for expanded weekend opening. The four LIFT libraries will aim at 9.00 a.m. to 10.00 p.m. opening in 2005/6 which will fulfil this Standard. |  |
| PLS 5 Percentage of libraries open more than 10 hours a week that have access to on-line catalogues | YES |
| Will achieve standard by December 2003, once all stock inputted |  |
| PLS 6 Percentage of static service points providing public Internet access | YES |
| Will achieve by December ’03, once Ordsall and Charlestown have relocated to permanent sites |  |
| PLS 9 Percentage of requests for books met within 7 days | YES |
| Completion of computerisation project and additional spending on books will assist in reaching this standard |  |
| PLS 11 Number of library visits per 1,000 population | NO |
| This is one of the key PLS and BVPIs at which the service plans are targeted. 2002/3 saw a 20% increase as the People’s Network and other developments came on stream. The plans for new library buildings and relocated branch services over the next 2 to 3 years could cause a downturn on this PLS as libraries are temporarily closed, temporarily relocated in less suitable premises, or working on reduced hours. Consultation with IPF will be required to assess the method of sampling during this period of radical change |  |
| PLS 13ii Percentage of child library users reporting success in gaining information as a result of a search or enquiry | YES |
| Children PLUS survey [2003/4] is expected to show the results of the improvements to staff training and ICT access for children over the last two years, resulting in meeting this Standard. |  |
| PLS 17 Annual items added through purchase per 1,000 population | YES |
| Increased Materials Fund will lead to this Standard being met in 2003/4 |  |
| PLS 18 Time taken to replenish the lending stock on open access or available for loan | YES |
| Increased Materials Fund will lead to this Standard being met in 2003/4 |  |
| PLS19i Numbers of staff per 1,000 population with appropriate management qualifications | NO |
| Local circumstances – e.g. the need for outreach to hard to reach communities, work on Sure Start and Reader Development – mean that traditional qualifications are not always relevant. The planned restructuring [see 2.4.6] will address these issues. |  |
| Pls19ii Numbers of staff per 1,000 population with appropriate ICT qualifications | YES |
| NOF ICT Training plan will reach completion in 2003/4 and standard will be met |  |

- 17 out of 28 Standards have been met by March 2003

- 25 out of 28 will be met by March 2004

  - Local Targets

    - Local targets from Annual Library Plan 2002 which were not met.

|  | INDICATOR | 2002/03 TARGET | 2002/03 ACTUAL | NOTES |
| --- | --- | --- | --- | --- |
| 1. | ISSUES |  |  | -7% and –11% Increased materials fund, marketing strategy, non-user surveys aimed at improvement |
|  | books/1,000 pop. | 4000 | 3707 |  |
|  | audio vis/1,000 pop. | 300 | 266 |  |
| 3. | HOMEWORK HELP CLUBS – USES | 1300 | 1259 | -3%. Increased promotion and closer work with schools |
|  | MEMBERSHIP OF PEOPLE’S NETWORK: SALFORD | 15,000 | 7,284 | -51% Delay in installation of People’s Network. Marketing initiatives, local launches, outreach workers aimed at improvement. See also Target 7. [below] |
|  | NO. OF CHILDREN (AGE 0<13) MEMBERS AS PERCENTAGE OF 0<13 POPULATION | 50% | 41% | -18% Rapid expansion of Bookstart and Bookstart and Beyond initiatives, plus marketing and closer work with schools |

    - Local targets from Annual Library Plan 2002 which were met by over 15%

|  | INDICATOR | 2002/03 TARGET | 2002/03 ACTUAL | NOTES |
| --- | --- | --- | --- | --- |
| 7. | USES OF PEOPLE’S NETWORK: SALFORD | 35,000 | 57,928 | +65% |
|  | CHILDREN INVOLVED IN ACTIVITIES/EVENTS/PROMOTIONS | 3,500 | 7366 | +110% |
| 10. | NO. VISITS TO AND BY SCHOOLS | 175 | 265 | +51% |
| 11. | NO. EVENTS HELD IN LIBRARIES |  |  |  |
|  | Library Organised - Children | 50 | 95 | +90% |
| 12. | NO. READER DEVELOPMENT PROMOTIONS |  |  |  |
|  | Displays | 32 | 42 | +31% |

    - Local Targets for Specific Groups

Other than for Services to Children local targets for specific groups have not been fully developed and this is recognised as a weakness.

Work has already taken place, with the Social and Community Services Directorate, the Development Services Directorate, the Chief Executive’s Directorate and other local agencies to gather baseline figures in order to establish local targets in these areas for monitoring in 2004/5. Work on benchmarking is ongoing amongst all members of the Greater Manchester Chief Librarians Group [includes Blackburn and Blackpool]

Outline local targets have been developed as follows:-

|  | PEOPLE WITH DISABILITIES | 2003/4 |
| --- | --- | --- |
| 1. | Items issued to housebound customers | Baseline from new mobile service determined in 2003/4. Target cannot be set to show continuous increase as services work to maximum capacity and have a waiting list Can be used to achieve extra capacity |
| 2. | Number of items issued to Visually Impaired People [Special needs Mobile] | As above |
| 3. | Number of items issued to Visually Impaired People [Branch Libraries] | Definitions being discussed |
| 4. | Service Satisfaction [users of Special Needs Mobiles] | Annual survey starts in 2003-4 |
| 5. | Percentage of mobile visits missed/cancelled | Baseline in 2003-4 |
| 6. | Number of uses of disability adapted People’s Network facilities | Monitoring methods for assessing use of adapted workstations and software. Baseline survey in 2003-4 |

| ETHNIC MINORITY COMMUNITIES |
| --- |
| 1. | New library users who consider themselves from ethnic minorities | At libraries with computerised membership Baseline in 2003-4 |
| 2. | Items loaned/used from Jewish Collection | Baseline in 2003-4 |
| 3. | Percentage of members who consider themselves from ethnic minorities | At libraries with computerised membership Baseline in 2003-4 |
| 4. | Numbers of People’s Network uses by ethnic minorities | Assessment methods being discussed |

| SOCIALLY EXCLUDED PEOPLE [see also Disability, Ethnic Minorities and Children] | 2003/4 |
| --- | --- |
| 1. | Membership of People’s Network | 20,000 |
| 2. | Number of PN sessions used | 75,000 |
| 3. | Number of Reader Development events | 40 |
| 4. | Number of people attending reader development events | 500 |
| 5. | Number of uses of Connexions Information Access Points | Baseline to be determined in 2003/4 |

| SERVICES TO CHILDREN [Some targets already developed] | 2003/4 | 2004/5 | 2005/6 |
| --- | --- | --- | --- |
| 1. | Homework Help Club usages | 1,300 | 1,400 | 1,500 |
| 2. | Children involved in activities/events | 7,500 | 7,750 | 8,000 |
| 3. | Number of events for children in libraries | 95 | 100 | 105 |
| 4. | Number of events for under 5s. | 200 | 300 | 350 |
| 5. | Number of children involved in events for under 5s | 2,500 | 3,500 | 4,000 |
| 6. | Number of visits to and by schools | 270 | 280 | 290 |
| 7. | Number of children joining a library as a result of receiving a Bookstart/Bookstart and Beyond pack | 200 | 300 | 400 |
| 8. | Percentage of 0<13 population who are library members | 50% | 55% | 60% |
| 9. | Percentage of Materials Fund spent on children [ultimate target to equal percentage of 0<13 as proportion of total population [currently 16%] | 15.5% | 16% | At least equal to the proportion of the total population |

- RESOURCES

  - SPACES

| STRENGTHS | CONSTRAINTS | CHALLENGES |
| --- | --- | --- |
| Wide branch network serving communities locally and often the only council building in a community Open, neutral culture Opportunities to rebuild and redesign four town centre libraries Opportunities to play key role in development of community ‘hubs’ or ‘campuses’ – 1 on line, 2 planned, further PFI opportunities in 2nd wave of LIFT Good level of building maintenance and of corporate Asset Management Planning Two new Special Needs mobile libraries | Financial restrictions could prevent best use of the opportunity High revenue cost of PFI leaseback arrangements | To maximise the opportunity for high quality design To maximise the opportunity for radical service redesign To maximise the opportunities for the library service to play its full corporate role in multi-use community sites To reconcile traditional views of the service amongst communities with the opportunity to fulfil “Framework for the Future”. |

|  | PRIORITIES | RESOURCE ADEQUACY | COMMITMENT |
| --- | --- | --- | --- |
| 1. | To fulfil PLS1 | Currently adequate | The City Council is committed to fulfilling the Public Library Standards |
| ONGOING |
| 2. | To maximise the number of libraries in multi-use community sites | Although one scheme has happened and 6 more are on line, capital resources are limited and revenue for lease back and service redesign is limited. | The City Council’s Asset management Plan has a key aim to reduce the number of buildings The City Council is committed to the LIFT scheme and is applying for PFI Credits. |
| ONGOING – dependent on LIFT, Sure Start and other community schemes [see Note Below] |
| 3. | To maintain the quality of library environments and to adapt them to the needs of a modern service. | Revenue budgets for furnishings and equipment are limited but have been used to good effect in partnership with corporate maintenance budgets | While additional revenue and capital are limited, the City Council is committed to providing a quality service, especially where multi-use sites maximise quality and close community cohesion. |
| ONGOING – rolling programme of building maintenance and refurbishment |
| 4. | Establish a library service in areas of need such as Blackfriars/Brookhouse | Currently inadequate but potential in Central Salford Redevelopment scheme. | The City Council is committed to this as part of the Review and ALPs, but resources are currently not available. |
| Aimed for 2005/6 |

NOTE:

TIMESCALES: -

The financial constraints and challenges will always be there, as the City Council balances priorities within limited resources. However, of the 16 branch libraries: -

- 3 libraries are in shared sites

- 1 opens in a new community school in September 2003

- 4 [main libraries] are to be developed as part of Primary Care Centres [2005]

- 1 has received funding for redevelopment under Sure Start [2004]

- There are plans for 2 more community ‘hubs’ to include a local  library [estimate 2005]

- 1 is planned to include a Tourist Information and Heritage Centre [2004]

- 1 is planned to develop closer physical and service links with the attached Youth Centre [2004]

- The potential for 2 more to merge under the second wave of LIFT is being examined.

- The location of the 16th is under review.

  - STOCK

| STRENGTHS | CONSTRAINTS | CHALLENGES |
| --- | --- | --- |
| £200,000 additional Materials Fund gives Salford adequate resources to develop and improve its stock and access to it. Specialist team of Children’s Services staff has been maintained Reader Development Officer mainstream funded Full computerisation to be completed in early 2004 Stock Management and Reader Development Strategies now complete Greater Manchester stock purchase consortium being established | A backlog of under-investment in stock leading to an ageing and declining stock Publishing world limited and short-term availability of some stock Socio-economic and cultural factors affecting audience responsiveness to reading and learning | Maximising the value of the additional resources Provision of new formats and new media. Meeting the needs and expectations of the diverse population |

|  | PRIORITIES | RESOURCE ADEQUACY | COMMITMENT |
| --- | --- | --- | --- |
| 1.. | Maximising the value of the additional resources | Good – materials spending in 2003/4 is above average at £2.6 per head | Proven by new funding |
| Ongoing |
| 2. | Provision of new formats and new media. | Adequate | Proven by new funding |
| Ongoing – key developments in 2003/4 with new funding |
| 3. | Promotion, marketing and market research | Limited | Commitment from corporate teams is likely |
| Non-user surveys 2003; Lapsed user survey 2004; Marketing Plan 2004 |

  - STAFFING

| STRENGTHS | CONSTRAINTS | CHALLENGES |
| --- | --- | --- |
| Some staff experienced in advanced ICT skills Specialist children’s team has been maintained Caring skills in branches and especially in Special Needs Service Growing number of externally funded outreach staff especially for BookStart and ICT | Numbers of staff do not meet current and developing need Current structure does not meet developing needs [see 2.4] | Restructuring within existing budgets Management of change Sustaining external funding or mainstreaming currently externally funded posts |

|  | PRIORITIES | RESOURCE ADEQUACY | COMMITMENT |
| --- | --- | --- | --- |
| 1. | Restructuring within existing budgets | Currently inadequate to meet current average staff levels | Management have the freedom to manage within budgetary limits and conditions of service agreements |
| APRIL 2004 |
| 2. | Management of change | External assistance required by all partners – likely to be funded jointly | Joint staff forums already taking place with support from Salford Direct, PCT and Personnel |
| Monthly joint staff forums at LIFT sites from July 2003 to service opening approx. 2005 |
| 3. | Sustaining external funding or mainstreaming currently externally funded posts | Currently OK. External funding streams need to be accessed regularly | Commitment from other departments and agencies to find funding for library partners. |
| Bids to SRB/ERDF/Sure Start by March 2004 Bids for growth to city council March 04, March 05 |

  - ICT

| STRENGTHS | CONSTRAINTS | CHALLENGES |
| --- | --- | --- |
| The People’s Network External funding for outreach Good partnerships within the council and outside agencies Corporate support for libraries ICT development and recognition of its corporate value Digitisation schemes in partnership with Heritage Services | Inadequacy of financial resource for clear sustainability and upgrading plans | Sustainability Ability to match new developments e.g. wireless technology, becoming a local ‘hotspot’ |

|  | PRIORITIES | RESOURCE ADEQUACY | COMMITMENT |
| --- | --- | --- | --- |
| 1. | Sustainability | Currently unclear | A very clear corporate commitment and drive |
| Bids for growth by Directorate ICT team |
| 2. | Ability to match new developments e.g. wireless technology, becoming a local ‘hotspot’ | Currently unclear | A very clear corporate commitment and drive |
| Continued work with corporate ICT and e-government teams |
| 3. | Sustaining and developing informal learning |  | Continuing partnerships with Community Education and Community ICT services |
| Continuing partnerships with Adult and Community Learning, Lifelong Learning Partnership, Community ICT, local IAG network, WEA etc. |