| PART 1 (OPEN TO THE PUBLIC) | ITEM NO |
| --- | --- |

#### REPORT OF THE LEAD MEMBER FOR

ARTS & LEISURE

TO THE CABINET ON 11 SEPTEMBER 2001

AND

TO THE SOCIAL SCRUTINY COMMITTEE

## ON

12 SEPTEMBER 2001

TITLE:	PROGRESS OF THE LIBRARY REVIEW AND THE STATUTORY PUBLIC LIBRARY STANDARDS

RECOMMENDATIONS:

- That Members note the progress made towards fulfilling the recommendations of the Library Review

- That Members note the necessary investment required to achieve the Public Library Standards by 2004

EXECUTIVE SUMMARY:

The report

- Provides a report on the achievement to date of the Annual Library Plan for 2001/2 and notes the shortfall in some of the necessary investment

- Describes the new statutory Public Library Standards, how Salford measures up to them and what targets must be achieved to meet the Standards by 2004

BACKGROUND DOCUMENTS:

- The Library Review

- “Comprehensive and Efficient” – Standards for Modern Public Libraries

- Annual Library Plan 2000

CONTACT OFFICER:  Robin Culpin, Head of Culture and Heritage

0161 736 9448.  robin.culpin@salford.gov.uk

WARD(S) TO WHICH REPORT RELATE(S):   All wards

KEY COUNCIL POLICIES:

- Introduction

1.1	The Library Review was approved in principle by Cabinet on June 13th, 2000 and was presented to the Social Scrutiny Committee on July 13th, 2000.  The Review was approved by the City Council on July  19th, 2000 subject to consultation with Community Committees.

1.2	The main recommendations of the Review were presented to seven out of the nine Community Committees.

1.3	The statutory Annual Library Plan was approved by Cabinet and sent to the Department for Culture, Media and Sport [DCMS] in September 2000 and received their top grading [grade 3 of a range from 0 to 3] for its quality.  The statutory Annual Library Plan for 2001 is due to be considered by Cabinet on September 25th, 2001, prior to submission to the DCMS.

1.4	The guidelines for the preparation of the 2001 Plan include the requirement to respond to the statutory Public Library Standards [DCMS . February 2001] in terms of: -

- Current performance

- Steps planned to ensure compliance with the Standards by March 2004.

- Estimated extra revenue funding required to comply with the Standards

  - This report details

A.	 Progress to date on the achievement of the Annual Library Plan 2000/2001

- The Statutory Public Library Standards - how Salford currently measures up to them, and what targets must be achieved to meet the Standards by 2004.

- Summary

2.1	Progress to date on the achievement of the Annual Library Plan 2000/2001

[See Appendix A]

    - The Library Review proposed a planned and coherent programme of investment and service variation over the three years to 2003/4 when the Public Library Standards need to be met.  2000/2001 is the first full year in which the three-year plan should take effect.

    - As Appendix A and the list below show, external funding and Directorate funding has been found to progress the development of the service, but there is significant shortfall in some areas:-

| Materials Purchasing Fund | £30k | No progress |
| --- | --- | --- |
| Backlog of stock shortfall | £100k | £25k from internal budgets |
| Computerisation | £10k | No progress |
| ICT for all libraries | £500k | NOF funds awaiting approval |
| ICT Training for staff | £65k | NOF funds approved |
| Staff – Reader Development | £13k in year 1 | Internal restructuring |
| Staff – ICT | £24k | Internal budgets |

    - In effect, much of the planned investment has been found, however, as Appendix B. shows and as the Library Review proposed, without significant funding for stock and the computerisation to manage it, several of the key Public Library Standards will not be met.

2.2	The Statutory Public Library Standards - how Salford currently measures up to them, and what targets must be achieved to meet the Standards by 2004. [See Appendix B]

    - As Appendix B shows,

- Salford’s branch network fulfils the Standards on access and opening hours [PLS 1 – 4], although the convenience of those hours will be subject to a further Standard to be developed

- Current arrangements already fulfil the Standards loan periods etc. [PLS 4,7,8]

- The People’s Network funding will allow the ICT Standards to be met by 2004 [PLS 6]

- Perceptions of our existing staff and management fulfil the satisfaction Standards   [PLS 12-15]

2.2.2	However, without sustained investment in stock, staff and computerisation over three years several of the key Standards will not be met by 2004, and could lead to the possibility of inspection and ‘special measures’. Especially,

PLS5		access to on-line catalogue

PLS9 		speed of response to requests

PLS11		visitor numbers

PLS17, 18	annual stock acquisitions

2.2.3	As Appendix B shows, Salford’s indicators for the above Standards are so low that only a sustained period of coherent investment can ensure that the targets, which are about to be sent to the Department for Culture, Media and Sport in the statutory Annual Library Plan, are realistic.

A.	Progress to date on the achievement of the Annual Library Plan 2000/2001,

|  | SUBJECT | 2001/2002 | Investment/Savings | Progress to 31/8/01 |
| --- | --- | --- | --- | --- |
| 1. | Branch Library Network [Rec. 1,2] | Assess existing library sites/staffing against cost, siting, partnership criteria | To be determined | Charlestown and Ordsall moved to temporary shared sites. Discussions on new central Walkden multi-purpose facility Feasibility proposed for alternative sites for Hope Library |
|  |  | Identify appropriate sites for new services | To be determined | Sites under consideration in Blackfriars area |
| 2. | Mobile and Special Needs Services [Rec. 3,4] | Phase out General Mobile Library | Save £30k | See below |
|  |  | Lease new Housebound and Special Needs vehicles | Revenue 20k | Specification for 2 new Special needs vehicles complete Timetables being redrawn General Mobile to be taken off road in 2002 |

|  | SUBJECT | 2001/2002 | Investment/Savings | Progress to 31/8/01 |
| --- | --- | --- | --- | --- |
| 3. | User/Non-user consultation [Rec. 5,6] | CIPFA Plus User Survey | Nil | Carried out in 2000/2001 Repeat in 2001/2 |
|  |  | Non-user Survey | Costs to be identified | Consultations taking place. |
| 4. | Resources – Books [Rec. 7 – 16] | Increase spending to Standard Intervention Point | Revenue £30k | No revenue increase |
|  |  | Address low stock levels | £100k | £25k from internal budgets |
|  |  | Define stock profile and stock standards for each level of branch | Nil | Awaiting computerisation of main libraries |
|  |  | Proactive promotion of stocks and services | See 7. Staff |  |
| 5. | Resources – audio-visual [Rec. 17-26] | Increase spending to national average | See 4 [above |  |
|  |  | Widen selection and availability of videos. Increase subscription charges. | Income £4k | Awaiting investment. See Section 4 |

|  | SUBJECT | 2001/2002 | Investment/Savings | Progress to 31/8/01 |
| --- | --- | --- | --- | --- |
| 6. | IT/ICT [Rec. 9 + 27-29] | Computerised Management System at 4 libraries | Revenue 10k | No revenue investment Eccles catalogue complete. On target for 2 libraries |
|  |  | Implement People’s Network Project | Capital [NOF] £486,000 City £46k match funding | Awaiting go-ahead from NOF |
|  |  | Implement NOF Training project | NOF £65,000 | Go-ahead from NOF received |
| 7. | Staff [Rec. 30, 31] | +2 ‘professional’ staff – reader development and ICT Development | Revenue £37,000 | Reader Development Officer starts Autumn 2001 [internal budgets] People’s Network Manager in post [internal budgets] |
| 8. | Income, fees and service adjustments Rec. 32 - 41 | Reduce loan period to 3 weeks | Increased income c.£1500 | User consultations taking place Planned for March 2002 |
|  |  | Develop and market Bookshop and book ordering facility | Increased income C.£3,000 | Increased marketing |

- B.	ASSESSMENT AGAINST PUBLIC LIBRARY STANDARDS

| Standard number | Standard | Standard Measure | Standard Met? (/ X | Authority’s measure of performance (2000/01) | Target for 2001/02 This year | Target for 2002/03 | Target for 2003/04 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| PLS1 (i) | Proportion of households living within specified distance of a static library | 95% | ( | 96% [1 Mile] | 96% | 97% | 98% |
| PLS1 (ii) | Proportion of households living within a specified distance of a library open during convenient hours | NYA |  | 96% [1 mile] | 96% | 97% | 98% |
| PLS2 (i) | Proportion of planned time that service points were not available to visitors because of emergency closure of central and branch libraries | NYA |  | 1.5% | 0.5% | 0.5% | 0.5% |
| PLS2 (ii) | Proportion of planned time that mobile service points were not available to visitors because mobile library visits/stops were missed or cancelled | NYA |  | 0.48% | 0.5% | 0.5% | 0.5% |

| Standard number | Standard | Standard Measure | Standard Met? (/ X | Authority’s measure of performance (2000/01) | Target for 2001/02 This year | Target for 2002/03 | Target for 2003/04 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| PLS3 (i) | Aggregate opening hours per 1,000 population for all libraries | 128 | ( | 131 | 131 | 131 | 131 |
| PLS3 (ii) | Proportion of aggregate opening hours that fall outside 9am to 5pm on weekdays | NYA |  | 19.6% | 19.6% | 19.6% | 25% |
| PLS4 | Percentage of larger libraries open at least 45 hours a week | 100% | ( | 100% | 100% | 100% | 100% |
| PLS5 | Percentage of libraries open more than 10 hours a week that have access to on-line catalogues | 100% | X | 0% | 12% | 50% | 100% |
| PLS 6 (i) | Total number of electronic workstations available to users per 1,000 population | 0.6 | X | 0.15 | 0.26 | 0.74 | 0.74 |
| PLS6 (ii) | Percentage of static service points providing public internet access | 100% | X | 25% | 50% | 100% | 100% |

| Standard number | Standard | Standard Measure | Standard Met? (/ X | Authority’s Measure of Performance (2000/01) | Target for 2001/02 This year | Target for 2002/03 | Target for 2003/04 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| PLS 7 | Normal book issue period | 3 weeks | ( | 4 | 4 | 3 | 3 |
| PLS 8 | Number of books that library users are allowed to borrow at one time | 8 | ( | 10 | 10 | 10 | 10 |
| PLS 9 (i) | Percentage of requests for books met within 7 days | 50% | X | 20 | 25 | 35 | 50 |
| PLS 9(ii) | Percentage of requests for books met within 15 days | 70% | X | 46 | 50 | 60 | 70 |
| PLS 9 (iii) | Percentage of requests for books met within 30 days | 85% | X | 79 | 80 | 85 | 85 |
| PLS 10 | Number of visits to the library Website per 1,000 population | NYA |  | 27.9 | 35 | 40 | 45 |
| PLS 11 | Number of library visits per 1,000 population | 6,000 | X | 3726 | 4300 | 5000 | 6000 |

| Standard number | Standard | Standard Measure | Standard Met? (/ X | Authority’s measure of performance (2000/01) | Target for 2001/02 This year | Target for 2002/03 | Target for 2003/04 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| PLS12 (i) | Percentage of adult library users reporting success in obtaining a specific book | 65% | ( | 75 | 77 | 80 | 83 |
| PLS12 (ii) | Percentage of child library users reporting success in obtaining a book | 65% | Available for 2001/2002 |  | 77 | 80 | 83 |
| PLS13 (i) | Percentage of adult library users reporting success in gaining information as a result of a search or enquiry | 75% | ( | 82 | 85 | 90 | 90 |
| PLS13 (ii) | Percentage of child library users reporting success in gaining information as a result of a search or enquiry | 75% | Available for 2001/2002 |  | 85 | 90 | 90 |
| PLS 14 (i) | Percentage of adult library users rating the knowledge of staff as ‘good’ or ‘very good’ | 95% | ( | 97.4 | 98 | 98 | 98 |
| PLS14 (ii) | Percentage of child library users rating the knowledge of staff as ‘good’ or ‘very good’ (same as PLS 15ii) | 95% | Available for 2001/2002 |  | 98 | 98 | 98 |
| PLS 15 (i) | Percentage of adult library users rating the helpfulness of staff as ‘good’ or ‘very good’ | 95% | ( | 98.4 | 98.5 | 98.6 | 99 |

| Standard number | Standard | Standard Measure | Standard Met? (/ X | Authority’s measure of performance (2000/01) | Target for 2001/02 This year | Target for 2002/03 | Target for 2003/04 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| PLS15 (ii) | Percentage of child library users rating the helpfulness of staff as ‘good’ or ‘very good’ (same as PLS 14ii) | 95% | Available for 2001/2002 |  | 98.5 | 98.6 | 99 |
| PLS16 | Quality index for stock (to be developed in 2001/02) | NYA |  | NYA | NYA | NYA | NYA |
| PLS17 | Annual items added through purchase per 1,000 population | 216 | X | 111 | 140 | 160 | 180 |
| PLS18 | Time taken to replenish the lending stock on open access or available for loan | 8.5 | X | 12.5 | 12 | 10.5 | 8.5 |
| PLS 19 (I) | Numbers of staff per 1,000 population with appropriate information management qualifications | NYA |  | 0.1 | 0.11 | 0.12 | 0.13 |
| PLS19 (ii) | Numbers of staff per 1,000 population with appropriate ICT qualifications | NYA |  | 0.1 | 0.17 | 0.33 | 0.42 |

Notes:

- The Recommendations of the Library Review proposed that without a coherent and early investment in stock, as well as the computerisation to manage it, and the staff to control and market it, the Library Service would not be able to meet the statutory Public Library Standards.

- The achievement against the Standards in the Year 2003/4 will determine whether Library Services will be further inspected or go into ‘special measures’.