| Part 1 (Open to the public) | ITEM NO. |
| --- | --- |

REPORT OF THE REGENERATION INITIATIVES CABINET WORKING GROUP

To the: Cabinet

On:	Tuesday 11th October ,2005

TITLE: Progress on Regeneration Programmes and Projects

RECOMMENDATIONS:
Members are requested to note this report

EXECUTIVE SUMMARY:
This report summarises the progress being made on key projects and programmes across the City.  This report is formatted according to Community Committee Areas.

BACKGROUND DOCUMENTS:
Community Plan, City Council Pledges, and Neighbourhood Renewal Strategy

ASSESSMENT OF RISK:
N/A

THE SOURCE OF FUNDING IS:
Various regeneration funds identified in the report

LEGAL ADVICE OBTAINED:
N/A

FINANCIAL ADVICE OBTAINED:
Nigel Dickens

CONTACT OFFICER:
Cath Inchbold, Assistant Director (Strategy and Regeneration), 0161 793 3796

John Bentley, Strategy and Resources Officer (Strategy and Regeneration) 0161 793 3449

WARD(S) TO WHICH REPORT RELATES:
All Wards

KEY COUNCIL POLICIES:
Regeneration

DETAILS:
N/A

Purpose of Report

To inform and up date on progress and issues surrounding key regeneration funding programmes and projects on a six weekly basis.

# Detail

This report summarises the progress being made on key projects and programmes across the City. It describes the activity in the Community Committee areas:

- Claremont and Weaste

- East Salford

- Eccles

- Irlam and Cadished

- Ordsall and Langworthy

## Swinton

# Summary of Key Issues

- Key developments have occurred over the past six weeks within the following areas:

| Pledge | Area | Key Developments |
| --- | --- | --- |
| All | Central Salford | A number of consultation and stakeholder events on draft Vision and Regeneration Framework undertaken in July – August 2005. Framework to be finalised in Autumn 2005. The Housing Market Renewal Scheme Update 2006 to 2008 is due to be submitted to the Office of the Deputy Prime Minister on Friday 7 October 2005. |
| All | Seedley & Langworthy | The Seedley & Langworthy Community Wardens were awarded ‘Team of the Year’ in the ODPM National Warden’s Awards. Seedley and Langworthy In Bloom announced as winner of the North West In Bloom 'Urban Regeneration award' for the third year running. |
| All | Charlestown & Lower Kersal | Announced as runner up in the North West in Bloom Urban Regeneration category. |
| Creating Prosperity | Salford Central Station | Network Rail confirmed as Project Manager for Phase 1. Phase 1 contract on site June 2006. Future improvement work will be lead by URC. |
| Enhancing Life | Higher Broughton | Vacant possession of the entire CPO No.1 area in Higher Broughton has now been achieved following intensive work to relocate the remaining residents over the last 8 months. Demolition of more than 200 units of housing is currently underway. Also construction of the first new build housing within Phase 1 of the development has started on the Playing Fields site with the new constructor partner Taylor Woodrow. |
| Enhancing Life | Lower Broughton | A new team consisting of a Sergeant, 4 PCs and 4 PCSOs has been set up to work in Higher and Lower Broughton. The team is based at Pendleton Police Station and aim to target persistent offenders and anti social behaviour in Lower Broughton. |
| Enhancing Life /Creating prosperity | Chapel Street | Network Rail confirmed as the Project Manager for Phase 1 improvements. |
| Enhancing Life /Creating prosperity | Greengate | Future context for Exchange Greengate will be established by URC’s Vision and Strategic Regeneration Framework. |
| Pledge | Area | Key Developments |
| Enhancing Life | Restoration Manchester Bury Bolton Canal | Maintenance funding now seems to be resolved. (Costs shared between City Council and developer of adjoining site). |

# Text boxes

###### Claremont and Weaste

Areas covered within this report:

Claremont Village

Weaste Renewal Area

- Work on the alleygating schemes in Weaste are complete, subject to some final snagging issues.

- Glendore, Tootal Road, New Cross Street and Tootal Drive block improvement scheme commenced Jan 2005 and works are still in progress.

Eccles New Road Renewal Area

- Lead member for Housing has now declared a clearance area with regards to 24 unsatisfactory properties within the Eccles New Road Area (Bridson Street). The Head of Law and Administration is to seal the Order and to take all necessary steps, including the publication of all statutory notices, to secure confirmation of the compulsory purchase order by the First Secretary of State and the vesting of the land in the City Council.

- The Weaste Seedley Claremont Area Action Plan process is now underway with the aim of building on opportunities in the area to create plans for a sustainable future. Lead Members for Housing and Planning have authorised the new masterplan area. The new draft brief is yet to be completed. Tenders expected from interested consultants by December 2005 and have the preferred consultant in post early 2006.

- Lead Member for Housing has now declared a clearance area for 35 properties in the Eccles new Road Area (Nelson Street). The Head of Law and Administration is to seal the Order and to take all necessary steps, including the publication of all statutory notices, to secure confirmation of the compulsory purchase order by the First Secretary of State and the vesting of the land in the City Council.

###### East Salford

Areas covered within this report:

Broughton

Chapel Street

Charlestown & Lower Kersal

Claremont Village

## Broughton

## Higher Broughton – Homeswap to new build

- Formal approval to utilise equity loan based products has now been agreed by the Lead Member of Housing following earlier legal difficulties.

- All residents that have been relocated from the Bottom Streets CPO No.1 area have now made formal applications for relocation assistance.

- Only two residents required legal action to remove them from properties in CPO No.1 area.

- All other residents have been rehoused into temporary accommodation until the first affordable homeswap properties are constructed in 2006/2007. The legal decant agreements have been signed and returned to the Council in most cases.

## Higher Broughton – Investigation works to playing fields

- The remediation of the Playing Fields is now back on track following earlier delays.

- Remediation of part of the site has now been completed and construction of the first houses has begun.

# Higher Broughton-Broughton Green Development and Related Issues

- Vacant possession of the entire site has been achieved.

- Demolition of Hanover Court is now nearly complete and demolition of another 100 units has recently commenced. This includes part of Newbury Place, Hampshire and Wiltshire Street, part of Wellington Street East, Rigby Street and Bradshaw Street North.

Lower Broughton

- An extensive ten-week consultation exercise was completed

8th August 2005.

- A new team consisting of a Sergeant, 4 PCs and 4 PCSOs has been set up to work in Higher and Lower Broughton. The team is based at Pendleton Police Station and aim to target persistent offenders and anti social behaviour in Lower Broughton.

- 14.07.05 the Lead Member for Housing approved the declaration of a clearance area for dealing with the unsatisfactory housing conditions of the properties 1 – 19 Moss Street.

Claremont Village

Duchy and Pendlebury Renewal Area.

- Resident consultation on ERDF Alleygating scheme improving the security of 87 properties.

- CPO notices served affecting 116 properties within (Duchy Road) clearance area.

- Extensive local consultation has contributed towards a final proposed design for the housing re-development of Duchy Road.

Charlestown and Lower Kersal

NDC

- Miller Homes and Inspired developments (OPUS) selected as Development Partner.

- Beacon Centre completed.

- Sports Village on site

- First stage of private housing improvements on Littleton Road completed.

- Arrowhead housing improvements underway

- Douglas Green Healthy Living Centre due to complete Sept 05

- St Aidan’s Healthy Living Centre underway.

- Alley-gating work commenced

Salford Innovation Park

- Funding for the project approved from all 3 funding sources, currently awaiting legal agreements.

Chapel Street (North)

Adelphi Media Quarter

- Terms now agreed between Salford University and Salford City Council for Adelphi Street and Meadow Road. Terms now agreed for Irwell Valley campus.

- Discussion over the valuation of Council owned land is ongoing.

Greengate

- Steering Group and Implementation Group to meet on 27th September to discuss consultant’s design/ engineering/ costs studies.

- Future context for Exchange Greengate will be established by URC’s Vision and Strategic Regeneration Framework.

Springfield Lane

- Magenta site hoardings have been erected on Trinity Way.

Eccles

Areas covered within this report:

Eccles

Liverpool Road

- Additional street signage ordered internally to be erected as soon as possible to enhance footway improvements.

- Footway Improvements completed 15/8/05 final 'snagging' works have been completed.

Eccles Town Centre

- Final studies received. Reported to Regeneration Initiatives Cabinet  working group on 22nd August.

Irlam & Cadishead

Areas covered within this report:

Barton

Barton Strategic Site

##### Red City Developments

- Counsels advice to be obtained in September

- Target Planning Panel – October

- Salford Reds business plan received and assessed by DTZ consultancy.

- Planning application for stadium and supporting areas submitted by RCD, and exclusivity agreement completed. Lease terms nearing agreement. .

##### Peel Holdings

- Planning application submitted for Port Salford.  Consideration of planning application for Port Salford progressing.

- Site allocation in the review Unitary Development Plan considered at Public Inquiry. Inspector’s decision is expected late 2005.

Ordsall & Langworthy

Areas covered within this report:

Chapel Street

Ordsall

Pendleton

Seedley Village

Salford Quays

Chapel Street (South)

Salford Central Station

- Network Rail confirmed as the Project Manager for Phase 1 improvements.

- Detailed design of Phase 1 now commissioned.

- Phase 1 contract will start on site June 2006 and be completed June 2007.

- Future improvement work will be led by the URC – Salford Central Station is one of five ‘Transformation Areas’ identified in the URC draft Vision.

Manchester Bury and Bolton Canal

  - Project on target to start on site late ’05.

  - Maintenance funding now seems to be resolved.

- Progress is being made on acquisition of land from Granada, with agents and solicitors appointed.

Ordsall

- Detail planning application drafted for new primary school and children’s centre.

- Heads of Terms for partnership with LPC agreed.

Pendleton

Pendleton Masterplanning

- Consortium (led by Halcrow) near completion of Stage 1A: Confirmation of key objectives, opportunities and constraints.

- Workshop Pendleton to take place 22nd – 24th September 2005.

Proposed TESCO adjacent to Shopping City

- Architect appointed for new Ecumenical Church.  Steering and Design Groups established. Planning Application to be considered on 6th October. Planning application for new RC Primary School submitted. CPO issues for both being progressed.

- Transport assessment being undertaken by Halcrow.

- Urgent need to agree Public Sector Position to enable discussions to be brought to a conclusion with Tescos/ Gubbay. Report to Cabinet to follow.

Salford Quays

Dock 9

- Planning application submitted for the erection of 4 towers on opposite side of The Quays loop road to the NV buildings. 600 apartments, retail on ground floor. Retail and traffic studies requested. Highways Agency have directed no decision be made pending traffic assessment.

- All three phases of NV building are under construction.

Clippers Quay

- Planning application submitted for approx 290 studio residential units (Abito) on former pub site.

Seedley Village

Seedley and Langworthy

- The Seedley & Langworthy Community Wardens were awarded ‘Team of  the Year’ in the ODPM National Warden’s Awards.

- Seedley and Langworthy In Bloom announced as winner of the North West In Bloom 'Urban Regeneration award' on 23 September for the third year running.

- A dispersal order covering the western section of the regeneration area began on 14th July 2005 and will be in place till 14th October 2005. To date there has been 221 people formally Dispersed and Warned).  6 persons have been arrested for Breaching the Order .

	Work has started on Fir Street and is expected to be completed end of September.  Demolition on Amos Street to be completed October 2005.

# Magistrates Court and Justice Centre Initiative

- Planning application refused at Planning Regulatory Panel July 2005. Alternative sites are currently being considered.

## LIVIA

- Site investigations have now been completed in relation to soil investigations and ecology of the site.  Results are not considered likely to affect the Forestry Commission decision to enter into lease arrangements.

- Match funding has been secured from a number of sources including the following: - Coalfield Communities Fund, landfill tax credits, S106 agreements, Council capital receipts, Home Office ‘Gate-It’ funding.

Swinton