| Part 1 (Open to the public) | ITEM NO. |
| --- | --- |

REPORT OF THE LEAD MEMBER FOR CHIEF EXECUTIVE

TO THE CABINET MEETING

ON 13TH DECEMBER, 2005

TITLE : CPA. Corporate improvement plan monitoring

RECOMMENDATIONS : That Members note the position regards implementation of the corporate improvement plan.

That Lead Members have regard to progress against the improvement activities in their discussions with directorates.

EXECUTIVE SUMMARY : The corporate improvement plan has been submitted on a regular basis since February, to monitor and comment on progress against the various corporate and service improvements in the plan.

The current position for each activity is shown towards the right of the monitoring statement, along with an ‘on target’ column where grey=on target/achieved, hatched= behind target, and black=not on target/not achieved.

The overall position is that most improvement activities (approximately 85%)are on target (grey shaded in the plan attached). Only 13 are behind target, and 1 not achieved.

The tables below identify the key focus areas.

BACKGROUND DOCUMENTS :

(Available for public inspection)

ASSESSMENT OF RISK:

High for council’s reputation

SOURCE OF FUNDING:

Funding is in place for the major aspects of the improvement plan

COMMENTS OF THE STRATEGIC DIRECTOR OF CUSTOMER AND SUPPORT SERVICES (or his representative):

- LEGAL IMPLICATIONS				Provided by : N/A

- FINANCIAL IMPLICATIONS			Provided by : Significant financial implications are identified in the plan.

PROPERTY (if applicable): N/A

HUMAN RESOURCES (if applicable):

Significant HR implications are identified in the plan.

CONTACT OFFICER :

Stan Frost 793 2563

WARD(S) TO WHICH REPORT RELATE(S):

ALL wards

KEY COUNCIL POLICIES:

Best Value, Budget Strategy, Communications and Public Relations, Employee matters, Health, Performance Management, Procurement Policies, Scrutiny, Strategy for Children and Young People.

DETAILS (Continued Overleaf)

Key focus areas

The areas below are key areas with potential problems flagged, for one reason or another, in the improvement plan. These are not necessarily big problems – in a number of cases timescales have moved back a little, and provided revised dates are achieved we will be able to demonstrate that we have delivered, come CPA inspection early next year.

| Area | Responsible Director | Improvement plan ref. | Comment |
| --- | --- | --- | --- |
| Performance management | JCW | 2.1, 2.2 | Behind target showing on improvement plan – timescale issues have arisen as the scale of the project, and issues around the software, have come to light. Interface with balanced scorecard has created further timescale issues. |
| Business continuity | Alan W | 2.7 | Behind target – revised June completion date now deleted |
| BME led diversity forum | Anne W | 3.4 | Behind target – completion date revised from end March to end September 2005 |
| Older people strategy | Anne W | 5.1 | To be submitted to Cabinet late November and LSP Jan 2006 |
| Procurement coordination team | Alan W | 5.5 | 3 posts to be appointed |
| 2*status delivery plan | MS | 6.1 | Awaiting re-inspection |
| Schools in special measures | JB | 6.3 | Not achieved. Harrop Fold High School in special measures for over 2 years. |
| Recycling targets | BJ | 6.5 | Very challenging 20% recycling target |
| Crime reduction | JCW | 6.6 | Assaults and wounding, and hate crime, reduction behind target |