SALFORD CITY COUNCIL

LOCAL DEVELOPMENT SCHEME

2006/7- 2008/9

Draft January 2006

Salford City Council

Local Development Scheme

Contents

Page

- Introduction

1.1	What is the LDS?	4

  - Submission and adoption of the LDS	4

  - What is a Local Development Framework?	4

### Table 1 : Glossary	6

- Progress in 2005/6

2.1	Progress on Documents	8

  - Implications for LDS	9

- Salford Local Development Framework

3.1	Saved Plan	12

  - Supplementary Planning Guidance	12

  - Statement of Community Involvement	13

  - New Local Development Documents	13

  - Annual Monitoring and Review	16

Table 2 : Schedule of Proposed LDD’s	17

Table 3 : Programme Management	20

Diagram 1 : Relationship between LDD Documents	23

Diagram 2 : Geographical Coverage of LDDs	24

- Profile of Local Development Documents

  - Statement of Community Involvement	25

  - Core Strategy	26

  - Pendleton Area Action Plan	28

  - Proposals Map	29

  - Housing 	30

  - Salford Green Space Strategy	31

  - Nature Conservation & Biodiversity	32

  - Planning Obligations 	33

  - Ellesmere Park	34

  - Design & Crime	35

  - House Extensions	36

  - Trees & Development	37

  - Telecommunications	38

  - Hot Food Take Aways	39

  - Sustainable Design and Construction Guide	40

- LDF Production Process

5.1	Resources	41

5.2	Document Production	41

5.3      Council Procedures	42

5.4      Evidence Base, Monitoring, Strategic Environmental

Assessment & Sustainability Assessment	43

Appendix 1: Schedule of Saved Policies	47

- Introduction

1.1	What is a Local Development Scheme?

1.1.1	This document is the city council’s second Local Development Scheme (LDS) (see Table 1 for a definition of the terminology). It describes what the city council is going to do to prepare new and revised planning policy for the city over the next three years (2006/7 – 2008/9) and also reviews the progress made in the production of new documents since the approval of the first LDS in April 2005.  The production of the LDS is a mandatory requirement of the planning system.

    - The LDS describes the individual documents, called Local Development Documents (LDD), that together make up Salford’s Local Development Framework (LDF). The document contains a profile of each document that is either currently being produced or that is being proposed.  The profile explains the purpose and status of the document, how it relates to the LDF as a whole, together with the timescales and targets for its preparation.

    - The LDS has 3 main purposes:

- To inform the public of the development plan and related documents that will make up the new planning policy framework

- To set out the timescales the public can expect for the preparation and review of these documents.  The timetable specifically includes “consultation milestones” to inform the public about opportunities to get involved with the plan making process and to let them know the likely dates for involvement.

- To establish and reflect council priorities and to enable work programmes to be set for the preparation of these development plan documents

    - The LDS has to be submitted to the Secretary of State, via the Government Office, for approval.  Government Office assess the LDS, having regard to:

- Whether there is a robust and appropriate approach to document preparation, particularly in terms of priorities;

- Whether the proposed time-scales for the preparation of the proposed LDD’s are realistic and deliverable;

- Whether the proposed information base is sufficiently comprehensive to underpin our proposed DPD’s.

- Whether there are any obvious omissions; and

- Whether the LDS is easy to understand in terms of accuracy and clarity of proposals.

1.2	What is a Local Development Framework?

    - Local Development Frameworks (LDFs) are part of the recent reforms of the planning system.  They replace the old system of Unitary Development Plans and Supplementary Planning Guidance.  This new system came into effect at the end of September 2004.

    - In broad terms the LDF is a framework for the location and design of new development and for protecting the natural and built environment.  It is sometimes called a “spatial” plan because it deals with the location and layout of developments and activities and how these affect people and the environment.

    - The LDF will consist of a number of documents called Local Development Documents.  Local Development Documents include 2 types of documents:

- Development Plan Documents (DPD) which comprise the Statutory Development Plan for the city and therefore will provide the basis upon which all planning decisions are made; and

- Supplementary Planning Documents (SPD) which are non-statutory and provide guidance on the implementation of policy contained in statutory documents.

    - LDDs can be prepared and updated separately. So rather than producing one Unitary Development Plan (and Supplementary Planning Guidance) the new system will allow the city council to produce a series of documents over different timescales that will progressively supersede the UDP.

    - The statutory development plan for the city will also comprise of the Regional Spatial Strategy (RSS) which is prepared by the Regional Planning Board – currently the North West Regional Assembly (NWRA).

Table 1 : Glossary

| Component | Abbreviation | Explanation |
| --- | --- | --- |
| Local Development Framework | LDF | The name given to a portfolio of Local Development Documents which will provide the framework for delivering the spatial planning strategy for the area. |
| Local Development Scheme | LDS | A 3 year programme that sets out the details, the timescales and the arrangements for production for each documents that will form part of the LDF |
| Local Development Document | LDD | A document that forms part of the LDF. LDD’s include 2 different types of documents which are explained below |
| Development Plan Document | DPD | An LDD that has been subject to an independent public inquiry run by a Planning Inspector. Once adopted following an inquiry these documents will have statutory status as defined by section 38(6) of the Planning and Compulsory Purchase Act 2004. |
| Supplementary Planning Documents | SPD | An LDD which is subject to public consultation but is not subject to an independent public inquiry. These will form a material consideration in determining planning applications but do not have the weight of development plan status. |
| Regional Spatial Strategy | RSS | A document that sets out the planning policies in respect of the development and use of land in the region which is prepared by the regional planning body. It will form a statutory part of the development plan for each district. |
| The Development Plan |  | Consists of the RSS and the DPD’s contained within the LDF. |
| Core Strategy |  | A DPD that sets out the vision, spatial strategy and core policies for the spatial development of the city. |
| Statement of Community Involvement | SCI | A document that forms part of the LDF and which sets out how the council will involve the community and other stakeholders in the preparation, alteration and review of all LDD’s and planning applications. The SCI will be subject to independent testing and all LDD’s will have to show how they have conformed with it. |
| Annual Monitoring Reports | AMR | An annual report which sets out the progress in terms of producing LDD’s against the timetable set out in the LDF and the progress in implementing policies |
| Sustainability Appraisal & Strategic Environmental Assessment | SA & SEA | All policies and proposals in LDD’s will be subject to Sustainability Appraisal that includes the requirements for a Strategic Environmental Assessment to ensure they reflect sustainable development principles. |

2.0	Progress in 2005/6

  - Progress on Documents

    - The current LDS for 2005/6 – 2007/8 was approved in April 2005.  This set out 16 LDDs that the city council would at least commence production of over the 3 year period it covered.  This included:

- The Statement of Community Involvement, Core Strategy and the Pendleton Area Action Plan, where work was due to be commenced but not completed within the 3 year period;

- The Proposals Map, which will initially be completed as part of the UDP but will then be updated as the Core Strategy and Pendleton AAP are produced; and

- A further 12 SPDs which would all be completed within the 3 year period.

    - Since the approval of the LDS, work has been commenced on the Core Strategy and the Pendleton Area Action Plan, together with 9 SPDs.  The production of these documents is progressing largely as timetabled within the LDS.  Work on the other documents within the LDS was not due to commence until after this financial year.  The first document to be adopted under the new system was the Lower Broughton Design Code SPD, in January 2006.

2.1.3	The city council is currently reviewing the UDP.  This review UDP will replace the adopted UDP as the saved plan when it is adopted in 2006.  As the “saved “ plan it will form part of the LDF for the city.  The process for reviewing the plan thus far has been as follows:

- Issues Paper consultation April 1999

- First Deposit Draft consultation February to March 2003

- Revised Deposit Draft consultation November 2003 to January 2004

- Pre-Inquiry Changes consultation June to August 2004

- Public Inquiry September 2004 to February 2005

- Inspector’s Report published September 2005

- Modifications consultation January to February 2006

2.1.4	The timetable published in the Revised Deposit Draft UDP in November 2003, and which informed the production of the first LDS, indicated that the Inspector’s Report would be published in May/June 2005 and the Plan Modifications in September 2005, with the replacement UDP adopted by the city council in January 2006. However, for reasons beyond the city council’s control, the Public Inquiry into the replacement UDP lasted until February 2005 rather than October 2004, which has resulted in the rest of the UDP review timetable being delayed.

2.1.5	The Plan Modifications were published in January 2006, and it is anticipated that the replacement UDP will be adopted by the city council in June 2006.

  - Implications for the LDS

##### Proposals Map

2.2.1	The city council is making good progress in the production of the Local Development Documents that are identified in its Local Development

Scheme. Only one of those documents, the Proposals Map, would currently appear likely to be subject to any delay.

    - The unexpectedly long UDP Inquiry and resultant delay in the publication of the Inspector’s Report, means that the date of adoption for the Proposals Map, which forms both part of the UDP and part of the Local Development Framework, will need to be put back from its current date of January 2006. It is considered that the new date should be June 2006, reflecting the additional time required for the UDP Inquiry (four months) and the timing of the local government elections in May 2006, which affects the approval process for the UDP.

Core Strategy

    - This delay in the adoption of the replacement UDP has implications for the timetable of the Core Strategy. The Local Development Scheme identifies the initial consultation on the Core Strategy commencing in January/February 2006. However, this would coincide with the publication of the city council’s responses to the UDP Inspector’s report and its proposed modifications to the UDP and Proposals Map, also now scheduled for January/February 2006 because of the extended UDP Inquiry. The city council is concerned that the modifications process could be compromised by simultaneously consulting on the Core Strategy, which will cover many of the same issues, and would effectively be reopening the debate at the same time as that debate is being brought to a conclusion in the UDP. This could also undermine the effectiveness of this front-loading of consultation in the Core Strategy process.

    - Consequently, the city council considers that it would be appropriate to delay the production of the Core Strategy until September 2006. This would enable the modifications process to be completed and the plan to reach adoption, reducing the potential for confusion, and would also have the benefit of allowing the initial consultation phase of the Core Strategy to be informed by the Draft Regional Spatial Strategy for the North West, which is due to be published in March 2006.  A revised timetable for the production of the Core Strategy is therefore included within sections 3 and 4 of this document.

###### Area Action Plans

    - The UDP Inspector’s Report makes a number of comments regarding the need for the city council to fully embrace the new development plan system, and advises that additional Area Action Plans should be brought forward to support the city’s regeneration. Indeed, the wording of some of his recommendations commits the city council to producing an Area Action Plan for Lower Broughton in the near future.  On-going discussions are being held with our development partner in Lower Broughton over the timetable and method of producing this document.   This revision of the LDS is therefore not in a position to formally include this document but we will review the LDS again once these discussions are finalised.

    - As well as Lower Broughton, the Inspector urges the city council to take full advantage of the new development plan system introduced by the Planning and Compulsory Purchase Act 2004, and to give consideration to producing more Area Action Plans in order to support regeneration activity within Salford.  In addition, recent Government guidance highlights the potential need for further Area Action Plans, if additional support is required for compulsory purchase orders.

2.2.7	The production of additional Area Action Plans therefore clearly has merits, however this must be balanced against the resources available to the city council to undertake such work to the necessary quality. The city council has identified a considerable number of Area Action Plans that it considers would be worth producing.  These are subject to on-going discussions with delivery bodies and development partners where appropriate.   The city council will need to carefully prioritise the production of these various documents against the level of resources available. These AAPs that have been identified for production will be brought forward in future revisions of the LDS as resources permit.

Waste

2.2.8	Ongoing discussions at the sub-regional level indicate a commitment to producing a joint Development Plan Document for Greater Manchester to address waste management issues, including the identification of sites. This will address the requirements of the new PPS 10 (Planning for Sustainable Waste Management).   The timetable for this is still being finalised and therefore it will have to be included in a future revision of the LDS.  Consideration is also being given as to whether a similar Greater Manchester approach would be appropriate for addressing minerals issues.

Sustainable Design and Construction

2.2.9	The current LDS identifies the production of a SPD on Recycling Facilities in New Developments, which is due to be commenced in June 2006.  It has been decided that this SPD should consider a wider range of issues and should be renamed Sustainable Design and Construction Guide, enabling a more comprehensive approach to be taken to sustainability.  The start of the production of this document will be delayed until November 2006.  This reflects the wider range and availability of resources required to produce the revised document.

Other Changes

2.2.10	The following minor changes are also being made to the LDS:

- Alterations to the boundaries of the Pendleton Area Action Plan and the Ellesmere Park Supplementary Planning Document, to reflect the results of initial consultation and evidence gathering;

- Amendment of the Pendleton Area Action Plan timetable to bring forward the submission stage by a month;

- Renaming of the Housing Market SPD to become the Housing SPD; and

- Updating of the detailed production processes to reflect alterations to the city council’s constitution.

3.0	 Salford Local Development Framework

  - Adopted Local Development Documents

3.1.1	The only Local Development Document that has been adopted thus far is the Lower Broughton Design Code, which was adopted in January 2006. This sets out the key design principles for the Lower Broughton area and supplements both the Adopted and Draft Replacement UDPs.

  - The Saved Plan

    - The provisions of the Planning and Compulsory Purchase Act allow for existing statutory plans to be “saved”.  Accordingly the existing UDP (adopted in 1995) is currently the saved plan for the city.

    - The city council is in the process of reviewing its Adopted UDP.  This review UDP will replace the existing Adopted UDP as the saved plan when it is itself adopted.  The Public Inquiry into the Revised Deposit Draft Replacement Plan closed on 28th February 2005 and the Inspector’s Report was published in September 2005.   The city council published its Plan Modifications in January 2006, and it is anticipated that the replacement UDP will be adopted by the city council in June 2006.

    - The Review UDP, after it is adopted, will continue as the saved plan until it is replaced by new DPDs as outlined in section 3.4.   (Appendix 1 sets out which policies in the Review UDP will be replaced by which LDD).  Consequently for the majority of the 3-year period covered by this LDS, planning policy will be provided by the existing or Review UDP.

3.3	Supplementary Planning Guidance

3.3.1	A number of Supplementary Planning Guidance (SPG) notes have been produced in association with the current adopted UDP and adopted by the council.  These comprise:

- SPG 1 Eccles Town Centre (approved 1996)

- SPG 2 Designing Out Crime (approved March 2002)

- SPG 3 Trees – Planning & Protection (approved May 2002)

- SPG 4 House Extensions (approved December 2002)

- SPG 5 Higher Broughton Regeneration Area (approved Sept 2003)

- SPG 6 Telecommunications (draft)

- SPG 7 Open Space associated with New Housing Developments (approved February 2004)

- SPG 8 Buile Hill Park Planning Brief (approved May 2004)

- SPG 9 Salford Shopping City (approved 2002)

3.3.2	Following the commencement of the Planning & Compulsory Purchase Act 2004, the council intends to continue to use these documents as “material considerations” in the determination of planning applications, until such time as they are replaced by DPDs or SPDs.

3.3.3	It is proposed that SPGs 2, 3, 4, 6 & 7 will be revised and republished as SPDs as outlined in section 3.4 (SPG 7 will form part of the Planning Obligations SPD).  It is not proposed that this will happen with the other SPGs, as it is considered that adequate planning policy is/will be provided elsewhere.

3.4	Statement of Community Involvement

3.4.1	It is a requirement of the Planning and Compulsory Purchase Act to produce a Statement of Community Involvement (SCI).  This sets out the standards and the approach to involving stakeholders and the community in LDDs and planning applications.  The production of this SCI is a high priority for the city and it will be commenced in 2006.  The document will be produced in close collaboration with the city’s LSP (Partners IN Salford) and the Community Committees.

3.5	New Local Development Documents

3.5.1	This section sets out the DPDs and SPDs that the city council has identified as priorities for production in the next 3 years.  Table 2 sets out a schedule of proposed Local Development Documents that will be prepared by the city council, together with their roles, chain of conformity and the main milestones to adoption.

3.5.2	Table 3 is a simple Gantt Chart providing an overview of the timetable and project management for preparing the LDDs.

3.5.3	Diagram 1 shows how the various documents that form the LDF relate to each other and Diagram 2 shows the geographical coverage of the documents that will not apply to the whole city.

3.5.4	In determining which documents to produce first, the priority has been to support the extensive regeneration work that is taking place in the city at present, in particular the work of the Housing Market Renewal Fund and the Central Salford Urban Regeneration Company.   As a result, in addition to the preparation of the Core Strategy and the Statement of Community Involvement, priority is being given to the preparation of a series of Area Action Plans to provide the planning framework for the regeneration work in these areas, although only one of these (the Pendleton Area Action Plan) has been formally identified in the LDS thus far.

3.5.5	As a result of the emphasis on the production of these Area Action Plans there will not be adequate capacity to start the production of a DPD to replace the other policies and proposals in the “saved” Review UDP until the DPDs outlined below are adopted.  It will therefore be necessary to save these policies for longer than the ‘normal’ three-year period (2009). (The proposal to save the policies for more than 3 years is subject to approval from the Secretary of State). Since these policies will have been tested at independent inquiry in 2004/5 it is considered that they will be able to provide an adequate basis for decision making until a replacement DPD can be adopted (estimated to be 2011).  Appendix 1 outlines which polices in the Review UDP it is expected will be replaced by the Core Strategy and other DPDs outlined in this LDS and which will require saving beyond 2009.  This is based on the policies in the plan that formed the basis for the inquiry and will need to be updated as the Review UDP progresses to adoption.

Development Plan Documents

3.5.6	The proposed Development Plan Documents listed below will start to progressively replace the saved policies from the Review UDP when adopted in 2006.  As a general principle area-based DPDs or SPDs will draw together all relevant strategies for the area they cover.

Core Strategy

Initial work has commenced on this document during 2005.  However as outlined in section 2, the timetable for its production has been revised, to accommodate the revised timetable for adopting the Review UDP and for the production of the new RSS.   The document will contain strategic policies to be applied across the city or to types of locations, but will not contain site-specific policies or proposals.  All other LDDs will be in conformity with the Core Strategy.

Pendleton Area Action Plan

## This will provide planning policy guidance for the regeneration of the Pendleton area.  The production of this document commenced during 2005 and the preferred options document is currently being prepared for consultation.  The public consultation on the submission document needs to be brought forward slightly so that it avoids the pre-election period.  It will now be in February and March 2007 rather than March and April 2007.

Supplementary Planning Documents

3.5.7	The proposed Supplementary Planning Documents are listed below.  The Lower Broughton Design Code SPD was the first to be adopted, in January 2006.  This SPD is related to policies in both the currently adopted UDP and the review UDP.  The remaining SPDs will be produced so that they are either adopted at the same time as the Review UDP or after it is adopted, and will therefore be related to polices in that document and where appropriate to policies in the emerging Core Strategy.

- Housing

- Salford Green Space Strategy

- Nature Conservation & Biodiversity

- Planning Obligations

- Ellesmere Park

- Design & Crime

- House Extensions

- Trees & Development

- Telecommunications

- Hot Food Take Aways

- Sustainable Design and Construction Guide

3.5.8	The Development Control section will be responsible for the production the last eight these documents.  The majority of these already exist as SPG, either adopted or in draft from, but need to be reviewed and converted to SPDs.

#### Proposed LDDs

3.5.9	The council proposes to commence work on a number of other LDDs over the lifetime of this LDS, but at this stage the resources and/or timetables for these documents are not finalised and so they cannot be formally included within this document.  Once these issues are clarified the council will review the LDS so that they can be included, however at this stage they are included so that the intention to produce them can be highlighted.

Lower Broughton Area Action Plan

This is a new DPD, which was recommended by the UDP Inspector.  It will provide planning policy guidance for the regeneration of the Lower Broughton area.  The DPD is linked to the SPD that was adopted in January 2006, which sets out the design principles for the area.

Other Area Action Plans

A number of other potential Area Action Plans have been identified, particularly within the Housing Market Renewal Area. These are currently being prioritised and will be included in future revisions of the LDS as resources allow.

Greater Manchester Waste DPD

Each of the ten Greater Manchester authorities has agreed to the principle of joint working to inform the preparation of their waste development plan documents.  This will involve the establishment of a dedicated team located within the Greater Manchester Geological Unit and will draw upon the skills of each of the ten authorities as well as industry and environmental bodies.  It is envisaged that this will take approximately three and a half years to complete.  The timetable for the document’s production is currently being finalised, and will be included in the next revision of the LDS.

Design Guidance

The city council recognises the importance of high quality design, and is currently working with CABE to identify the most appropriate form of design guidance for the city. One or more design-based LDDs are therefore likely to be included in the LDS in the near future.

Mosslands Strategy

The council considers that it will be important to produce a spatial strategy for the Mosslands area and consultants are currently producing a vision for the area.  However at this stage the timescale for any future document still remains uncertain.

3.5.10	The need for further LDDs not currently outlined in the LDS may be identified in the future, and will be incorporated in any review of this LDS.  Changing circumstances may also mean that it is no longer appropriate or necessary to prepare some of the LDDs identified within this LDS.  If this is the case then it will be explained in the next review of the LDS.

3.6	Annual Monitoring Report

3.6.1	The council is required to monitor annually how effective its policies and proposals are.  A report is published in December each year which assesses:

- whether the council is meeting, or is on track to meet, the targets and milestones in the LDS, and if not, the reasons why;

- whether the council is meeting, or is on track to meet, the policies and related targets and milestones set out in the LDD’s and if not, the reasons why;

- what impact LDD policies are having on other targets set at national, regional or local level;

- are the policies in the LDD’s achieving what they intended;

- whether any policies need to be replaced, to ensure the city meets sustainable development objectives;

- whether any policies need to be replaced to reflect changes in national or regional policy; and

- what actions need to be taken if policies need to be replaced.

3.6.2	As a result of monitoring the city council will consider what changes, if any, need to be made and will bring forward any such changes through the annual review of the Local Development Scheme.  Approval will be required from the Secretary of State for the LDS each time it is reviewed.

3.6.3	The first Annual Monitoring Report was published on 21st December 2005 and is available for inspection at the main civic centre and on the council’s web site (www.salford.gov.uk).

Table 2 : Schedule of Proposed Local Development Documents

a) Development Plan Documents

| Document Title | Status | Brief Description | Chain of Conformity | Participation on Preferred Options & Proposals | Date for Submission to SoS | Proposed Date for Examination | Proposed Date for Adoption |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Statement of Community Involvement | N/A | Sets out proposals engaging the community and stakeholders in the preparation of LDD’s and planning applications. | Must be in conformity with regulations | November – December 2006 (Participation on draft SCI) | August 2007 | January 2008 | May 2008 |
| Core Strategy | DPD | Sets out vision, objectives and spatial development framework for the city. | Must be in general conformity with RSS. All other LDD’s to be in conformity with Core Strategy. | September - October 2007 | July 2008 | January – February 2009 | October 2009 |
| Pendleton Area Action Plan | DPD | Provides planning policy guidance for the regeneration of the Pendleton area. | With the plan strategy of the adopted UDP, policy ST1 in “saved” Review UDP. | May – June 2006 | February 2007 | September – October 2007 | June 2008 |
| Proposals Map | DPD | To map development plan policies and proposals. | With Core Strategy, RSS and adopted DPD’s. |  |  |  | To be updated each time a DPD is adopted |

b) Supplementary Planning Documents

| Document Title | Status | Brief Description | Chain of Conformity | Consultation on Draft SPD | Proposed date for Adoption |
| --- | --- | --- | --- | --- | --- |
| Housing | SPD | To provide more detailed guidance on housing policy, particularly in relation to HMRF. | With policy ST1, ST2, and H1-9 of “saved” review UDP. | May – June 2006 | November 2006 |
| Salford Greenspace Strategy | SPD | To provide detailed guidance on the provision of green space in the city. | With Recreation Policies in adopted and “saved” Review UDP. | February – March 2006 | August 2006 |
| Nature Conservation & Biodiversity | SPD | To provide guidance on the implementation of nature conservation policies. | With policies EN7 A-E in the “saved” Review UDP. | February – March 2006 | August 2006 |
| Planning Obligations | SPD | To provide advice and information to applicants and their agents on planning obligations. | With policy DEV5 in Review UDP | May – June 2006 | December 2006 |
| Ellesmere Park | SPD | To provide detailed guidance on development in the Ellesmere Park area. | With Design Policies in “saved” Review UDP | May – June 2006 | November 2006 |
| Design & Crime | SPD | To provide detailed guidance on designing out crime. | With policy DES 11 in “saved” Review UDP | February – March 2006 | July 2006 |
| House Extensions | SPD | To advise householders and their agents on policy guidelines for residential extensions. | With policy DES8 in “saved” Review UDP | February – March 2006 | July 2006 |
| Trees & Development | SPD | To provide information and advice on standards for new and existing trees within developments. | With policies ENV 9 & 10 in “saved” Review UDP | February – March 2006 | July 2006 |
| Telecommunications | SPD | To provide guidelines on which applications for mobile phone masts will be assessed and on related telecommunications issues. | With policy DEV1 in “saved” Review UDP | February – March 2007 | September 2007 |
| Hot Food Take Aways | SPD | To advise applicants and their agents on the policy guidelines for Hot Food Take Aways. | With policy S4 of “saved” Review UDP | February – March 2007 | September 2007 |
| Sustainable Design and Construction Guide | SPD | To provide guidance to developers on the integration of sustainable design and construction measures. | With policies ST14 and EN17A of “saved” Review UDP. | June - July 2007 | December 2007 |

Table 3: Programme Management

a) Development Plan Documents

b) Supplementary Planning Documents

Diagram 1:	Relationship between Local Development Documents

4.0	Profiles of each Local Development Document

  - Statement of Community Involvement

# Overview

| Role & Subject | The SCI will set out how the city council will consult on all Local Development Documents, and their accompanying Sustainability Appraisals as well as on planning applications. It will set out how we will identify key stakeholders and consultees, the methods of engagement that will be used and how representations will be dealt with and responded to. |
| --- | --- |
| Coverage | City-wide and involving organisations external to the city. |
| Status | Non Development Plan Local Development Document |
| Conformity | Must at least met the minimum requirements in the regulations and will have regard to the community involvement standards developed by Partners IN Salford. |

# Timetable

| Stage | Dates |
| --- | --- |
| Commencement of Production | April 2006 |
| Early consultation | June – July 2006 |
| Public Participation on draft statement | November – December 2006 |
| Date for Submission to SoS | August 2007 |
| Public Consultation on Submission document | September – October 2007 |
| Pre-Examination Meeting | October 2007 |
| Examination | January 2008 |
| Estimated Date for Adoption | May 2008 |

# Arrangements for Production

| Organisational Lead | Council’s Head of Planning |
| --- | --- |
| Political Management | Cabinet for all pre-submission stages Council’s Environmental, Housing and Planning Scrutiny Panel will be involved in reviewing the evidence and results of consultation on the Draft SCI. Full council for adoption. |
| Internal Resources | Plans Team, Development Control and LSP Community Involvement Team |
| External Resources |  |
| Stakeholder Resources | Partners IN Salford to provide key link to community planning |
| Community & Stakeholder Involvement | Prior to consultation on the draft, specific and general consultation bodies will be canvassed for their views on issues and advice will be sought from the LSP. |
| Monitoring & Review Mechanisms | The SCI is intended to be a long term document. The Annual monitoring report will highlight any problems. |

4.2	Core Strategy

# Overview

| Role & Subject | The Core Strategy will: Set out the long-term spatial vision for the city (up to 2021), and the overall strategy for delivering that vision; Identify the overall level of different types of development (including housing, employment, retail, and leisure) that is envisaged in the city during that period, and the general geographical distribution of that development; Define the city’s hierarchy of town and neighbourhood centres; Identify the main improvements in infrastructure that are required to support that scale and distribution of development; Set out the strategic spatial policies for the city; Set out the broad vision and strategy for individual parts of the city, identifying the key issues in each area; Include a Key Diagram; and Identify the links with, and support the delivery of, other key strategies and plans, including the Community Plan. |
| --- | --- |
| Coverage | City-wide |
| Status | DPD |
| Conformity | With National Planning Guidance, RPG/RSS and having regard to Salford’s Community Plan |

Timetable

| Stage | Dates |
| --- | --- |
| Commencement of Production | September 2006 |
| Initial Public consultation on issues and initial SA report | January – February 2006 |
| Public Participation : Preferred Options & Proposals | September – October 2007 |
| Date for Submission to SoS | July 2008 |
| Public Consultation on Submission document | July – August 2008 |
| Pre-Examination Meeting | October 2008 |
| Examination | January – February 2009 |
| Estimated Date for Adoption | October 2009 |

# Arrangements for Production

| Organisational Lead | Council’s Head of Planning |
| --- | --- |
| Political Management | Cabinet for all pre-submission stages except SA Scoping Report. Council’s Environmental, Housing and Planning Scrutiny Panel will review evidence and results of consultation at preferred options stage. Full council for submission and adoption. |
| Internal Resources | Plans Group |
| External Resources | All Directorates will be involved in key stages of production. |
| Stakeholder Resources | Partners IN Salford to provide key link to community planning |
| Community & Stakeholder Involvement | Prior to consultation on options, specific and general consultation bodies will be canvassed for their views on issues and advice will be sought from the LSP on realistic and reasonable options. |
| Monitoring & Review Mechanisms | The Core Strategy is intended to be a long term document covering the period 2006-2021. The Annual Monitoring Report will examine contextual issues and whether development is conforming to the Strategy. |

# 4.3	Pendleton Area Action Plan

# Overview

| Role & Subject | To provide planning policy guidance for the physical, social and economic regeneration of the Pendleton area. Will include proposals for design and layout, scale and type of land uses, traffic management, open space, community uses and housing types. |
| --- | --- |
| Coverage | Pendleton |
| Status | DPD |
| Conformity | With the plan strategy of the adopted UDP, policy ST1 in “saved” Review UDP. |

# Timetable

| Stage | Dates |
| --- | --- |
| Commencement of Production | April 2005 |
| Initial Public consultation on issues and initial SA report | August - September 2005 |
| Public Participation : Preferred Options & Proposals | May – June 2006 |
| Date for Submission to SoS | February 2007 |
| Public Consultation on Submission document | February – March 2007 |
| Pre-Examination Meeting | June 2007 |
| Examination | September – October 2007 |
| Estimated Date for Adoption | June 2008 |

# Arrangements for Production

| Organisational Lead | Assistant Director (Spatial Planning) |
| --- | --- |
| Political Management | Cabinet for all pre-submission stages Full council for adoption. |
| Internal Resources | Plans Group & Housing Strategy Section |
| External Resources | Consultants will be heavily involved in the production of this document |
| Stakeholder Resources | Partners IN Salford to provide key link to community planning. |
| Community & Stakeholder Involvement | Prior to consultation on options, specific and general consultation bodies will be canvassed for their views on issues. |
| Monitoring & Review Mechanisms | The Annual Monitoring Report will examine the contextual issues and identify specific areas where change is needed. |

4.4	Proposals Map and Inset Maps

# Overview

| Role & Subject | To map development plan policies, designations and proposals |
| --- | --- |
| Coverage | Whole city (Proposals Map); part of city (Inset Maps) |
| Status | DPD |
| Conformity | With existing adopted DPDs |

Timetable

| Stage (Adoption of DPDs) | Dates |
| --- | --- |
| Review UDP | June 2006 |
| Pendleton Area Action Plan | June 2008 |
| Core Strategy | October 2009 |

# Arrangements for Production

| Organisational Lead | Council’s Head of Planning |
| --- | --- |
| Political Management | Adoption (and adoption of updates) delegated to Head of Planning to reflect adopted development plan policies and proposals at the time. |
| Internal Resources | Plans Group |
| External Resources | Outsource hard copy printing and web site links. |
| Stakeholder Resources | N/A |
| Community & Stakeholder Involvement | We will test a range of colour schemes, map scales and sizes with interested parties before we have the hard copies printed. We will use web feedback during the first month of publication on the web to adjust web presentation. |
| Monitoring & Review Mechanisms | N/A |

4.5	Housing

# Overview

| Role & Subject | To provide more detailed guidance on housing development within the city. It will address issues relating to the city’s housing market, the house type and mix sought in various parts of the city, affordability and issues relating to student accommodation. |
| --- | --- |
| Coverage | City wide |
| Status | SPD |
| Conformity | With policy ST1, ST2, and H1-9 of “saved” review UDP |

# Timetable

| Stage | Dates |
| --- | --- |
| Commencement of Production | May 2005 |
| Preparation of Draft SPD | November 2005 – March 2006 |
| Public Participation | May – June 2006 |
| Estimated Date for Adoption | November 2006 |

# Arrangements for Production

| Organisational Lead | Assistant Director (Spatial Planning) |
| --- | --- |
| Political Management | Cabinet for all stages before adoption Full council for adoption. |
| Internal Resources | Plans Group, Housing Strategy |
| External Resources |  |
| Stakeholder Resources | Partners IN Salford to provide key link to community planning. |
| Community & Stakeholder Involvement | Prior to consultation on draft, specific and general consultation bodies will be canvassed for their views on issues. |
| Monitoring & Review Mechanisms | As part of the Annual Monitoring Report. |

4.6	Salford Greenspace Strategy

# Overview

| Role & Subject | To provide detailed guidance on the distribution of green space provision within the city. It will set out standards of provision and how these standards will be met, deficiencies and strategic connections between important areas of greenspace and urban neighbourhoods. |
| --- | --- |
| Coverage | City-wide |
| Status | SPD |
| Conformity | With Recreation policies in both the adopted and “saved” Review UDP and policy H8 in the “saved” Review UDP. |

# Timetable

| Stage | Dates |
| --- | --- |
| Commencement of Production | May 2005 |
| Preparation of Draft SPD | October – December 2005 |
| Public Participation | February – March 2006 |
| Estimated Date for Adoption | August 2006 |

# Arrangements for Production

| Organisational Lead | Assistant Director (Spatial Planning) |
| --- | --- |
| Political Management | Lead Member for all stages before adoption Full council for adoption. |
| Internal Resources | Environment Group |
| External Resources | Environmental Services, Sport England, CABE Space |
| Stakeholder Resources | Partners IN Salford to provide key link to community planning. |
| Community & Stakeholder Involvement | Prior to consultation, specific and general consultation bodies will be canvassed for their views on issues. |
| Monitoring & Review Mechanisms | As part of the Annual Monitoring Report. |

4.7	Nature Conservation and Biodiversity

# Overview

| Role & Subject | To provide guidance on the implementation of the nature conservation policies, with particular reference to the location and condition of wildlife corridors and ‘priority’ habitats and species, with a view to setting targets for the protection, enhancement and (where possible) the re-establishment of those habitats and species. |
| --- | --- |
| Coverage | City-wide |
| Status | SPD |
| Conformity | With policies ENV 7 A-E in the “saved” Review UDP. |

# Timetable

| Stage | Dates |
| --- | --- |
| Commencement of Production | May 2005 |
| Preparation of Draft SPD | October – December 2005 |
| Public Participation | February – March 2006 |
| Estimated Date for Adoption | August 2006 |

# Arrangements for Production

| Organisational Lead | Assistant Director (Spatial Planning) |
| --- | --- |
| Political Management | Lead Member for all stages before adoption Full council for adoption. |
| Internal Resources | Environment Group, Environmental Services |
| External Resources | GMEU, English Nature, Environment Agency, Lancashire Wildlife Trust, RSPB, Red Rose Forest |
| Stakeholder Resources | Partners IN Salford to provide key link to community planning. |
| Community & Stakeholder Involvement | Prior to consultation, specific and general consultation bodies will be canvassed for their views on issues. |
| Monitoring & Review Mechanisms | As part of the Annual Monitoring Report. |

4.8 	Planning Obligations

# Overview

| Role & Subject | To provide advice on the use of planning obligations within the city. As well as general guidance on the use of Section 106 agreements within the city, it will give specific advice on the requirements for: new open space or open space improvements as part of new housing developments affordable housing in association with new developments infrastructure and public realm works transport improvements local employment and training provision in association with large developments |
| --- | --- |
| Coverage | City-wide. |
| Status | SPD |
| Conformity | With policy DEV5 in the “saved” Review UDP. |

# Timetable

| Stage | Dates |
| --- | --- |
| Commencement of Production | June 2005 |
| Preparation of Draft SPD | January – April 2006 |
| Public Participation | May – June 2006 |
| Estimated Date for Adoption | December 2006 |

# Arrangements for Production

| Organisational Lead | Associate Director Regulatory Services (Urban Vision) |
| --- | --- |
| Political Management | Lead Member for all stages before adoption Full council for adoption. |
| Internal Resources | DC, Plans Group |
| External Resources | Housing Strategy Economic Development |
| Stakeholder Resources | Partners IN Salford to provide key link to community planning. |
| Community & Stakeholder Involvement | Prior to consultation, specific and general consultation bodies will be canvassed for their views on issues. |
| Monitoring & Review Mechanisms | As part of the Annual Monitoring Report. |

4.10	Ellesmere Park

# Overview

| Role & Subject | To provide detailed guidance on development within the Ellesmere Park area. |
| --- | --- |
| Coverage | Ellesmere Park |
| Status | SPD |
| Conformity | With Design policies in the “saved” Review UDP. |

# Timetable

| Stage | Dates |
| --- | --- |
| Commencement of Production | June 2005 |
| Preparation of Draft SPD | January –April 2006 |
| Public Participation | May – June 2006 |
| Estimated Date for Adoption | November 2006 |

# Arrangements for Production

| Organisational Lead | Associate Director Regulatory Services (Urban Vision) |
| --- | --- |
| Political Management | Lead Member for all stages before adoption Full council for adoption. |
| Internal Resources | DC |
| External Resources |  |
| Stakeholder Resources | Partners IN Salford to provide key link to community planning. |
| Community & Stakeholder Involvement | Prior to consultation on draft, specific and general consultation bodies will be canvassed for their views on issues. |
| Monitoring & Review Mechanisms | As part of the Annual Monitoring Report. |

4.11	Design and Crime

# Overview

| Role & Subject | To provide guidance for developers on designing out crime, including the issue of alley-gating. (Review of current SPG) |
| --- | --- |
| Coverage | City-wide |
| Status | SPD |
| Conformity | With Policy DES 11 in the “saved” Review UDP. |

Timetable

| Stage | Dates |
| --- | --- |
| Commencement of Production | June 2005 |
| Preparation of Draft SPD | November – December 2005 |
| Public Participation | February - March 2006 |
| Estimated Date for Adoption | July 2006 |

# Arrangements for Production

| Organisational Lead | Associate Director Regulatory Services (Urban Vision) |
| --- | --- |
| Political Management | Lead Member for all stages before adoption Full council for adoption. |
| Internal Resources | Plans Group |
| External Resources |  |
| Stakeholder Resources | Partners IN Salford to provide key link to community planning. |
| Community & Stakeholder Involvement | Prior to consultations, specific and general consultation bodies will be canvassed for their views on issues. |
| Monitoring & Review Mechanisms | As part of the Annual Monitoring Report. |

4.12	House Extensions

# Overview

| Role & Subject | To advise householders and their agents on policy guidelines for residential extensions. (Review of current SPG) |
| --- | --- |
| Coverage | City-wide |
| Status | SPD |
| Conformity | With Policy DES8 in the “saved” Review UDP. |

# Timetable

| Stage | Dates |
| --- | --- |
| Commencement of Production | June 2005 |
| Preparation of Draft SPD | November – December 2005 |
| Public Participation | February - March 2006 |
| Estimated Date for Adoption | July 2006 |

# Arrangements for Production

| Organisational Lead | Associate Director Regulatory Services (Urban Vision) |
| --- | --- |
| Political Management | Lead Member for all stages before adoption Full council for adoption. |
| Internal Resources | DC |
| External Resources |  |
| Stakeholder Resources | Partners IN Salford to provide key link to community planning. |
| Community & Stakeholder Involvement | Prior to consultation, specific and general consultation bodies will be canvassed for their views on issues. |
| Monitoring & Review Mechanisms | As part of the Annual Monitoring Report. |

  - Trees & Development

# Overview

| Role & Subject | To provide detailed guidance for the protection of existing trees and the provision of new trees in development proposals. (Review of current SPG). |
| --- | --- |
| Coverage | City-wide |
| Status | SPD |
| Conformity | With Policies ENV9 and ENV 10 in the “saved” Review UDP. |

# Timetable

| Stage | Dates |
| --- | --- |
| Commencement of Production | June 2005 |
| Preparation of Draft SPD | November – December 2005 |
| Public Participation | February - March 2006 |
| Estimated Date for Adoption | July 2006 |

# Arrangements for Production

| Organisational Lead | Associate Director Regulatory Services (Urban Vision) |
| --- | --- |
| Political Management | Lead Member for all stages before adoption Full council for adoption. |
| Internal Resources | DC |
| External Resources |  |
| Stakeholder Resources | Partners IN Salford to provide key link to community planning. |
| Community & Stakeholder Involvement | Prior to consultation, specific and general consultation bodies will be canvassed for their views on issues. |
| Monitoring & Review Mechanisms | As part of the Annual Monitoring Report. |

4.14	Telecommunications

# Overview

| Role & Subject | To provide guidelines on which applications for mobile phone masts will be assessed and on related telecommunications issues |
| --- | --- |
| Coverage | City-wide |
| Status | SPD |
| Conformity | With policy DEV1 in “saved” Review UDP. |

Timetable

| Stage | Dates |
| --- | --- |
| Commencement of Production | June 2006 |
| Preparation of Draft SPD | September – December 2006 |
| Public Participation | February - March 2007 |
| Estimated Date for Adoption | September 2007 |

# Arrangements for Production

| Organisational Lead | Associate Director Regulatory Services (Urban Vision) |
| --- | --- |
| Political Management | Lead Member for all stages before adoption Full council for adoption. |
| Internal Resources | DC |
| External Resources |  |
| Stakeholder Resources | Partners IN Salford to provide key link to community planning. |
| Community & Stakeholder Involvement | Prior to consultation, specific and general consultation bodies will be canvassed for their views on issues. |
| Monitoring & Review Mechanisms | As part of the Annual Monitoring Report. |

4.15	Hot Food Take Aways

# Overview

| Role & Subject | To advise applicants and their agents on the policy guidelines for Hot Food Take Aways. |
| --- | --- |
| Coverage | City-wide |
| Status | SPD |
| Conformity | With policy S4 of “saved” Review UDP. |

# Timetable

| Stage | Dates |
| --- | --- |
| Commencement of Production | June 2006 |
| Preparation of Draft SPD | September – December 2006 |
| Public Participation | February - March 2007 |
| Estimated Date for Adoption | September 2007 |

# Arrangements for Production

| Organisational Lead | Associate Director Regulatory Services (Urban Vision) |
| --- | --- |
| Political Management | Lead Member for all stages before adoption Full council for adoption. |
| Internal Resources | DC |
| External Resources | Environmental Services, Encams |
| Stakeholder Resources | Partners IN Salford to provide key link to community planning. |
| Community & Stakeholder Involvement | Prior to consultation, specific and general consultation bodies will be canvassed for their views on issues. |
| Monitoring & Review Mechanisms | As part of the Annual Monitoring Report. |

  - Sustainable Design and Construction Guide

# Overview

| Role & Subject | To provide guidance for developers on the integration of sustainable design and construction measures in new developments, including energy efficiency, rainwater recycling, and the provision of recycling facilities. |
| --- | --- |
| Coverage | City wide |
| Status | SPD |
| Conformity | With policies ST16 and EN17A of “saved” Review UDP. |

# Timetable

| Stage | Dates |
| --- | --- |
| Commencement of Production | November 2006 |
| Preparation of Draft SPD | February – April 2007 |
| Public Participation | June – July 2007 |
| Estimated Date for Adoption | December 2007 |

# Arrangements for Production

| Organisational Lead | Associate Director Regulatory Services (Urban Vision) |
| --- | --- |
| Political Management | Cabinet for all stages before adoption Full council for adoption |
| Internal Resources | Plans Group |
| External Resources | GMGU, Environmental Services |
| Stakeholder Resources | Partners IN Salford to provide key link to community planning. |
| Community & Stakeholder Involvement | Prior to consultation on draft, specific and general consultation bodies will be canvassed for their views on issues. |
| Monitoring & Review Mechanisms | As part of the Annual Monitoring Report. |

5.0	LDF Production Process

5.1	Resources

    - The production of documents that will form part of the LDF will be led by the Spatial Planning Section.  Within this section the Plans Group will have overall responsibility for the production process but the team will receive support from the other groups within the section and the Planning Regeneration Section on appropriate documents.

    - The Development Control Section, which forms part of Urban Vision (a JVC between the city council and Capita/Morrisons), will have responsibility for the production of a number of the SPDs that will provide detailed guidance for those submitting planning applications. These are:

- Planning Obligations;

- Ellesmere Park;

- Design & Crime;

- House Extensions;

- Trees & Development;

- Telecommunications;

- Hot Food Take Aways; and

- Sustainable Design and Construction Guide.

    - Staff in Economic Development, Housing Strategy and Education and Leisure will also provide input and support to the production process as and when necessary.  Links with these teams have already been established through the process of reviewing the UDP.

    - Links have been established with Partners IN Salford who will be responsible for the review of the Community Plan for Salford, so that this will be co-ordinated particularly, with the production of the Core Strategy of the LDF.  Partners IN Salford have also set up its own “Good Practice in Community Involvement Project” and staff from this will be actively involved in the consultation on LDD’s, as well as in the production of the SCI.

    - Consultants will be engaged on specific projects where there is a lack of expertise or capacity in house.  Currently consultants are leading on the production of the Pendleton AAP and they were heavily involved in the production of the Lower Broughton Design Code SPD.  It is envisaged that they may be used in a similar way in the future.

  - Document Preparation and Public Involvement

    - The table below sets out the four main stages for producing a document with full development plan status.

| SUMMARY OF MAIN STAGES IN PREPARING A DPD |
| --- |
| 1 | Pre - Production | Background studies and information gathering Production of Scoping Report for Sustainability Appraisal |
| 2 | Production | Identify and assess options Consult on Preferred Options Report and Sustainability Appraisal (statutory 6 week consultation) Consider responses and prepare submission document and Sustainability Appraisal Submit to Secretary of State |
| 3 | Examination | 6 week period for representations on submitted document Examination into soundness of the document by an independent inspector |
| 4 | Adoption | Inspector issues binding report Council adopts document |

    - For SPDs, the process is slightly simplified, as there is no submission or examination.

    - Further information on LDF procedures is contained in publications from the Government, including a guide for the public entitled “Creating Better Places To Live: A Guide To The Planning System In England” available from the Office of the Deputy Prime Miister Publications (tel: 0870 240 3701) or on the ODPM website (www.odpm.gov.uk)

5.3	Council Procedures and Reporting Protocols

5.3.1	For each DPD and the SCI, the levels of political responsibility are as follows:

- Cabinet approval for the scope of the document;

- Lead Member for Planning approval for all other stages prior to the production of the preferred options document;

- Cabinet approval for all preferred options documentation; and

- Full council resolution required for submission and adoption stages.

    - For each SPD, the levels of political responsibility are as follows:

- Executive Decision (Lead Member for Planning) for all stages except adoption; and

- Full council resolution required for adoption stage.

    - The Environmental, Housing and Planning Scrutiny Committee will be involved in the discussing the issues and options of a number of key documents that relate to their work areas.  At present they will be involved in this way on the following documents.

- Core Strategy;

- Housing SPD;

- Greenspace Strategy SPD; and

- Planning Obligations SPD.

As new documents are added to the LDS, the Scrutiny Committee will assess which they consider they should be involved in. Other Scrutiny Committees will also be involved in the production of LDDs as appropriate.

  - Risk Assessment

    - In preparing the LDS, it was found the main areas of risk relate to the following.

- Staff Turnover.  It is inevitable that over a 3-year period there will be a turnover of staff within the sections responsible for producing documents.  It is not possible to predict where and when this will happen but in devising the programmes for the production of the documents sufficient slack has been built in to allow for a normal turnover of staff.

- Dynamic nature of the regeneration processes.  The regeneration process and funding are subject to many external factors.  Many of the LDF documents are seeking to support these programmes but the timescales for production of documents may be too lengthy to support this work effectively.  We will minimise this risk by working closely with GONW to find a practical solution to enable the planning process to support the delivery of the regeneration activity in the city.

- Community fatigue. The community are being consulted by many different agencies over a wide range of issues.  We will seek to minimise consultation fatigue by consulting on a number of documents at the same time and also by co-ordinating consultation activity with other agencies through Partners IN Salford.

- Capacity of PINS and other agencies to cope with demand nation-wide. At this stage, assumptions have had to be made about the exact availability of PINS to hold examinations but arrangements can be firmed up through the year and adjustments made when the LDS is next reviewed.  Their capacity is out of our hands but we have given early warning of our programme to them.

- “Soundness” of DPDs. We will minimise this risk by working closely with GONW and PINS at all milestone stages and in the run up to submission of DPDs.

- Legal Challenge. We will minimise this by ensuring that DPDs are “sound” and founded on a robust evidence base and well audited stakeholder and community engagement systems.

- Programme Slippage. We have built some slack into the later part of the programme for contingency.

  - Evidence Base, Monitoring, Strategic Environmental Assessment (SEA) and Sustainability Appraisal (SA)

    - To facilitate the formulation of documents within the LDF and in order to provide a robust evidence base for a baseline Sustainability Assessment that incorporates a Strategic Environmental Assessment, we will need to gather a comprehensive range of background information and survey material. The scope of the information is broad ranging, encompassing environmental, economic, social and physical elements.

    - In order to make the most efficient use of resources, existing ‘in house’ survey material and data will be utilised where it is up to date or can be built upon.  Where technical studies require particular expertise, then work will be commissioned from external consultants.

    - The council actively monitors a number of key areas.  In particular it already produces the following documents;

- Residential Development and Land Availability  - produced annually and monitoring the grant and take-up of residential planning permissions;

- The Urban Potential Study – looking at the city’s previously used land resource;

- The Affordable Housing Needs Appraisal – examining the volume and characteristics of need within the city – due to be complete in Spring 2006;

- Housing Moves Surveys – examining housing moves into new dwellings in Salford and into dwellings vacated by movers into new build stock;

- Housing Market Demand – an examination of the housing market in the city and components of housing need;

- Vitality and Viability Studies – produced bi-annually for the 4 town centres to monitor them against the town centre health check indicators;

- Retail and Leisure Development and Land Availability - produced annually and monitoring the grant and take up of retail and leisure planning permissions;

- Surveys to inform the Salford Greenspace Strategy, which will be extended to assess the existing and future needs of communities for open space, sport and recreation facilities, to comply with the requirements of PPG 17;

- Industrial Development and Land Availability – produced annually and monitoring grant and take up of industrial planning permissions;

- Office Development and Land Availability – produced annually and monitoring the grant and take up of office planning permissions;

- Unemployment Update – produced quarterly and looking at unemployment claimants and rates in Salford wards;

- Employment Workplace based survey – produced annually and looking at jobs by employment sector by wards;

- National Land Use Database  - produced annually and monitoring previously developed land within the city;

- The Derelict Land Survey – produced every 2 years and monitoring the quantity and distribution of derelict, underused and neglected land within the city;

- Salford Annual Baseline Review – produced annually and monitoring a range of statistics relating to the incidence and distribution of deprivation within the city;

- Early Warning System Quarterly report – produced quarterly and examining changes in relative levels of deprivation at postcode level in Salford;

- Index of Deprivation – produced on an ad hoc basis following the publication of data by ONS and analysing the findings for Salford;

- 2001 Census – city and ward profiles; and

- Strategic Flood Risk Assessment – due for publication in early 2006.

    - To inform the work of the Housing Market Renewal Initiative a major research project is currently being undertaken (Research, Foresight and Intelligence) by consultants for both Manchester and Salford City Councils.  The information that this project generates will become a key part of the information base for both plan production and Sustainability Appraisals.

    - The requirements of the Strategic Environmental Assessment (SEA) Directive have been linked with Regulations covering Sustainability Appraisals.  From this flows the need for the process of LDD preparation to:

- identify strategic alternatives;

- collect base-line monitoring information;

- predict significant environmental effects more thoroughly;

- secure greater consultation with the public and environmental authorities; and

- address and monitor the significant environmental effects of the plan.

    - As part of the process, the council must:

- prepare a sustainability appraisal report on the significant effects of options and the draft plan;

- carry out consultation on the draft plan and accompanying sustainability appraisal report;

- take into account the sustainability appraisal report and the results of consultation in decision making; and

- provide information when the plan is adopted and show how the results of the Sustainability Appraisal have been taken into account.

    - In order to comply fully with Regulations, secure efficient working and provide a robust and transparent evidence base, SA & SEA will be embedded into production of LDDs at the very start of preparation and updated at each milestone stage.

Appendix1 : Schedule of Saved Policies

This table represents the council’s initial views on the what policies are likely to be replaced by the various DPD’s that we anticipate preparing in this 3 year period.  As a result of consultation these documents may change significantly and therefore it will be necessary to refine this table to reflect this.  The table is also based on the policies in the Review Plan as submitted to public inquiry but these may change as a result of the inquiry, requiring the table to be updated.

| Policy Number | Policy Name | Destination | Comments |
| --- | --- | --- | --- |
| Chapter 2 | Plan Strategy | Replaced by Core Strategy when adopted | Includes Vision & 7 Aims of Plan |
| Chapter 3 | Spatial Framework | Replaced by Core Strategy when adopted |  |
| ST1 – ST17 | Strategic Policies | Replaced by Core Strategy when adopted |  |
| MX1-4 | Mixed-Use Development | Save policies beyond 2009 until DC Polices DPD is adopted | MX1 may be incorporated into the Core Strategy. |
| DES1-11 & 13 | Design polices | Save policies beyond 2009 until DC Polices DPD is adopted |  |
| H1A | Managing the Supply of Housing | Replaced by Core Strategy when adopted |  |
| H1 & H3 – H8 | Housing policies | Save policies beyond 2009 until DC Polices DPD is adopted | H1 may be incorporated into the Core Strategy. |
| H9 | Sites for New Housing | All but H9/13 saved beyond 2009. H9/13 replaced with allocation in Pendleton Area Action Plan. |  |
| E1 | Strategic Regional Site: Barton | Replaced by Core Strategy when adopted. | Dependent on Core Strategy being able to designate sites. |
| E2 & E2A | Innovation Park and Knowledge Capital | May be replaced by Core Strategy when adopted, otherwise will be saved beyond 2009. |  |
| E3, E5, E6 | Employment and economic policies. | Save policies beyond 2009 until DC Polices DPD is adopted |  |
| S2 | Retail and Leisure Development within Town and Neighbourhood Centres | Retail Hierarchy will be replaced by Core Strategy, rest of policy will be saved beyond 2009 until DC Polices DPD is adopted |  |
| S2B – S4 | Retail and Leisure Policies | Save policies beyond 2009 until DC Polices DPD is adopted |  |
| S5 | Site for New Retail Development | Replaced with allocation in Pendleton Area Action Plan. | If site has planning permission will not need to be included in plan. |
| EHC0 – 5, 6/1, 6/3, 6/4, 7, 8 &9 | Education, Health & Community Facilities Policies | Save policies beyond 2009 until DC Polices DPD is adopted. |  |
| EHC6/2 | Site for the Provision of Health Facilities - Pendleton | Replaced with allocation in Pendleton Area Action Plan. |  |
| A1 – A2 & A4 -A15 | Accessibility Policies | Save policies beyond 2009 until DC Polices DPD is adopted. |  |
| A3 | Metrolink | Replaced by Core Strategy when adopted | First sentence of policy will not be incorporated into Core Strategy so will need to be saved beyond 2009. |
| EN1-2, EN 4 – 6, EN 7 A-E, EN 8-18 | Environmental Protection and Improvement policies | Save policies beyond 2009 until DC Polices DPD is adopted. |  |
| CH2-10 | The city’s Heritage Policies | Save policies beyond 2009 until DC Polices DPD is adopted. |  |
| R1- 2, R 4-6, R8 | Recreation Policies | Save policies beyond 2009 until DC Polices DPD is adopted. |  |
| R3 | Regional Park | Replaced by Core Strategy when adopted |  |
| DEV 1-7 | Development Policies | Save policies beyond 2009 until DC Polices DPD is adopted. |  |
| W1 | Waste Management | Save policy until replaced by Greater Manchester Waste DPD | Timetable for the Waste DPD not yet fixed, so unsure whether need to save beyond 2009. |
| M1-M2 | Minerals | Save policies beyond 2009 until DC Polices DPD is adopted. |  |
| Appendix 2 & 3 | Disabled, Cycle, Motorcycle and Car parking standards | Save policies beyond 2009 until DC Polices DPD is adopted. |  |
| Appendix 4 | Indicative flood plains | Replaced by Core Strategy when adopted. |  |

# Text boxes

Local Development Framework

Local Development Scheme

Statement of Community Involvement

Annual Monitoring Report

Saved UDP Policies and Proposals Map

Pendleton Area Action Plan

Proposal Map

Error! Not a valid link.

Core Strategy

Error! Not a valid link.

Error! Not a valid link.

Supplementary Planning Documents

Supplementary Planning Guidance

Regional Spatial Strategy

SA/SEA