Background

A fundamental Best Value Review of Home to School and Social Care Transport Services in Salford has been undertaken in the last eighteen months.

The findings of the review, including a series of recommendations, are reported in the Final Report

this document

The purpose of this report is to provide an Improvement Plan in the form of a set of Action Plans to ensure that the changes identified by the Best Value Review Team are achieved.

Progress has already been made in a number of areas and these are reported on in the Action Plans.

The primary organisational change identified by the Review Team, and already agreed in principle by Scrutiny, is the need for the establishment of a centralised Passenger Transport Unit (PTU).

In preparing the Action Plans, it is recognised that many of the proposed changes will need to be implemented by the PTU and, therefore, the proposed timetable allows time for its creation. Issues relating to the Authority’s duty of care, however, need addressing immediately.

financial implications

Salford currently spends in excess of £3.5m annually on the provision of passenger transport services. The review has identified a number of areas of improvement for the procurement and delivery of these services, detailed in the action plans. Whilst it is not possible to quantify the level of savings that may accrue from the introduction of these changes it is reasonable to assume, by comparison with the experience of other authorities, that they will deliver savings in the future.

The minor changes already introduced by Social Services in conjunction with Ring and Ride has already achieved a saving of £15,000 per annum. Furthermore, the review has highlighted the shortcomings of the current arrangements for procuring and managing external transport for adult service users. A saving of say 10% on this provision, through the introduction of more robust procedures, would achieve savings of a further £15,000 per annum. This is a conservative estimate and it is likely that the actual savings will be in excess of this amount.

The review of home to school transport has shown that whilst the provision is currently the subject of competitive tender there are a number of factors that are influencing the relatively high unit cost, compared to other LEAs. These include:

a shortage of specialised vehicles resulting in high contract prices

greater dependence on low-occupancy vehicles (i.e. taxis)

a high number of taxis carrying only 1 passenger.

Whilst the high use of taxis and the low occupancy rates may be partly due to local policies and circumstances, it is reasonable to assume that the application of the scheduling, co-ordination and procurement recommendations in the Action Plans will result in a more cost effective service.

The review has identified a number of quality issues that relate to the Authority’s duty of care. The introduction of appropriate quality standards, monitoring, risk assessments and training will result in additional cost if no other action is taken. However, a number of options, including quality partnerships and longer-term contracts, are detailed in the Task Notes. The adoption of these options should assist in stimulating the supply side of the market and stimulate operators to invest in higher quality vehicles, whilst keeping costs at a competitive level.

Ultimately the delivery and cost of these passenger transport services are demand driven. Whilst the changes in the management and delivery of the services recommended by the Review Team will provide a more cost effective service, a review of the existing eligibility criteria is essential if resources are to be targeted at those service users most in need of assistance.

Action Plan 1 : Management of the Service

| Recommendations | Stakeholder Department(s) | Lead Officer(s) | Action already Taken | Timescale | Resource Implications | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| The establishment of a central Passenger Transport Unit to commission and manage all home to school and social services transport. | Education Social Services Environmental Services | LW / EM | Agreed, in principle, by Cabinet (24/9/02) | July 2003 | Establish new team from re-deployment of existing resources |  |
| Prepare detailed service specifications for the different activities undertaken | Education Social Services Environmental Services | LW / EM | Work in progress | July 2003 |  | Integral part of establishing PTU |
| Develop SLAs that provide for regular monitoring of performance and standards | Education Social Services Environmental Services | LW / EM | Work in progress: Review of other local authority models being undertaken | July 2003 |  | Integral part of establishing PTU |
| Review all management systems and processes and ensure sufficient resources are provided to deliver an efficient and cost effective service | Education Social Services | PTU | Review of systems and processes underway. | Dec 2003 |  | Good practice identified will be replicated across the teams. Performance measurement issues need to be addressed. |

Action Plan 2 : Policy Issues

| Recommendations | Stakeholder Department(s) | Lead Officer(s) | Action already Taken | Timescale | Resource Implications | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| Review policy in respect of transport for pupils with special educational needs | Education | LW | Draft criteria prepared | July 2003 |  | Consultation essential |
| Review of transport policies and working arrangements for post-16 students, in partnership with educational establishments and the Learning & Skills Council | Education Colleges Learning & Skills Council | LW | Meeting of partnership arranged | Mandatory statement by 31 May 03 |  | Consultation exercise underway |
| Adopt the “Guidelines for the identification of road safety hazards and the assessment of risk of walked routes to schools” produced by the Local Authority Road Safety Officers’ Association | Education | LW | Contact made with other agencies | Dec 2003 |  | Marginal impact, lower priority |
| Review the policy relating to transport for adult services, including consideration of the introduction of a charge | Social Services | EM | Draft criteria prepared | July 2003 |  | Consultation essential |
| Agree clear criteria in respect of the provision of passenger assistants | Social Services Education | EM / LW | Identified the need for a formal hierarchy of need in relation to provision and to support | July 2003 |  |  |
| The conditions of service of all drivers and passenger assistants be reviewed | Social Services Education | EM / LW | Issues identified to Director with a request that urgent consideration be given to fast-tracking negotiations | July 2003 | Not yet identified | Cannot wait for the Job Evaluation process |
| Ensure that: all Council reports consider the possible implications and costs for transport services and that budgets are adjusted to reflect the resulting savings / additional costs members are provided with reports reviewing eligibility criteria and also giving clear financial information on the cost of transporting different categories of service users | Corporate Services Education Social Services | LW / EM | Issue identified to Corporate Service for consideration | July 2003 |  | Transport issues are critical in an authority in Salford’s geographical location Look to build into Scrutiny Agenda |

Action Plan 3 : Customer Focus

| Recommendations | Stakeholder Department(s) | Lead Officer(s) | Action already Taken | Timescale | Resource Implications | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| Agree a service consultation plan | Education Social Services Environmental Services | LW / EM | Draft consultation plan developed (Education) | July 2003 |  | Need to extend to all stakeholders |
| Produce improved information leaflets for service users | Education Social Services | LW / EM | Leaflets produced and distributed to all stakeholders (Education) Written versions prepared, pictogram versions in preparation (SS) | July 2003 |  |  |
| Set communication targets and monitor performance | Education Social Services | LW / EM /PTU | Currently meeting corporate standards | July 2003 |  | Need to develop to ensure implementation of service delivery |
| VMS – continue to improve customer focus | Environmental Services |  |  | On-going |  | Need to develop SLAs with Social Services and Education teams |

Action Plan 4 : Quality Standards

| Recommendations | Stakeholder Department(s) | Lead Officer(s) | Action already Taken | Timescale | Resource Implications | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| Review of approaches to stimulate greater commercial involvement: longer contracts quality partnerships resource tendering operation-only contracts increased in-house provision | Education Social Services Environmental Services | PTU |  | December 2003 |  | Continuing requirement |
| Define quality standards and instigate standard monitoring and reporting of actual service delivery | Education Social Services Environmental Services | LW / EM / PTU | Passenger assistant monitoring system introduced (Education) | July 2003 |  | Need for corporate standards There is a training requirement to ensure that the officer monitoring has the technical capabilities in respect of passenger safety items Requires immediate attention |
| Review training arrangements for drivers, passenger assistants and external drivers | Education Social Services | LW / EM | Some training already delivered to drivers and passenger assistants | July 2003 |  | Need for corporate standards Requires immediate attention |
| Formalise a corporate transport risk assessment process and extend to all service users | Education Social Services | LW / EM | Currently preparing / updating risk assessments on all in-house service users (SS) Transport staff and passenger assistants received wheelchair assessment training from Karen Gibson (Education) | July 2003 |  | Needs for corporate standards. Requires immediate attention |
| Review the arrangements for providing appropriate information to drivers / passenger assistants | Education Social Services Legal Services | LW / EM | Commissioners have to prepare a risk assessment on all new service users and pass to service provider | Autumn 2003 |  | Data protection and other implications need to be considered |

Action Plan 5 : Improving Efficiency

| Recommendations | Stakeholder Department(s) | Lead Officer(s) | Action already Taken | Timescale | Resource Implications | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| Review of: route planning and vehicle occupancy rates route planning vehicle mix vehicle occupancy rates | Education Social Services | PTU |  | December 2003 |  |  |
| Determine a formal hierarchy of transport | Education Social Services | PTU |  | September 2003 |  | Complex exercise |
| Investigate the potential benefits of increasing parental / carers mileage allowances | Education Social Services | PTU | Pilot scheme with foster carers in Social Services | For next academic year |  | Evaluate Pilot |
| Improve travel training arrangements | Education Social Services | LW / EM | Opportunity for using mobility officers (SS) being investigated to replicate model in Education. | For next academic year | Start-up costs, but potential cost-savings in long term | Better use of resources |
| Review sickness cover arrangements | Social Services |  | In monitoring attendance, issues have arisen around conditions of service | July 2003 |  | Better use of resources |
| Investigate the feasibility of replacing existing meals-on-wheels vans with MPVs, which could then be used for school and / or day centre work | Social Services Environmental Services | PTU |  | December 2003 |  | Consultation with clients required |
| Market testing of both the in-house service and the service provided by VMS | Environmental Services Social Services | PTU |  | December 2003 |  | Investigation required |
| The benefits of including maintenance packages in all future lease agreements be further explored | Environmental Services | MT |  | December 2003 |  | Comparison of both models required |
| The potential for better use of existing resources by means of co-operation with other agencies be investigated | Social Services Education |  | 14 service users who formerly had taxis placed onto Ring and Ride at an approx. annual saving of £15,000. The GMPTA is also looking at ways of strengthening local community transport associations and they suggest they could provide services to education and social services. | December 2003 |  |  |
| Review arrangements for commissioning and managing external transport (Social Services) | Social Services | EM / PTU |  | July 2003 |  | Implications for Childrens Services (SS) |

Action Plan 6 : Financial Issues & Benchmarking

| Recommendations | Stakeholder Department(s) | Lead Officer(s) | Action already Taken | Timescale | Resource Implications | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| Review the budget setting procedure to make it more realistic and involve shared responsibility | Education Social Services | LW / EM |  | December 2003 |  |  |
| Improved budget reporting arrangements | Education Social Services | LW / EM |  | May 2003 |  | Scrutiny |
| Develop a formal set of Performance Indicators for annual reporting and sharing with other authorities (on a confidential basis) | Education Social Services Environmental Services | LW / EM | Discussed with local ATCO group. Hoping to agree PIs by November 2003 | December 2003 |  |  |

# Text boxes

## Salford City Council

Home to School and Social Care Transport

## Implementation Plan

April 2003

#### REPORT INFORMATION

First Draft Created On: 19/03/2003 08:36

Last Revision Saved On: 21/03/03 10:48

Name of File: 223'1 Implementation Plan 210303 JT

File Size: 119296 Kb

Version (Revision) Number: 8

Total Prep & Editing Time To Date: 144

| Quality Assurance |
| --- |
| Author | NT |
| Team Leader |  |
| Director | JT |

### The TAS Partnership Limited

Specialist Consultants in Public Transport