## Sheet1
Project: Buile Hill Park - Delivering the Master Plan | 2002 | [8 empty] | 2003 | [11 empty] | 2004 | [11 empty] | 2005 | [11 empty] | 2006 | [11 empty] | 2007 | [11 empty] | 2008
| Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
Consultations with community | bar: 2002 Apr to 2002 Jun
Report to Cabinet | bar: 2002 Jul
Liaisons with HLF and partners | bar: 2002 Aug to 2002 Dec
Prepare detailed Business Plan | bar: 2002 Sep to 2003 Mar
Submit capital bids | bar: 2002 Sep to 2002 Nov
Submit stage 1 H.L.F. bid | bar: 2003 Apr
Receive stage 1 H.L.F apporval | bar: 2003 Oct
Prepare stage 2 H.L. F bid | bar: 2003 Oct to 2004 Apr
Submit stage 2 H.L.F bid | bar: 2004 Apr
Receive stage 2 H.L.F apporval | bar: 2004 Aug
Conservatory restoration: | bar: 2004 Jun to 2005 Jun
Recreation of Buile Hill gates and Lodge, Restoration of Vinery | bar: 2004 Sep to 2005 Jul
Restoration of Hall setting, decorative planting, upgrade car park and footpath links | bar: 2004 Sep to 2006 Mar
Recreation of Seedley Entrance Gates and Lodge | bar: 2004 Sep to 2006 Jul
Reinstate Seedley Park Lake: | bar: 2005 Jun to 2006 Sep
Reintroduce Seedley Park Fountain, Edgings, Footpaths and Steps | bar: 2005 Jun to 2007 Mar
Reintroduce Bandstand, Decorative Planting, Restore Amenity Grasslands, | bar: 2005 Jun to 2007 Mar
Upgrade Entrance at Gore Crescent, Lower Seedley Rd, and Southgarth Rd | bar: 2005 Jun to 2007 Mar
Interpretation of Former Lake Involving Artist: | bar: 2005 Jun to 2007 Mar; 2007 Jul to 2008 Mar
Provide quality setting for seating, planting, create wildlife/ interpretation area. Upgrade entrances at Hart Hill, Weaste lane North and South. | bar: 2005 Jun to 2007 Mar; 2007 Jun to 2008 Mar
Refurbuish toilets | bar: 2006 Oct to 2007 Jul

## Sheet2
| 2004/5 | 2005/6 | 2006/7 | 2007/8
| £ | £ | £ | £
H.L.F | 800000 | 776355 | 551500 | 272144
City of Salford | 200000 | 194089 | 137876 | 68036
Total | 1000000 | 970444 | 689376 | 340180 | 3000000