Appendix C

BEST VALUE REVIEW – BIRTHS, MARRIAGES, DEATHS

IMPLEMENTATION PLAN

# CHALLENGE

| ISSUE | ACTION | TIMESCALE | RESPONSIBLE PERSON | PROGRESS |
| --- | --- | --- | --- | --- |
| Develop clear aims/ objectives for the service that support our Corporate Aims | To meet all statutory requirements as prescribed by the General Register Office, and achieve fully acceptable mark. To meet the divergent needs of Salford’s communities at some of the most important times of their lives and to do so in an efficient, courteous and sympathetic fashion. To consult with staff to ensure aims/objectives are being met and that staff are aware of corporate aims and how they link to RO aims | Ongoing Ongoing | All staff All staff All staff | Achieved Aims and objectives agreed with staff and members and publicised with customers and in Service Plan Achieved |
| Develop mechanisms for measuring how well we are achieving our aims | Aims are described in yearly Service Plan with monthly and quarterly updates Service Plan to be reviewed following decision on new aims and objectives Targets are set against Performance Indicators, all targets monitored daily, weekly, monthly. |  | CA/RW | Performance Indicators/Targets confirmed in new Service Plan 2004/05 Achieved Achieved |
| Re-visit aims and objectives in light of forthcoming legislative changes. | Staff consultation to discuss aims/objectives and review/amend where necessary e.g. future aims to include:- To make Salford RO one of the leaders moving forward with vital change in Registration Promote equalities/ value diversity within our community Make service more accessible and customer friendly/ improve technology | Monthly staff meetings | All staff CA/RW | Achieved New aims/objectives now determined See pages 6 - 17 |

CITIZENSHIP

| ISSUE | ACTION | TIMESCALE | RESPONSIBLE PERSON | PROGRESS |
| --- | --- | --- | --- | --- |
| Training programme for staff | SR’s to attend mock ceremony at Liverpool Discussion and feedback with staff at next staff meeting Concise notes and information about how Salford will perform ceremonies and where etc Organise Training Day for staff / mock simulation ceremony Staff to see live ceremonies in turn before performing themselves |  | RW/VP All staff RW RW All staff | Achieved Achieved Achieved Achieved First ceremony taken place 20th April 2004. |
| Anticipate effect on staffing establishment | All registration staff to participate in ceremonies Casual registrars to be used in case of staff shortages Contact personnel for advice on amendments to job descriptions Appoint part time member of staff to assist with extra workload Designate Citizenship Officer status to current member of staff and award increment for extra responsibility |  | All staff AR CA CA | Agreed SRs and DSRs to take turns in performing ceremonies Job descriptions amended and agreed Achieved Achieved |
| Cost to the Authority and to Applicants | Each applicant to pay the authority £68.00 Determine how payments will be made – direct from applicant or via Home Office Consult Home Office Re: ability for Authority to set own fees for ceremonies Consult Home Office Re: Timescale of payments Estimate additional costs for hiring of Council Chambers (£10 per hour), costs of providing refreshments and attendance of Mayor/ Deputy Mayor Consult Cathy Pickup (Members Services) Estimate and decide on costs of gift/commemorative certificate |  | CA/RW CA/RW CA/RW CA/RW/AR/CP CA CA/RW/AE/AR | Achieved – payments direct to authority as and when applicants are approved for Citizenship. Authority can set fees for individual ceremonies Council Chamber booked and hiring is free due to Mayor’s attendance Achieved Information Pack and Pen to be given to each applicant |
| Cost to the authority etc | Set fees for individual ceremonies |  | CA/RW | Achieved – as Approved Premises |
| Likely take up | The Home Office has undertaken a postal code exercise to give an estimated figure for Salford of 389 ceremonies |  |  | Roll out of applicants not as frequent as first anticipated due to delays at the Home Office. |
| Decide who will undertake the ceremonies and consider role for the Mayor | Two members of staff will be required from the Register Office All applicants to be booked in and ID Checked One member of staff to conduct ceremony – SRs and DSRs Mayor or Deputy Mayor to be consulted and invited to attend ceremonies – consult with Cathy Pickup Decide whether to raise profile of Salford i.e. with local press/ Communications Dept – to contact Ian Andrew |  | All staff CA/RW RW/CP AR | Achieved Checklist devised for booking in 4 members of staff to take turns Achieved and Mayors speech written For reasons of security it was decided not to invite any press coverage of ceremonies |
| Publicity/Marketing | Devise poster for Office to publicise Citizenship Ceremonies and services offered by Salford Consult printing for costs etc Advertise ceremonies on internet Ensure all posters and internet contain Home Office contact number rather that RO number |  | RW/CH CA RW CH | Achieved Laminated signs displayed in office and full information detailed on website Achieved Achieved |
| Frequency of ceremonies | Decide on frequency of ceremonies following seminar on ceremonies to see how long the registration will take Discuss possibility of ceremonies taking place once a month Plan for individual ceremonies – consult with Home Office |  | CA/RW CA/RW CA/RW | Achieved – Council Chamber booked 3rd Tuesday of each month with up to a maximum of 34 applicants at any one ceremony Individual ceremonies offered at Approved Premises for higher fee |
| Conduct of the ceremony including refreshments etc | Consult with Cathy Pickup to clarify provision of refreshments and costs Consider merchandising products etc |  | CA/RW/AR | Achieved Devised info pack from Salford in conjunction with Home Office pack |
| Location of ceremonies | Council Chamber seat up to 60 people but applicants will have to be given opportunity to bring guests Consider Worsley Court House/Buile Hill Park as larger venues Consideration given to Council Chamber or Mayors Parlour for smaller ceremonies List suitable venues for individual ceremonies Draw up timetable of ceremonies and suitable venues |  | BVR Team | Achieved - Council Chamber booked with public gallery available to allow up to 2 guest per applicant. These venues suitable for larger individual ceremonies Mayor’s Parlour booked for smaller ceremonies – deadline for booking appropriate venue two weeks before ceremony date. Time Table/Approved Premises listed |

BABY NAMING/RE-AFFIRMATION OF VOWS/PARTNERSHIP CEREMONIES

| ISSUE | ACTION | TIMESCALE | RESPONSIBLE PERSON | PROGRESS |
| --- | --- | --- | --- | --- |
| Training programme for staff | Consider level of training required as transition from performing current ceremonies to new ones should not require intensive training Devise training plan and notes once procedures in place | June 2004 | CA/JK RW | Partnership/Citizenship Ceremonies now running. All SRs/DSRs to take turns after watching ‘live’ ceremony Training notes completed for Partnership/Citizenship Ceremonies |
| Anticipate effect on staffing establishment | Re-Evaluate staffing structure following citizenship ceremonies to analyse work load and effect on staff After initial implementation evaluate customer demand for new services Plan rotas and decide whether more casual registrars should be employed | June – September 2004 | CA/RW | Part time post already employed for citizenship ceremonies |
| Cost (to the Authority and to applicants) | Determine fees in line with other Local Authorities who seem to be charging similar to Register Office weddings so as not to discriminate (£60 notice fees - £37.50 on day of wedding) Determine fees for Baby Naming Ceremonies at higher rate in line with other Local Authorities (similar to Approved Premises) Staffing costs i.e. fees for attending ceremonies/overtime to be considered when weekend work required Decide whether ceremonies be incorporated into the normal working diary. | July 2004 July 2004 July 2004 | CA/RW CA/RW CA/RW CA/RW | Achieved –fees set as RO and APs |
| Likely Take Up | Devise survey to give to Birth informants to seek interest in Baby Naming Ceremonies For other ceremonies promote office and new services offered. (Rather than spend time money on surveys to seek interest as these changes will be coming into force following RRO) | July 2004 | All staff | Decision to go ahead with services rather than devise survey. Promote naming ceremonies by giving info leaflet out at birth registrations |
| Publicity/Marketing | Update internet to include new services offered Update choice of music/poetry and have selection of ceremonies on internet Advertise/promote marriage co-ordinator service Consider advertising in Gay Press for Partnership Ceremonies Devise Information Leaflets for all new ceremonies Analyse costs/contact graphics for printing | July 2004 June – Dec 2004 July/Aug 2004 July/Aug 2004 July 2004 | RW/JK CA/RW CA/RW/JK/SL CA/RW | In Progress – JK gathering info from all other offices on what services/packages they offer |
| Conduct of ceremonies including music/poetry | Offer similar services to current weddings to include choice of readings/poems and music Allow couples to choose their own ceremonies and add their own words SRs and Registrars to be present to conduct ceremony and register Ceremonies to be included in current working diary Staff to work on Rota basis | August 2004 | CA/RW/VP/JK CA/RW/VP/JK | Commitment Ceremonies finalised and first ceremony in June |
| Location of ceremonies | Consider whether ceremonies to take place at Register Office Current refurbishment plans to incorporate 2nd marriage room. Consider this room to be used for other ceremonies Consider ceremonies being conducted at Approved Premises |  | CA/RW | Partnership ceremonies agreed to take place at RO Agreed |
| Timescales for introduction | Consult with Civil Ceremonies Ltd for information on performing Commitment Ceremonies Analyse costs for using Civil Ceremonies and decide whether these services can be offered prior to RRO being passed Consider baby naming/re-affirmation of vows ceremonies to be introduced once reform order has been passed |  | CA/RW CA/RW/AE CA/RW/All staff | Following Local Government Act 2003 these services can be offered independently of any other outside Agency. Partnership/Commitment Ceremonies now completed. In process of gathering info for all other ceremonies – Decision to implement these ASAP before RRO |

LGA “BETTER PRACTICE” STANDARDS

| ISSUE | ACTION | TIMESCALE | RESPONSIBLE PERSON | PROGRESS |
| --- | --- | --- | --- | --- |
| Determine which standards are not currently meeting the LGA Better Practice Standards | Facilities and Accommodation Information leaflets published including minority languages Consult with printing and obtain costs for printing leaflets Plans for refurbishment include 2nd marriage room and a separate brides room Consult with Dave Lyons, Development Services for initial surveys and costs Determine budget/costs Invite Tenders Refurbishment to start and timetable given from Development Services Contact Emergency Planning for fully developed comprehensive business/continuity, recovery plans for any disasters at RO Devise written plans Performance Management and Consultation Independent external audit of service – consider IIP or Charter Mark Results of customer surveys to be made public and accessible in office and on internet – survey issued Oct/Nov 2003 Devise Action Plan following customer survey Next survey to include Funeral Directors/ Hospitals/Coroners, other communities etc Assess service and score against Good Practice Guide implementing areas of non compliance in Business Plan/Service Plan Report to Management/Proper Officer findings Personnel and Staff Development Review Training Policy/Strategy Devise new Training system and identify training unit Allow for feedback and review provision All staff to train as DSRs for future changes in registration to allow a multi disciplined staff Accessibility and Service Standards All staff to wear name badges Review Service Plan and targets to include number of complaints received, time to deal with complaints etc | Sept 2004 June 2004 July 2004 On going | SL CA/SL CA/RW/DL CA/AE AE DL CA EP Dept AE/AR/RW RW CA/RW All staff RW RW RW/JK/LC JK/LC All staff JK CA/RW | Achieved Graphics produced leaflet – now ready Anticipated completion date end June 04 Agreed Achieved One contractor employed Achieved Awaiting final plans Draught IIP format completed. Accreditation to be sought prior to March 2005 Achieved Achieved – action plan to include Car Park repairs, Consideration to Refreshments in waiting areas, Refurbishment of reception area and gents toilet Achieved In progress Achieved – training unit devised with records of training/reviews maintained Achieved Only one member of staff remaining to train as DSR Achieved Achieved Corporate Complaints Procedure to be adopted. All complaints received at RO to be monitored and actioned |
| Ascertain the resources required to meet those standards where the service is currently deficient including capital, staffing, and all necessary changes to procedures | Identify what changes/improvements should be made to building and where budget is coming from Identify any staffing deficiencies in particular to new services being introduced Devise evaluation plan for new services | July 2005 | CA/RW CA/RW CA/RW/AR | Achieved – improvements/refurbishments plans in process Achieved – part time clerical assistant/deputy registrar employed |

CHALLENGE WHETHER OUR STANDARDS OF CUSTOMER CARE AND THE SERVICE ITSELF MEET THE REQUIRMENTS OF THE DIVERSITY OF THE POPULATION THAT THE SERVICE SERVES

| ISSUE | ACTION | TIMESCALE | RESPONSIBLE PERSON | PROGRESS |
| --- | --- | --- | --- | --- |
| Location of Premises:- BDM presence within Lift Centres Effect on Budget How these proposals complement the need for better access in the competitive environment following vital changes in Registration | Consult with BPR Team on info for timescale of Lift Project etc Consult with BPR Team on costs/IT equipment etc for outstationed Registrars Implement presence of Registrar in Lift Centre rather than Call Centre staff Liaise with BPR and NHS with regards to presence of Registrar at Hope Hospital Consider link with Bereavement Services who are hoping to have presence in Hope Hospital Attend meetings with BPR Team/NHS trust and Bereavement Services to discuss progress they are making Consult regularly with Lift Project to action Registrars presence in various centres (Part Time) Consult staff on who will work in Outstations/Organisation of office and decide on hours present at outstations i.e. once or twice a week/late night etc | Dec 2005 Ongoing Dec 2005 July 2004 June 2004 Ongoing Ongoing Oct 2005 | CA/RW/AR CA/RW/AR CA/RW VP/KL VP/KL VP/KL CA/RW All staff | Initial consultation with Andrew Pringle. Uncertain what accommodation will be available for Registrars due to limited space for “drop in” services In progress – accommodation for Registrars to register deaths and identified. IT equipment/costs now identified to allow actioning presence at Hope Hospital. Awaiting software from GRO – NHS to install on their PC Monthly meetings with CRM/ to include Lift Project Decide after implementation of RRO July 2005 onwards. Lift centres anticipated to be completed by Dec 05 |
| Opening hours including staffing implementations | Management and staff decision to be made on change of hours Await to see what presence Registrars can have in Lift Centres and Hospitals to enable late night service Action Registration of Births at Hope Consider security issues if late night offered at Register Office Consider weekend opening Survey results may not show a great demand for change of hours but management to determine whether change of hours would keep in line with “better practice” | June 2004 Dec 2005 Aug 2004 Dec 2005 March 2006 | All staff CA/RW CA/RW CA/RW CA/RW/AE | For death registrations at Bereavement Centre. 2 days agreed Monday PM – Thursday AM initially. Awaiting results of new customer survey to determine any other hours Decision to offer more flexible hours at hospital/lift centres initially Awaiting RRO implemented to analyse effect on LA providing services Delay until RRO passed to determine demand for other services and hours |
| Suitability and standard of decoration of premises | Devise plans for alterations/refurbishment to current building to include 2 new offices for SRs, second marriage room, brides room, extension to current general office, staff room Confirm budget provision Draft specification Invite Tenders Work completed | June 2004 | DL AE DL DL DL | Completed Completed Completed Completed Anticipate completion by June 2004 |
| Efficiency in dealing with customers | Monitor targets in place to measure efficiency in dealing with members of the public Publish service standards on internet as well as in office Compare service standards with other local authorities (info obtained from internet) Discuss and review targets and standards with all staff Implement any changes and amend Service Plan as necessary Action monthly meetings with call centre management to ensure high standard of customer efficiency |  | RW/SB/LC RW RW All staff RW CA/RW | Achieved Achieved Achieved Achieved Achieved Achieved – customer feedback/comments discussed and actioned where necessary |
| Processing of payments, inc credit/debit card payments | Meeting with Hannah Yates to discuss payment systems Salford uses Visit Rochdale RO to review their system Consult with Hannah Yates/ Ian Rodger for implementation Confirm budget provision Consult staff and organise staff training |  | CA/RW AR/VP CA/VP/AR AE CA | Achieved Achieved Achieved Achieved Achieved |
| Standards of Courtesy | Yearly customer satisfaction survey produced to demonstrate standard and levels of customer care Analyse results and discuss with staff and Call Centre to ensure high standards of customer care maintained Review service standards to include customer care standards Discuss with staff standards of courtesy and implement basic standards internally Publish standards in office and on website Consider staff attending Customer Care courses – liaise with Personnel to implement |  | All staff/KL CA/RW/C Haslam RW RW RW JK/LC | 2003 survey completed Achieved Achieved Achieved Achieved Awaiting decision to allow 2 members of staff to attend course |
| Uniforms/ Clothing Allowance | Invite suppliers of uniforms to visit office and provide costs Devise report to present to Alan Eastwood Confirm budget provision Decision approved/denied |  | JK JK/RW AE AE | Achieved Achieved Achieved Uniforms granted and ordered |
| Compliance with the DDA | Meeting with Equalities Officer and Disabilities Officer from Personnel to assess building and services offered Devise list of changes to be implemented as follows:- Repositioning of doorbell to disabled access Consider partial covering of disabled access for wet weather Consider customer survey in other languages and larger font for the partially sighted Consider additional questions such as Ethnic Origin/Registered Disabled etc to determine how many of our customers need extra facilities Consider sign language training for staff Identify costs Ensure Fax Number clearly advertised in office and on website for the hard of hearing Consider information leaflets in Braille or contact RNIB for assistance when required – have information and contact numbers Consider staff training on Equal Opportunities and Disability Customer Care Course | May 2004 May 2004 July 2004 July 2004 July 2004 July 2004 June 2004 July 2004 | CA/RW DL DL All staff All staff CA/RW CA.RW/AE RW CA/RW JK/LC | Achieved Uncertain due to location of access whether building could accommodate shelter Contacted Personnel – awaiting decision to attend external courses Achieved |
| Extent to which ethnic minority requirements are catered for including publication of information in minority languages | Liaise with other local offices to compare information leaflets Add paragraphs to back of info leaflets in most common languages used i.e. Urdu, Gujarati and Arabic (to state if you need any help or assistance please telephone…) Consult with printing to arrange leaflets and identify costs Display poster for Language Line and telephone numbers for interpreters required Add information onto website in other languages and telephone numbers for further assistance | June 2004 | SL SL CA/SL SL RW/SL | Achieved Achieved Achieved – graphics completed leaflets and budget provided Achieved |
| Publication of information in Braille Facilities for the hard of hearing Access to and including staff implications facilities for the disabled | See compliance with DDA for actions to be taken |  |  |  |
| Plan for legislative changes following Registration Reform Order | Confirm date for RRO being passed Attend meetings with LACORS/GRO and Local Meetings between neighbouring authorities Establish Registration Review Team to plan/manage/implement changes Consider appointing Change Manager with ability and authority to drive change forward Consider staffing implications including impact on service following choices of service provider to public, loss of revenue etc– i.e. interim appointments, natural wastage, re-deployment, new job descriptions in consultation with union, new staffing structure, hours of work, salaries Engage stakeholders e.g. Authorised Persons, Clergy, Approved Premises, Hospitals, Doctors, Funeral Directors ensuring communication throughout managing changes Consider partnership options for delivering of services Outline financial consequences of national service review i.e. loss of revenue from certificates, registrations and impact of notices of marriage given in any district/AP licence fee and accommodation requirements/costs in light of future changes in contrast to fees for additional services/ Consider amalgamation with neighbouring authorities/signposting to nearest service provider Implement key areas as soon as possible to be one of leaders in vital changes as follows:- Visit Manchester RO for advice on Partnership Register/Re-Affirmation of Vows/Baby Naming Ceremonies Decide whether to use Civil Ceremonies Ltd or set up independently Determine fees for these ceremonies Implement Partnership Register Implement Citizenship Ceremonies Implement Baby Naming Ceremonies Implement Renewal of Vows Ceremonies Determine provider of secular funerals Organise staffing Rota Outstation Registrars to provide more flexible service:- in hospital In Lift Centre Develop policy on approval of venues/commercial/private/one off marriages/outside venues including health and safety issues/list of celebrants etc Undertake Risk Assessment for LA failing to deliver successful implementation of review and develop Business Continuity Plan Organise on line records for viewing historic entries in registers in anticipation of registers being stored elsewhere Plan for storage of records maintaining public access Plan for IT requirements/internet/links with GRO/National Database/hospitals Confirm possibility of issuing ID Cards for extra revenue Plan for future auditing/accounting procedures for all services | Ongoing July 2004 July 2004 Jan – June 2005 Ongoing Ongoing July 2004 Ongoing August 2004 August 2004 July 2004 July 2004 July 2004 Dec 2005 July 2005 Sept 04 August 04 July 2005 Dec 04 March 06 May 04 | CA/RW CA/RW AE/AR/CA/RW AE AE CA/RW BVR Team/JK/AM RW AE/CA/RW CA/JK CA/JK CA/RW CA/JK CA/RW CA/RW/VP/JK CA/RW/VP/JK AE/AR/CA/RW CA/RW CA/VP/KL AE/CA/RW CA/RW CA/RW/AE CA/RW/AE/AR CA/RW/AE CA/RW/AE CA/RW/AE CA/RW/AE | First stage RRO anticipated July 2005 Second stage RRO anticipated Nov 05 Currently BVR Team – Determine who will manage change when BVR Review complete Preliminary plans in place to develop partnership with Approved Premises for promotion of wedding services In progress of financial analysis – future proposal report compiled detailing services planned to attract customers/revenue Alan Eastwood attending regular meetings with Proper Officers Achieved Achieved – set up independently. Partnership Ceremonies now available. Achieved Achieved Achieved In progress In progress In progress – AR in consultation with Bereavement Services Presence of Registrar in Hospital imminent. Accommodation/PC use identified In discussion with Paul McGeein for Doc Management/cost analysis In process of identifying accommodation for FHU Subject to RRO enactment |

CHALLENGE HOW NEW TECHNOLOGY CAN BE USED TO IMPROVE THE SERVICE

| ISSUE | ACTION | TIMESCALE | RESPONSIBLE PERSON | PROGRESS |
| --- | --- | --- | --- | --- |
| Ease of accessing services including:- On Line Appointments Applications and Registration Telephone application and Registration | Appointments made via call centre/ decide whether feasible to have on line appointments due to nature of business and questions asked at time of appointment Consider whether local offices can offer telephone and online registrations following RRO in line with GRO offering these services Action telephone/on line registrations if possible Applications to be accessible via internet as soon as credit card facilities set up Introduce on line application forms Applications via email – develop system whereby staff contact applicant requesting payment details once search for certificate completed Telephone applications to be implemented when credit card facilities have started Advertise in office and on website that credit card facilities now available | July 06 September 06 June 2007 July 2004 July 2004 | CA/RW/PS/JM CA/RW CA/RW/AE CA/RW/AM/LC CA/RW/AL/CW CA/RW/AM/LC RW/LC RW | Subject to RRO Enactment and Review period by GRO Jane Myers in process of actioning this Achieved Achieved Achieved |
| Integration within the CRM system | Appointments made by the Call Centre Consider whether payments and applications will still need to be directed to the Register Office or if the Call Centre can assist Consider the impact of the establishment of a National Call Centre with further details from GRO | Sept 04 July 04 | CA/RW CA/RW/AE/AR CA/RW/AE/AR | Achieved Further meetings with call centre to determine feasibility Draft report on implications for Salford in progress |
| Possible use of Document Management technology | Contact Paul McGeein to prioritise Doc Management for the RO Identify timescales Identify what exactly would be Doc Managed i.e. Registers/Indexes Prioritise this due to fact that Registers and Indexes must be moved from RO and stored as public records as soon as RRO passed Identify costs and determine budget | June 2004 June 2004 June 2004 June 2004 | AR/CA/RW AR CA/RW AR AR/AE | Initial meeting taken place – awaiting costs. Project code now been given to allow full analysis/costs by Paul McGeein |

PROGRAMME IN VISIONING, MID POINT AND OPTIONS CHALLENGE SESSIONS WITH INTERNAL CHALLENGE PANELS

| ISSUE | ACTION | TIMESCALE | RESPONSIBLE PERSON | PROGRESS |
| --- | --- | --- | --- | --- |
| Determine who is on challenge panels | Draft challenge panel for approval Draft Options/Final challenge panel | June 2004 | AR AR | Achieved Final Challenge set for 29/6/04 |
| Consider whether external challenge is necessary | Register office inspected with Service Wide Review Consider Proper Officer from Manchester Register Office to attend panel Consider local funeral director to attend panel | June 2004 June 2004 | AR/CA AR/CA | Achieved with findings implemented. Invitees include Bereavement Services/Funeral Director and HM Inspector |

### CONSULT

CONSULT WITH ALL STAKEHOLDERS; USERS OF THE SERVICE, STAFF AND PARTNERS

| ISSUE | ACTION | TIMESCALE | RESPONSIBLE PERSON | PROGRESS |
| --- | --- | --- | --- | --- |
| Survey of Users | Issue yearly survey to customers to complete whilst in office Wedding Surveys posted and returned in pre-paid envelopes 250 surveys issued – divided between all customers for births, deaths, marriages, certificate applications and family history Complete Analysis with Carolyn Haslam Feedback and procedures reviewed by staff |  | All staff All staff RW/CH All staff | Achieved Achieved Achieved – Action plan devised following results of surveys |
| Focus Group with Registrars | Set up independent Focus Group with staff Decide who will attend focus group Decide nature of focus group and what will be discussed Decide follow up action/liaison with management | June 2004 | AR/RT/RW RT/RW RT/RW CA/RW | Achieved Achieved Achieved In progress |
| Questionnaire to local hospitals, Muslim/Jewish Community, Approved Premises, Local Disabled Groups, Undertakers/Funeral Directors, Coroners, Local History Society and Public | Devise new yearly survey to include issues in vital changes i.e. telephone and internet registrations/opening hours/places of marriage civil and religious demand/commemorative certificates Consider questions to verify what users expect from the service provided, any plans other stakeholders have etc linked to RRO Issue new survey to all users including the public Analyse results and review feedback/results | September 04 September 04 September 04 Oct/Nov 04 | All staff All staff All staff All staff |  |
| Other council directorates – Social Services, NPHL, Bereavement Services, Elections, Revenues and Benefits | Consider links with Bereavement Services Consider working along side BS in one stop shops/hospitals/Lift Centres etc Consider Bereavement Services issuing info on Registration and assisting with Registration duties e.g. Secular funerals | June 2004 Dec 2005 Dec 2004 | All staff All staff All staff | Already established accommodation with Bereavement Services at Hope Hospital to allow death registrations there. |

### COMPETE

COMPETITION IS ANTICIPATED AS PART OF “..DELIVERING VITAL CHANGE” WITH REMOVAL OF RESTRICTIONS WHERE PEOPLE CAN MARRY

| ISSUE | ACTION | TIMESCALE | RESPONSIBLE PERSON | PROGRESS |
| --- | --- | --- | --- | --- |
| Determine a forward strategy for responding to the proposed changes including:- Draft Marketing Strategy (USP) Competitive scale of charges within constraints laid down by GRO Publicity brochures, enhanced websites, advertising provision/capacity to take business from outside Salford | Produce marketing strategy Consultation with staff at team meetings to develop a strategy for best way forward Determine Unique Selling Point e.g. do we include wedding rehearsals in price of wedding Consider legality of offering expanded wedding co-ordinator service Produce detailed business proposal examining projected expenditure & revenue generating opportunities Identify fees for weddings e.g. different fees for different days, times, seasonal, higher fee for 2 people attending etc Complete brochure of fees to be published on internet Enhance website e.g. include all wedding services offered, ceremonies, choice of words, extended music and poetry selection Promote Salford RO, and devise new brochure i.e. getting venues to advertise and pay for brochure Attend wedding fares to promote Salford and services offered | August 2004 June 2004 July 2004 August 2004 August 2004 Nov 2005 Mar 2006 August 2004 Sept 2004 Sept 2004 | RW/AM All staff CA/RW/All staff CA/RW/AE/AR RW/AR/AM CA/RW RW RW CA/JK All staff | Draft marketing strategy devised by Andrea Matthias Initial report drafted detailing costings/revenue generating opportunities including adverts, increased fees, partnership links with local businesses/Approved Premises and setting up of Family History Unit |
| Look at arrangements for banking etc. Consider if services would be reduced with debit/credit card facilities | Good service currently provided by Securicor at reasonable cost. Consider whether this should be changed Review after RRO – awaiting instructions for banking/accounting arrangements following changes to Registration. | Nov 2005 | CA CA/RW | Arrangements in place to review when contract to be renewed and new tenders invited Currently bank once a week with monetary limits set for each Registrar |

COMPARE

| ISSUE | ACTION | TIMESCALE | RESPONSIBLE PERSON | PROGRESS |
| --- | --- | --- | --- | --- |
| Complete benchmarking study and analyse results | Distribute questionnaire to 10 neighbouring Local Authorities Analyse results and compare services |  | CA AR/RT | Achieved Achieved – complete with recommendations |
| Compare standards and performance of the service with LGA Better Practice Guidance | Standards reviewed and action those which do not meet Better Practice standards (see LGA Better Practice Standards – page) Complete Better Practice questionnaire and compare with other Local Authorities | July 2004 | CA/RW RW | See LGA Better Practice Standards for areas to be actioned Completed – awaiting contact from North Yorks authority to compare results |
| Compare the costs of the service with other comparable authorities | Certain costs to be compared and analysed from Benchmarking information |  | AR/RT | Achieved - recommended not to increase fees for approved premises in next financial year |
| Compare income received with other comparable authorities | Review fees for Approved Premises as at present this is the only area which the Local Authority has any control over Compare fees for Approved Premises on benchmarking analysis Review/analyse notices and Registration Targets once RRO passed | March 2006 | CA/RW AR/RT CA/RW | Achieved – new fees set Achieved – see Benchmarking Report |
| Compare staffing establishment and structures | Compare staff in similar sized authorities from benchmarking information Consider structure changes following RRO Consider Family History Unit following RRO as staffing duties should change and allow staff more time to dedicate to this area | July 2005 July 2005 | AR/RT CA/RW CA/RW/SL/AE/AR | Achieved – see Benchmarking Report Initial proposals to be included in Marketing strategy/Business Proposal Report to include costs/feasibility/location etc |
| Compare training provision with other authorities and consider whether there is scope for shared training provision with others | Devise new Training Unit within Salford RO Devise computer system and record staff development and training Offer concise feedback to staff to allow maximum development Continue internal training in particular DSR duties with a view to vital changes coming into place Review training system and liaise with other offices for possibilities of shared training | Ongoing July 2005 | JK/LC/RW JK/LC/RW JK/LC All staff JK/RW | Achieved Achieved Achieved and on going Only one member of staff left to train as DSR |