SALFORD CITY COUNCIL

DEVELOPMENT PLANNING SERVICE

BEST VALUE REVIEW

# SERVICE IMPROVEMENT PLAN

April 2003

# AREAS FOR IMPROVEMENT

DP 1 - PROPOSED BEST VALUE PERFORMANCE INDICATOR ON PLAN MAKING – The Government is proposing to introduce a new Best Value Performance Indicator on plan making from April 2003 (BVPI 200). The current UDP was adopted in November 1995 and continues to form a robust basis for decision-making. However, the Development Planning Section is increasingly focusing its resources on reviewing the UDP to ensure an up-to-date policy framework that helps to meet the challenges facing the City.

# IMPROVEMENT TARGETS

| Indicator | Baseline 2001/02 | 02/03 to date | 03/04 | 04/05 | 05/06 | 06/07 |
| --- | --- | --- | --- | --- | --- | --- |
| a) Does the authority have a development plan (or alterations to it) that has been adopted in the last 5 years and the end date of which has not expired? | No | No | No | No | Yes | Yes |
| b) If ‘No’, are there proposals on deposit for an alteration or replacement, with a published timetable for adopting those alterations or the replacement plan within three years? | No | Yes | Yes | Yes | Yes | N/a |

# PERFORMANCE IMPROVEMENT PLAN

| Action Points | Actions Required | Timescale | Responsible Officer | Reason for Improvement | Resources |
| --- | --- | --- | --- | --- | --- |
| Short Term |  |  |  |  |  |
| DP 1.1 Undertake key technical work to support UDP at Inquiry stage. | Urban potential work Housing needs assessment Industrial areas assessment Other Directorates (Housing/C. Exec’s) to support. | Spring 2004 Autumn2003 Winter 2003 | G Gentry / J Reehill J Reehill /Housing D Evans /Chief Execs | A great deal of technical work will be required to support policy and deal with objections to policy at Inquiry. | Tenders to be sought UDP budget / staff time UDP and Housing Budgets / staff time UDP budget and SRB 5 |
| Medium Term |  |  |  |  |  |
| DP 1.2 The revised draft UDP is a key priority in the section’s work programme and has to be delivered to adoption by April 2006. | Direct resources from within the section and Directorate to ensure an adequate ongoing focus on UDP review work. | April 2003 – January 2006 | D Evans/ G Gentry | To ensure that adequate resources are focused on the UDP so that the BVPI can be met | Plans Group – 4 staff 75% time Topic Champions (x7 – time dependent on levels of representations) UDP Budget / Planning Delivery Grant – studies and Inquiry costs (incl legal and consultants fees) , publication costs etc £400,000 |
| Achieved/Ongoing |  |  |  |  |  |
| A1.1 Secure early corporate agreement on the approach to be taken in the UDP | A Core Group of Lead Members and Officers established to discuss strategy, issues and sites. | June 2002 |  | To ensure corporate agreement on key issues early in the process, to avoid losing time later on by having to revisiting them |  |
| A1.2 Ensure revised UDP informed by community views/plans. | Area Plans agreed through consultation with Community Committees and endorsed by Council. | February 2002 |  | Replacement UDP informed by community views. Also informs Neighbourhood Renewal Strategy. |  |
| A1.3 Ensure that the revised draft UDP provides a basis for translation to a Local Development Framework after the Planning Bill becomes an Act (Summer 2003). | Revised draft UDP :- - is rooted in the Community Plan. - Plan Strategy links appropriately to other corporate strategies and plans. Is succinct and does not replicate national or regional policy/guidance. Includes a statement of community involvement | November 2002 |  | To reflect government advice and to ensure plan can be rapidly translated into LDF arrangement April 2004, whilst keeping to April 2006 adoption target. |  |
| A1.4 Ensure that the process for producing the UDP is streamlined | Analyse the development plan regulations to ensure that all statutory processes are followed | November 2002 |  | To avoid the experience of some other local authorities of having to repeat stages of the process |  |
| A1.5 Revised UDP to the be placed on 1st deposit February 2003. | Plan placed on 1st Deposit on 17th February | February 2003 |  | Essential if 2006 adoption target is to be realised. |  |

# AREAS FOR IMPROVEMENT

DP 2 - BEST VALUE PERFORMANCE INDICATOR ON THE PERCENTAGE OF NEW HOMES BUILT ON PREVIOUSLY DEVELOPED LAND – The City Council already achieves top quartile performance on this indicator, but it will be important to ensure that actions are taken to ensure that this excellent performance is maintained.

# IMPROVEMENT TARGETS

| Indicator | Baseline 2001/02 | 02/03 to date | 03/04 | 04/05 | 05/06 | 06/07 |
| --- | --- | --- | --- | --- | --- | --- |
| Percentage of new homes built on previously developed land places the City in the top quartile (BVPI 106) & meets RPG requirement (minimum 90%) | top quartile (97%) | top quartile (minimum 90%) | top quartile (minimum 90%) | top quartile (minimum 90%) | top quartile (minimum 90%) | top quartile (minimum 90%) |

# PERFORMANCE IMPROVEMENT PLAN

| Action Points | Actions Required | Timescale | Responsible Officer | Reason for Improvement | Resources |
| --- | --- | --- | --- | --- | --- |
| Short Term |  |  |  |  |  |
| DP 2.1 Improve monitoring systems | Increase the frequency of data collection from annually to quarterly | Winter 2003 | J Reehill | To improve the information available to inform decision-making | Existing staff time (once new systems in place, no net additional staff time) |
| DP 2.2 Involvement in NWDA pilot to test and work through the concept of “Brownfield Land Management Action Plans” | Work with NWDA & partners on delivering the pilot project. | tba | C Findley | To work to ensure that re-use of brownfield land continues to be maximised. To ensure involvement in regional agenda setting and meeting Community Plan and UDP objectives | Existing staff time & external funding (NWDA) |
| DP 2.3 To actively bring forward brownfield sites for development. | identify and assemble brownfield sites proactively undertake site investigations | Ongoing Ongoing | P Baker/ M Arnold / B Whitmarsh P Baker/ N Lowther | To remove obstacles to bringing forward brownfield land in commercially marginal locations. | Existing and HMRF funded staff / HMRF capital / NWDA funding |
| Achieved |  |  |  |  |  |
| A2.1 Ensure an up-to-date policy framework that guides housing development to brownfield sites | Progress the review of the UDP, and ensure an emphasis on brownfield sites | February 2003 |  | To provide sufficient policy support to guide housing development to brownfield sites |  |

# AREAS FOR IMPROVEMENT

DP 3 - EFFECTIVE IMPLEMENTATION OF POLICIES, PLANS AND STRATEGIES – The Development Planning Section makes an important contribution to the development control process, and can help to ensure that it is both speedy and results in high quality development. Equally, it is important to ensure that the City Council’s planning policies continue to be successfully implemented through the development control process.

# IMPROVEMENT TARGETS

| Indicator | Baseline 2001/02 | 02/03 to date | 03/04 | 04/05 | 05/06 | 06/07 |
| --- | --- | --- | --- | --- | --- | --- |
| % of responses to the Development Control Section made within 10 working days | tba | tba | 80% | 85% | 85% | 90% |

# PERFORMANCE IMPROVEMENT PLAN

| Action Points | Actions Required | Timescale | Responsible Officer | Reason for Improvement | Resources |
| --- | --- | --- | --- | --- | --- |
| Short Term |  |  |  |  |  |
| DP 3.1 Ensure appropriate policy advice is given to applicants for planning permission in pre-application discussions. | Undertake a full assessment of the success of the Development Team Approach | Spring 2004 | G Gentry / T Mitchell | Ensures that the benefits of the approach are maximised. | Existing staff time |
| DP 3.2 Provide more written advice for prospective developers. Improve guidance given to applicants on policy requirements. | Prioritise SPG:- - Urban Open Space Strategy Open Space in housing developments - Student accommodation Broughton Park/Ellesmere Park Planning obligations MBB Canal Area Action Plans | Draft approved for consultation by Autumn 2003 Autumn 2003 Spring 2004 Spring 2006 Summer 2005 Autumn 2003 Ongoing | N Lowther N Lowther G Gentry G Gentry D Percival C Brereton G gentry | To increase the level of certainty for developers regarding policy and its implementation. | Existing staff time (provision within work programme) |
| DP 3.3 Ensure that planning policy continues to be relevant and up-to-date | Monitor the implementation of planning policy and strategy through the development control system. Establish regular liaison meetings with Development Control, and a feedback mechanism to tell us when policy is inadequate, difficult to implement, or hard to understand. | Winter 2003 | G Gentry & DJolley | Ensures that any problems with, or shortage of, planning policy can be identified and rectified. | Existing staff time |
| Achieved |  |  |  |  |  |
| A3.1 Improve the quality and speed of policy advice to Development Control | Commence weekly meetings within the Development Planning Section to discuss the weekly list of planning applications, focussing on major developments. Provide a single coordinated response to Development Control with a clear conclusion rather than individual officers commenting separately. Develop a checklist to ensure that responses include all relevant material. | June 2002 June 2002 June 2002 |  | Ensure that policy and regeneration issues are raised early in the decision-making process in order to improve the quality and speed of decision-making, and support performance on BVPI 109. Ensures that the policy interpretation is clear, ensuring that policy is properly implemented, leading to better and quicker outcomes. Ensures a comprehensive response, assisting in better quality decisions and outcomes. |  |
| A3.2 Improve the quality and quantity of policy advice in pre-application discussions with potential applicants for planning permission | Establish and contribute to a Development Team, to provide coordinated pre-application advice to developers and ensure that policy and regeneration issues are raised early on in the development control process. | January 2002 |  | Assist potential applicants by speeding up the process and providing clearer advice, and help to improve the quality of applications and therefore of outcomes. |  |
| A3.3 Monitor the implementation of planning policy and strategy through the development control system. | Monitor reports to the Planning and Transportation Regulatory Panel to determine how policy and regeneration are being taken into account during the decision-making process. Annual visit of the Panel to recent developments that they granted planning permission for | June 2002 (looking at reports from April 2002) November 2002 |  | Ensures that the policies, plans and strategies of the Development Planning Section are being effectively implemented, in order to secure high quality outcomes To ensure effective monitoring of development quality |  |

# AREAS FOR IMPROVEMENT

DP 4 - FOCUS ON WHAT MATTERS – The Development Planning section supports the Community Plan and the Neighbourhood Renewal Strategy through its leading role in securing the physical regeneration of the City. Corporate priorities impact significantly on the section’s work programme and have to be effectively managed and delivered.

# IMPROVEMENT TARGETS

| Indicator | Baseline 2001/02 | 02/03 to date | 03/04 | 04/05 | 05/06 | 06/07 |
| --- | --- | --- | --- | --- | --- | --- |
| Percentage of items identified in the Annual Service Plan that are: - Achieved - Substantially achieved - Partly achieved - Not achieved | 43% 0% 19% 38% | tba tba tba tba | 60% 10% 30% | 70% 10% 20% | 75% 10% 15% | 80% 10% 10% |

# PERFORMANCE IMPROVEMENT PLAN

| Action Points | Actions Required | Timescale | Responsible Officer | Reason for Improvement | Resources |
| --- | --- | --- | --- | --- | --- |
| Short Term |  |  |  |  |  |
| DP 4.1 Community Plan Living Environment Forum to be developed as a Strategic Development Partnership. | Section will facilitate the Forum, with Housing and Environmental Services. Other partners may be required to service/develop the forum. | Summer 2003 | C Findley | This will help identify stakeholder / partner priorities & therefore help coordinate work priorities.. | Existing (provision within work programme) |
| DP 4.2 Prepare Derelict Land Strategy | Develop a derelict land strategy for Salford, which sits within the context of regional/sub-regional strategies and programmes, and connects to Salford’s own Neighbourhood Renewal Strategy. | Spring 2004 | A Partington | A number of strategies and programmes are emerging at regional and sub-regional level, which must be integrated with Salford’s own approach. | Existing (provision within work programme) |
| DP 4.3 Improve mechanisms for coordination of work with Chief Executives Economic Development Service | Establish liaison structures and monitoring process. Investigate EDU joining the Development Team approach for pre application consultations on major development proposals | Autumn 2003 Summer 2003 | D Evans / S Kitchen (Chief Execs) G Gentry / P Mahoney (Building Control / S Kitchen (Chief Execs) | Changes in staff have weakened the informal joint working arrangements. To ensure effective co-ordination and improve customer service | Existing (provision within work programme) Existing staff time |
| Medium Term |  |  |  |  |  |
| DP 4.4 Integrate LA 21 into the Community Plan | Section will facilitate discussion with other directorates & partners to establish mechanisms for integration of LA 21 into the Community Plan at next review | Community Plan review (2005/6) | C Findley / T Jones (Chief Execs) | Efficiency & effectiveness, rationalisation of strategies in line with latest advice from ODPM. Explicit linkage of regeneration & sustainability through the Community Plan | Existing (rationalisation) |
| Ongoing |  |  |  |  |  |
| DP 4.5 Ensure adequate staffing levels to deliver agreed work programme. | Monitor staffing needs in line with agreed work programme. Ensure speedy filling of posts which become vacant. | Ongoing | D Evans / C Findley | To ensure ability to deliver agreed work programme | Existing |
| Achieved |  |  |  |  |  |
| A4.1 Secure adequate staffing resources to meet work requirements | 5 vacant posts filled in the last year Service provided has to align to budget available – progress in key areas now being made, although difficulties still exist (4.5 posts still vacant) | October 2002 |  | Within the Directorate’s cnstrained budget, priority has been given to filling some key planning posts after a period of considerable difficulty. However, budget pressures continue to constrain the ability to support all the City Council’s priorities. |  |
| A4.2 Identify need for planning resource to support HMRF programme | Resource identified, job description/person specs now prepared | February 2003 |  | Extent of potential land use change means planning input to Manchester / Salford HMRF will be essential. Cannot undertake within existing capacity. |  |
| A4.3 Identify partners for Community Plan Living Environment Forum | Initial partnership of Living Environment Forum identified. | February 2003 |  | Forum one of seven underpinning Community Plan and LSP. |  |

# AREAS FOR IMPROVEMENT

| DP 5 - PERFORMANCE MANAGEMENT – Improving the Development Planning Section’s performance management systems. |  |
| --- | --- |

# IMPROVEMENT TARGETS

| Indicator | Baseline 2001/02 | 02/03 to date | 03/04 | 04/05 | 05/06 | 06/07 |
| --- | --- | --- | --- | --- | --- | --- |
| Production of an approved annual work programme | No | No | Yes | Yes | Yes | Yes |
| Percentage of items identified in the Annual Service Plan that are: - Achieved - Substantially achieved - Partly achieved - Not achieved | 43% 0% 19% 38% | tba tba tba tba | 60% 10% 30% | 70% 10% 20% | 75% 10% 15% | 80% 10% 10% |
| Percentage of annual / quarterly work programme targets achieved | tba | tba | 75% | 80% | 85% | 90% |

# PERFORMANCE IMPROVEMENT PLAN

| Action Points | Actions Required | Timescale | Responsible Officer | Reason for Improvement | Resources |
| --- | --- | --- | --- | --- | --- |
| Short Term |  |  |  |  |  |
| DP 5.1 Develop a clear and deliverable work programme for the Development Planning Section. | Identify and introduce a mechanism for identifying and focussing on priorities and developing the section’s work programme, to be updated quarterly and reviewed annually, with reports to Lead Member. Produce a prioritised work programme for the section. Produce work programmes for individual members of staff. | Spring 2003 Spring 2003 Summer2004 | D Evans D Evans D Evans / G Gentry / N Lowther / P Baker | Ensure that the section concentrates on delivering its priorities Resource directed to achieve council ambitions Better day to day management | Existing staff time Existing staff time Existing staff time |
| DP 5.2 Improve the management of requests for new work | Establish a commissioning unit to manage requests for new work Briefs to be required for key pieces of work, which set clear targets / outputs Develop skills of estimating time required to undertake work. | Spring 2003 Spring 2003 Ongoing | C Findley / D Evans D Evans All | Ensure that the section concentrates on delivering its priorities. Better day to day management To ensure that there are clear targets for staff Better day to day management | Existing staff time Existing staff time Existing staff time |
| DP 5.3 Ensure that the key priorities and proposed work outcomes of the section accurately reflects the Directorate’s Annual Service Plan | Link Service Plan and Work Programming | Annually | D Evans / P Mallinder | To maintain strategic focus in work priorities | Existing staff time |
| DP 5.4 Undertake process mapping for key work | Process map the UDP post 1st Deposit | Summer 2003 | G Gentry | To ensure clear programme targets set and achieved to meet BVPI | Staff time |
| DP 5.5 Streamline monitoring of performance indicators | Identify and agree changes to the planning application form, DC reports & alterations in building control data recording required in order to speed up data collection. | Summer 2003 | J Reehill / D Jolley | Essential to measuring performance in key areas. | Existing staff time |
| DP 5.6 Secure improvements to the way in which consultants are used | Produce a protocol on the use of consultants. | Spring 2004 | D Percival | To ensure that output from the use of consultants is optimised. Production of a protocol will assist in ensuring consultants are used appropriately and effective. | Existing staff time |
| DP 5.7 Learn from Best Practice from around the country | Set up mechanism for identifying best practice from elsewhere and for ensuring that this can be used to drive further improvement. | Winter 2003 | D Percival | To ensure that staff can learn from relevant sources of experience. | Staff time |
| DP 5.8 Improve the induction of new staff | Improve starters’ pack, including information on community strategy, equal opportunities policies, Council structures & decision making procedures, key contacts, charges, H&S responsibilities, etc | Autumn 2003 | P Mallinder / D Evans | To ensure that staff are fully equipped to deliver the agreed work programme | Staff time and limited revenue costs (reproduction costs etc) |
| DP 5,9 Develop a standard approach to project management | Trial a new “project management and monitoring” approach for all significant projects Review this approach | Summer 2004 Spring 2005 | D Percival D Evans / D Percival | Integrate monitoring arrangements into working networks. | Staff time Staff time |
| DP 5.10 Implement benchmarking with family authorities | Commence collection of the data for Sandwell Benchmarking Group indicators Identify any changes required in order to speed up data collection, such as modifications to the planning application form and DC reports, alterations in building control record keeping | Spring 2003 Autumn 2003 | J Reehill / D Percival D Jolley / J Reehill / D Percival | Essential to measuring performance in key areas. | Existing staff time |
| Ongoing |  |  |  |  |  |
| DP 5.11 Seek to establish a Directorate strategic partnership | Contribute to Directorate initiative to create a strategic partnership with a private sector partner, | Summer 2004 | D Evans | To develop a strategic partnership to aid the continuous improvement of service | Staff time |
| DP 5.12 Continue to develop time recording system | Develop time recording system in conjunction with work scheduling | Summer 2004 | D Evans / G Gentry / N Lowther / P Baker | To ensure that an effective system of time recoding linked to work scheduling is developed as a management tool | Staff time |
| DP 5.13 Develop the performance culture within the section. | Focus staff on key work programme priorities through regular updates / briefings and through the annual appraisal process etc. | ongoing | D Evans / G Gentry / N Lowther / P Baker | To maintain staff focus on priorities | Existing staff time |
| Achieved |  |  |  |  |  |
| A5.1 Introduce a time-recording system | Time-recording system | September 2002 |  | Help to manage workloads and develop work scheduling / costing skills. |  |
| A5.2 Raise skill level in IT applications | Make European Computer Driving Licence Programme available to staff. | April 2002 |  | Appraisals identified a wide spread concern at inadequate IT skills. European Computer Driving Licence Programme implemented. |  |
| A5.3 Staff appraisals system | Implement annual programme. Review process to maintain relevance. | 2000 ongoing |  | Adopt good management practice Ensure that the system remains fit for purpose |  |

# AREAS FOR IMPROVEMENT

DP 6 - CUSTOMER CARE – Ensure a high level of customer care, in particular relating to the accessibility of the service.

# IMPROVEMENT TARGETS

| Indicator | Baseline 2001/02 | 02/03 to date | 03/04 | 04/05 | 05/06 | 06/07 |
| --- | --- | --- | --- | --- | --- | --- |
| Percentage of external customers who are dissatisfied with the availability of officers | - | 17% | - | 10% | - | 10% |
| Percentage of Councillors who are dissatisfied with the speed of responding to enquiries | - | 42% | - | 10% | - | 10% |
| Percentage of internal customers who are dissatisfied with the availability of officers and (or?) the speed of responding to enquiries | - | 15% | - | 10% | - | 10% |
| % of written correspondence (including e-mails) which is replied to within 5 working days | - | - | 90% | 90% | 95% | 95% |
| Percentage of new published documents produced by the Development Planning Section that are available on the internet | tba | 75% | 85% | 100% | 100% | 100% |

# PERFORMANCE IMPROVEMENT PLAN

| Action Points | Actions Required | Timescale | Responsible Officer | Reason for Improvement | Resources |
| --- | --- | --- | --- | --- | --- |
| Short Term |  |  |  |  |  |
| DP 6.1 Provide written information on the service | Produce an information leaflet setting out what the Development Planning Section does and who does what, and including service standard. | Autumn 2003 | D Evans | Provide clarity to customers. | Staff time and c £500 printing costs |
| DP 6.2 Improve cover arrangements in office. | Group Leaders to continue to ensure office cover during opening hours explore providing late night cover on Thursdays Produce protocol Consult with staff and unison Staff rota Commence cover | Ongoing Spring 2003 Summer 2003 | G Gentry / N Lowther / P Baker D Evans D Evans | No systematic approach to ensuring officer availability during office hours at present. Support to DC colleagues and improved customer service improved customer service | Existing staff resources (change in work patterns) Existing staff resources (change in work patterns) Existing staff resources (change in work patterns) |
| DP 6.3 Ensure that those speaking/reading languages other than English are able to access the service | Incorporation of text in different languages in main documents and publicity leaflets indicating where language assistance can be found (eg via Language Line, Salford Link) | Spring 2003 | G Gentry / N Lowther / P Baker | Need to ensure open and transparent service for all customers. | Additional revenue costs in securing translation costs. Total will vary according to volume of material published. |
| Ongoing |  |  |  |  |  |
| DP 6.4 Develop strategy for improving feedback from customers. | Customer surveys Focus group | April 2004 | D Percival | To maintain a consistent process of customer consultation/feedback. | Existing staff time and limited revenue costs (reproduction / postage / venue costs etc) |
| DP 6.5 Ensure that service is accessible electronically | Place copies of all major publications on the Council’s website | ongoing | G Gentry / N Lowther / P Baker | To maximise access to the service electronically – in accordance with government advice | Existing staff time |
| Achieved |  |  |  |  |  |
| A6.1 Provide information on the service on the Council’s web-site. | Develop a dedicated Development Planning Section of the City Council’s web site, explaining the service, incorporating the following: Basic information about the service; First Deposit Draft Review UDP; Adopted UDP; | Feb 2003 Feb 2003 Feb 2003 |  | Little information presently available. E-enabled information will improve customer service generally and accessibility to service information in particular | Existing staff time |
| A6.2 Area Plans – consultation approach. | Using Planning Aid to facilitate Community Committee sessions – generally welcomed outcome, feeds into UDP review. | 2002 |  | To ensure community engagement in plan making process |  |