Bolton Salford and Trafford Mental Health NHS Trust

Salford Directorate

Consultation Action Plan

Updated 19th September 2006

PROPOSALS FOR THE MODERNISATION AND RE-DESIGN OFIN-PATIENT SERVICES AND SUPPORTED HOUSING WITHIN OLDER PEOPLE SERVICES

KEY THEMES & ACTIONS ARISING FROM THE CONSULTATION PROCESS AND ACTIONS TAKING PLACE TO ADDRESS ISSUES

The Department of Psychiatry for Later Life provides mental health services for older people in Salford. The service has recently undertaken a period of formal consultation for Phase 1 of the redesign of inpatient services and extending the number of tenancies in the supported housing scheme.

During the consultation process a range of comments have been received from a variety of sources, i.e. written formats, notes of formal meetings, informal discussions held with staff and interested parties generally.  From the responses received there have not been explicit concerns expressed about the proposed service models.

Objectives identified from the consultation include:

- Whole systems model of services for older people being established in Salford

- Understanding local needs and supply of bed resources for older people with mental health problems, ensuring that there are a sufficient number of beds available locally, in the short, medium and long term

- Financial Planning/Use of Financial Resources

- Sharing risks in the event of the proposed service changes

- Ward Environments

- Workforce Planning/Skill Mix/Roles of Staff

- User/Carer involvement and Support / PPI Forum

Penny Evans	Interim Director Salford Mental Health and Social Care

Lyn Jones	Assistant Director Later Life Services

Mary Lee	Business and Development Manager

Tom McDonald	Deputy Director/Director of Joint Commissioning Salford PCT

Simon Large 	Interim Chief Executive

Julia Clark	Assistant Director Community Health and Social Care

Andrew  O Shaunessy	Consultant Public Health

Ann Loutitt	Project Manager of Later Life Mental Health Services

Steve Dixon 	Deputy Director of Finance, Salford PCT

Andy McDermott	Assistant Director, Trafford

Lynn Dormer	Assistant Director, Bolton

Steve Smith	General Manager - Salford Royal Hospitals

###### Malcolm Courtney	Capital Projects Manager - BSTMHT

Garry Pomfret	CPA Lead – Later Life Services

Tony Ridding	Community Psychiatric Nurse, BSTMHT

Mary Lee	Business Manager, BSTMHT

Objective 1

Whole systems model of services for older people being established in Salford

Intended Outcomes

- Whole systems model to be developed and agreed, to include specifics such as Community Mental Health Teams, Day Services, Mental Health support to Intermediate Care, General Hospital Liaison.

|  | Actions Required | Target Date | Accountability | Information |
| --- | --- | --- | --- | --- |
| 1.1 | Appointment of a specific Project Manager | Completed 28th July 2006 | Salford PCT | Manager appointed to co-ordinate and steer whole systems development |
| 1.2 | Project Steering Group established | Completed 30th September 2005 | Tom Mc Donald (chair) | Group to provide an over-arching framework to achieve actions required for the development of integrated mental health services for older people. The membership includes representatives from statutory, voluntary and user/ carer forums. |
| 1.3 | Work continues to progress locally with partner agencies re specific service models such as Community Mental Health Teams Day Services - Intermediate Care - Hospital liaison | 25th August 2006 Not completed 29th September 2006 | Ann Loutitt Julia Clark Lyn Jones Mary Lee | A consultation paper to be completed with costings outlining proposals for new service models for discussion/ratification by BSTMHT, PCT, and Community Health and Social Care Services, to be presented as a joint consultation document. |

Objective 2

Understanding local needs and supply of bed resources for older people with mental health problems, ensuring that there are a sufficient number of beds available locally, in the short, medium and long term

###### Intended Outcome

- Short, medium, long term planning in respect of needs analysis/supply of resources needs to be completed by all partners.

|  | Actions Required | Target Date | Accountability | Information |
| --- | --- | --- | --- | --- |
| 2.1 | Internal work within the Trust on bed availability, usage, demands for beds, forecasting work and trends | 27th October 2006 | Mary Lee | Detailed work is underway to determine needs and capacity for inpatient services using a Statistical Process Control system. This data will then be used to inform bed management and operational procedures. |
| 2.2 | Analysis of need/trends by Lake & Lacey. | Completed 25th March 2005 |  | The Lake and Lacey review indicated in March 2005 that there appeared to be an over-reliance on longer stay capacity within inpatient services, compared with comparable localities. In addition, the report indicated that there has to be additional developments within community based services to provide alternatives to inpatient care. |
| 2.3 | Further work to develop long term planning for community based resources, which will provide alternative models of care. | 25th August 2006 | Andrew O Shaunessy | Collection of data including morbidity, age profile across the city, resources currently available to support older people with mental health problems eg; EMI homes, nursing homes, extra care sheltered housing. This information will inform the allocation of available resources for community mental health teams and day services |
| 2.4 | Community Health and Social Care to continue with the analysis of the requirements for residential and nursing home beds, to inform long term planning. | 29th September 2006 | Julia Clark | A process of data analysis has commenced within the local authority to inform future requirements for respite and intermediate care beds across the city. |

Objective 3

Financial Planning/Use of Financial Resources

Intended outcome

- Develop and agree resources to support the model for Older People in Salford

- Partner agencies to ensure transparent financial processes are in place

|  | Actions Required | Target Date | Accountability | Information |
| --- | --- | --- | --- | --- |
| 3.1 | Agreement has been reached between Bolton, Salford and Trafford Mental Health Trust and the Local Authority to provide transparency for financial planning as part of finalising a whole systems model | Completed 28th July 2006 | Simon Large Tom McDonald | A meeting has taken place and agreement reached for joint financial planning. Salford City to provide delivery of financial profile for White Meadows – To establish what resources will be available to re-invest into new model of service. |
| 3.2 | Once there is agreement about the whole systems model, the trust will release the £140k to support developments in alleviating potential bed capacity issues | Completed 28th July 2006 | Lyn Jones Julia Clark | Monies have been made available, and a plan for the use of these monies has been agreed. However, put on hold until the financial details of new service model are agreed |

Objective 4

Sharing risks in the event of the proposed service changes

###### Intended Outcomes

- Clear Bed Management Policy needs to be in place to promote consistent and active management of in-patient bed resources

- Protocols in respect of Risk Management and Transfer of Care need to be established between partner agencies

|  | Actions Required | Target date | Accountability | Information |
| --- | --- | --- | --- | --- |
| 4.1 | Review of current care pathways and bed management processes and the development of operational procedures to support the inpatient models. | 29th September 2006 | Lyn Jones | Work continues with the development of operational procedure guidelines for inpatient services. This work is being developed jointly with the local authority, user and carers. This work is on target. |
| 4.2 | Provide an up to date view of current bed usage and capacity | Completed 30th June 2006. | Lyn Jones Mary Lee | Initial work completed. |
| 4.3 | To provide evidence of any additional home support packages/residential/nursing placements required in the immediate short, medium and long term as a result of the potential service changes | 29th September 2006 | Julia Clark, | Work has commenced across the city to identify current requirements as a baseline for requests for future provision. |
| 4.4 | To develop a risk sharing protocol between partner agencies specifically in the areas of both potential external and specialist placements. | 29th September 2006 | Lyn Jones Julia Clark Mary Lee Steve Dixon Salford Service Director | Salford Service Director to arrange a series of meetings with relevant personnel to develop and agree a risk sharing protocol. |
| 4.5 | To ensure effective use of later life in-patient bed resources across the district services. | 29th September 2006 | Lyn Jones Andy McDermott Lynn Dormer | To develop a bed management protocol for Later Life Services across ¦Bolton, Salford and Trafford to ensure effective use of bed resources across the Trust. Work has commenced. On target. |
| 4.6 | Establish Transfer of Care Protocol between the local Hospital Acute Trust and the Mental Health Trust | 29th September 2006 | Lyn Jones Steve Smith Penny Evans | A meeting to agree a protocol has been arranged for 4th August 2006. |
| 4.7 | Review existing protocols/processes in respect of partner agency support to in-patient services within older people, to include, use of Care Programme Approach and clarity of responsibilities. | Review completed 25th August 2006 | Lyn Jones Garry Pomfret (CPA Lead) | Later Life Service CPA forum which includes Social Workers from East and West Patch Teams continues to ensure compliance with the revised CPA Policy. Further work on clarity of roles has been incorporated into re-design work. |
| 4.8 | Profiling and understanding the needs of patients in the Acute Hospital setting with complex needs, i.e. both physical and mental ill health. | 27th October 2006 | Tony Ridding Andrew O’Shaunessy | Work programme agreed and staff released from BSTMHT to undertake this work. Analysis to be completed by Andrew O’Shaunessy. BST have had one meeting with SRH. Chasing up and awaiting dates from SRH to progress work. |
| 4.9 | Bed management Policy in place locally, within Older People’s Services. | 29th September 2006 | Lyn Jones & Matrons | Bed management policy to be evaluated September 2006 to ensure it supports effective use bed resources within the service. On target. |

Objective 5

Ward Environments

Intended Outcome

- Current ward environments require some additional capital investment and environmental changes to support the revised service

|  | Actions Required | Target date | Accountability | Information |
| --- | --- | --- | --- | --- |
| 5.1 | Engagement work with external agencies, patients, carers and staff in the refurbishment process | Completed 28th July 2006 | Lyn Jones Malcolm Courtney | Project design team engaged to work with staff patients and carers to agree a programme of work for refurbishment to inpatient areas and supported tenancies. Work ongoing to achieve refurbishment programme. |
| 5.2 | Capital Investment – Within the consultation paper the Trust has clearly identified capital funding to support agreed changes to the physical environment. i.e. £350k agreed by BST Trust board meeting, to be made available during 06/07, to support the future programme of capital works | 2006/07 | Lyn Jones Mary Lee | Detail plans are being prepared for a capital programme of work and a schedule is being agreed. BSTMHT to engage contractors to action work schedule to commence September 2006. Areas identified for improvement are; Armitage Ward – Woodlands Ellesmere Ward – Meadowbrook Claremont Ward – Meadowbrook Supported Tenancies On target |

Objective 6

Workforce Planning/Skill Mix/Roles of Staff

###### Intended Outcome

- Changes to workforce/skill mix in the revised specific service areas

|  | Actions Required | Target Date | Accountability | Information |
| --- | --- | --- | --- | --- |
| 6.1 | Workforce plan for Inpatient Later Life Service to be identified to support the redesign Workforce plan for community and day services redesign to be developed. | Completed 28th July 2006 29th September 2006 | Lyn Jones Mary Lee Lyn Jones Julia Clarke Mary Lee | Stage 1 completed and budgets allocated to support inpatient redesign. Stage 2 work underway with Community Health and Social Care to develop workforce plan for CMHT’s and Day Services. On target. |
| 6.2 | Work has been completed on patient profiling across the service identifying the care needs of the in-patient population | Completed 30th June 2006 | Lyn Jones Lesley Jones | Information from this piece of work is being used to inform operational procedures, workforce planning and training. |
| 6.3 | HR Strategy being developed locally, taking into account specific changes to service delivery areas | Completed 28th July 2006 | Lyn Jones Kathryn Davies | Work has commenced and an HR strategy has been agreed to address employment and personnel issues in support of the new service models. Aspiration interviews for staff to commence September 2006. HR Strategy being implemented. |

Objective 7

User/Carer involvement and Support / PPI Forum

Intended Outcome

- Active engagement of service users and carers throughout the redesign process

|  | Action required | Target Date | Accountability | Information |
| --- | --- | --- | --- | --- |
| 7.1 | PPI feedback relating to extending the consultation process and providing an executive summary of the consultation proposals | Completed 30th June 2006 |  | Consultation period extended to 11 weeks |
| 7.2 | Potential service changes/proposals for modernisation /redesign are consistently processed via the existing Partnership Boards locally, development groups and PPI/ User/Carer Forums | Phase 1 Consultation 3rd April 2006 to 19th June 2006 | Service Director Lyn Jones | Phase 1 Inpatient Re-Design |
| 7.3 | Potential service changes/proposals for modernisation /redesign are consistently processed via the existing Partnership Boards locally, development groups and PPI/ User/Carer Forums | Phase II Consultation 25th September 2006 to 22nd December 2006 | Service Director Lyn Jones | Phase 2 Community & Day Services Re-Design |
| 7.4 | Establishment of work groups to support elements of the redesign include service user and carer representatives. | Completed 28th July 2006 | Lyn Jones | Through Reach Beyond (service user carer initiative) users, carers and volunteers are already established within the service, advising participating and influencing a number of service initiatives. - compliant |