# Best Value in Salford

Review of Services to Disabled Adults and

People in Need of Sensory Services

June 2005

Improvement Plan

## 1.	BASELINE INFORMATION

1.1	Performance Assessment Framework Performance Indicators, which can be attributed to Physical and Sensory Services

| INDICATOR | 2002/3 BASELINE | 2003/4 PERFORMANCE | 2004/5 PERFORMANCE | 2005/6 TARGET | 2006/7 TARGET |
| --- | --- | --- | --- | --- | --- |
| Theme: Access |  |  |  |  |  |
| D55 | Acceptable waiting times for assessment | Not Applicable | 75 | 87.00 | 90 | 91 |
| (The percentage of assessments completed within 28 days from first contact) |  |  |  |  |  |
| Performance Rating | N/A | 4 (next to highest banding | 5 (estimated, highest banding) |  |  |
| D56 | Acceptable waiting times for care packages | Not Applicable | 76 | 85.40 | 88 | 89 |
| (The percentage of packages of care with all elements in place within 4 weeks of the date of the completion of the assessment) |  |  |  |  |  |
| Performance Rating | N/A | 4 (next to highest banding | 5 (estimated, highest banding) |  |  |

| INDICATOR | 2002/3 BASELINE | 2003/4 PERFORMANCE | 2004/5 PERFORMANCE | 2005/6 TARGET | 2006/7 TARGET |
| --- | --- | --- | --- | --- | --- |
| Theme: Individual Care |  |  |  |  |  |
| B11 | Intensive home care as a percentage of intensive home care and residential care | 36 | 36 | 33.70 | 33 | 33 |
| (The number of households receiving intensive home care as a percentage of all adults and older people in residential and nursing care and households receiving intensive home care) |  |  |  |  |  |
| Performance Rating | 5 (highest banding) | 5 (highest banding | 5 (estimated, highest banding) |  |  |
| C27 | Admissions of Supported Residents aged 18-64 to residential/ nursing care Note: a lower rate is the best performance | 3.13 | 1.3 | 2.09 | 2 | 2 |
| (per 10,000 population aged 18-64) |  |  |  |  |  |
| Performance Rating | 4 (next to highest banding | 3 (average banding) | 5 (estimated, highest banding) |  |  |
| C28 | Intensive Home Care | 26.1 | 25.21 | 23.80 | 23 | 24 |
| (The number of households receiving intensive home care per 1,000 population aged 65 or over) |  |  |  |  |  |
| Performance Rating | 5 (highest banding) | 5 (highest banding | 5 (estimated, highest banding) |  |  |

| C29 | Adults with Physical Disability Helped to Live at Home | 3.52 | 4.2 | 11.93 | 11 | 11 |
| --- | --- | --- | --- | --- | --- | --- |
| (The percentage of adults with physical disabilities helped to live at home per 1,000 population aged 18-64) |  |  |  |  |  |
| Performance Rating | 3 (average banding) | 3 (average banding) | 5 (estimated, highest banding) |  |  |
| C51 | Direct Payments | 27.62 (= 46 people) | 38.36 (= 64 people) | 68.01 (= 114 people) | 95 (= 160 people) | 109 (= 184 people) |
| (Adults and older people receiving direct payments at 31 March per 100,000 population aged 18 or over) |  |  |  |  |  |
| Performance Rating | 2 (next to lowest banding) | 3 (average banding) | 3 (average banding) |  |  |
| The number of people with physical/sensory impairments on direct payments was | 30 | 43 | 83 |  |  |
| D41 | Delayed hospital discharge/transfers of care | 34 | 30 | 15.32 | 14 | 12 |
| (The number of delayed transfers of care per 1000,000 population aged 65 or over) |  |  |  |  |  |
| Performance Rating | 4 (next to highest banding | 4 (next to highest banding | 5 (estimated, highest banding) |  |  |
| D54 | Percentage of equipment and adaptations delivered within 7 days | 97 * | 87.7 | 91.28 | 94 | 95 |
| (The percentage of items of equipment and adaptations delivered within 7 days) |  |  |  |  |  |
| Performance Rating | 5 (highest banding) | 5 (highest banding) | 5 (estimated, highest banding) |  |  |

Notes:

1.  	* this performance figure relates to the previous indicator definition of equipment costing less than £1,000 delivered within 3 	weeks of assessment

## 2.	IMPROVEMENT PLAN

## 2.1	Achievements since the start of the Best Value Review April 2004

| THEME / Issue | Action | Reason for Action | Date |
| --- | --- | --- | --- |
| ACCESS |  |  |  |
| Access to information on local resources. | Develop web based information system ‘Ask SID’ Initially developed for older people’s service this will form the basis of a user data base of services. Information officer post funded through Performance Grant (£16k) | Access to information is the number one priority for users. Information enables empowerment. | June 04 |
| Widen access to day opportunities | A new ‘Enablement’ service based In-House, to deliver short term focused work, linking users to mainstream services. Due to start April 2005 – Delayed due to CRB checks. Funded via the Access Grant. (£60k) | The underlying view from the “promoting independence “ events was that many people did not know what else was available other than the traditional day opportunities. Those who were aware of some of the possibilities felt that, different ways of providing day opportunities should be promoted to enable choice but also enable gradual change. | April 2005 |
| Timely Access to services. | Equipment Services extended to 6 day week same day delivery for urgent needs. Funded Access Grant (£ 22k) Improved waiting times for assessment: Community Occupational Therapy Social work service Additional posts – Access Grant (£45k) The Physical Disability team have reviewed their duty systems to ensure a more effective use. This will enable people the option of self assessment or assessment at the office plus clearer information on what the team can offer. | Right Care, Right Time, Right Place. | Sept 2004 March 2005 |
| Access to meaningful data on service use | Data cleansing exercise for Best Value review provides a robust baseline for data collection. This has included increasing staff awareness on the importance of gathering and inputting the correct information. | Service Planning and performance monitoring | March 2005 |
| INDIVIDUAL CARE |  |  |  |
| Individuals to have more control over their care plan. | Increase uptake of Direct Payments – through funding Voluntary Sector support project. (Access grant £64.5k) Numbers already increased from 2002/3 baseline but this will be a continued focus | Promoting independence: Government agenda. | April 05 |
| Home Care: Commission on quality not just who can do the job quickly | Independent Homecare Commissioning is being restructured to geographical basis commencing June 2005. (Currently 30 providers across city.) | This was raised particularly in relation to home care services; many people raised the huge variation, which exists in localities. Service users felt the promotion of commonly agreed standards and the training of providers by commissioners would enable expectation of what constitutes “Quality” to be more universal | June 2005 |
| Housing Adaptations – reduce waiting times and bureaucratic process. | Partnership Board has directed services to review processes and contracting arrangements: for private and public sector. Recommended list of contractors Process for stair lifts and hoists | Long waiting times leading to complaints. | Feb05 – to continue to Sept 05 |
|  | Special Needs Housing Team moved from NPHL to the Joint Equipment Services at Burrows House | To create more seamless service / single access point | Dec 04 |
| Equipment tailored to individual care needs. | Integrated Community Therapy and Equipment Service under Health Act Flexibilities formed with pooled budget. Community Assessment Officer to Review need for equipment. Access Grant (£30k) Sensory Equipment to be administered through central equipment service. Develop Assisted Technology options: SMART House opens May 2005 to pilot Assistive Technology (joint with NPHL) Sub group formed to prepare bid for grant 06/07 | Promote Independent Living | April 2004 May 2004 Dec 2004 May 2005 |
| Robust Hospital Discharge arrangements | Project Officer (4months) to work with SRHT/CSSD/PCT to develop protocols – starts April 2005. (funded from delayed discharge grant £7k)) Through Partnership Board – audit of discharge arrangements at Hope Hospital to be completed. | To ensure safe discharges and seamless transition back to community. | April 2005 Sept 2005 |
| Develop joint Audiology Services | Project Officer 3 years – funded through TOPPS (£160k) to develop joint service approach. | Seamless services | April 2005 |
| Support to and assessment of Carers. | Carers assessment social worker appointed. Funded from Carers grant (£30k) | Carers play a key role in supporting disabled people and need support themselves | Dec 2004 |
| CITIIZENSHIP |  |  |  |
| Physically disabled people and those in need of sensory services to have the same recognition as other users groups. | Creation of Partnership Board to take forward strategic Director and performance monitoring of services. | Partnership working. | September 2004 |

## 2.2	Detailed Improvement Plan what needs to be done over the next three years

| THEME | ACTION | TIMESCALE | RESPONSIBLE OFFICER | REASON FOR IMPROVEMENT | RESOURCES |
| --- | --- | --- | --- | --- | --- |
| ACCESS |
| Access to information | Develop Information / Communications Strategy : building on SID Review and improve Web based information provision | By Dec 06 | Deputy Director - Via new Communication officer post | Top access priority from user perspective identified in consultation. Best practice comparison shows scope for development. | PO4 New post needed – communication office |
|  | Develop links with the Call Centre and City’s Think Customer | By Dec 06 | Communication Officer (new post) |  | PO4 See above |
| Increased promotion of available services | Promote /market service through Salford publications | Start April 06 | Communications officer | Best practice comparison and consultation results. | PO4 See above |
|  | Ensure staff in Local Authority and NHS have access to database - SID | July 05 – LA July 06 - NHS | PM –IT services Communication officer | To ensure delivery of this and the first priority – access to information | Existing resources PO4 See above |
|  | Improve information re access to financial advice under Community Legal Services | By Dec 06 | Communication Officer | Best practice comparison and consultation results. | PO4 See above |
| Develop Single Point of Contact | Bring together disability services around single access point at Burrows House . | By April 2006 | AD – adults AD - resources | To deliver streamlined services | Accommodation for non-disability staff currently at Burrows House |
| Access to day opportunities | Work with Leisure, Education to improve access to mainstream services. Develop access to employment services. Develop local authority role as employer of disabled people. | Start Dec 05 | PM - Disability AD –Adults AD – Leisure | Improving service in line with best practice and “New Vision for Adult Social Care” | New enablement officers. Existing managers of services. |
| Develop community / Neighbourhood based opportunities | Support small community groups. Awareness training to community committees | Start Dec 05 | AD - Community | Improving service in line with best practice and “New Vision for Adult Social Care | Training resources |
| Independent advocacy service | Explore type of service needed, how this can best be provided through voluntary sector and cost of funding service. | Start April 06 | PM- disability AD- Adults | Consultation and Best Practice findings | Funding to be researched. ~ £30k pa |
| Individual Care |
| Work with individuals to see what they want. Include Life Goals in Service Planning - | Develop Person Centred Planning Approach – including health needs (with users and carers) | By Dec 06 | PM - Disability | Consultation Single Assessment Process | Joint with Health. Consultancy time (£5k) Link with LD services |
|  | Develop integrated working with Health – creating care pathways | By April 07 | AD- Adults | National Service Framework | Joint with Health Management time. |
|  | Develop joint indicators with NHS | By April 06 | AD – Adults PCT | NSF | Performance officer time. |
| Need to be less risk adverse | Develop a Risk Assessment Protocol with service users and deliver awareness training for all staff. Taking into account issues of ‘capacity’ and recent legislation in this area. | By April 2006 | AD- Adults | Independence, Well-being and Choice Green Paper | Consultancy time (£2k) |
| Staff awareness and training | Develop training package with Disability Forum / service users. | By April 2006 | PM – disability AD- Adults | Consultation results | Trainer x 12 days (£5k) Release all staff for training. |
| Commission on quality. | Use Quality Framework developed in learning difficulties service to develop quality services | Start April 2006 | PM - Contracts | New Vision for Adult Social Care; Best Practice comparisons | Development officers time |
|  | In house Home Care moving to short term Intermediate Care Services | By September 2005 | PM – Care support |  | Existing managers |
|  | Develop role of service users and carers in monitoring quality (example Stoke) | By April 2006 | PM – contracts User Development worker |  | Existing staff Customer feedback to be commissioned. |
| Tailor equipment to meet individual needs. | Link assessment for equipment with the single assessment process – enable other professionals to order equipment. Review equipment on annual basis – possibly through Call Centre telephone review (links to Person Centred Planning) | Start April 2006 Start December 2005 | PM – CES PM - CES | Single assessment process; Consultation | Training post – joint with health (£30k) Call centre staff |
| Develop comprehensive approach to Housing needs. | Ensure connections between special needs housing service, handyperson service, housing grants team etc. to deliver a timely response to individual needs. Review processes within Housing Adaptations already started. | By April 2006 | PM – Community Equipment | To enable people to live safely within own home | Existing managers |
| Range of rehabilitation for long-term neurological conditions | With PCT develop action plan in line with National Service Framework | By 2006 | AD -Adults | NSF | With health – existing managers |
|  | Develop service with PCT – (role of the Maples currently under review) | By 2006 | AD - Adults |  |  |
| Carers support | Increase provision of Respite Care options | Start June 2005 | PM - Disability | Carers strategy | £20k carers grant |
| Citizenship |
| Sensory representation on partnership board | Place to be offered on Board | By October 2005 | PB Chair Users development worker | Consultation | Interpreter for all meetings £12k pa |
| Development of supported employment /choice | Extend employment services to include those with physical / sensory impairments | Start September 2005 | DD – commissioning | New vision for adult social care; Social Inclusion | Access to work RNIB |
|  | Evaluate Enablement service | April 2006 | PM - Disability |  | Existing managers |
|  | Work with Local Authority Employment Strategy | By April 2006 | AD- Adults Head of service LD |  | Existing Managers |
| Quality of life | New Directorate will work to improve access and support to use recreation and leisure facilities | September 2005 | Director / Deputy / AD’s | Consultation | Existing resources |
| CORPORATE ISSUES |  |  |  |  |  |
| ACCESS |  |  |  |  |  |
| Environmental access | Review DDA audit information - Physical access to buildings. Consult with a range of service users. Develop transparent method of prioritising action with input from disabled people. |  | Development Services | Meeting legislation | Corporate centre |
|  | Ensure planning application presentations address accessibility issues |  | Planning and Housing | Meeting legislation | With Planning Section |
| Environmental access | Ensure dropped kerbs are appropriately situated? |  | Development services | Meeting legislation | With Planning Section |
| CITIZENSHIP |  |  |  |  |  |
| Transport – strategy | Offer awareness training for taxi drivers – link to licensing |  | Environmental services | Consultation | Pay Trainer |
|  | Local Authority representative to take up the issues with GMPTE |  | LA rep to GMPTE | Consultation |  |
|  | Develop Ring and Ride service |  |  | Consultation | Research investment opportunities |
| Employment Opportunities | LA to ensure positive role in employing disabled people |  | HR | Disability Discrimination Act |  |
| Listening to disabled people | Ensure the needs of disabled people are consulted upon, and acted upon in all areas of local authority services. Give feedback to people – including why things cannot be done. | Starting now | Chief Executive All Chief Officers | DDA | Existing Resources |
| Quality of life | Develop a corporate approach to disabled peoples’ needs and form part of each Directorate’s strategy. Promote positive image of disabled. | By April 2006 | Director Chief Executive | DDA | Existing Resources |
| Social inclusion | Ensure mainstream services are all fully accessible. Promote a positive image of disabled people within all marketing / publications etc. | Starting now | Chief Executive All Chief Officers | DDA | Existing resources Marketing strategy |