COMMUNITY ICT STRATEGY - DRAFT OUTLINE PLAN

OUTLINE APPROACH:

Identify main areas of work required

Break the main areas in to manageable tasks

Identify task dependencies/sequence of the tasks.

Identify responsibilities - what tasks can be progressed by individuals/small groups?

BASIC PRINCIPLES FOR THE DEVELOPMENT AND IMPLEMENTATION OF THE STRATEGY:

| PRINCIPLE | COMMENT |
| --- | --- |
| Acceptance that access to ICT's is an important factor in economic and social inclusion | ICT's are means to end. Developing the skills to ensure individuals are able to benefit economically (job skills), socially (communication/information) and in access to services. |
| Community involvement/ownership central to success | CVS in particular should provide useful link. |
| There is a need for different types of facilities including outreach work. | Existence of barriers - some will not go in to a formal setting e.g. a school or while others will not go to any kind of establishment even somewhere like CREST. Need to attract/encourage all. |
| Different types of facilities and the services offered by each need to complement each other. | Funding undoubtedly going to be difficult hence maximum benefit needs to be derived from available resources. Even if same service but at different times. |
| Every area of the city requires appropriate facilities | Consultation/needs identification should therefore be undertaken on an area basis e.g. by ward. However, funding opportunities will be greater in some areas compared with others. |
| Facility must be capable of being sustained | More likely if supported by community with appropriate skills and community ownership |
| Evolving strategy | Needs/skills/facilities/funding opportunities will change over time |

IDENTIFICATION OF MAIN TASKS:

|  | MAIN TASK | SUB TASK | COMMENT |
| --- | --- | --- | --- |
| NO. | DESCRIPTION | DESCRIPTION |  |
|  | Wider consultation of strategy document | Community & Social Services (e.g. Area Co-ords), Members, Education & Leisure (e.g. Com Ed, Schools ICT), Housing (e.g. tenants participation), Chief Execs. | Their comment and gateway to Community consultation |
|  | Mapping current provision (facilities/training resources) | Identify/map current facilities which are accessible to the public i.e. Schools, Community facilities, other public - libraries, schools and private sector provision including colleges, One Stop Shop/Telematics Suite Include proposed library facilities from NOF funding, SCIP. Identify role/functions/services provided by each. | Distinguish between 'users' in the community and 'support' groups like Crest who can be developed in to centres |
|  | Mapping current networks and their linkages | Identify current relevant networks e.g. Superjanet, Schools. Peoples network Identify their function/purpose and links, if any, with other networks | Jon Burt Potential North West Grid? |
|  | Develop network options | Identify impact of other initiatives e.g. people's network, Schools. Consider potential for businesses/SME inclusion As far as possible produce costed alternatives | Jon Burt, link with funding possibilities |
|  | Develop and promote community advice framework for advising/supporting groups in the purchase of ICT's | Develop complete package - awareness, advice, purchasing, installation, training, technical support Publicise/market to community groups | Community based e.g. Crest. Dependent on capacity being created so CREST central to community capacity building |
|  | Identify other initiatives and their linkages | Libraries - people's network - presence in most wards Link with community facilities, Isaware information and initiatives. | Need to maximise those linkages |

|  | MAIN TASK | SUB TASKS | COMMENT |
| --- | --- | --- | --- |
| NO. | DESCRIPTION | DESCRIPTION |  |
|  | Develop advice framework for promoting Lifelong Learning in relation to ICT's | Link with communications network - making sure that up to date information is available Involvement of specialist advice agencies e.g. SETAS | Link with LLLP group Seamless progression through the system |
|  | Identification of community need within each geographical area | Consultation/discussion with individual communities Involvement of CVS, Community & Social Services staff, Housing etc SWOT analysis of current facilities Compare with current provision to identify gaps |  |
|  | Identification of changes to facilities required to fill needs gap in each geographical area | Consultation/discussion with individual communities Involvement of CVS, Community & Social Services staff Consider role of local employers in the provision of resources | Phased approach |
|  | Identify/develop appropriate funding alternatives | Develop individual projects - area specific, authority wide involvement of Chief Execs to identify appropriate funding alternatives Start with areas/facilities most likely to attract funding Implications of successful DfEE/NOF bid | Partly based on results of consultation exercise |
|  | Develop communication framework covering the various providers | Base information from providers - courses, facilities, costs How can this be distributed efficiently and effectively? How can this be kept up to date e.g. using the web? |  |
| 12 | Encourage internet content that will in turn encourage public access. | Liaise with City Council directorates and I.T. services units/groups Make guidelines/best practice widely known |  |
| 13 | Establish a project management framework and communication structure | Covering the successful implementation and co-ordination with other related projects |  |