Task

Joint Health Promotions

Overview of task

To assist the Health City Forum in delivering sustainable improvements in health and reductions in health inequalities through improved communications and take-up of services through optimum use of our joint resources

Objectives of task

To maximise take up of Health and Salford City Council services and support networks through optimum use of our joint resources To sustain a change in lifestyle that will enhance their quality of life Improving access to our services through targeting vulnerable groups/ through reducing organisational barriers Improve communications with Salford residents, thereby empowering them to take responsibility for their personal well being In conjunction with the Healthy City Forum enable the meeting of key community plan objectives and the PCT Local Delivery Plan Supporting and delivering national initiatives at a local level to Salford citizens Improve access to Benefits services through utilisation of access to citizens via health facilities To satisfy the following; LSP aims Government agendas such as the Department of Health document “Tackling Health Inequalities: A programme for action” Joint PCT/SCC performance targets for example Support the PCT in assisting at least 1450 people in Salford to give up smoking in 2004/05 Achieve a 6% reduction in mothers who smoke during pregnancy Reduce the number of delayed hospital discharges by 20% (compared to 2003/04) Work with the PCT to develop a range on health and well-being initiatives Achieve 95% response rate to environmental Health complaints and requests within 3 working days of receipt In accordance with the key aims and objectives of the joint SCC/PCT policy document “Health Inequalities in Salford-as local strategy for action” where the following priority action areas have been established The very young and their families Older people Smoking and tobacco control Nutrition and Physical activity

Potential deliverables

A co-ordinated approach to the effective dissemination of public health information through: Leaflets Use of Salford Direct call centre Training key front line customer services staff Training key front line visiting staff from within SCC and other Agencies including, benefits, welfare rights visiting officers Drop in sessions/Face to face counter services Web Media coverage

“Quick wins” within project

Flu Jabs Campaign Smoking Cessation Uptake in screening in both women’s and men’s health Drug wastage Get fit for summer Sexual health Organ donor card distribution Targeted accident prevention

Key Milestones

Flu jabs: Planning. Early Jan 2004 to end April 2004 (Including staff training and campaign publicity) Launch. October 2004 to January 2005 to achieve appropriate PCT target Smoking Cessation: Planning. February 2004 Launch. March 2004 and ongoing Uptake in screening in both women’s and men’s health: Planning. February 2004 Launch. April 2004 and ongoing over 12 months on targeted priority groups and geographical City locations Drug Wastage: Planning. March 2004 subject to meeting pharmacy group and agreeing approach Launch. TBC Get fit for summer: **** (Promote Immunisation and Vaccinations for children/holiday Immunisation/leisure activities/link to School Health/sun screening advice) Planning. February 2004 Launch. May 2004 Sexual Health: Planning. In conjunction with developing PCT strategy around reducing teenage pregnancy and sexually transmitted diseases Launch. TBC Organ Card Distribution: Planning. Subject to agreement with various Hope Hospital agencies Launch. TBC Targeted Accident Prevention: (Large scale and ongoing campaign requiring consensus of multi agency groups. Planning and launch subject to continuation of dialogue) Elderly: Prevention of falls Children: Burns/scalds road safety/fireworks Development of SCC/Salford PCT health Inequalities Strategy December 2003

Project resources

Project Lead: Anne Brown Project Officers: Flu Jabs. Julie Marsh (PCT) Smoking Cessation. Erica Kinnisburgh (PCT) Screening. Jane Kelly (PCT) Sexual Health/Family Planning. Pat McCormack (PCT) Drug Wastage. Peter Jones (PCT) Fit for Summer. Healthy City forum rep (NB. Salford Direct staff to be allocated to each area. Other PCT/Health staff to be confirmed as planning stage progresses)

Task

PALS (Patient Advisory Liaison Service) and PPI Patient and Public Involvement) Awareness

Overview of task

Advise and support the citizens of Salford in raising awareness and usage of the PALS service and contributing to the PPI agenda

Objectives of task

To identify and train PALS champions within both the PCT and SCC customer services staff To assist Salford PCT in meeting statutory obligations involving patients and the public in monitoring services To empower Salford residents to maximise health care opportunities and ensure that they are delivered to the appropriate standard in accordance with appropriate targets To encourage Salford citizens in participating/contributing to patient forums and developing local health strategies To resolve patient and service user concerns and issues quickly and effectively Making the journey through the NHS as easy as possible and if necessary signposting accordingly

Potential deliverables

Record and improve health service delivery and identify trends PALS Accredited staff Joint training and development programmes with PCT and SCC Improved communication and public participation Improve service user awareness

“Quick wins” within project

Staff training completed by end June 2004 Improved distribution of PALS information around SCC/Health locations

Key Milestones

Increase patient forum attendance by XXX by June X staff to have participated in PALS customer care awareness training by June 2004 Explore possibilities of integrating PALS awareness within SCC/PCT induction programme X% increase PALS service enquiries

Project resources

Project Lead: Andy Muir (PCT)/Pam Woods (Hope) Project Team: John Tanner, Lynne Goslin (Salford Direct)

Task

Integration of Salford General Practitioners within the collaborative service provision agenda

Overview of task

To pilot integration work specifically between SCC and GP’s surgery to inform the future development of this relationship, particularly focusing how such interaction can be re-engineered to improve the quality of services to our mutual customers

Objectives of task

Pilot work with nominated GP practise to achieve: An understanding of the issues around ICT integration Reduce administrative burdens on GPS through improved system integration with SCC Promote awareness off GP surgery services and SCC services to ensure improved signposting to SCC services Build up an understanding of future integrated relationships particularly within the LIFT environment where GP/SCC and Salford PCT services will jointly be provided

Potential deliverables

Specification of potential IT integration needs Some pilot testing of integrated IT development work Training and development of appropriate staff to raise awareness of the range of services provided across al organisations Process template to be created for likely shape of the level of integration between GP services and other organisations within the LIFT environment The provision of benefits advice services in GP’s surgeries building upon the work currently undertaken in this area by SCC Social Services Directorate

“Quick wins” within project

Visit to Halton BC to learn from other pilot working arrangements in this area Some pilot testing of integrated IT development work which is likely to be around the blue badge application process BPR work to understand current processes within GP environment and likely shape on the level of integration between GP services and other organisations within the LIFT environment Benefits outreach work within GP surgeries to promote take-up of benefits to Salford residents Documentation review to facilitate easier patient referrals. This will be investigated as part of the proposed BPR work within PCT clinics

Key Milestones

On Line authorisation of benefits entitlement to be tested XX Application for services from GP surgeries on line XX Repeat prescription ordering through SCC facilities XX LIFT Service redesign work to be completed by XX

Project resources

Anne Brown (Lead) Martin Vickers Andrew Pringle Nominated GP’s surgeries (2)

Task

Provision of a single point of contact to facilitate the prompt and effective delivery of all multiple agency services (Health, Social Care, Benefits, Voluntary Sector, Spiritual, Operational and Legal) to those who are either anticipating or undergoing a bereavement.

Overview of task

To ultimately develop the best possible customer care for the citizens of Salford based upon empowerment, prevention and where appropriate re-engineered services.

Objectives of task

These services will be based upon the seamless integrated provision of care through the ease of access to bereavement services, delivered in a consistent manner from all agencies involved

Potential deliverables

To deliver the following benefits: For the patient or relative: ease of access to services to make the process of loss/bereavement as easy to deal with as is permissible given the difficult nature of this life event, and to improve the patients care experience. For SCC and NHS: it will reduce co-morbidity, produce efficiencies of scale through a joint provision of services, increase efficiency and improve access to services via a single point of contact in terms of LIFT and other joint working initiatives.

“Quick wins” within project

Mapping out of multi-agency service provision around the death/bereavement scenario (end January 2004) Produce a high-level service design model to establish areas of service synergy, duplication and gaps as a basis for future joint working (February 2004)

Key Milestones

Include as a pilot working with district nurses over verification of death and subsequent info flow via a central hub Produce an information pack for people suffering bereavement to ensure more effective signposting of services available/actions required at this time

Project resources

Andrew Pringle. Team Leader Hannah Yates/Merlyn Reid (BPR) Anne Brown (PCT) Janet Roberts (Hope) Anne Brown PCT Janet Roberts (Hope)

Task

Provision of a one-stop shop for benefits/health and financial advice specifically in the area of home visits, debt collection, advice surgeries and benefits take-up campaigns/health promotional work.

Overview of task

The theme will examine the best opportunities for Benefits Advice Agencies to work collaboratively to ensure that access to social security benefits advice services are accessible for existing/potential claimants. The working model will explore how resources in this area can be collectively deployed so that duplication of effort is avoided.

Objectives of task

Joint team intervention should result in an overall net additional take-up of benefits and, contribute to the successful delivery of Pension Credit and other major changes in the delivery of social security benefits within the Government’s modernisations of the benefits system In terms of overall costs to partners, that the outputs outweigh any additional costs of service provision Improvement in the quality of life and independence of vulnerable persons, resulting from pre-emptive intervention before time of acute need this could be for example, a reduction in acute admissions of older people to hospital, etc., thereby creating savings to the NHS A detectable improvement in local economies brought about by increased benefit entitlements feeding though, for example, to create jobs The provision of accessible, seamless benefits services which are simple to understand, use and communicate with To harness the resources of all available resources to ensure that vulnerable groups within Salford do not suffer financial exclusion in accordance with the Authority’s current Working Group established to tackle this issue

Potential deliverables

Joint procedural approach where legislation allows in the provision of benefits advice the visiting of benefits claimants the promotion of benefits take-up through the development of an integrated take-up marketing strategy The use of joint resources where legislation allows in provision of services within the areas overleaf Successful implementation of Pensions Credit and other legislative social security benefit changes in accordance with national expectations of potential take-up implications within Salford Tangible increases in benefits take-up across the whole range of social security benefits in respect of the joined-up initiatives within the Theme Increase in the numbers of organisations who are in a position to verify benefits claims information on behalf of Benefits Agencies e.g. Housing Associations so that claimants are able to access the benefits service at their convenience Greater integration of benefits advice when dealing with vulnerable people who owe multiple debts so that income maximisation and financial stability for such individuals can be achieved more quickly The use of shared information systems where legislation permits to enable successful achievement of all theme objectives

“Quick wins” / Key Milestones within project

Creation of Project Documentation following workshop with all key stakeholders (March, 2004, initial planning meeting held 9th February, 2004) Delegation of some benefits advice resources internally between Salford Direct and Welfare Rights (April, 2004) Financial inclusion workshop held 5th March, 2004 across Agency Groups and the voluntary sector where Theme 1 issues were discussed Use of joint visiting protocols across all Benefits Advice Agencies (June 2004) Implementation of joint advice surgeries at Hope Hospital (Salford Direct, Welfare Rights, CAB, Pensions Service) (February, 2004), further development of such outreach work within the Health Promotion sessions currently planned (Smoking cessation, male/female screening) Implementation of benefits verification services within Libraries network (April, 2004) Delegation of benefits verification responsibilities to external organisations such as Housing Associations (July 2004) (potential Housing Associations, Irwell Valley, Northern Counties) Planned pre-emptive intervention work by Benefits Agencies in cases where existing vulnerable benefits claimants are in receipt of support from Social Services Directorate and in cases where debtors owe multiple debts

Project resources

Project Lead: Martin Vickers (Head of Customer Services) Dr Peter Kawalek (Manchester Business School) Keith Darragh/Richard Bundy/Steve Quinn Welfare Rights (Social Services Directorate) Joe Coogan Supporting People (Chief Executives Directorate) Dave Parsonage, Jacki Wilde (Pensions Agency) Job Centre Plus (To be confirmed) Anne Brown Salford Primary Care Trust Melanie Anderson (Hope Hospital CAB) Sarah Spence, Libraries Service (Education Directorate) Diana Martin (Chief Executives Directorate) Representatives to be confirmed from Irwell Valley, Northern Counties Housing Associations Voluntary Agencies to be confirmed from Salford Financial Inclusion Working Group

Task

To undertake BPR analysis within Salford PCT clinics.

Overview of task

This project will consist of a high level analysis of the services provided by clinics to allow decisions to be made about the possibility of providing those services within the LIFT buildings

Objectives of task

To undertake BPR analysis within Salford PCT clinics to understand existing working practices, to recommend changes to those working practices in order to meet future service delivery needs specifically in terms of LIFT centre delivery, to understand the degree of integration between these services and other services which will be provided within the new LIFT centres, and to map the process for the effective management of this change.

Potential deliverables

The PCT BPR representatives will work in conjunction with City Of Salford BPR team to; Identify all the processes inside the functional areas which will have been identified by clearly defined terms of reference Identify the future needs and business improvements Identify and interview stakeholders, observing, mapping and analysing current processes and service metrics, and analysing the effectiveness of current support systems Understand the business context, analyse the effectiveness and efficiency of current processes, generate ideas for process improvements and help develop the vision for subsequent process redesign and implementation Identify specific citizen life events so that services can be tailored to meet the requirements of these events Identify any areas where benchmarking may be useful, and carrying out benchmarking Assist in the identification and clarification of future protocols Assist in the review and development of the process redesign and subsequent post implementation evaluation. Assist in development of appropriate training and development programmes to achieve the business changes required

“Quick wins” within project

The analysis will mainly be carried out in one clinic by April 04. One other clinic will be investigated and a workshop will be held with staff from other clinics to verify the findings during the same month

Key Milestones

High level analysis of the functional areas of the Primary Care Trust and partner organisations, including interactions within the PCT and with external agencies and clients, produced by XXXXX. This will enable us to scope the boundaries and size of the BPR work required in any future phase

Project resources

Project Lead Ewen Locke Salford Advance) Ray Vet/Merlyn Reid (BPR) Anne Brown Operational Head of Service (PCT) Various members of the LIFT Staff Development group

Task

The integration of joint training and development programmes for potential front line SCC/PCT LIFT Centre staff in particular the development of a joint Customer Service NVQ programme and the European Computer Driving Licence (ECDL)

Overview of task

To examine the possibility of the joint development of training and development programmes in particular the development of a joint Customer Service NVQ programme and the European Computer Driving Licence (ECDL) programme

Objectives of task

To train front line clinic staff, SCC Customer Services staff and Libraries staff in advance of the LIFT centre opening in priority areas such as working with technology and customer care so that consistent, high quality front-line services will be provided within the Centres

Potential deliverables

A joint LIFT training and development programme for SCC/PCT front line staff A baseline assessment of existing training needs Consistency of approach in terms of customer service quality across all front line service providers within the new Centres Continued sharing of service standards, working practices and procedures through the sharing of approach between front-line staff Development of joint customer care standards to be adopted by front line staff within LIFT Centres To have xx PCT xx Salford Direct and XX library staff trained in NVQs by XXXXXX

“Quick wins” within project

Pilot NVQ/ECDL programme to commence with limited number of staff Baseline assessment of potential front line training needs to be assessed Awareness sessions in respect of Customer Care NVQ and ECDL to take place specifically for the pilot group of staff The continued development of the LIFT Staff Development Group in support of these initiatives

Key Milestones

Outcomes of BPR work in clinics to be finalised so that conclusions may be drawn about PCT future service delivery implications Clarification from SCC/PCT by XXX of the organisational shape of front line resources within the LIFT Centres Development of joint LIFT training and development programme by XX Pilot training programme to commence XX Launch of full training programme

Project resources

John Tanner (Lead) Anne Brown Staff side (PCT?) Amanda Rice Salford Advance Training Unit Customer Service NVQ provider Debbie Brown SCC HR/PCT HR representative Teaching and Learning Directorate with the PCT

Task

Sharing of complaints handling methodologies between SCC and PCT to disseminate good practice and endeavour to develop consistent and uniform procedures where possible

Overview of task

To examine the possibility of integrating complaint handling procedures across SCC and PCT to improve access to the process, to maximise efficiencies for complainants within that process through the sharing of good practice, and to develop consistent complaints handling standards across both organisations

Objectives of task

Improved communications to Salford residents about complaints handling processes within both organisations to encourage access to those processes through use of web developments and front line staff PCT complaints handled and monitored via call centre/front line services to agreed protocols and vice versa Joint approach to be developed in conjunction with SIFT Plan 2 (PALS (Patient Advisory Liaison Service) and PPI (Patient and Public Involvement) Development of joint electronic complaint handling processes Development of joint customer care standards to be adopted by front line staff within LIFT Centres

Potential deliverables

Uniform complaint handling procedures across SCC/PCT A joint training and development programme for SCC/PCT front line staff specifically in respect of complaints handling matters Consistency of approach in terms of complaints handling across all front line service providers within the new Centres Potential development of uniform electronic complaints handling systems

“Quick wins” within project

Baseline assessment of existing complaints handling protocols (May 2004) Pilot group of staff to test the concept of dealing with complaints across organisations (XX) PCT to examine the potential use of SCC’s electronic informal complaints handling system Uniform protocols to be established

Key Milestones

Baseline assessment to be undertaken (May 2004) Assessment of SCC complaints management systems to be undertaken (May 2004) Pilot group to commence integrated complaint handling (June 2004) Wider roll out plan of complaints handling to be determine (September 2004)

Project resources

Joint project lead Stephen Fryer, PCT complaints person Amanda Rice Anne Brown Andy Muir Pam Woods

Task

The provision of joined up PR strategies specifically in respect of LIFT developments but also in respect of SIFT developments between SCC and PCT

Overview of task

The development of a robust, cohesive PR strategy to ensure that Salford residents are effectively communicated with and involved with in respect of future services to be delivered within the LIFT Centres and in respect of joint SIFT developments.

Objectives of task

Joint PR strategy for SIFT activities and LIFT Consultation to be established Joint working protocols to be established between SCC and PCT to support the effective delivery of the strategy

Potential deliverables

Joint PCT/SCC PR strategy in respect of LIFT/SIFT developments Joint training and development of SCC/PCTstaff in respect of communications issues

“Quick wins” within project

Baseline assessment of existing PR strategies/working practices to be established Further joint promotional work to be undertaken in respect of SIFT developments Joint PR strategy to be determined in respect of SIFT/LIFT developments

Key Milestones

Baseline PR assessment (May 2004) Further joint promotional work to be undertaken in respect of SIFT developments (April 2004) Joint PR strategy to be determined (July 2004)

Project resources

Simon Malcolm /Christine Southern (Project Lead) Communications Group (SCC/PCT)

Task

The delivery of one stop shop advice service through Salford Direct’s Call Centre/face to face and web facilities in respect of various City Council services in support of LIFT/SIFT developments as articulated by SCC’s “Think Customer” strategy

Overview of task

The inclusion of various new City Council services within Salford Direct’s communication channels

Objectives of task

To provide one stop shop advice service for Salford residents to improve access and take up of services To provide high quality customer care standards to Salford residents To integrate within the front line SCC facilities services which are critical to the effective operation of the LIFT Centres, services which are deemed to be priority with the community plan themes To provide more holistic front line services across the broad range of SCC activities

Potential deliverables

Integration within Salford Direct’s front line service the following business areas: Anti Social Behaviour referrals Reporting of race hate crime Childrens and young peoples services Blue Badges Bus Passes Free School Meals Work Permits Chaperones licences Highways Services Traffic management Libraries services

“Quick wins” within project

Anti Social Behaviour referrals (May 2004) Reporting of race hate crime (May 2004) Childrens and young peoples services (August 2004) Blue Badges (May 2004) Bus Passes (May 2004) Free School Meals (May 2004) Work Permits (May 2004) Chaperones licences (May 2004) Highways Services (May 2004) Traffic management (August 2004) Libraries services (December 2004)

Key Milestones

See above

Project resources

Andrew Pringle (Project Lead) Think Customer Programme Board Graham Boyd

Task

To examine opportunities for utilising consultation methodology adopted by Salford Direct for consultation on broader issues particularly in respect of Health matters

Overview of task

Salford Directs approach to customer consultation works on the theory that we need to ‘know today what our customers want tomorrow.’ Salford Direct is committed to involving it’s customers in shaping how services are delivered. The very essence of how each service is delivered revolves around ‘thinking customer back’ and not ‘organisation forward.’ In order to do this we have to know what customers expect form us as service providers and reengineer service delivery backwards working on this concept. Salford Direct currently utilises exit surveys in face-to-face outlets and customer ringbacks for telephony customers, an approach which has provided timely service user feedback to develop improved service which is extremely responsive to customer needs. Through sharing of such good practice with PCT it is felt that there may be opportunities to undertake joint consultation using these established techniques.

Objectives of task

To utilise existing good practice within SCC to provide “real time” feedback from service users of SCC/PCT services To endeavour to seek greater participation in such exercises, particularly within Health from service users To determine the potential roll-out of this approach across the broad range of SCC/PCT services To share all aspects of consultation good practice, not only in terms of capturing customer views in the first instance but also in providing feedback and implementing changes thereafter

Potential deliverables

Assessment of baseline position within both organisations in terms of consultation Pilot consultation project across some PCT/SCC services Development of potential roll-out plan for future development of joined-up consultation

“Quick wins” within project

Pilot project to commence (May 2004)

Key Milestones

Assessment of baseline position (April 2004) Identification of potential Health consultation projects (April 2004) Pilot project to commence (May 2004)

Project resources

Martin Vickers (Lead) Anne Brown Alison Dalley Alan Campbell

# Text boxes

Improving Health IN Salford

# SIFT: Team Plan 1 Joint Health Promotions

# SIFT: Team Plan 2

# PALS (Patient Advisory Liaison Service) and PPI (Patient and Public Involvement)

# SIFT: Team Plan 3 Pilot Integration with GP’s

# SIFT: Team Plan 4

Proving the Concept of the Life Events model through development of the Bereavement Centre

# SIFT: Team Plan 5

Providing joined up health and benefits advice IN Salford

# SIFT: Team Plan 6

Business Process Re Engineering within PCT clinics

# SIFT: Team Plan 7 Joint training and development

# SIFT: Team Plan 8 Complaints handling

# SIFT: Team Plan 9 Joint PR strategy

# SIFT: Team Plan 10 Development of SCC front line services in support of LIFT/SIFT developments

# SIFT: Team Plan 11 Joint service consultation