# Report To Lead Member For Corporate Services 26th August 2003

## CORPORATE SERVICES REVENUE BUDGET MONITORING 2003/04

### AS AT 15th AUGUST 2003

The Corporate Services budget for 2003/04 is £6.706m.  An analysis of the budget over the main expenditure heads is shown at Appendix 1.

## Budget monitoring to 15th August 2003 has identified the following: -

## Salaries

Expenditure on salaries to August 2003 compared to the profiled budget for the three months to date shows the following position: -

| Division | Budget | Actual | Variance |
| --- | --- | --- | --- |
|  | April-August 2003 | April-August 2003 | (-)Under/ (+)over |
|  | £000 | £000 | £000 |
| Finance | 2365 | 2305 | -60 |
| IT Net | 1137 | 1099 | -38 |
| Salford Advance | 441 | 421 | -20 |
| Customer Services | 2231 | 2230 | -1 |
| Law & Admin | 1640 | 1646 | 6 |
| Misc. Finance | 58 | 49 | -9 |
| Total | 7872 | 7750 | -122 |

The overall position shows that expenditure on salaries (which includes agency and overtime costs) is within the budget for the period April to August 2003.  The main variations are: -

- Finance – a number of posts have not been filled within FSG and the number of payroll posts has recently been reduced by four which will reduce the costs per transaction processed, part of the payroll saving will be used to fund the improvement and relocation of the FSG Contact Centre.

- Salford Advance and IT Net salaries reflect the withdrawal of the R & R package in June 2003 and the budget provision required to the review grading of key posts.

- Law & Administration salaries include overtime payments for Legal Services staff who are dealing with the increase in RTB applications.  The additional costs arising will need to be charged against the additional capital receipts generated.

## Savings

Corporate Services savings agreed during the budget process are: -

|  |  | Achieved to date |  |
| --- | --- | --- | --- |
| Saving | £000 | £000 | Details |
| Energy Saving initiatives | 67 | 65 | Savings from the renegotiation of gas and street lighting contracts |
| Reduction in Internal Audit | 33 | 33 | 1.5 posts deleted arising from restructure |
| IT Services – reduction in staffing costs | 200 | 200 | Deletion of R&R package from 30th June 2003 |
| Share of £250k top sliced savings | 28 | 15 | Purchasing savings on target to be achieved |
| Total | 328 | 313 |  |

Budgets for the year have been reduced to reflect these agreed savings.

#### Budget Issues

The key budget risks continue to be monitored on an ongoing basis. Significant issues to be aware of at this stage are:

- Benefits – The mid-year estimates show the projected cost of Council Tax and Housing Benefit to be £41m and compared to the budget will result in a net overspend to the Council of £240k.

- Schools Broadband – There is a budget provision in 2003/04 of £515,000 to meet further costs related to the roll out of broadband to schools, issues are:

  - the additional cost of completing the project need to be quantified so that the adequacy of the budget provision can be assessed

  - the annual running costs following project completion need to be calculated

  - the position relating to the recovery of installation costs from secondary schools should be determined

- Enterprise XP – currently there is no budget provision for this project:

  - The full cost and phasing of expenditure for the project should be identified as part of the business case

  - Funding for the project should be agreed

  - Ongoing running costs should be calculated and funding established

- Identification and Referral of Children at Risk (IRT) – government funding of £100,000 has been awarded to introduce a system to support the IRT initiative with a further £100,000 to be provided by the Greater Manchester e-government group, this will fund a joint IRT project to be led by Salford:

  - The cost and phasing of the project needs to be identified

  - Overall funding for the project should be agreed

- NPHL

  - the accommodation costs for the NPHL contact centre were £68,000 for which funding needs to be identified

  - initial operational charges have been made to NPHL the costs and income relating to the service will be monitored to assess the charges made

- New Statutory Licensing Regulations will require additional resources to implement changes and carry out additional work in relation to liquor licences, previously undertaken by the Magistrates Court. Approximately three additional members of staff will be required and will not result in any additional income. The regulations come into effect in January 2004 with additional costs of £20k 2003/04 and £80k 2004/05.

- The cost of configuring SAP to provide financial and HR systems for the Leisure Trust is estimated at £20k.

- LIFT – costs of £19,000 have been incurred in relation to the provision of legal advice from Cobbetts, funding for these costs needs to be identified

## Budget Risks

Other budget risks that have been identified continue to be monitored relating to:

- Strategic Partnering

- Potential loss of business (e.g. support services to schools , NPHL, leisure trust)

- Grant aided initiatives – E-Government programme, National CRM Academy

- Document management – licence implications

- Council Tax /Benefits system – cost implications

- Legal Services Management system – the budget includes a provision for the replacement of the system.

- CPO income (compensation for property lodged with Courts where owners unknown)

- Impact of single status – reduction in working hours from September 2003.

- Income from licensing, registration, land charges etc.

At this stage no specific budget impact has been identified in relation to these issues.

G. Topping

Assistant Director of Corporate Services

(Accountancy & Exchequer)

19th August 2003