Members of the Scrutiny Committee

| Councillor B. Pennington (Chair) |  | Councillor J. King |  |
| --- | --- | --- | --- |
| Councillor S. M. Cooke |  | Councillor B.J. Lea |  |
| Councillor P.W. Dobbs | A | Councillor I.D. Lindley |  |
| Councillor D. Fernandez |  | Councillor G.C Loveday |  |
| Councillor C. Gray |  | Councillor J.A. Mullen | A |
| Councillor J.R. Jones |  | Councillor J.F. Pooley | A |

Present =Apologies received =  A

Officers and invitees present:

Co-opted members:	Reverend Paxton,  Mrs J Elderkin, and Mrs S Thompson

Invitees and Officers: 	Councillor K Mann, John Stephens, Terry Stringer, Faith Mann, Linda Pride, Kevin Wolstencroft Russell Bernstein and Amanda Carbery

Apologies:			Reverend Archer, Jeremy Michelson,  and Councillor J Warmisham

| Item Responsible Member Officer | Discussion | Action Required By | Timescale |
| --- | --- | --- | --- |
| 3. High Schools Private Finance Investment Initiative Kevin Wolstencroft | A verbal update on the current position relating to PFI 2 Hope, Buile Hill and Harrop Fold High Schools was given as follows:- Work had been carried out with Headteachers /external advisers to produce a curriculum analysis for each school, schedules of accommodation, room data sheets and an output specification A Bid for additional credits was submitted on 4 March 2005 – decision was not expected until after the general election A preferred bidder to be appointed by late June 05 It will take 18 months minimum to complete the building works completion date – autumn 2007 It was agreed:- That the update be shared with the Headteacher of Harrop Fold High School That the concerns of the Scrutiny Committee regarding the delay in relation to credits from the DfES be conveyed to the relevant officers at the DfES | Kevin Wolstencroft Kevin Wolstencroft | May 2005 May 2005 |
| 4. Inclusive Strategy for Children and Young People – update on progress Faith Mann | Members requested information on the following:- How the effectiveness of the post of champion for children and young people is to be measured The new structures for the Children’s Services Directorate Numbers of young people participating at the moment The co-ordination of Anti-social Behaviour orders | Brian Wroe Report due at June meeting Faith Mann Under consideration by Strategy and Regeneration Scrutiny Committee | May 2005 June 2005 May 2005 ongoing |
| 5. Salford Youth Service Best value Review Improvement Plan Linda Pride | It was agreed:- That a progress report be submitted in 6 months time detailing the barriers that are preventing recommendations from being achieved A report be submitted to each political executive committee detailing progress in each political executive’s area | Linda Pride Linda Pride | November 2005 November 2005 |
| 6. Intensive Support Programme – case studies of two schools – PART 2 ITEM John Stephens Terry Stringer | Members welcomed the report and congratulated School Improvement Service on the work undertaken. It was agreed: That a case study on a school where liaison with the school improvement service had failed to bring about improvements be brought to a future meeting | Terry Stringer | Include in work programme |
| 8. Work Programme Amanda Carbery | Members raised the issue of nutrition and the effect that food and diet has on children’s behaviour. Members referred to the extra £280m which the government had announced to tackle the school meals “crisis” but had concerns as to whether this money would actually be spent on improving ingredients in school meals or be spent on re-establishing kitchens in those schools that had in recent years phased out their catering facilities. It was agreed: That the Lead Member for Children and Youth be requested to raise this issue with relevant officers and report back to a future meeting. | Councillor J Warmisham | To be agreed |