Response to APA recommendations

| Recommendation | Assistant Director | Action | Timescale | Lead Officer | Measurement of Success |
| --- | --- | --- | --- | --- | --- |
| Being Healthy |  |  |  |  |  |
| Reduce obesity rates for children and young people. | PG | New strategy and identify lead officers. |  |  |  |
|  |  | Implementation team to develop response plan e.g. identify action in other local authorities. |  |  |  |
|  |  | Incubator workshop to develop an action plan for the city. |  |  |  |
|  |  | Use Spotlight model for an area of the city. |  |  |  |
|  |  | Marketing campaign — raise awareness |  |  |  |
| Reduce teenage conception rates. | FM | Work closely with PCT to introduce Challenge and to review and re-focus the Teenage Pregnancy Strategy. This work will be carried out in close consultation with GONW lead for Teenage Pregnancy. | Jan 08 — June 08 | Lesley Craven | Reduced teenage conception long term target |
| Reduce dental decay. | PG | New strategy and identify lead officers. . |  |  |  |
|  |  | Implementation team to develop response plan e.g. identify action in other local authorities. |  |  |  |
|  |  | Incubator workshop to develop an action plan for the city. |  |  |  |
|  |  | Use Spotlight model for an area of the city |  |  |  |
|  |  | Marketing campaign — raise awareness |  |  |  |
|  |  | Review findings of fluoride research |  |  |  |
| Reduce admissions to hospital relating to substance misuse. | PG | Review structure and service for children and young people and substance misuse. |  |  |  |
|  |  | Review and revise general strategy and action plans. |  |  |  |
|  |  | Review strategies relating to reducing admissions to hospital |  |  |  |
| Staying Safe |  |  |  |  |  |
| Ensure that children on the Child Protection Register are allocated to a person qualified as a social worker and that there are sufficient qualified and experienced staff to run a safe child protection service. | PW | Children on CPR are now all allocated to a qsw. Monitoring and early warning arrangements in place. | Ongoing | M.Kemp | Maintenance of 100% allocation of children on register to qsw. |
|  |  | Review existing staffing levels to determine whether capacity is sufficient. | Feb 2008 | M.Kemp |  |
| Ensure thresholds are set at a level that enables children in need and their families to access appropriate services; ensure thresholds are clearly understood by staff in all agencies. | PW | Continue roll out of CAF integrated working training. | March 2008 & Ongoing | A.Hampson & Locality Managers | Achieve national average level of conversion off referrals to initial and core assessments |
|  |  | Review threshold applied by Duty & Investigation Team.. | Feb 2008 | A.Hampson & M.Kemp |  |
|  |  | Review interface between Duty & Investigation & Locality Teams | Feb 2008 | Paul Woltman |  |
| Develop, and adequately resource, effective early intervention services that reduce the need for children to be looked after. | PW | Strategy partly dependent on invest-to-save bid. | Dec 2007? | Paul Woltman | Reduction in looked after numbers of 10% over three years. |
|  |  | Complete work on design of an integrated service | March 2008 | Paul Woltman |  |
|  |  | Continue development of SureStart Family Support services | March 2008 | Jane Middleton |  |
| Enjoy and Achieve |  |  |  |  |  |
| Educational outcomes at age 16: increase the percentage of five A*-C GCSE or equivalent including English and mathematics. | JS | Implement the National Strategies for School Improvement, including all appropriate intervention strategies (e.g. SISP). | 2007-2009 | Jan Rowney | Universal and targeted programmes within the NS implemented effectively and judged positively by schools and RD monitoring. |
|  |  | Implement transformational approaches to teaching, learning and curriculum organisation. | 2007-2010 | Jan Rowney | Collaborative and complementary curriculum models in place. ICT embedded in curriculum engagement. |
|  |  | Build, through targeted continuous professional learning programmes, leadership capacity at middle and senior levels of school leadership. | 2007-2008 and on-going | Jan Rowney | Leadership judgements in OfSTED and SEF consistently good or better |
|  |  | Ensure that robust and appropriately challenging targets are agreed in all schools/settings. | 2007-2008 | Phil Smith | All DCSF requirements for target-setting met. Ambitious targets set in all schools/settings. Level of ambition consistently judged `high' by SIPs. |
|  |  | Use of ASTs and Lead Departments to develop and share best practice in maths and English. | 2007-2008 | Jan Rowney | Improved capacity in core departments judged by SIPs. |
|  |  | Supporting the development and implementation of National Diplomas | 2007-2010 | Bev Walker | All Diploma lines implemented within planned timescales and to high quality. |
|  |  | Provision of high quality, accessible revision materials and programmes in maths and English | 2007 and annually | Cathy Starbuck | All children & young people able to access interactive revision materials. |
|  |  | Brokering of high quality study support for targeted schools. | 2007 — 2008 and annually | Jan Rowney | All targeted schools to receive one session from brokered consultant. |
|  |  | Exploitation of opportunities offered within Greater Manchester Challenge | 2008 — 2011 | Jan Rowney | Success measures to be added as specifics are determined within the Challenge. |
| Reduce the percentage of children and young people in care missing 25 days or more schooling. | PW | Review target group and action plans | Jan 2008 | Pat Matson Peter McNamara | Reduction in numbers missing 25 days or more school to national average. |
|  |  | Review action plans for each child at risk | Jan 2008 | Pat Matson |  |
|  |  | Establish monthly progress monitoring | Immediate & ongoing | Pat Matson Peter McNamara |  |
| Positive Contribution |  |  |  |  |  |
| Develop systems to routinely seek the views of children and young people and to determine the range of activities they have used. | PG/FM | Develop Youth Participation Strategy for the council and its partners. | April 2008 | Cath Connor | Participation Strategy approved and adopted by Lead Member and CMT. |
|  |  | Develop a structure for Youth Forums across the city and for a Youth cabinet | December 2008 | Cath Connor | Youth forums and Youth Cabinet in place and functioning effectively. |
| Reduce the number of first time entrants to the youth justice system | FM | Use FTE analyses tool to inform service delivery | Feb 08 | Tom Healy/ Pauline Copeland | Analyses of salient risk factors which lead to entry |
|  |  | Set up YISP implementation group | March 08 | Brenda Lee/ Pauline Copeland | YISP being operated consistently across the 8 Neighbourhood management areas |
|  |  | Develop working relationship with LPDG to increase the effectiveness of YISP | March 08 | Tom Healy/Pauline Copeland | Increased levels of appropriate referrals |
|  |  | Develop TOP's programme for primary schools | March 08 | Pauline Copeland | Reduction in FTE's |
|  |  | Ensure that at least 20% of YISP cases receive a parenting intervention | March 08 | John Gill/ Pauline Copeland | Reduction in FTE's |
| Economic Wellbeing |  |  |  |  |  |
| Continue to increase the proportions of young people in education, employment or training post-16. | FM | NEET reduction to be priority for the 13-19 strategy. | July 2008 | Faith Mann | NEET figure to continue to reduce target is 7.0 % by Nov 2008. |
|  |  | Utilise new funding streams (LIDF and ESF) to commission pieces of work aimed at NEET reduction. | Jan 2008- onwards | Faith Mann |  |
|  |  | Revise tender specification for Connexions service and put Connexions service out to tender. | 2008-2009 | Faith Mann |  |
| Continue to improve educational outcomes post-16, including in English and mathematics | FM | Establish this as a priority in 13-19 strategy. | July 2008 |  |  |
| . |  | Work closely with colleges and LSC to address curriculum needs in relation to this target. | 2008-09 |  |  |