SALFORD YOUTH SERVICE

POST-OFSTED IMPROVEMENT PLAN

Objectives for Improvement

- To support young people’s achievement by creating appropriate opportunities for high quality informal learning

- To increase young people’s participation at all levels within the Youth service Including attendance and the planning and evaluation of provision

- To achieve a high quality of youth work practice

- To increase the efficiency of the service

- To ensure the safety of young people engaging with the Youth Service

Objective 1	To support young people’s achievement by creating appropriate opportunities for high quality informal learning

| Performance Indicators | Baseline 2004-05 | Target 2005-06 | Target 2006-07 |
| --- | --- | --- | --- |
| Increase the % of young people aged 13-19 gaining recorded outcomes |  |  |  |
| Increase the % of young people aged 13-19 gaining accredited outcomes |  |  |  |

Performance Improvement Plan

| Weakness Identified | Actions | End date | Lead responsibility | Resource implications | Progress | Action outstanding |
| --- | --- | --- | --- | --- | --- | --- |
| Young people's achievement is unsatisfactory in too many sessions | Hold awareness-raising days for staff leading to production of action plans for raising achievement incorporated into Unit Development Plans. | 01/09/2005 | AYO Partnerships and Projects |  | Level 3s meeting 25th July; Accreditation group meeting 1/9/05 then monthly |  |
|  | Establish a consistent system for recognising young people's achievement where appropriate via local certificates etc. | end September 2005 | AYO Partnerships and Projects |  | Local certificate template drafted; shared at meeting 25/7; agreed at accreditation meeting and is already being used | Local certificate to be distributed to staff and to be used by them |
|  | Train staff to use system for recognising and recording young people's achievement via use of local certificates etc | end September 2005 | AYO Partnerships and Projects |  | Agenda item for 25/7 [start of ongoing process] and repeated with accreditation group 1/9 |  |
| Weakness Identified | Actions | End date | Lead responsibility | Resource implications | Progress | Action outstanding |
|  | Set targets for achievement for each unit | 01/09/2005 | AYO Partnerships and Projects |  | Accreditation panel identified [this becomes an agenda item for their first meeting] |  |
| Accreditation does not effectively underpin young people's learning | Identify relevant accredited pathways for Youth Service provision | end August 2005 | AYO Partnerships and Projects | £5,000 | Action completed |  |
|  | Identify staff to pilot new accreditation e.g. YAA, AQA | end September 2005 | AYO Partnerships and Projects |  | Youth achievement training 19/8, initially for level 3s+ accreditation level 2s - AQA training booked for 28/9 |  |
|  | Produce training plan to implement and embed the use of accreditation across the service | end November 2005 | AYO Quality & Workforce development |  | Youth achievement training 19th August, initially for level 3s+ accreditation level 2s- |  |
|  | Set targets for accreditation for each unit, linked to Individual Progress Plan | Sep-05 | AYO Partnerships and Projects |  |  |  |
|  | Identify Accreditation champion in each Neighbourhood Management area | end July 2005 | AYO Partnerships and Projects |  | Action completed |  |
| The management of the curriculum is inadequate and the curriculum framework does not provide sufficient guidance to staff | Produce revised curriculum framework based on an analysis of need and the views of young people. | end September 2005 | SMT |  |  |  |
|  | Produce training plan to implement and embed the curriculum framework across the service | Oct-05 | AYO Quality and Workforce development |  | Training group working on plan. |  |
|  | Produce a bank of tried and tested resources and examples of good practice to be kept in each centre/project. | Sep-05 | AYO Operations | £1,000 | Resources requested from staff have now been received | Resources will be collated in Sept and other resources purchased as per SMT mtg 22/8 |
|  | Develop policy for allocation of resources to centres/projects | Feb-06 | SMT |  |  |  |

Objective 2 	To increase young people’s participation at all levels within the Youth Service including attendance and the planning and evaluation of provision

| Performance Indicators | Baseline 2004-05 | Target 2005-06 | Target 2006-07 |
| --- | --- | --- | --- |
| Increase the % of young people aged 13-19 participating in Youth Service provision |  |  |  |
| Increase the number of participants from vulnerable groups (e.g. NEET, at risk of offending, at risk of drugs, alcohol or substance abuse etc) |  |  |  |
| Monitor the % of young people aged 19-25 who take part in Youth Service provision focused around supported housing, homelessness, young parenthood, unemployment, disability and other specific needs, and measure outcomes. |  |  |  |
| Monitor the % of 11-13 year old young people who take part in Youth Service provision, in areas where it is deemed that work with this age group is essential as a foundation for work with older young people, and measure outcomes. |  |  |  |

Performance Improvement Plan

| Weakness Identified | Actions | End date | Lead responsibility | Resource implications | Progress | Action outstanding |
| --- | --- | --- | --- | --- | --- | --- |
| Low attendance | Devise a "membership" pack informing young people of the benefits of participation and encouraging active involvement | end November 2005 | AYO Partnerships and Projects |  | Participation pathway explored at SMT and shared with operational team - responses by 2/9/05 [next step to take to young people] |  |
|  | Develop a marketing strategy for the Service, utilising different media and methods for raising awareness of the Service amongst young people and increasing recruitment of young people. | Jan-06 | AYO Partnerships & Projects |  | What now - meet with, share with SMT, also meeting Jeff Millington about corporate image etc 19/7. Meeting with Masha Vitali plus What Now publication - agreed to purchase |  |
| Weakness Identified | Actions | End date | Lead responsibility | Resource implications | Progress | Action outstanding |
|  | Establish working group to explore how membership can be defined and recorded in relation to detached work, and how young people involved with detached work can link into Area Fora and City 2000. | Sep-05 | AYO Partnerships & Projects |  | Accreditation group to explore as membership linked to participation and membership - meeting agenda item 1/9/05 |  |
|  | Identify a member of staff in each centre/project to be the "champion" for participation and link to City 2000 | Jul-05 | Level 3 staff |  | Discussed with staff at operational meeting and supervision |  |
|  | Provide training as necessary to staff to support staff in increasing participation levels. | Sep-05 | AYO Quality & Workforce Development | £3,000 | Training group working on plan |  |
|  | Establish flow from members' committees or fora to membership of City 2000 | Feb-06 | AYO Partnerships and Projects |  | Participation pathway blueprint with operational team - awaiting response by 2/9/05 |  |
|  | Explore possibility of Area Fora, linked to Neighbourhood Management and to City 2000 | Feb-06 | AYO Partnerships and Projects |  | Explored at SMT, next step city 2k to explore - as above, blueprint agreed with operations manager |  |
|  | Membership/participation targets for the Service, based on local ward date to be agreed with level 3 staff. | Sep-05 | AYO Operations/Level 3 workers |  | Work done on identifying geographical targets | Needs to be refined in Sept. |
|  | Progress towards targets to be monitored and reported on a monthly basis. | Ongoing | Level 3 staff |  |  |  |
|  | Review membership fees across the service | Initial report to Lead member September 2005 | AYO Operations/Level 3 workers | £4,000 for swipe cards | Discussions with young people and staff have been held | 25p (members) and 35p (non-members) suggested |
| Young people are insufficiently involved in negotiating targets for their own learning | Pilot Individual Progress Plan for each young person in a given project/unit, to be negotiated with the individual and reviewed regularly with young people. | end October 2005 | AYO Partnerships and Projects |  | Agenda item for level 3 meeting already outlined. Joyce meeting Danny Bentham to collect and process forms to date. Evidence taken to Accreditation group and August staff meeting - ongoing and done |  |
|  | Individual Progress Plan to be rolled out across the service following evaluation of the pilot | Nov-05 | AYO Partnerships and Projects |  | Analysed in accreditation group meeting, 1/9/05 |  |
| Young people are insufficiently involved in negotiating, planning and evaluating the curriculum | Members’ committee/forum to be established in each centre/project and to be involved in quarterly QIG meetings | Dec -05 | Level 3 staff |  |  |  |

Objective 3 	To achieve a high quality of youth work practice

| Performance Indicators | Baseline 2004-05 | Target 2005-06 | Target 2006-07 |
| --- | --- | --- | --- |
| Increase the number of sessional staff who are qualified to national standards. |  |  |  |
| Produce a revised quality assurance document that is fit for purpose and meets the requirements of JAR. | QA document last revised 2000 | Revised QA document to be produced | QA document and processes to be reviewed annually |

Performance Improvement Plan

| Weakness Identified | Actions | End date | Lead responsibility | Resource implications | Progress | Action outstanding |
| --- | --- | --- | --- | --- | --- | --- |
| The quality of youth work practice is unsatisfactory in too many sessions | Produce revised Quality Assurance document | end September 2005 | AYO Quality & Workforce development |  | Audit of skills and staff needs devised. To be undertaken with staff in Sept. |  |
|  | Produce training plan to implement and embed the QA document across the service | early December 2005 | AYO Quality & Workforce Development |  | Training group working on plan. | Needs assessment model agreed / implemented |
|  | Set up Quality Improvement Group, to meet quarterly | Dec-05 | AYO Quality and Workforce development |  |  | Names to be agreed and contacted |
|  | SMT to visit and sample provision as part of the QA process using OFSTED framework for inspection | ongoing - to begin July 2005 | All SMT |  | Calendar circulated | Calendar dates to be specific and preparation session on Sept 9th completed |
|  | Develop a programme of events to bring workers together to share good practice | Sep-05 | Level 3 staff | £10,000 | WAD and YWW wkg groups meeting. 5 events at up to £2000 each | ?!WW and 2 others to be agreed |
|  | All staff to have regular supervision and annual appraisal, using the Directorate appraisal model | All appraisals to be completed by December 2005 | All SMT |  | Appraisals have begun |  |
| Weakness Identified | Actions | End date | Lead responsibility | Resource implications | Progress | Action outstanding |
|  | Monitor supervision and appraisal and keep guidelines under review | Ongoing | SMT |  |  |  |
|  | Produce standard session plan and evaluation format, to be used by all staff and to be compatible with MIS | Sep-05 | AYO Quality & Workforce Development |  | Standard session plan has been drafted | Standard session plan to be piloted by staff; evaluation of session plan to be completed by 21st Sept |
|  | All staff to produce session plans and sessional evaluation to an agreed format | Oct-05 | Level 3 workers |  |  | Agreed model to be drafted and distributed |
|  | Produce standards for format and quality of reports to ensure consistency of presentation and analysis. | Oct-05 | AYO Quality & Workforce Development |  |  | Format to be decided on |
|  | Policies and Guidelines to be brought up to date and distributed to all staff | Sep-05 | SMT |  | Work on policies and guidelines begun |  |
| A high proportion of sessional staff are unqualified and the training opportunities for them are inadequate | Buy in appropriate training course leading to NVQ award in Youth Work for sessional staff | Oct 05 | AYO Quality and Workforce development | £20,000 | Training to begin September for 24 staff – completion in 12 months |  |
|  | Secure AI training for internal staff | End June 2005 | AYO Quality and Workforce development |  | All management team and JNC3s undertaking training on 13/14th Sept |  |
|  | Begin delivery of rolling programme of in-house training leading to NVQ award in Youth Work for sessional staff | Begins July 2005 | AYO Quality and Workforce Development |  | System in place and timetable on line |  |
|  | Develop training plan for service based on service needs and feed back from appraisal | Oct 05 | AYO Quality and Workforce Development |  | Training group working on plan; training needs analysis questionnaire developed | Questionnaire to be completed with staff by line managers |

Objective 4  	To increase the efficiency of the service

Performance Improvement Plan

| Weakness Identified | Actions | End date | Lead responsibility | Resource implications | Progress | Action outstanding |
| --- | --- | --- | --- | --- | --- | --- |
| The systems for recording young people’s learning are insufficiently developed | Youth base database (MIS) from NYA to be implemented and operational | end December 2005 | AYO Quality and Workforce development | £5,000 | Systems agreed. Discs for system to be bought/installed in Sept; training for staff in Sept | Decision on Youthbase IT lead worker to be made |
|  | Evaluate likely impact of MIS on administrative support with the service and review allocation of resources accordingly | end December 2005 | SMT |  | Youthbase online for piloting - Dec |  |
|  | All achievements and outcomes, both incremental and lateral, to be recorded on MIS database | Jan-06 | Level 3 workers |  | Youthbase online for piloting – Oct/Dec |  |
|  | Establish a system for recording and monitoring young people’s progress in accredited and non-accredited pathways for all units, linked to new MIS | end October 2005 | AYO Partnerships and Projects |  | Action completed |  |
|  | Train staff to use new system for recording and monitoring achievement | end October 2005 | AYO Partnerships and Projects |  |  | Dates for training to be agreed with consultant and staff |
| High ratio of staff to young people means that some staff are inappropriately deployed | Agree targets for engagement with young people with each Unit, based on risk assessment, nature of programmes etc and revise deployment of staff accordingly | Dec-05 | AYO Operations |  | Initial figures from 2001 Census considered and outcomes being explored by Operational team | To be completed |
|  | Clarify how contacts with young people are to be recorded and ensure that this is being consistently understood and applied by staff | Sep-05 | SMT |  |  |  |

| Weakness Identified | Actions | End date | Lead responsibility | Resource implications | Progress | Action outstanding |
| --- | --- | --- | --- | --- | --- | --- |
| Service management has failed to address key issues and implement key developments | Produce a 3 year strategic development plan for the Service which clearly responds to current and foreseeable issues facing the Youth Service and ensure that this is understood and supported by all staff | Apr-06 | PYO |  |  |  |
| Target setting, monitoring and reviewing are weak | Contacts to be reported on a monthly basis in order to inform local and service planning. | Sep-05 | All staff |  |  |  |
|  | Progress towards achievement of all service targets to be monitored on a monthly basis | Sep-05 | SMT |  |  |  |
| The service has no overall needs assessment to assist the planning of provision | Customer satisfaction survey to be carried out - to ask users of the service what they want from the service | Analysis of findings by mid October 2005 | AYO Operations | £2,500 for both this survey and the following one | 2 meetings with staff and young people have made decisions re how to do | Draft to young people beg Sept |
|  | Survey of non-users to be carried out, to find out what would make the service more attractive to them | Analysis of findings by mid November 2005 | AYO Operations |  | 2 meetings with staff and young people have made decisions re how to do | Draft to young people beg Sept |
|  | Hold regular meetings with Neighbourhood Management team to assess changes in pattern and level of needs in order to assist service planning | Ongoing | AYO Operations |  | Exploring Options with D Martin |  |
| Priority groups of the service are not sufficiently identified | Identify priority groups for the service and secure Cabinet approval for this prioritisation | Oct 05 | SMT |  |  |  |

Objective 5 	To ensure the safety of young people engaging with the Youth Service

| Performance Indicators | Baseline 2004-05 | Target 2005-06 | Target 2006-07 |
| --- | --- | --- | --- |
| Increase the number of staff who have accessed child protection training |  |  |  |
| Increase the number of staff who have been CRB checked within the past 3 years |  |  |  |

Performance Improvement Plan

| Weakness Identified | Actions | End date | Lead responsibility | Resource implications | Progress | Action outstanding |
| --- | --- | --- | --- | --- | --- | --- |
| Arrangements to safeguard young people are inadequate - | Explore the issue of CRB checks with Personnel in order to secure improvement | Sep-05 | AD | Appx £4,000 | Agreed that all staff who have been with the Service more than 2 years to be re-checked and 3 year rolling programme of checks to be established. |  |
|  | Ensure that guidelines on how to deal with child protection issues are available and accessible to all units | Jul-05 | SMT |  |  |  |
|  | Provide child protection training to staff across the service | Sep-05 | AYO Quality and Workforce development |  | To be delivered to all service – Oct/Jan online | Booklets to be distributed to all staff in the interim |
| Much of the accommodation is unfit for purpose | Produce a premises review paper for Lead member based on findings from discussions with political executives. | July 05 | AYO Operations |  | Discussed with level 3s | Discover dates of pol execs and visit to update. |