REPORT OF THE STRATEGIC DIRECTOR OF HOUSING AND PLANNING

TO THE LEAD MEMBER FOR PLANNING

ON 26th March 2007

____________________________________________________________________

TITLE: MONTON SPEED MANAGEMENT SCHEME PHASE 2

____________________________________________________________________

RECOMMENDATIONS:

That consideration be given to the acceptance of a quotation in the sum of £201,017.23 from Tarmac Ltd to carry out Phase 2 of the construction of traffic calming measures on Monton Road and Half Edge Lane.

____________________________________________________________________

EXECUTIVE SUMMARY: The purpose of this report is to seek the authority to accept the quotation from Tarmac Ltd in the sum of £201,017.23 to carry out  the construction of traffic calming measures on Monton Road and  Half Edge Lane.

____________________________________________________________________

BACKGROUND DOCUMENTS:

(Available for public inspection)

Report to Lead Member for Planning 30th January 2006

Report to Lead Member for Planning 10th April 2006

Report to Lead Member for Planning 23rd October 2006

____________________________________________________________________

ASSESSMENT OF RISK: Low

____________________________________________________________________

SOURCE OF FUNDING: Block 3 Transport Capital Programme

____________________________________________________________________

LEGAL IMPLICATIONS: Provided by: N/A

____________________________________________________________________

FINANCIAL IMPLICATIONS: Provided by Nigel Dickens: Funded from 2007/2008 Block 3 Highways Capital budget

____________________________________________________________________

## COMMUNICATION IMPLICATIONS: N/A

____________________________________________________________________________

VALUE FOR MONEY IMPLICATIONS: N/A

___________________________________________________________________________

_________________________________________________________________________

CLIENT IMPLICATIONS: Darren Findley: Scheme to be accounted for in 2007/2008 Block 3 Highways Capital Programme

_________________________________________________________________________

PROPERTY: N/A

___________________________________________________________________

HUMAN RESOURCES: N/A

___________________________________________________________________

CONTACT OFFICER: John Pedder – Tel 0161 779 4884

___________________________________________________________________

WARD(S) TO WHICH REPORT RELATE(S): Eccles

___________________________________________________________________

KEY COUNCIL POLICIES: Community Safety

___________________________________________________________________

DETAILS: (Continued overleaf)

_________________________________________________________________________

BACKGROUND

- Proposals for a speed management scheme were put forward to the Traffic Management unit on 29th June 2005.

- The route has been identified as having a high number of casualties especially involving vulnerable road users.

- Public consultations have been carried out in January 2005 and September 2005.

- The consultations included discussions with various Residents Associations.

- The proposals were approved for advertising by Lead Member for Planning on 30th January 2006.

- At the meeting of the Lead Member on 10th April 2006 approval was given to the Transport Capital Expenditure for 2006 / 2007.

- Included in the programme is an allocation for the Monton Speed Management Scheme.

- In accordance with the Rethinking Construction Framework Agreement, the scheme has been allocated to Tarmac Ltd who have provided a quotation for Phase 2 based on a Target Price form of contract.

  - Phase 1 of the scheme of the scheme was carried out by Tarmac in November 2006.

### DETAILS

- The scheme was split into two phases, the first of which was carried out concurrently with the Worsley Road Resurfacing Scheme without having an adverse effect on the resultant traffic flows.

- The first phase comprised:

Clarendon Road

- Raised junction plateaux at either end

- 2 sets of speed cushions

Monton Road / Half Edge Lane

- Signing works

Retexturing the carriageway to improve skid resistance at various locations

  - The second phase comprises:

- Mini roundabout at junction of Albert Road and Half Edge Lane

- Mini roundabout at junction of Wellington Road and Monton Road

- 2 no full width raised plateaux on Monton Road at its junctions with Hawthorn Avenue and Francis Street

- New puffin crossing on Monton Road between Monton Avenue and Stafford Road

- Reconstruction of zebra crossing west of Clarendon Road so that it is placed on a raised plateau

- Cutting back of foliage on Monton Road between Wellington Road and Cavendish road to improve street lighting

### FINANCIAL IMPLICATIONS AND RECOMMENDATIONS

    - The cost summary for Phase 2 of the scheme is as follows:

| Works | £198,010.35 |
| --- | --- |
| Statutory Undertakers Diversions and Electrical Connections | £8,248.86 |
| Fees | £23,032.00 |
|  | £229,291.21 |

- A fuller breakdown of the cost of the scheme is shown on the tender Approval Pro Forma which is attached to this report

- The scheme will be funded from the Block 3 Transport capital Programme 2007 /2008

### CONCLUSION

- Implementation of this scheme will improve highway safety for pedestrians and help reduce the number of accidents within the coverage of the scheme.

#### Malcolm Sykes

#### Strategic Director For Housing and Planning

# TENDER APPROVAL - PROFORMA

For use in seeking the approval of the Lead Member for Customer and Support Services to proceed with a Capital proposal

| REPORT TO LEAD MEMBER FOR CUSTOMER AND SUPPORT SERVICES |
| --- |
| Title of Scheme : Monton Speed Management Phase 2 |
| Recommendations (please append report to your service Lead Member) |
| Scheme Details (please append report to your service Lead Member) |
| Tender Details (please append report to your service Lead Member) |
| Estimated - Start Date : March 2007 Estimated - End Date : July 2007 |
| FINANCIAL DETAILS |
| Recommended Tenderer : Tarmac Ltd. Tender Cost (quotation) : £198,010.35 |
| Breakdown of Scheme Cost : | 05/06 £000‘s | 06/07 £000‘s | 07/08 £000‘s | Later £000‘s | Total £000‘s |
| Contract |  |  | 201 | - | 201 |
| Fees |  |  | 21 | 2 | 23 |
| Other (Specify) Service Diversions |  |  | 8 | - | 8 |
| Total Cost |  |  | 230 | 2 | 232 |
| Phasing of Expenditure (£000‘s) |
|  | Apr | May | June | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar |
| This Year |  |  |  |  |  |  |  |  |  |  |  |  |
| Next Year | 50 | 50 | 43 | 40 | 47 |  |  |  |  |  |  |  |
| Following Year |  |  |  |  | 2 |  |  |  |  |  |  |  |
| Note : The monthly cash flow above should be consistent with the contract start and end dates shown above and should allow for normal time lapses which will occur between work being done, claimed for, certified and paid, as well as retentions. Please consult your Capital Accountant if you need assistance with this or any other part of this proforma. |
| Is Scheme In The Current Approved Capital Programme ? Yes / No Yes |
| Funding Identified : | 05/06 £000‘s | 06/07 £000‘s | 07/08 £000‘s | Later £000‘s | Total £000‘s |
| Supported Borrowing |  |  | 230 | 2 | 232 |
| Unsupported Borrowing (see note 1) |  |  |  |  |  |
| Grant (Specify) DfT Grant Specific |  |  |  |  |  |
| Capital Receipts |  |  |  |  |  |
| Other (Specify) |  |  |  |  |  |
| Total |  |  | 230 | 2 | 232 |

#### REVENUE IMPLICATIONS

Are there any revenue implications of this proposal ? No If Yes, please complete the table below Are there any other financial implications

| Details | Budget Code | Part Year | Full Year |
| --- | --- | --- | --- |
|  |  | £ | £ |
| Estimated Cost |  |  |  |
| Staffing (please specify) : |  |  |  |
| Other Running Costs (please specify) : |  |  |  |
| Capital Financing Costs (see Note 1 below - only to be completed where the use of unsupported borrowing is planned) |  |  |  |
| Total Estimated Cost |  |  |  |
| To be met from : |  |  |  |
| Total Funding/Income |  |  |  |
| Net Revenue Cost/(Saving) |  |  |  |

Note 1 : If unsupported borrowing is to be used, capital financing costs can be provided by your Accountant and you should show in the table how revenue savings can be made to fund these costs. Please consult your Accountant if you need assistance with completing this or any other part of this form.

Decision of Lead Member Customer and Support Services Approved/Not Approved

# Text boxes

Part 1 ( Open to The Public)

ITEM NO 8