REPORT TO CUSTOMER AND SUPPORT SERVICES LEAD MEMBER

9TH February 2009

###### Budget Monitoring 2008/09

This report is to update the Lead Member on the position at the 31st January 2009 relating to the directorate’s revenue budget.

The position in relation to employee costs (including overtime and agency costs) is as follows: -

| Division | Budget | Actual | Variance |
| --- | --- | --- | --- |
|  | April - Jan 2008 | April – Jan 2008 | (-) under/(+) over |
|  | £000 | £000 | £000 |
| Finance | 6151 | 6108 | -43 |
| ICT Services | 3794 | 3709 | -85 |
| Customer Services | 6706 | 6666 | -40 |
| Law & Admin | 3627 | 3626 | -1 |
| HR | 3107 | 3029 | -78 |
| Misc. Finance | 110 | 109 | -1 |
| Total | 23495 | 23247 | -248 |

A projection of salaries to 31st March (based on actual to date and a projection of October salaries, November includes all back pay) shows an overall under spend of £249k

| Division | Budget April - March 2008 | Actual April – Jan 2008 | Projection to 31st March 2009 | Variance (-) under/(+) over |
| --- | --- | --- | --- | --- |
|  | £000 | £000 | £000 | £000 |
| Finance | 7382 | 6108 | 7329 | -53 |
| ICT Services | 4554 | 3709 | 4457 | -97 |
| Customer Services | 8059 | 6666 | 7999 | -60 |
| Law & Admin | 4352 | 3626 | 4348 | -4 |
| HR | 3713 | 3029 | 3633 | -80 |
| Misc. Finance | 132 | 109 | 131 | -1 |
| Total | 28192 | 23247 | 27897 | -295 |

Summary of the significant issues that have an impact on the budget and how they can be funded

| Budget issues | 2008/09 |
| --- | --- |
|  | £000 |
| ICT in the Community | 70 |
| ICT Sprint training income reducing | 20 |
| Home working ongoing costs | 98 |
| Advice team – reduced income | 70 |
| Reduced income from land charges | 400 |
| Loss of services/ reduction in service to all External companies Customer Services – Call Centre Law & Administration – Procurement - Out of Hours service | 130 8 18 |
| HRA SLA reduction | 250 |
| Loss of legal services income from GMPA | 20 |
| Overspend on HR training programme | 50 |
| Reduction in printing income and cost overspend | 80 |
| Total | 1214 |
| Funded by |  |
| Under spend on salaries | 295 |
| Additional income from sale of service to all External Services ICT Service SAP/Payroll | 119 35 |
| Additional court cost income | 450 |
| Underspend on Gateway budget allocation | 100 |
| Increment budget | 200 |
| Total | 1199 |
| Overall deficit | 15 |

2008/09

Based on the above projection expenditure should be contained within the directorate budget for the year providing that strict control continues to be applied to the filling of vacancies and all non essential expenditure.

Note

Contribution to the TIF referendum of £200k will be charged to the directorate but is expected to be funded corporately.

Irene Topping

5/02/08