|  | PART I (OPEN TO THE PUBLIC) | ITEM NO. |
| --- | --- | --- |

REPORT OF THE HEAD OF LAW AND ADMINISTRATION

TO LEAD MEMBER BRIEFING MEETING ON 18th OCTOBER 2004

TITLE : Procurement Strategy (draft): update on progress.

RECOMMENDATIONS : That the meeting note the progress made to date on the formulation of the Procurement Strategy and the further action required prior to the Strategy’s adoption and implementation.

EXECUTIVE SUMMARY : It is a requirement for all authorities to produce, and regularly update a procurement strategy. The draft represents the current, updated version, which identifies procurement policy and projected activity for the period 1 April 2005 to 31 March 2006. It includes an action plan and procurement plan, both of which will be developed and expanded during the implementation of the Strategy.

BACKGROUND DOCUMENTS : (available for public inspection) Procurement Strategy (Draft) 2005 / 2006

ASSESSMENT OF RISK : There is a high risk of a negative effect on the City Council’s CPA rating if an effective procurement strategy is not in place. There is a high risk of loss of benefits from a co-ordinated approach to procurement. There is a risk that key policies (e.g., SME and Third Sector Enterprise development) will suffer without effective procurement to support them.

SOURCES OF FUNDING : Not applicable

LEGAL ADVICE OBTAINED : Alan R. Eastwood, Head of Law & Administration

FINANCIAL ADVICE OBTAINED : Not applicable

CONTACT OFFICER : Alan R. Eastwood, Head of Law & Administration (0161) 793 3000 Gary Amos, Assistant Director (Procurement) (0161) 793 3878

WARD(S) TO WHICH REPORT RELATE(S) : All

KEY COUNCIL POLICIES : All

DETAILS Work completed: Draft Procurement Strategy (including action plan and procurement plan). Procurement Guidance Notes produced (though these will be expanded and modified). Savings plan drafted (also included in ‘Think Efficiency’ exercise). Procurement questionnaire issued. Vision statement drafted. S.L.A. drafted. Links established with Regional Centre of Procurement Excellence. Link established with Salford P.C.T. Work in progress: Resource plan being developed for the establishment of the Procurement Co-ordination section. Training and briefing information being compiled. Inter-authority work teams being formed to support the actions of the Regional Centre for Procurement excellence. Work to be undertaken: Procurement Board and Procurement Officers’ Forum to be established to manage and implement the Procurement Strategy. Spend analysis to be undertaken. Responses to the procurement questionnaire to be analysed. Procurement plan to be completed Procurement Co-ordination section to be established.