Salford City Council

“SCC’s Corporate Approach to delivering the Employment Plan”

## Corporate Employability Action Plan (2006 – 2007)

| No. | Priority | Description | Key Actions | Deadline/Progress | Lead |
| --- | --- | --- | --- | --- | --- |
| 1. | Develop a joint Information / performance management system to inform planning and targeting of services to the community. | Investigate corporate approach to GIS (Geographical Information System). | Agree corporate approach. | Corporate mapping initiative – GIS being under taken. The council is nine months into a twelve month initiative that will; establish a spatial data dictionary and repository of ‘fit-for-purpose’ data, implement an intranet mapping system for data sharing, and provide an internet mapping system for informing and interacting with the public. A supplier has been selected (CadCorp Ltd) and work commissioned which will: Give all users simplified access to complex data Provide a new and powerful method interaction with the public Increase data sharing Improve services Implementing Electronic Government objectives Enhance CRM for non-address based reports/requests (Phase II) Reduce the Freedom of Information burden Allow the map visualisation of address based data Combine of disparate data sets Assist in the identification of cause and effect Driving the initiative forward, Paul Coward, Corporate GIS Consultant Customer and Support Services Directorate ICT Services Division E-Government Services Section. Developments: Development of Intranet and Internet systems commissioned for implementation in June and July 2006 Initial data sets for web-mapping systems identified Data Audit under way to determine quantity and quality of spatial data Shared Spatial Data Warehouse commissioned for implementation in July Timescales Phase 1 webGIS rollout in June/July with Phase II (Additional data and functionality) in August/September 2006 Spatial Data Warehouse to be implemented in July 2006 after which incremental population can begin by all directorates September 2006 everything in place by then to be handed over to a new member of staff with GIS responsibilities. | Paul Coward ICT, Customer & Support Services |
|  |  | Need to gain corporate “buy-in” – system dependant upon what info is input. | Establish Funding requirements. Look at costs to implement and operate a corporate GIS. Investigate funding of GIS via top slicing across directorates | Paul Coward working on this with Dave Hunter. Developments: Presented to Corporate ICT Board, Elected Members Technical Group, Neighbourhood Managers and Urban Vision Management Team. Ongoing dialogue with; existing user community; Capita (Urban Vision); Corporate ICT Board; and ICT staff involved with other potentially related projects. | Customer & Support Services |
|  |  | Development of ward profiles | Ward profiles will be developed which will give an overview of key stats, performance information and consultation results on a ward by ward basis | Paper based ward profiles will be made available during July 2006. Following that work will begin in ensuring that the internet/intranet based information portal delivers all the information available in the ward profiles. | Alan Tomlinson |
|  |  | Development of Salford City Council Research Strategy |  | July 2006 | Alan Tomlinson |
| 2 | Raise profile of employability agenda. | Employability agenda needs to be “championed” corporately at a senior level. | Nominate Directorate Employability Champions | Directors Team considered this on 18th May 2006 | Chief Executive & Directors |
|  |  |  | Consider if Employability should become a Cabinet Work Plan Priority | Directors Team considered this on 18th May 2006 will be available at the Scrutiny meeting | Chief Executive & Directors |
|  |  |  | Consider Employability as a core element on the Balanced Score Card, which each directorate would need to address | Directors Team considered this on 18th May 2006 | Chief Executive & Directors |
|  |  |  | Commitment to development of a Cabinet Work Group | Directors Team considered this on 18th May 2006 | Chief Executive & Directors |
| 3 | Improve Access to SCC Employability Services | Potential co-location/joining-up of employability services. | Commitment to corporate approach to commissioning /location of services e.g. Jobshop service, Children’s Centres Libraries, 1-stop-shops, Supported Employment Centres | ED/Children’s Services/ Community Health and Social Care to consider scope for joint delivery/co-location of complimentary services. Mapping of existing and planned locations required, followed by joint planning meeting. | Chief Executive & Directors |
|  |  | Develop Web based and telephone access to Information and services for Employment, Learning & Skills | Use “Think Employability” as vehicle for delivery Review & re-launch Employability Web pages Pilot 1 telephone number for Employment, Learning & Skills Provision | Think Employability is on the Service Improvement Agenda An Action Plan has been drafted detailing timeframes for both Web Access and phone pilot | ED (Emily Kynes) & Customer & Support Services (Richard Cohen) |
|  |  | Improve Co-ordination of Work Placements across SCC | Consider either extension of Business education Partnership (BEP) Contract with Salford Foundation, or extension of role for HR to Co-ordinate ALL SCC placements (provide a single point of contact) | Directors Team considered this on 18th May 2006 | Chief Executive & Directors |
| 4 | Improve communications and understanding of internal structures and responsibilities to enable close partnership working around the employability agenda. | Raise Inter agency / department awareness. | Improve access to information via Intranet / Website & Ensure links to partners | This will be addressed via Think Employability Project described above. | ED (Emily Kynes) & Customer & Support Services (Richard Cohen) |
|  |  | Consider pooling of resources/Joint working | Coordinate / join up Action Plans and undertake joint bids for external funding e.g. ESF. | Salford’s Economic Development Forum and Salford Lifelong Learning Partnership have now merged (Salford Economic Development, Learning & Skills Partnership). The EDSLP should seek to co-ordinate/endorse bids for Employment, Learning & Skills projects in Salford. Directors to consider & advise on internal/cross directorate pooling /alignment of resources | EDLSP Chief Executive & Directors |
|  |  | Commitment to ongoing communications & joint working | Develop Joint Action Learning Set. Action Learning Sets – cross directorate representation by officers, specific tasks / challenge to be set | Directors to consider scope of a Joint Action Learning Set NB. Note relationship with ‘Transform Network’ established at last Directors Team meeting. | Chief Executive & Directors |
| 5. | Raise the profile of opportunities, activities & achievement Salford | Develop Co-ordinated Communications Strategy for Employability Agenda | Promote good practice Raise aspirations of citizens Celebrate achievements Raise awareness of opportunities | Directors to nominate Marketing & Communications representative to Corporate Employability Group | Chief Executive & Directors |
|  |  | Raise profile of agenda with Senior Manager and gain buy-in to plans | Take Corporate Employability Action Plan to Leadership Road show | Directors Team considered this on 18th May 2006 | Chief Executive |
|  |  | Consider Annual Salford Employment, Learning & Skills celebration SCC/ Partnership event | Annual celebration of achievements to recognise Employers, trainees & Learners Certificates / Awards to be presented for achievements and good practice | Directors Team considered this on 18th May 2006 | ED to Lead |
| 6. | Recruitment practices to foster wider access into employment within the City Council. | Develop role of SCC as an exemplar Employer and work with other Public sector partners to rollout joint initiatives | Deliver on SCC as Employer Action Plan Continue to input to Public Sector Employers Group | SCC as an Employer Plan endorsed at Strategy and Regeneration Scrutiny Committee 01.11.04 SCC as an Employer Progress report to Customer Services Scrutiny Committee on 25th April 2005 Further reports on a quarterly basis. SCC as an Employer Group and Public Sector as an Employer Group now merged and called Public Sector Employers Group Public Sector Employers Action Plan agreed at Public Sector Away Day held Jan 05. First Action from Plan Public Sector – Jobs In Salford recruitment event held on 13th September 2005. SCC as an Employer Group and Public Sector as an Employer Group now merged and called Public Sector Employers Group. Group has now not met since September 2005 – Question whether it should continue as a ‘standing’ group or brought together for particular initiatives? LSP has agreed to convene a meeting of the Public Sector group to agree new priorities & joint strategies | HR LSP |
|  |  | SCC HR Review and HR team to embrace employability agenda, with support from ED and other directorates | Roll out of Options tool kit approach to SCC recruitment and selection. | Options launched. -September 2005 Review of Recruitment & Selection Code of Practice to include ‘Options’ and provide practical advice and steps for recruiting a more diverse workforce. Complete by 31st July 2006. Programme of training for managers on new processes etc. from September 2006 to March 2007 Now embedded within First Line Managers Training | HR |
|  |  | Corporate employment/ engagement target groups to be set | Consider setting new/additional “Diversity/Inclusion” targets by directorate. Key target groups e.g. local people, BME, disabled, people on IB., ex-offenders, people aged 50+, children leaving care, people with learning difficulties etc. | Individual Directorate targets for BVPI groups have been set and are reviewed at QPEs and Director’s Performance Quarterly. Consider whether additional targets need to be set for groups not included in BVPIs e.g. looked after children and people with disabilities. Directors to consider/decide on which should be SCC target groups | HR Chief Executive & Directors |
|  |  | Positive Action Programmes/ Strategies top encourage target groups into employment in SCC Consider continuation of current strategies & development of new ones | Develop a Core and management competency framework | Core and management competency framework now established. To be introduced into recruitment and selection. By 31st July 2006. (see above). | HR Chief Executive & Directors |
|  |  |  | Develop a Clerical/admin pool to meet temporary staffing needs & provide routeway into employment for target group | Clerical/admin pool established targeting BME and Disabled applicants. Ongoing 22 people employed through admin/clerical pool to date |  |
|  |  |  | Extended schools work experience placements | Extended work experience placements for yr 10 and 11 children disaffected from academic achievement. Ongoing. Extended work experience placements for looked after children. From September 2006 |  |
|  |  |  | Establish a partnership with supported employment | Establish a partnership with supported employment organisation to develop access routes for people with significant disabilities. May 2006. Deliver at least one supported employment job in each Directorate by April 2007 (as per previous agreement by Directors) |  |
|  |  |  | Undertake Job Fairs | Joint Public Sector Recruitment Event held September 2005 Undertake Job Fairs to attract applicants from BME, disabled and young people. Ongoing. |  |
|  |  |  | Develop a “Young Ambassadors” Programme to encourage people under 25 into employment in SCC Children’s Services to consider rollout of Young Ambassadors programme to deliver “Raising Aspirations” Campaign | Young ambassadors to undertake promotions at schools and colleges. Ongoing. 3 Schools to be visited a term |  |
|  |  |  | Develop Initiatives to increase BME recruitment | Initiatives to increase BME recruitment into social care workforce. Ongoing. Clerical/admin pool established and ongoing. |  |
|  |  |  | Establish schemes for increasing employment of ex-offenders | Establish schemes for increasing employment of ex-offenders and people involved with drugs and alcohol. Introduce ‘Gateway’ by December 2006. |  |
|  |  |  | Develop a “Public sector Apprenticeship” to be piloted in SCC | Develop in Partnership with LSC by March 2007. First Intake April 2007 |  |
|  |  | Consider Development of SCC Positive Action Programme to provide routeway for target groups into employment in SCC/other employers | Develop a Positive Active Training Programme & secure funding | Directors Team considered this on 18th May 2006 | ED/HR |
|  |  | Consider Salford Mentoring project to train employers/managers/supervisors in how to support & mentor unemployed Salford residents on work placements, in training and in work | Develop and secure funding for Salford mentoring project | Directors Team considered this on 18th May 2006 | Chief Executive & Directors |
| 7. | Improve Skills of SCC Workforce | Agree a strategy for the delivery of Skills for Life (Move On) training to existing employees and new recruits | Agree targets | The Council’s new competency framework aspires to a minimum ‘level 2’ workforce. Extrapolation of national statistics for the local government workforce suggests that approximately 1000 employees are below ‘level 1’ in literacy and 4000 in numeracy. As an interim it is proposed setting a target of achieving minimum of’ 2500 employees raising their qualification in literacy and numeracy by one level by 2011. Assuming this is delivered at 500 a year this would contribute 30% of Salford’s enhanced (LPSA2) targets by July 2009. SCC to consider signing up to the GO local Govt award It is estimated that each employee would need on average 20 hours tutoring to achieve the qualification. The cost of the tutoring will be met by the LSC. The Skills for Life strategy for local authority employees should map the city’s Skills for Life Strategy A pilot Skills for Life programme is nearing completion, managed by a Joint Steering Group (including members and Trade Unions). The infrastructure is currently weak, and an increase in ULR and learning champions needs to be developed. An additional post financed through LPSA2 will become available to support the process across the public sector. Skills for Life is also a priority for the Organisational Development Team in HR and, as other public sector organisations eg PCT, Ambulance Service etc are also developing a Skills for Life strategy, this should be referred to the Public sector Employers’ Group | Directors Lifelong Learning Directors HR, Lifelong Learning |
|  |  | Adopt an overall plan to continue to develop low skilled staff (Train to Gain) |  | In addition to basic skills training the government is promoting a ‘train to gain’ approach for low-skilled staff to achieve a level 2 qualification (NVQ or otherwise). This training is funded by the LSC and Salford has 300 free places in 2006/7 (which is likely to continue on the basis of the 2006/7 opportunities being used up). This process will increase individual employability and improve workforce skills and performance. Although there are existing programmes for NVQ qualification is some service areas there is no overall approach that can maximise the available funding. From this a development plan for low-skilled staff can be devised and delivered. | Directors HR, Lifelong Learning |

# Text boxes

ITEM No 6