| SERVICE IMPROVEMENT PLAN NO. 1 INWARD INVESTMENT |  |
| --- | --- |

ENCOURAGING INVESTMENT IN THE CITY – The Review consultation work identified areas of improvement centred on the supply of sites and premises for businesses, the need to bring forward sites and consolidate existing employment areas, and opportunities for closer working with MIDAS (Manchester Investment & Development Agency Service.

# IMPROVEMENT TARGETS

| Indicator ED 1 – Business Investment | Baseline 2001/02 | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ED 1 – Business Investment Total number of ‘inward investment’ enquiries dealt with per annum Number of re-locations and re-investments annually as a result of ‘inward investment’ Number of jobs created and safeguarded from firms moving to, or re-locating within, the area following ‘inward investment’ enquiries Cost per job created and safeguarded through ‘inward investment’ | 227 26 618 new 478 safe £182 | 186 19 699 new 143 safe £154 | 250 50 1000 new 320 safe £151 | 250 60 1000 new 320 safe £151 | 250 60 1000 new 320 safe £151 | 250 60 1000 new 320 safe £151 | 250 60 1000 new 320 safe £151 |

Notes:  The Improvement Targets have been set at the levels above for the following reasons:

The forecast by Manchester Enterprises within the sub regional Economic Development Strategy suggests that over the next five years economic development in the Greater Manchester area will flat line. The figures for 2002/03 represent inward investment enquiries handled by MIDAS only (unlike the subsequent years given which include those also handled by Salford City Council). These increases are dependent on Salford City Council implementing the following; Firstly the successful appointment to the current vacant Senior Business Liaison Officer post; secondly the introduction of a new client management system across the Economic Development section, along with the accompanying increased monitoring and revised performance management systems.  In relation to ED 1 d) the targets set relate to direct staff costs only and exclude overhead costs, and whilst new jobs created can be verified jobs safeguarded is open to interpretation.

| How Identified | Objective | Action | Timescale | Performance Measure / Outcome | Lead Responsibility | Resources |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Start | End (or Review |  |  |  |
| BV focus group Internal stakeholders Feedback from users Comparison visits to beacon councils | 1 Formalisation of communication protocols between SCC Development Planning and SCC Economic Development to improve partnership working | Designated officer for Economic Development and Development Services established Workshop to develop joint work programmes and define roles and responsibilities Strengthen partnership with Development Services to establish a formal mechanism to bring forward Inward Investment opportunities Investigate the possibility of co–location of development surveyors within the Economic Development Section | ACHIEVED Jun 2003 - Dec 2003 Jun 2003 – Apr 2004 Aug 2003 – Mar 2004 | ED 1 Increase in the number of referrals from Development Services A revised model of service delivery where Development Services (Planning) acts as a catalyst between SCC and the private developer, identifying opportunities for future investment | E Colledge S Kitchen C Findley (Dev. Services) S Kitchen C Findley S Kitchen C Green | Existing Existing Existing Potential funding associated with Central Salford strategy |

| How Identified | Objective | Action | Timescale | Performance Measure / Outcome | Lead Responsibility | Resources |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Start | End (or Review |  |  |  |
| BV focus group Internal stakeholders Feedback from users Comparison visit to Gateshead MBC | 2 Improve partnership working arrangements with MIDAS: Put in place an improved Property Pilot database Create a Service level agreement with MIDAS | Develop partnership working at operational level to ensure continuity of service and aftercare Database updated more frequently and the development of a more systematic mechanism for local partners to validate the data Review progress after six months, if further improvement needed appraise option of inputting properties internally Formalise monitoring and evaluation with MIDAS to ensure resources maximised Survey of user satisfaction with aftercare services | Apr 2003 – Mar 2004r ACHIEVED Review Jun 2003 Jun 2003 – Mar 2004 Aug 2003 review annually | On going ED 1 More up to date database generating a larger number of successful relocations | J Hall J Glonek (MIDAS) J Hall S Khatun (MIDAS) J Hall J Glonek C Green S Kitchen | Existing Existing £20,000 possible need for additional staff Existing Existing |

| How Identified | Objective | Action | Timescale | Performance Measure / Outcome | Lead Responsibility | Resources |
| --- | --- | --- | --- | --- | --- | --- |
| BV focus group Internal stakeholders Feedback from users | 3 Analyse existing employment areas to ensure that sites and premises retain and attract businesses | Survey stock including older industrial stock and managed workspace provision. Consider above in light of plans for Central Salford, Salford West and Economic Development Zones Implement recommendations or review for existing stock Develop a strategy for the disposal and development of new products with targets to be established annually | Jun 2003 – Sep 2003 Nov 2003 – Mar 2004 Sep 2003 – Sep 2008 Sep 2003 – Sep 2008 | ED 1 | E Colledge D Evans (Dev Planning) E Colledge C Findley (Dev Planning) S Kitchen C Findley E Colledge D Evans | £50,000 |

| How Identified | Objective | Action | Timescale | Performance Measure / Outcome | Lead Responsibility | Resources |
| --- | --- | --- | --- | --- | --- | --- |
| BV focus group Internal stakeholders Feedback from users Gateshead Comparison case study | 4 Improve quality of property information for users (businesses, estate agents, developers) | Consultation exercise with property agents and developers Conduct survey of users of the property search facility Establish working group to implement a Property Forum Consider annual promotion of Salford’s properties and sites | Jun 2003 – Oct 2003 Dec 2003 – Mar 2004 Dec 2004 – Mar 2005r Dec 2004 | ED 1 Property Forum established Annual Property Show | P.McCann / E.Colledge P.McCann P.McCann / E.Colledge P.McCann / C Findley (Dev Services) | Existing Existing Existing £10,000 |