Salford

Crime and Disorder Reduction Partnership

Strategy Implementation Plan

2002 – 2005

draft status as at 13th June 2002

Contents:

1.	Cross Cutting Issues					Page 3

2.	Nuisance and Disorder					Page 6

3.	Violent Crime						Page 12

4.	Vehicle Crime						Page 14

5.	Burglary							Page 18

6.	Hate Crime 						Page 21

Please return any comments to:				Salford Community Safety Unit

Elmstead House

Partington Lane

Swinton

M27 0SS

Tel: 0161 793 3576

Fax: 0161 793 3579

e-mail: community.safety@salford.gov.uk

| CROSS CUTTING ISSUES |
| --- |
| Actions | Lead Agency / Officer | Funding | Output target and date(s) |
| 1. Provide Citizenship Education Programme, including victim awareness and community issues | Salford Community Safety Unit/ Officer – Education and Leisure Inspection and Advisory Service In Service training programme and Healthy Scheme | From existing resources | Programmes in schools by September 2002 |
| 2. Develop and implement a strategy to reduce the fear of crime | Press and Public Relations | Funding required | By June 2002 |
| 3. Develop and implement Crime and Disorder Communications Strategy | Press and Public Relations / Salford Community Safety Unit | From existing resources | Strategy in place by June 2002 |
| 4. Implement Witness Outreach Strategy | Salford Community Safety Unit | From existing resources | Increase the proportion of witnesses accessing the service by 2% per annum |
| 5. Deliver targeted Crime Stoppers campaigns in high crime areas | Crime stoppers | Funding required | Four campaigns by September 2003 |
| 6. Develop Victim Support Service and seek funding to extend work with burglary victims. Private tenants, victims of hate crime and children as victims and witnesses | Victim Support | Funding required | Development of service through increased funding |
| Develop Crime and Disorder Partnership consultation plan | Consultation worker – GMPS / Salford Community Safety Unit | From existing resources | June 2002 |
| Provide video interviewing for vulnerable / intimidated witnesses | GMP | From existing resources | By July 2002 |
| Research feasibility and implement schemes to target prolific offenders | GMP / Probation | Funding required | By April 2003 |
| Continue to develop schemes to provide opportunities for reparation work by offenders on Community Punishment Orders in communities and agreed with Partnership | Probation | From existing resources | By July 2002 |
| Implement schemes for reparation by young offenders and increase the amount of reparation work to 60% of all interventions | YOT | From existing resources | By March 2002 |
| Crucial Crew Programme for all year 6 covers “Operation Hawk” Victim Awareness” | Multi – agency programme co-ordinated by Inspection Advisory. PSPE |  |  |
| Magistrates Initiative Primary ?????? | Co-ordinated by Inspection Advisory / PSPE |  | 9 schools per year |

| CROSS CUTTING ISSUES |
| --- |
| Actions | Lead Agency / Officer | Funding | Output target and date(s) |
| 14. Deliver Communities Against Drugs project to tackle drug markets, strengthen communities and tackle drug related crimes | CAD Co-ordinator | Communities Against Drugs | By September 2002 |
| Develop initiative to target premises where stolen goods are disposed of | GMP / Trading Standards | Funding required | Initiative in place by December 2002 |
| 16. Work in partnership to implement and develop services to tackle the links between drugs and crime | DAT | Funding required | Ongoing |
| 17. Develop citywide strategy for wardens | Salford Community Safety Unit | DLTR, ERDF | Strategy in place by March 2003 |
| 18. Implement Neighbourhood Support Schemes in the Kenyon and Brookhouse estates | Salford Community Safety Unit | DLTR, ERDF | Schemes implemented by September 2002 |
| 19. Improve response to repair of street lights | Salford Community Safety Unit / Development Services | To be confirmed | To be confirmed |
| Develop a Corporate Security Strategy to cover provision of CCTV, guarding and mobile patrols | Salford Community Safety Unit | From existing resources | Strategy in place by December 2002 |
| Implement CCTV schemes in Patricroft, Salford Shopping Centre and Schools | Housing / Development Services | Home Office | Schemes implemented by December 2002 |
| 22. Develop a citywide approach to alcohol misuse | To be identified | To be identified | To be developed |
| 23. Develop funding strategy | Salford Community Safety Unit | From existing resources | Funding strategy produced annually in March / April |
| 24. Review and develop information sharing procedures | Salford Community Safety Unit | From existing resources | Information protocols signed by partner agencies by September 2002 |
| 25. Develop pooled budget opportunities | Salford Community Safety Unit | From existing resources | Pooled budgets identified by March 2003 |
| 26. Develop and implement a Partnership Training Strategy | Salford Community Safety Unit | From existing resources | Training plan produced by September 2002 |
| 27. Drug Prevention Training, Healthy Schools, Drug Alcohol and Tobacco Initiative. DAT Young People Strategy Group | Education and Leisure |  |  |

| NUISANCE AND DISORDER |
| --- |
| Helping Victims and Witnesses |
| Actions | Lead Agency / Officer | Funding | Output target and date(s) |
| 1. Increase use of rental bond scheme for victims of anti-social behaviour who wish to relocate | Head of Private Sector housing | To be confirmed by December 2002 | To be confirmed by December 2002 |
| Tackling Offending |
| LEGAL ACTION/ANTI-SOCIAL BEHAVIOUR POLICY |
| Actions | Lead Agency / Officer | Funding | Output target and date(s) |
| 2. Make greater use of Anti-Social Behaviour Orders and other legal action including injunctions and court orders to address more serious cases of juvenile nuisance and anti-social behaviour | Crime and Disorder Solicitor / Principal Anti-Social behaviour Officer | From existing resources | Prototype Anti-Social Behaviour database in operation by May 2002 Ongoing development of reporting systems by September 2002 Training for agencies delivered by July 2002 |
| 3. Implement Anti-Social Behaviour Policy and broaden out training for case conferencing and anti-social neighbours to identify appropriate interventions | Crime and Disorder Solicitor / Principal Anti-Social Behaviour Officer | From existing resources | Training for relevant agencies and Community Sector teams delivered by July 2002 |
| 4. Publicise successes where Anti-Social Behaviour action has been taken against prolific offenders | Head of Press and Public Relations, City Council | From existing resources | Link into Communication Strategy May 2002 |
| 5. Increase the use of the Mediation Service in case working with anti-social behaviour cases | Mediation Service | SRB5 / NDC / Other | To be confirmed |
| 6. Develop further use of appropriate information gathering techniques including CCTV, use of diaries and professional witnesses | Crime and Disorder Solicitor / Principal Anti-Social Behaviour Officer | NRF / Existing | Funding needs identified September 2002 |

| NUISANCE AND DISORDER |
| --- |
| JUVENILE NUISANCE STRATEGY |
| Actions | Lead Agency / Officer | Funding | Output target and date(s) |
| 7. Develop, agree partnership Juvenile Nuisance Strategy and protocols to identify and address juvenile nuisance through:- Citywide approach Hot spot approach | YOT Manager / Assistant Director, Education and Leisure / GMP | Children’s Fund / CAD / NRF / Existing resources | Agree strategy and protocols by September 2002 |
| 8. Following agreement, as a Partnership, implement procedure for: Responding Sharing information Youth diversion Early intervention and case working Enforcement | YOT Manager / Assistant Director, Education and Leisure / GMP | Cad / Children’s Fund/ NRF / OTHER | Implement approach initially on pilot areas or citywide by December 2002 |
| 9. Develop more detailed set of ‘tension’ indicators to highlight emerging patterns of juvenile nuisance citywide and link with crime | Salford Community Safety Unit | From existing resources | Detailed ‘tension’ indicators in place by August 2002 |
| 10. Recruit and develop further outreach Youth workers from City Council and Voluntary Sector to engage with young people in identified ‘hotspot areas’ | Assistant Director, Education and Leisure / YOT Manager | Connexions / NRF / Other | Funding and recruitment strategy in place by December 2002 Establish 3 new youth work teams |
| Consult and work with young people through Youth Commission and other innovative methods to ensure that provision and activity, match local needs | Assistant Director, Education and Leisure | From existing resources | Improve knowledge of needs of young people in local areas citywide by March 2003 |

| NUISANCE AND DISORDER |
| --- |
| ALCOHOL |
| Actions | Lead Agency / Officer | Funding | Output target and date(s) |
| 12. Expand use of random Test Purchasing operations to supermarkets, off-licences and other licensed premises to prevent sales to those underage | Head of Trading Standards | From existing resources | Four trading standards ‘operations’ per year |
| 13. Act on information from public on locations where alcohol sold to those underage and take appropriate legal enforcement | Service Manager Head of Trading Standards | From existing resources | Re-assess impact in April 2003 |
| 14. Explore use of ‘Proof of Age’ scheme in certain areas | Crime Reduction Partnership / DAT | From existing resources | Report on possible pilot project submitted February 2003 |
| PREVENTION/SCHOOLS |
| Actions | Lead Agency / Officer | Funding | Output target and date(s) |
| Develop service for children and young people at risk of becoming involved in offending through parenting initiatives, preventative work around schools and other work | Children’s Fund Co-ordinator | Children’s Fund / Sure Start | Funding programme agreed June 2002 |
| Increase provision and initiatives in relation to excluded pupils | Assistant Director, Access and Inclusion | From existing resources | Increase number of pupil referral unit places from 81 part-time to 104 full-time by September 2002. To ensure all permanently excluded pupils access full-time education within 15 days from September 2002 |
| Reduce absences in Primary and Secondary schools through ‘ truancy sweeps’ and other measures | Assistant Director, School Improvement / Education Welfare Service? | Street Crime Initiative / existing resources | Assessment of truancy sweep programme by September 2002 |

| NUISANCE AND DISORDER |
| --- |
| FIRE AWARENESS |
| Actions | Lead Agency / Officer | Funding | Output target and date(s) |
| Deliver fire awareness campaigns in schools in hotspot locations | GM Fire Service | From existing resources | Strong link to overall target to reduce malicious false calls to GM Fire Service by 10% by March 2005 |
| 19. Continue use of ‘The Arson’ project around addressing offending behaviour in relation to arson-related offences | GM Fire Service / YOT Manager | From existing resources | Strong link to overall target to reduce malicious calls to GM Fire Service by 10% by March 2005 |

| Improving Locations |
| --- |
| PRIVATE SECTOR HOUSING |
| Actions | Lead Agency / Officer | Funding | Output target and date(s) |
| 20. Extend use of landlord accreditation scheme to include private landlords in all parts of city | Head of Private Sector Housing | From existing resources | Increase levels of landlords accredited from 30 to (To be confirmed) Agree targets by December 2002 |
| 21. Improve levels of support for Private Sector landlords in addressing anti-social tenants, including information packs and dedicated support officers | Head of Private Sector Housing | From existing resources | To be confirmed |
| YOUTH PROVISION / DIVERSION |
| Actions | Lead Agency / Officer | Funding | Output target and date(s) |
| Develop a Youth Provision Strategy (in connection with Youth Nuisance Strategy) for improved use of new and existing youth, sports, leisure and other facilities, such as use of PODS, youth shelters etc. | Education and Leisure | Funding element to be fully development December 2002 | Youth Provision Strategy agreed October 2002 Increase expenditure by Youth Service per head of youth population from £59.94 to £69.00 Increase participation of young people in sporting activities |
| 23.Develop Youth Inclusion or Sparky programmes to divert young people in priority areas | YOT Manager / Education and Leisure | From existing resources / SRB / NDC / Other | One additional SPARKY project developed per year |

| NUISANCE AND DISORDER |
| --- |
| ABANDONED VEHICLES |  |
| Actions | Lead Agency / Officer | Funding | Output target and date(s) |
| 24.Implement a citywide initiative to facilitate early removal of abandoned vehicles | Assistant Director, Environmental Services | City Council / GMP/ GM Waste Disposal Authority | Reduction in numbers of Fire Service calls to vehicle fires (To be confirmed) Review progress March 2003 |
| GRAFFITTI / LITTER |  |
| Actions | Lead Agency / Officer | Funding | Output target and date(s) |
| 25.Implement early removal of graffiti in hot spot areas | Assistant Director, Environmental Services | From existing resources | Remove racist and offensive material within 24 hours of report |
| 26.Develop Strategy for expanding graffiti removal service | Assistant Director / Environmental Services | NRF / Other / Existing resources | Improved response citywide to requests for graffiti removal |
| 27.Implement fast track initiatives around litter and fly tipping in hot spot areas, including Seedley and Langworthy and Broughton | Assistant Director, Environmental Services | From existing resources | Response within 24 hours of report |
| 28.Develop litter Enforcement Officer post to undertake enforcement action on litter and fly tipping and lead litter buster initiative | Assistant Director, Environmental Services | NRF / Other / Existing resources | Funding for post to be confirmed by October 2002 |
| NOISE |  |
| Actions | Lead Agency / Officer | Funding | Output target and date(s) |
| 29.Develop further the use of noise pollution monitoring and collation of legal action against neighbour nuisance | Principal Pollution Control Officer, Environmental Services | From existing resources | Agree protocol for use of noise in anti-social behaviour cases by October 2002 |

| NUISANCE AND DISORDER |
| --- |
| PUBLIC TRANSPORT |  |
| Actions | Lead Agency / Officer | Funding | Output target and date(s) |
| 30.Implement initiatives to reduce levels of disorder in and around public transport and take enforcement action | GMPTE / GMP / Salford Community Safety Unit | From existing resources / NRF / Bus Companies / Metrolink / GMPTE | Initiatives developed as part of citywide approach by March 2003 |
| 31.Develop work in schools regarding dangers of disorder on public transport | GMPTE / GMP | From existing resources | Work in schools to commence September 2002 |
| 32.Explore dedicated officer role to work with public transport companies to identify issues and develop initiatives | GMPTE / GMP / Salford Community Safety Unit | NRF / GMPTE / Bus Companies / Metrolink | Post agreed October 2002 |
| URBAN SPACE |  |
| Actions | Lead Agency / Officer | Funding | Output target and date(s) |
| 33.Develop and implement an urban open spaces strategy to improve the quality and perception of the inner area environment | Assistant Director – Planning | From existing resources and to be confirmed | Strategy in place December 2002 |
| 34.Explore the role of the urban country side rangers to engage with young people and communities to promote environmental and litter awareness | Assistant Director – Environmental Services | From existing resources | Decrease in cost of litter and environmental nuisance (To be confirmed) |
| 35.Implement community based environmental projects and clean ups in priority areas | Principal Planning Officer / Groundwork | To be confirmed | Improved ‘ownership’ of by local communities Decrease in cost of litter an environmental nuisance (To be confirmed) |

| VIOLENT CRIME |
| --- |
| Helping Victims and Witnesses |
| Actions | Lead Agency / Officer | Funding | Output target and date(s) |
| 1. Identify long term funding for the post of Domestic Violence Co-ordinator | Domestic Violence Policy and Strategy Group | Funding required | Funding in place by September 2002 |
| 2. Deliver Domestic Violence Training Strategy and train a pool of trainers | Domestic Violence Policy and Strategy Group | Sure Start / New Deal / GMPA | Staff trained across agencies by December 2002 |
| 3. Consult with victims of Domestic Violence and Street Crime about their needs | Community Consultative Worker, GMPA | From existing resources | Ongoing consultation with Women’s Consultation Group |
| 4. Develop and deliver support groups for women and seek funding to continue | Health Visitor, Domestic Violence Co-ordinator, Primary Care Trust | Sure Start / New Deal | One group held in each committee area by 2005 |
| 5. Deliver Freedom Group programmes for survivors of domestic violence | Health Visitor, Domestic Violence Co-ordinator, Primary Care Trust | Sure Start / New Deal | Meet demand for groups and / or deliver one group in each committee area by 2005 |
| 6. Deliver personal safety training to vulnerable groups, including young people, at risk of street robbery | GMP / Education / Community Safety Unit | From existing resources | Training delivered |
| Provide advice to small and medium sized businesses on personal safety and on risk management | Commercial Risk Management Advisor, Salford Community Safety Unit | From existing resources | Provide advice to 360 businesses per annum |
| Research initiatives to tackle bullying and seek funding | Community Safety Unit | From existing resources | Report produced by December 2002 |
| Pilot peer support scheme in one high school to give information on sources of support for young victims and street crime prevention | Victim Support and Witness Service | Pilot funded from existing resources and Childrens Fund | Pilot completed and evaluation report by December 2002 |

| Location | Violent Crime |
| --- | --- |
| Actions | Lead Agency / Officer | Funding | Output target and date(s) |
| Deliver targeted initiatives at “hotspot” locations for robberies | Robbery Unit Sergeant, GMP | From existing resources | Six initiatives each quarter |
| Extend enforcement of Door Safe Scheme for licences premises with entertainment licences | Salford City Council – Licensing Unit | From existing resources | Four inspections of door staff each year |
| Implement CCTV Schemes for Patricroft, schools and Salford Precinct | Development Services, Salford City Council | Funding obtained from the Home Office | Work to start by September 2002 |
| Research schemes aimed at reducing alcohol related violence | Salford Community Safety Unit | From existing resources | Report with proposals agreed by partners by March 2003 |
| Research street crime in “hotspot” areas (Eccles, Swinton and Langworthy and Broughton) | Salford Community Safety Unit | From existing funding | Report by July 2002 |
| Continue and extend Pub Watch schmes to facilitate the exchange of information on violent customers | Watch Co-ordinator / GMP | From existing resources | Existing schemes to meet ten times per year. Report on feasibility of additional schemes by March 2003 |

| Offenders | Violent Crime |
| --- | --- |
| Actions | Lead Agency / Officer | Funding | Output target and date(s) |
| 16. Develop and use the Multi-Agency Protection Panel to protect communities from identified offenders at risk of committing violent/sexual offences | GMP/Probation | From existing resources | Ten meetings each year |
| 17. Deliver initiatives in the Street Crime Action Plan to reduce street crime offending by young people | YOT | From existing resources | Initaitves ongoing. Work with young people in custody at Hindley in place by September 2002 |
| 18. Deliver “Think First” and alcohol (ASRO) programmes to offenders on probation | Probation | From existing resources | Appropriate programme delivered to all offenders on probation |
| 19. Deliver programmes for convicted domestic violence perpetrators | Probation | From existing resources | Appropriate programme delivered to all offenders on probation |
| 20. Deliver initiatives in the Street Crime Action Plans to prioritise street crime cases | Probation | Fr4om existing resources | Initiatives in place by July 2002 |
| 21. Implement Street Crime Initiative Action Plans | Community Safety Unit | Funding from Street Crime initiative and other funding sought | Refer to street crime action plan |

| VEHICLE CRIME |
| --- |
| Helping Victims and Witnesses |
| Actions | Lead Agency / Officer | Funding | Output target and date(s) |
| Carry out further analysis of victimised persons, vehicles, and locations | Salford Community Safety Unit analyst | From existing resources | Publish findings by July 2002 |
| Marketing campaign to educate owners of security measures to be taken and to promote Park and Ride Initiatives | Communications and Public Relations Team | P.S.A’s | Communications Strategy in place by August 2002 Increase persons using Park and Ride scheme x 25% by March 2003 |
| Implement Repeat Victimisation Initiative. To contact all victims with advice letter / literature | Operational Policing Unit | From existing resources | All reported victims to receive advice as of April 2002 |
| Seek commercial sponsorship – to provide security devices for repeat victims | Crime Reduction Advisors | From existing resources | Sponsorship from two companies by September 2002 |
| Increase accessibility of crime scene surgeries and provide crime prevention advice | Crime Reduction Advisor / Crime Scene Examination Unit | From existing resources | All persons attending surgeries to be offered advice, as of July 2002 |
| 6. Research potential to expand Park and Ride initiatives | Salford Community Safety Unit | From existing resources | By December 2002 |
| 7. Approach local car dealers to give out preventative advice when selling cars | Crime Reduction Advisor | From existing resources | Six main dealers to participate by August 2002 |
| 8. Approach monitoring organisations / insurance companies give out preventative advice and promote safe parking sites | Crime Reduction Advisor / Salford Community Safety Unit | From existing resources | Formation of formal links by December 2002 |
| 9. Research potential to use Name and Shame initiative re car parks with poor security | Salford Community Safety Unit and Communications and Public Relations Team | From existing resources | Report by September 2002 |
| 10.Lobby for change in legislation re rights of consumer and responsibilities of car park owners | Salford Community Safety Unit | From existing resources | Representation made via GONW / local MP x September 2002 |

| VEHICLE CRIME |
| --- |
| Tackling Offending |
| Actions | Lead Agency / Officer | Funding | Output target and date(s) |
| Targeted police initiatives within victimised areas | Operational Policing Unit | From existing resources | Four police initiatives by December 2002 |
| More Crime Scene examination of vehicles – establishment of secondary surgery at Swinton Police Station | Operational Policing Unit | From existing resources | 40% of all vehicle subject of crime to be examined and August 2002 |
| Use of Automatic Registration Plate recognition equipment | Operational Policing Unit | Safer Communities Initiative | Six operations by March 2003 |
| Establish multi-agency group to reduce ability to sell stolen vehicles | Salford Community Safety Unit / Trading Standards Office | From existing resources | Formation of group by September 2002 |
| Pilot rolling road blocks to identify offenders | Operational Policing Unit | From existing resources | Pilot scheme in place by September 2002 |
| Expand diversionary activities such as GEARS etc, including accredited courses | Youth Service | Children’s Fund | Provision of additional activities by March 2002 |
| Provide behavioural programmes aimed at offenders involved in vehicle crime | Probation and YOT | From existing resources | Specific programmes in place by December 2002 |

| VEHICLE CRIME |
| --- |
| Improving Locations |
| Actions | Lead Agency / Officer | Funding | Output target and date(s) |
| Improve levels of security in Local Authority car parks towards Secure Car Parks Award | Group Engineers | CAD | Improvements at six car parks to gain award – August 2003 |
| 19. Improve levels of security in commercial car parks towards Secure Car Parks Award | Crime Reduction Advisor | CAD | Improvements at six parks to gain award – August 2003 |
| Tighter control of planning restrictions to ensure acceptable security levels at car parks | Local Authority planning department | From existing resources | All planning department staff to be provided with additional training by December 2003 |
| Increase longevity of car parks when providing planning permission in order to encourage expenditure on security | Local Authority planning department | From existing resources | All planning department staff to be provided with additional training by December 2003 |
| Use of police mobile CCTV systems in victimised areas | Operational Policing Unit and Salford Community Safety Unit | From existing resources | Six police initiatives x March 2003 |
| 23. Expansion of parking restrictions in victimised areas | Group Engineers – Salford Community Safety Unit analyst | Community Safety Budget | Identification and selection of areas for restrictions by September 2002 |
| Research potential use of warning signs at hot spot locations | Salford Community Safety Unit | From existing resources | September 2002 |
| Pilot Homelink initiative whereby vehicles parked outside homes are linked into the home security system | Housing | From existing resources | Evaluation of system x December 2002 |
| Immediate removal of abandoned vehicles to prevent arson | Environmental Services | From existing resources | April 2002 |

| VEHICLE CRIME |
| --- |
| Actions | Lead Agency / Officer | Funding | Output target and date(s) |
| Development of SARA, problem solving and other training for wardens, security staff, local authority attendants and accredited persons in victimised areas resulting in a more visible presence in hot spot areas | Salford Community Safety Unit | Partnership Development Fund | Training commenced x March 2003 |
| Enhancement of effective lines of communication between the above, police and community safety team | Salford Community Safety Unit | From existing resources | Protocol for exchanging information in place by March 2003 |
| Subject to the success of the Police Bill, accreditation of above persons to provide additional powers | GMP | From existing resources | Within twelve months of Bill being successful |

| BURGLARY |
| --- |
| Helping Victims and Witnesses |
| Actions | Lead Agency / Officer | Funding | Output target and date(s) |
| 1. Develop and deliver a burglary prevention awareness raising campaign | Salford Community Safety Unit | PSA | Campaign developed by December 2002 |
| 2. Develop and deliver a business security campaign and promote the Business Security Grants Scheme, which includes Risk Assessment Service. | Salford Community Safety Unit | Economic Development, NRF, Chamber | Campaign developed by December 2002 |
| 3. Ensure all victims of repeat domestic burglary are referred to the Burglary Reduction Initiative Team. | Operational Policing Units | Police | System for referrals in place by June 2002 |
| 4. Ensure all elderly victims of domestic burglary are referred to Help the Aged ‘handy van’ service. | Burglary Reduction Team | Housing, CAD | All elderly victims of domestic burglary to have access to service by September 2002 |
| 5. Promote and support development of Home Watch schemes, particularly in hotspot areas and areas with Neighbourhood Liaison Schemes. | Police Watch Co-ordinator | Police | Watch Co-ordinator to have targeted each hotspot area by April 2003 |
| 6. Promote and support development of Business Watch schemes in areas with high crime rates. | Police Watch Co-ordinator | Police, Economic Development | Watch Co-ordinator to have targeted each hotspot area by April 2003 |

| Tackling Offending |
| --- |
| Actions | Lead Agency / Officer | Funding | Output target and date(s) |
| 7. Identify most prolific offenders and target with intensive Probation support | Probation | Prolific Offenders Fund, CAD | 20 most prolific offenders identified and targeted by April 2003. |
| 8. Identify most prolific drug using offenders and target with intensive Probation and Drugs Service support | Probation | Prolific Offenders Fund/CAD | 20 most prolific drug using offenders identified and targeted by April 2003. |
| 9. Develop and deliver campaign to target those who handle stolen goods. | Police & Trading Standards | CAD | Two dedicated Trading Standards Officers in post by August 2002. |

| BURGLARY |
| --- |
| Improving Locations Commercial and Residential Burglary Plans |
| Actions | Lead Agency / Officer | Funding | Output target and date(s) |
| 10. Promote Secured by Design initiative via National House Building Association and individual businesses | Police | From existing budgets | NHBA consulted by December 2002. |
| 11. Examine possibility of fast-tracking planning applications that are based on crime prevention measures. | Planning Dept | From existing budgets | Feasibility report produced by September 2002. |
| 12. Apply minimum security standards as a condition to all private sector property renovation grants | Private Sector Housing Section | From existing budgets | Condition introduced by March 2003. |
| 13. Apply minimum security standards to local authority landlord accreditation scheme | Private Sector Housing Section | From existing budgets | Condition introduced by March 2003. |
| 14. Encourage the University to apply minimum security standards to university private landlord accreditation scheme | Police Campus Liaison Officer | From existing budgets | Negotiations held by December 2002. |
| 15. Continue to implement and develop Burglary Reduction Initiative including introducing a graded response to repeat victims and implementing targeted projects in hotspot areas. | BRI Team | Housing/CAD/PSA | Graded response and targeted projects developed and introduced by December 2002 |
| 16. Continue to implement and develop the Business Security Grants Scheme to include prioritised allocation of resources in victimised areas and a review of the level of grants allocation. | Economic Development | SRB5, Safer Communities Initiative | Options appraisal completed by August 2002. Delivery of new conditions from September 2002. |
| 17. Develop and deliver spending plan for Small Retailers Security Initiative. | Salford Community Safety Unit | Home Office | Spending plan developed by June 2002. |

| BURGLARY |
| --- |
| Actions | Lead Agency / Officer | Funding | Output target and date(s) |
| 18. Expand Quaywatch Service to include key holding and response service. | Salford Community Safety Unit | Service Users | Service expanded from June 2002. |
| 19. Develop and deliver marketing and promotions campaign to increase subscription to Quaywatch Service. | Salford Community Safety Unit | Safer Communities Initiative | Campaign developed and delivered by December 2002. |
| 20. Ensure all partner agencies comply with the approved list of security providers | Development Services | From existing budgets | No unapproved security providers being used by partner agencies by April 2003 |
| 21. Implement pilot monitored home alarms scheme on The Valley Estate, Swinton and Littleton Road, Pendleton | Housing | Service Users | Pilot running by September 2002 |
| 22. Ensure all Local Authority void properties are secured within 24 hours | Housing/Corporate Security | PSA, CAD | All LA void properties to be secured within 24 hours by April 2003 |
| 23. Examine introduction of alarms in void properties where need identified | Housing /Corporate Security | PSA, CAD | Alarm installation and response service to be examined by September 2003 |
| 24. Liase with Registered Social Landlords and accredited Private Sector Landlords to ensure their void properties are secured within 24 hours | Community Safety Unit | From existing resources | Discussions held with RSLs and PSLs by April 2003. Building Control Officer in post by September 2002. |
| 25. Investigate possibility of supplying alarm installation, monitoring and response service to RSLs as part of corporate security | Community Safety Unit | PSA/Service Users | Investigations complete and recommendations made by April 2003 |
| 26. Ensure prompt securing of void properties were landlord can’t be identified or is not accredited. | To be confirmed | PSA | Building Control Officer in post by September 2002. |
| 27. Operate compulsory purchase orders/enforced sales procedures on properties which have been secured but remain vulnerable | To be confirmed | PSA | Liaison with CPO officers by August 2002. |
| 28. Develop and deliver strategy to ensure security of vulnerable public buildings | Salford Community Safety Unit | From existing funds, NRF | Security strategy developed by September 2003 |
| 29. Develop alley gating schemes in hotspot areas | Salford Community Safety Unit | PSA/CAD/Housing | Schemes developed by December 2003. |

| HATE CRIME |
| --- |
| Helping Victims and Witnesses |
| Actions | Lead Agency / Officer | Funding | Output target and date(s) |
| 1. Develop a strategy to address the needs of Black and Minority Ethnic communities for the Witness Outreach Service | Community Safety Unit | Safer Communities Initiative | Strategy implemented by October 2002 |
| 2. Increase staff capacity to develop the local authority response to the needs of Black and Minority Ethnic communities Hate Crime Co-ordinator Black and Minority Ethnic worker for Community Chest Community and Race Relations Officer | Salford Community Safety Unit Social Inclusion Unit GMP | Community Safety Budget To be confirmed GMP | In post by August 2002. First step to map existing reporting facilities and develop links with BME communities To be confirmed Existing post holder will work closely with the Hate Crime Coordinator |
| 3. Develop a centralised co-worker scheme to work alongside front-line service delivery staff to improve contacts with Black and Minority Ethnic service users | GMP / Social Inclusion Unit | Funding streams to be developed | To be confirmed |
| 4. Continue to lobby Government for a better planned process for placing asylum seekers, so that we are aware where asylum seekers are being placed and can plan for that | Asylum Seekers Steering Group | From existing resources | Ongoing |
| 5. Implement training and volunteer recruitment recommendations in line with National Victim Support policy re: the Lawrence Report | Victim Support Salford | Funding to be identified | To be confirmed |
| 6. Develop linkages with Black and Minority Ethnic groups / communities | Probation Service | To be confirmed | Plans to be developed |

| HATE CRIME |
| --- |
| Actions | Lead Agency / Officer | Funding | Output target and date(s) |
| 7. Develop an effective reporting network for hate crimes in venues other than police stations: Develop additional reporting centres to increase opportunities to report hate crimes Identify language needs / provision of appropriate reporting material and communication and information requirements to promote reporting centres | Community Safety Unit / GMP Salford Community Affairs team working with all partner agencies | Safer Communities Initiative/mainstream funding | An additional 10 centres established by April 2003 Increase the number of reported hate crime incidents by 30% by March 2005 |
| 8. Implement the Information Sharing Protocol in relation to sharing information on hate crime reports | Community Safety Unit / GMP Community Affairs Unit and all agencies | From existing resources | By July 2002 |
| 9. Achieve individual agency/departmental targets for increase of hate crime reports | Community Safety Unit Hate Crime Coordinator and all agencies | From existing resources | 30% increase in each agency by March 2005 |
| 10. All public authorities to review their services as part of the Race Equality Scheme process and develop an action plan to address appropriate service delivery for BME communities | Personnel of each agency | From existing resources | Action Plans to be drawn up by June 2002 |
| 11. Develop an anti-racist bullying policy for schools | Refugee and Asylum Seekers Service, Education Dept | To be confirmed | To be confirmed |
| 12. Implement an Equality Policy in schools | Equality Officer City of Salford Personnel | From existing resources | Implemented by May 2002 |
| 13. Develop appropriate service level agreements re: reporting hate crime / staff training for Arms Length Housing Management | Salford Community Safety Unit / Housing Dept | From existing resources | By September 2002 |
| 14. Develop a pupil / teacher hate crime reporting process in schools (Race Relations Amendment Act) | Equality Officer City of Salford Personnel | From existing resources | To be confirmed |

| HATE CRIME |
| --- |
| Actions | Lead Agency / Officer | Funding | Output target and date(s) |
| 15. Develop an anti-homophobic / transphobic bullying policy in schools | Equality Officer City of Salford Personnel | From existing resources | To be confirmed |
| 16. Develop a co-ordinated multi-agency approach to racial harassment (see below) | Salford Multi Agency Racial Harassment Forum (SMARHF) | From existing resources | Ongoing |
| 17. Implement the Combating Racial Harassment Project to develop a community response to racial harassment | SMARHF / Victim Support Salford | Community Safety grant/Funding bid to Lottery | Advertise post by July 2002 Implement the recommendations of the SMARHF Steering Group by end of project (2004) |
| 18. Develop Community Committee membership so that it reflects the diversity of the local community | Community Safety Unit / Neighbourhood Committee Co-ordinators | Social Inclusion funds | To be confirmed |
| 19. Develop targeted education programmes for Black and Minority Ethnic groups to increase their knowledge and confidence re reporting harassment | Community Safety Unit Community Development Worker | To be confirmed | Pilot project in Broughton delivered by December 2002 and rolled out to other areas subject to evaluation |
| 20. Develop project seeking to research the needs of refugees and asylum seekers and offer practical support with key agencies working together | RAPAR | SRB5 funded (2002/2003) | Project plan to be confirmed |
| 21. Develop appropriate consultation and feedback systems including ‘ customer satisfaction’ measures for victimised communities and hard to hear groups | Community Safety Unit | Community Safety budget and pooled resources | See cross cutting Communications Strategy |

| Tackling Offending |
| --- |
| Actions | Lead Agency / Officer | Funding | Output target and date(s) |
| 22. Develop a programme of tolerance and diversity issue based education in schools (Citizenship Programme) | Assistant Director, S1, Education and Leisure Directorate/ Salford Community Safety Unit | From existing resources | Programme introduced in schools by September 2002 |

| HATE CRIME |
| --- |
| Improving Locations |
| Actions | Lead Agency / Officer | Funding | Output target and date(s) |
| 23.Target personal safety and security enhancement projects towards victimised communities | Police /Community Safety Unit | From existing resources/Neighbourhood Renewal Fund/Community Safety budget | Ongoing |
| 24. Develop research and intelligence capacity within the Community Safety Unit to identify victimised communities and hate crime hot spots | Analyst – Community Safety Unit | From existing resources | In post by May 2002. Develop analytical capacity by August 2002 |