FUNDAMENTAL BEST VALUE REVIEW

CRIME AND COMMUNITY SAFETY - SECTION 17 RESPONSIBILITIES

SALFORD CITY COUNCIL

IMPROVEMENT PLAN 2001 – 2005

AND POSITION STATEMENT AT AUGUST 2002

## INTRODUCTION

This Improvement Plan reflects the findings and recommendations of the fundamental Best Value review (2000/2001) and feedback from the Best Value Inspectorate.  It will be used as a basis to significantly improve how the City Council discharges its statutory responsibilities to reduce crime and disorder in all that it does.  The Improvement Plan articulates “urgent and ambitious” aspirations against a realistic backdrop of the time needed to change culture in a large, multi-functional organisation.

| JOHN WILLIS, CHIEF EXECUTIVE | COUNCILLOR T. ULLMAN CHAIR - SCRUTINY PANEL | COUNCILLOR D. LANCASTER LEAD MEMBER, - COMMUNITY SAFETY |
| --- | --- | --- |

# CONTENTS

|  | PAGE NO. |
| --- | --- |
| 1. PROGRAMME FOR IMPLEMENTATION | 4 |
| 2. POLICY AND STRATEGY | 5-6 |
| 3. LEARNING FROM THE BEST VALUE REVIEW | 7-9 |
| 4. PARTNERSHIP WORKING | 10-14 |
| 5. RESOURCES STAFF TRAINING AND DEVELOPMENT | 15-22 |
| 6. COMMUNICATION | 23-25 |
| 7. PERFORMANCE MANAGEMENT | 26-28 |
| 8. CONSULTATION | 29-30 |
| 9. GLOSSARY | 31 |

1. IMPROVEMENT PLAN - PROGRAMME FOR IMPLEMENTATION

2. POLICY AND STRATEGY

Objective: To provide a clear strategy to focus and co-ordinate all future crime & disorder activity within the partnership.  To maximise the potential of the partnership and ensure strategic support and cross directorate/agency working to tackle crime and disorder.

| Action | Timetable | Performance/Measure/Outcome | Lead Officer | Current Position |
| --- | --- | --- | --- | --- |
| Undertake a Crime and Disorder Audit Utilise existing communication mechanisms and consultation networks to consult as widely as possible on the Crime and Disorder Audit findings. Evaluate responses and amend Audit as necessary. Evaluate the current Crime and Disorder Strategy Evaluate other Crime Reduction Partnership strategies: Select from Greater Manchester Partnerships Home Office Family Groupings (Group 13) ( Review all strategies and operational plans related to Crime and Disorder Develop 3 year Crime and Disorder Strategy | 30th August, 2001 30th September, 2001 30th September, 2001 30th September, 2001 30th September, 2001 30th November, 2001 | Audit completed Evaluation report on consultation findings Amend Audit, as necessary Produce Evaluation Report Produce Evaluation Report Produce Review report to inform partners and the development process for the new 3 year Crime Reduction Strategy Draft Strategy Completed | GD/Crime Reduction Partnership GD/Crime Reduction Partnership GD GD GD GD/ Crime Reduction Partnership | Completed Completed Completed and fed into audit and new strategy Reviewed other strategies and fed into development of new strategy Completed and fed into audit and new strategy Reviewed other strategies and fed into development of new strategy Completed. |

2. 2. POLICY AND STRATEGY

# Objective: To provide a clear strategy to focus and co-ordinate all future crime and disorder activity within the partnership. To maximise the potential of the partnership and ensure strategic support and cross directorate/agency working to tackle crime and disorder.

| Action | Timetable | Performance/Measure/Outcome | Lead Officer | Current Position |
| --- | --- | --- | --- | --- |
| Consultation exercise on draft crime reduction strategy. Evaluate responses and amend strategy as necessary All Crime and Disorder related strategies and service plans to ensure clear links with the new 3 year Crime Reduction Strategy Implement, monitor and evaluate the new Crime Reduction Strategy | 30th December, 2001 31st March, 2002 April 2002 – March 2005 | Amend strategy as necessary Where necessary, targets, action plans and performance indicators revised to complement new 3 year Crime Reduction Strategy Local Authority Directorates and Partner agencies Service and Financial Plans to clearly link to new 3 year Crime Reduction Strategy Monitor key P.I.’s on quarterly basis Evaluate Strategy implementation on a bi-annual basis | GD/Crime Reduction Partnership GD/All Directors/Crime Reduction Partnership GD/All Directors/Crime Reduction Partnership GD/Crime Reduction Partnership | Completed Currently reviewing new service plans Currently reviewing new service plans Implemented and ongoing. Monitoring and evaluation undertaken as part of new performance management system |

3. LEARNING FROM THE BEST VALUE REVIEW

Objective: Conclude the review of key elements of the Salford Crime Reduction Partnership to improve strategic support and joint working.

| Action | Timetable | Performance/Measure/Outcome | Lead Officer | Current Position |
| --- | --- | --- | --- | --- |
| Receive final views of the Best Value Inspectorate and consider in relationship to the Improvement Plan Review the following: 1. - Crime Reduction Partnership Executive Group - Policy Champions Group - Community Sector Teams - Youth Offending Team Drug Action Team Safer Salford | (see Pam Lowe re date) 30th September, 2001 15th June, 2001 | Improvement Plan amended as necessary Review reports to Lead Member Develop relevant Action Plan in relation to outcomes and link Best Value Improvement Plan Report outlining structural changes to Safer Salford produced for Cabinet | GD/PL/Personnel GD/PL/Personnel CG/MBS | Received final report in February 2002. Amended plan as necessary Review of Exec. Group and Drug Action Team to be undertaken. Community Sector Teams currently underway. All others completed. Completed |
| 2. Consultation (Refer to section 8: Consultation, for detailed actions) Key Crime Reduction initiatives within Salford - CCTV - Mobile Security Patrols - Targeting anti-social behaviour offenders - Witness support service - Community Watch | Various Dates (Refer to section 8: Consultation) 30th September, 2001 | Various (Refer to section 8: Consultation) Review reports to Lead Member/Cabinet to consider appropriateness of current initiatives and are they delivering effectively and achieving value for money. Individual programmes may be amended and will have clear link to new 3 year crime reduction strategy | Relevant Project Managers/GD | Refer to Section 8 CCTV and Mobile patrols ongoing. All others completed. |

| 3.. LEARNING FROM THE BEST VALUE REVIEW |
| --- |
| Action | Timetable | Performance/Measure/Outcome | Lead Officer | Current Position |
| Integrate Crime and Disorder Considerations into the Best Value process. Consider need for an increase in the level of investment in tackling youth crime and disaffection e.g. extending the number of outreach workers, utilising the services of other providers | By 31st May, 2001 By 31st July 2001 | Crime and disorder considerations added to Best Value toolkit and communicated to all Directorates and Best Value Review Teams All second year and subsequent Best Value Reviews to include crime and disorder implications in service profile 4 ‘C’ analysis and final report. Report to Lead Member and Cabinet detailing costed options for investment in tackling youth crime and disaffection Youth Strategy considers investment potential for tackling youth crime and disaffection | PL Best Value Review Teams/Scrutiny Cttee/Cabinet MC/CG/SCRP MC | Currently reviewing approach to Best Value. Findings will inform ‘toolkit’ (implement by October 2002). Best Value Group will be utilized to communicate new approach and other key messages. Substantial investment allocated via NRF, Childrens Fund, SRB5, Behavioural Improvement Programme, Connexions. Steve Hassall developed draft proposal re youth and community investment in relation to tackling youth crime and disaffection. Final date for delivery to be confirmed. |

3. LEARNING FROM THE BEST VALUE REVIEW

| Action | Timetable | Performance/Measure/Outcome | Lead Officer | Current Position |
| --- | --- | --- | --- | --- |
| Undertake research into initiatives and sources of funding to support such initiatives that act as a deterrent to criminal behaviour e.g. alleygating, CCTV, lighting etc. | By 30th June 2001 | Report to Cabinet outlining sources of funding and initiatives to follow | All Directors | Various research undertaken and ongoing. Includes Neighbourhood Wardens; Burglary; Car Crime; Anti-Social Behaviour Orders; Domestic Violence; Victim Support and Racial Harassment; Alleygating; I.S.S.P.; Referral Orders; Arrest Referral etc. Funding identified and aligned with findings. |
| Objective: Review housing management arrangements in relation to anti-social behaviour as part of Best Value review of area housing services. |
| Consult tenants Benchmark service Map processes Carry out review | November 2001 – April 2002 | Revue completed and necessary actions implemented and monitored quarterly | GR | Completed |

4. PARTNERSHIP WORKING

Objective: To continue to improve partnership working and to achieve a “seamless” approach between strategic working and local delivery.

| Action | Timetable | Performance/Measure/Outcome | Lead Officer | Current Position |
| --- | --- | --- | --- | --- |
| Establish an Officer Working Group (OWG) from all Directorates within the City Council and partner agencies to oversee implementation of the Improvement Plan All partner agencies and authority directorates to identify a senior member(s) of staff who will act as the lead officer(s) for Crime and Disorder. Develop role specification for contact officers (to include their requirement to co-ordinate training, communications and delivery of crime and disorder initiatives) Provide training for contact officers | 30th June 2001 By 30th June 2001 30th June 2001 31st August, 2001 | Nominations of team members received from all Directorates and partner agencies. Terms of reference/schedule of meetings/work programme agreed with OWG and reported to Lead Member and Cabinet. Database of key contacts established Salford Partnership Operational Manual amended to include details Specification produced Training plan agreed and delivered | CG/Directors/ Heads of partner agencies CG/OWG GD/Salford Crime Reduction Partnership Personnel Personnel/GD | Convened and will now approach through existing mechanisms of C&D Partnership. Improvement Plan to feed into Crime Reduction Strategy. Completed To be completed To be completed To be included within the Training Strategy |
| Utilise staff appraisals to ensure the contact role is being delivered Review and re-launch the Salford Crime Reduction Partnership Operational Manual. Develop and incorporate a joint partnership problem solving approach based on police SARA model and local authorities model | August 2001 – ongoing 30th December, 2001 | Staff appraisals delivered Revised operational manual produced All agencies/directorates consulted and signed up Marketing launch Available in hardback, CD Rom, Intranet, etc. | All managers and relevant staff Salford Crime Reduction Partnership/GD | To be undertaken Review and relaunch to be undertaken. Problem solving training planned to be delivered this financial year. |

4. PARTNERSHIP WORKING

| Action | Timetable | Performance/Measure/Outcome | Lead Officer | Current Position |
| --- | --- | --- | --- | --- |
| Together with the North West Centre for Change, Manchester Business School, research how to further improve local delivery of the Salford Crime Reduction Strategy Create specific roles within Safer Salford to improve partnership working. Reference is made to the following key posts. | 30th September, 2001 31st Oct 2001 | Report findings to Salford Crime Reduction Partnership Incorporate findings into the development of the new 3 year Crime Reduction Strategy Staff recruited | Salford Crime Reduction Partnership CG\GD | Course completed and findings fed into development of new strategy. Completed |
| (1) Appointment of Crime and Disorder Analyst | 30th September, 2001 | Posts created, providing the following benefits to the partnership: (1) Improved collection and dissemination of key data and indicators Improved monitoring of partnership performance and key initiatives Improved performance management information Improved communications between agencies. |  | Staff in post (May 2002) and implementing role requirements. |

4. PARTNERSHIP WORKING

| Action | Timetable | Performance/Measure/Outcome | Lead Officer | Current Position |
| --- | --- | --- | --- | --- |
| Appointment of 4 Principal Policy Officers Appointment of Corporate Security Services Co-ordinator | 31st October, 2001 31st October, 2001 | (2) Improved co-ordination of strategic and local working Improved linkages between agencies and initiatives Provision of best practice advice at strategic and local level Improved ability to ensure local consultation impacts on strategic and service delivery. Development and implementation of a City Wide Strategy for CCTV Co-ordination of security services between directorates, partner agencies and the private sector Improved communications between partners Development of corporate specifications and operating standards for partners Improved resource procurement opportunities |  | Staff in post (February 2002) and implementing role requirements. Staff in post (May 2002) and implementing role requirements. |

4. PARTNERSHIP WORKING

Objective:  (a)	Introduce pilot scheme for Home Link Alarms on two council estates.

- Extend Salford’s Supported Tenancies scheme for vulnerable tenants including formerly homeless applicants.

- Introduce Landlord accreditation and licensing schemes for private sector landlords.

| Action | Timetable | Performance/Measure/Outcome | Lead Officer | Current Position |
| --- | --- | --- | --- | --- |
| (a) Carry out consultation Set up monitoring arrangements Fit alarms (b) Recruit additional staff Identify additional clients Implement service 40 additional single tenants and 15 additional families (c) Introduce Landlord accreditation scheme in Langworthy and Seedley Extend Landlord accreditation to Lower Kersal and Charlestown Introduce a Landlord licensing scheme in Salford following legislation | July 2001 – January 2002 January – February 2002 Sept 2001 – Sept 2002 | Consultation completed Alarms implemented Staff in post Additional clients identified Services provided Evaluation of impact of service delivery re: repeat victimisation Accreditation scheme introduced Accreditation introduced Licensing scheme introduced | NS JS BO | Purchase of partner company compromised contractual agreements. Need to seek other partners. Housing and Community Safety Unit to co-ordinate new approach. Staff recruited and implementation underway Completed first Annual Report produced. Expansion plans to Cabinet (10.9.02). Extension to Kersal/Charlestown in next 12 months. New Legislation “talked out” in Parliament. Currently awaiting new time slot. |

4. PARTNERSHIP WORKING

Objective: (a)	To ensure effective partner working relationships

- To develop effective inter-agency working

| Action | Timetable | Performance/Measure/Outcome | Lead Officer | Current Position |
| --- | --- | --- | --- | --- |
| (a) Ensure each Community Committee and Political Executive respond to Crime and Disorder issues by establishment of effective working relationships with Community Sector teams on a regular basis (b) Neighbourhood / Area Co-ordinators working with Police and Safer Salford to develop respective CST’s | Review quarterly 31st October 2001 | Arrangements for production, resourcing, implementation and monitoring of the Local Action Plans/CRS for each SDA in place Number of anti social behaviour offenders Number of crime conferences held Monitoring of re-offending rates Monitoring of reductions in local crime and disorder incidents related to targeted local actions Draft LAP’s submitted to SCRP annually for quality control CST’s in place and operating effectively | Neighbourhood & Area Co-ordinators/Sector Sergeants GD/Sub Divisional Police Commander Area Co-ordinators /Chief Inspectors/GD | Implemented and ongoing Database implemented and information supplied to partnership Database implemented and information supplied to partnership Currently under development Currently under development Completed previously. Is being developed with Principal Community Safety Officers Development of Teams currently underway and supported by Principal Community Safety Officers |

5. RESOURCES, STAFF TRAINING AND DEVELOPMENT

Objective: Resources  To ensure that appropriate staffing resources are available to deliver the Crime Reduction Strategy and that staff are suitably skilled and trained.

| Action | Timetable | Performance/Measure/Outcome | Lead Officer | Current Position |
| --- | --- | --- | --- | --- |
| Subject to the Review findings (refer to Section 3), ensure the Youth Offending Team has appropriate levels of resources to achieve its aims and objectives - Assess current level of resources using appropriate management services measurement techniques. - Assess wider implications such as impact on the Probation Service - Identify required levels of resources to achieve aims and objectives - Make recommendations for appropriate staffing levels Implement the findings of the Safer Salford Review to ensure that the necessary resources are available to develop and implement the Crime and Disorder agenda Ensure that sufficient administrative and clerical support is available for Neighbourhood Co-ordinators - Identify current administrative and clerical support and implement | By 30th September 2001 31st October, 2001 30th June 2001 | Report to Lead Member and Cabinet on the resource requirement for the Youth Offending Team Posts recruited (refer to section 4. Partnership working to identify key roles) Additional administrative and clerical support provided for Neighbourhood Co-ordinators | TM/RSB CG/GD AW/RSB/ST | Management & service review by Tom McDonald. Action identified under NRF proposals with YOT staffing to be enhanced Completed Posts recruited |

5. RESOURCES, STAFF TRAINING AND DEVELOPMENT

| Action | Timetable | Performance/Measure/Outcome | Lead Officer | Current Position |
| --- | --- | --- | --- | --- |
| Appoint staff Revise Directorate procedures for dealing with anti-social behaviour and including corporate/inter-agency working Provide comprehensive training package for Housing Staff Recruit additional solicitor and admin officer | July 2001 – July 2002 Sept 2001 Sept 2001 | Staff in post Revised procedure available Training completed Staff in post Number of cases undertaken Repeat victimisation rates | MJ/GS AE | Staff in place. Procedures revised and training provided. Further training planned for October 2002 re. I.T. and equality issues. Legal capacity being addressed by Best Value Review and subsequent Implementation Plan |

| 5. RESOURCES, STAFF TRAINING AND DEVELOPMENT |
| --- |
| Objective: Staff Training and Development – (a) Provide a training and development programme in response to the Section 17 statutory obligation. (b) To clarify role expectations in respect of crime and disorder |
| Action | Timetable | Performance/Measure/Outcome | Lead Officer | Current Position |
| (a) 1. To meet the knowledge and skills development needs of those employees who have specialist roles in crime and disorder reduction: - Executive Group; Policy Champions; Safer Salford Staff; Youth Offending Team; Drug Action Team; Area Co-ordinators; Neighbourhood Co-ordinators; Sector Sergeants; Staff from core community safety initiatives within the city (i.e. Burglary reduction; domestic violence; neighbourhood wardens etc, Partners agencies, Staff within regeneration initiatives) - Briefings for service managers from all Directorates - Briefings for senior managers from all Directorates | April – Sept 2001 August – Sept 2001 August – Sept 2001 | Number trained Training evaluation forms Impact of training monitored via staff appraisals Number briefed Provision of Crime & Disorder related service and financial plans and staff training | DH/AM DH/GD | More training to be delivered. Community Safety Unit/Personnel currently developing/implementing Crime and Disorder Training Strategy supported by resources from Government Office (North West) More training to be delivered. Community Safety Unit/Personnel currently developing/implementing Crime and Disorder Training Strategy supported by resources from Government (North West) |
| 5. RESOURCES, STAFF TRAINING AND DEVELOPMENT |
| Action | Timetable | Performance/Measure/Outcome | Lead Officer | Current Position |
| (b)Training to staff to reflect: - C+D Awareness (Section 17) - C+D Strategy + Partnership structures - Operational Manual - Related strategies and regeneration activities - Effective communications - Consultation in relation to strategy and delivery of initiatives - Performance Management and evaluation | 30th September 2001 and ongoing | Training delivered Impact monitored via staff appraisals | DH/GD/Line Managers | More training to be delivered. Community Safety Unit/Personnel currently developing/implementing Crime and Disorder Training Strategy supported by resources from Government Office (North West) |

5. RESOURCES, STAFF TRAINING AND DEVELOPMENT

Objective: To clarify role expectations in respect of crime and disorder

| Action | Timetable | Performance/Measure/Outcome | Lead Officer | Current Position |
| --- | --- | --- | --- | --- |
| To enable managers to include effective reference to crime and disorder reduction in the appointment, induction and appraisal of all employees and provide effective feedback on performance against s17 responsibilities Briefing personnel staff on the introduction of model phrases to be included in Job Descriptions and Person Specifications and how to reflect levels of involvement in recruitment materials Training for managers with regard to the amended Recruitment and Selection Code of Practice Development of specific materials for induction of all employees and employees moving into new jobs Amend Appraisal and Development Policy and guidelines | June 2001 May – Dec 2001 October 2001 June 2001 | Personnel staff introduce new expectations in recruitment materials and existing job descriptions At least one trained manager per recruitment panel Materials prepared and in use for induction programmes All appraisals include reference to crime and disorder responsibilities | DMB/HT DH/DMB DH Directors | Guidelines issued and disseminated Commenced and training ongoing Induction programme currently under review. Proposed re-launch by October 2002. Completed |

5. RESOURCES, STAFF TRAINING AND DEVELOPMENT

| Action | Timetable | Performance/Measure/Outcome | Lead Officer | Current Position |
| --- | --- | --- | --- | --- |
| To mainstream crime and disorder reduction issues into the full range of training undertaken by the City Council Promote the development of skills in preventing, avoiding and reporting incidents of crime and disorder |  |  |  | Refer to Crime & Disorder Training Strategy |
| Amend content of management development programmes Develop a ‘toolkit’ for Trainers to support the introduction of crime and disorder issues into mainstream training Develop ‘briefing packs’ for managers to use in team briefings etc Amend training, Appraisal and Development Policy and guidelines | May 2001 October 2001 August 2001 June 2001 | Contained in all programmes Toolkit developed and trainers briefed, training commenced Briefing pack produced All policies and appraisals include reference to crime and disorder issues and responsibilities | DH DH IA/DH DH | Amended Part completed. GD/DH to identify further proposals. To be undertaken. New process of Team Briefings presents opportunities for delivery. Completed, but currently being reviewed. |
| Promote personal safety training for frontline employees | Quarterly monitoring of implementation | Number of employees trained | Directors | Ongoing within C&SS/Housing Services. Further work to be undertaken. Refer to Training Strategy |
| Continue with programme of race and cultural awareness training Review and disseminate Violence to Staff Policy and Guidelines | Quarterly monitoring of implementation August 2001 | Number of employees trained New Policy disseminated to all employees New Policy disseminated to all employees | DH DB/IA DB/IA | Housing & Social Services underway. Further work to be undertaken. Refer to Training Strategy Policy in production. New draft almost complete |

5. RESOURCES, STAFF TRAINING AND DEVELOPMENT

Objective: 	To clarify role expectations in respect of crime

| Action | Timetable | Performance/Measure/Outcome | Lead Officer | Current Position |
| --- | --- | --- | --- | --- |
| Include in Members Training Programme All training to be reviewed for its content and amended appropriately | December 2001 April 2002 | Improved knowledge of issues by members All Directorate Training Plans report on performance in relation to crime and disorder | DH Directors | Published guidelines to all Councillors last year. Further work to be undertaken. Charles Green/Martin Smith to raise with Directors |
| Identify costed options including sources of funding for mainstreaming Section 17 based training and awareness | 30th June, 2001 | Report detailing options to be produced for Scrutiny Committee | GD/DH | Partnership Development Funding identified (2002-03). Considering use of “pooled budget” |
| Ensure roles of existing staff reflect the City Council’s Crime and Disorder (Section 17) responsibilities as soon as possible | By 31st March 2002 | All job descriptions revised to include reference to individual responsibilities and awareness of the City Council’s Crime and Disorder (Section 17) responsibilities. | All Managers/DH | Further work to be undertaken. Currently considering options |

6. COMMUNICATION

Objective:  To improve communication and understanding across all Directorates and Partner Agencies, to respond with a co-ordinated approach to Crime and Disorder issues.

| Action | Timetable | Performance/Measure/Outcome | Lead Officer | Current Position |
| --- | --- | --- | --- | --- |
| Audit and review all existing and proposed mechanisms for communications. Rationalise above information and develop a Partnership Communications Strategy Implement new Communications Strategy. Monitor on quarterly basis re: performance Evaluate on annual basis | 31st August 2001 31st March 2002 March 2002 – March 2005 | Database produced Review report produced and findings discussed by C & D partnership Strategy Produced and all partners consulted and signed up Report to Salford Crime Reduction Partnership annually | IA / Crime Reduction Partnership IA / Crime Reduction Partnership IA / Crime Reduction Partnership | Audit completed Progress report to C&D Progress Group Strategy developed and currently being implemented Ongoing |

6. COMMUNICATION

Objective:  To improve understanding of role of Crime and Disorder in order to inform policy review and development.

| Action | Timetable | Performance/Measure/Outcome | Lead Officer | Current Position |
| --- | --- | --- | --- | --- |
| Effectively utilise current mechanisms/ existing networks to communicate the following: Crime Audit and strategy development process Operational Manual Monitoring information i.e. Annual Reports, quarterly reports on CS Terms / Policy champions Group / P.I’s Crime Reduction Programme Regeneration initiatives Safer Salford Restructure Database of community safety initiatives CCTV strategy and list of current and future developments C & D solicitor and work in relation to targeting offenders of anti social behaviour Protocols for sharing information | Ongoing until March 2002 (monitor quarterly) | Press releases provided Articles in Salford People and related publications Partner feedback sessions Effective information sharing amongst partner agencies | IA /Project Managers/Salford Crime Reduction Partnership | Ongoing |

6. COMMUNICATION

| Action | Timetable | Performance/Measure/Outcome | Lead Officer | Current Position |
| --- | --- | --- | --- | --- |
| Ensure that the Local Education Authority produces a policy statement defining and identifying specific responsibilities for the following: Truancy / exclusions Support for disaffected young people School security Drugs policy etc - Bullying Ensure LEA policy statement is circulated to all relevant agencies | By 30th June 2001 By 30th June 2001 | Policy statement and definitions produced in consultation with schools and effectively communicated to all relevant agencies Policy statement effectively communicated to all relevant agencies. | MC/Schools MC | All sections have a policy statement. Completed |

7. PERFORMANCE MANAGEMENT

Objective:  To ensure that the City Council is able to determine the effectiveness of delivering the Crime Reduction strategy and monitor and evaluate its impact to inform future policy.

| Action | Timetable | Performance/Measure/Outcome | Lead Officer | Current Position |
| --- | --- | --- | --- | --- |
| To ensure that Crime and Disorder is a key aspect of the City Council’s and other partners performance management systems. Directorate Service Plans to clearly identify the Directorate contribution to ‘Making Salford a Safer Place’ and linkages to the new 3 year Crime Reduction Strategy. | September 2000 to March 2001 By 31st March 2002 | Best Value Improvement Plan Service Plans Area Plans Work Programmes Appraisals Individual Directorate Service Plans include aims / objectives / targets / identified level of resources and performance measures, agreed by Lead Member, Cabinet and Salford Crime Reduction Partnership | All Directors/Lead Members/GD/ Crime Reduction Partnership All Directors / Lead Members / Safer Salford | Integrated into authorities corporate performance management Currently reviewing new service plans. |
| Develop a framework/model for service/ initiative level evaluation Proposal to Directors for consideration Proposal to Salford Crime Reduction Partnership for approval Apply agreed corporate standard to ‘crime’ and all other activities. | 31st July, 2001 31st August, 2001 30th September, 2001 From agreement | Development of a corporate standard for evaluating services / initiatives impact on corporate objectives Corporate resource allocations informed by performance management analysis Consideration of effectiveness / impact of actions at service and corporate levels. Actions developed, as necessary. | PL All Directors / Lead Members / CG/Joint Chairs and Crime Reduction Partnership | To be undertaken. Currently considering options To be undertaken. Currently considering options To be undertaken. Currently considering options To be undertaken. Currently considering options |

7. PERFORMANCE MANAGEMENT

Objective: Review performance monitoring arrangements for anti-social behaviour

| Action | Timetable | Performance/Measure/Outcome | Lead Officer | Current Position |
| --- | --- | --- | --- | --- |
| (1) Ensure the Youth Offending Teams aims and objectives are monitored; and (2) Aligned with new 3 year Crime Reduction Strategy and Corporate Policy (1) Drug Action Teams aims and objectives are monitored; and (2) aligned with new 3 year Crime Reduction Strategy and Corporate Policy Introduce performance recording module as part of new integrated housing computer system Provide quarterly performance reports to Area Housing Committees and Lead and Deputy Lead Members for Housing | Quarterly March 2002 Quarterly (2) March 2002 October 2001 From December 2001 | YOT Service Plan integrated with the Chief Executives Service Plan and new 3 year Crime Reduction Strategy Monitoring report to be produced for Scrutiny Committee every 6 months and Crime Reduction Partnership (quarterly) DAT Service Plan integrated with the Chief Executives Service Plan Monitoring report to be produced for Scrutiny Committee every 6 months and Crime Reduction Partnership (quarterly Performance information available including number of cases dealt with and levels of repeat victimisation | TM/PL TM DAT Chair & Co-ordinator/PL DAT Chair & Co-ordinator MJ/GS | Ongoing Completed Ongoing Completed Completed Ongoing |

7. PERFORMANCE MANAGEMENT

Objective: To ensure appropriate, timely information is available to inform performance management, policy review, strategy and initiative targeting.

| Action | Timetable | Performance/Measure/Outcome | Lead Officer | Current Position |
| --- | --- | --- | --- | --- |
| Ensure effective information systems are designed to record the financial costs of crime: Systems should be supported by protocols that assist in the identification of such crimes. - Ensure information protocols are communicated to all directorates (for actions see target 6) - Monitor and evaluate recorded costs of crime information - Ensure resources are available for the crime and community profiler database to be operated and maintained - Monitor and evaluate the information obtained from the crime and community profiler database. This information to be utilised to develop the audit process and oversee the effective implementation of individual Crime and Disorder LAPs CAPs to be developed on annual basis and monitored quarterly | By 30th June 2001 Ongoing 30th September, 2001 Quarterly Annually with quarterly monitoring | Electronic information systems and protocols in place that provide the means of identification of the cost of crime within the City Council. Information reported to Lead Member, Cabinet and Salford Crime Reduction Partnership every six months to assist in the targeting of remedial action Resources established to operate and maintain the crime and community profiler. LAPs on Crime and Disorder reported every 3 months to Lead Member and Salford Crime Reduction Partnership Monitoring, development and the implementation of LAPs | AW AW/CG/SCRP CG/GD GD/SCRP Neighbourhood Co-ordinators/Sector Sergeants/GD | Discussions held with Directorates to identify crime related costs. Cost centres identified and reports created on SAP. Further clarification and communication to be undertaken and need to set up regular reporting structure. Staff recruited Implemented and ongoing Ongoing |

8. CONSULTATION

Objective:	(a) To improve the effectiveness of current consultation arrangements

(b) To develop alternative approaches to consultation order to improve effectiveness and feedback to Policy Development

| Action | Timetable | Performance/Measure/Outcome | Lead Officer | Current Position |
| --- | --- | --- | --- | --- |
| (a) Undertake an evaluation of the effectiveness of current public consultation exercises within the City on crime and disorder issues. This evaluation to include consultation with: Directors Community Groups Hard to Reach Groups PCCG’s Crime and Disorder partners Other outside partners (b) | By 31st August 2001 | Interim report to Lead Members and Cabinet on current public consultation within the City on Crime and Disorder issues. Final report to Lead Member and Cabinet on public consultation within the City on Crime and Disorder issues. | GD/PL GD/PL | To be undertaken. Currently considering options to develop this role. To be undertaken. Currently considering options to develop this role. |
| Undertake an options appraisal for the future delivery of public consultation within the City on Crime and Disorder issues linking to the Councils Corporate objectives. The options appraisal to include: Good practice from other organisations Advice from Beacon Councils Use of new technology | By 30th September 2001 | Production of a draft public consultation strategy (including feedback) for the City Council in relation to Crime and Disorder issues, which draws together the different approaches and ensures that consultation findings are fed directly into service delivery considerations. | GD/PL | To be undertaken. Currently considering options to develop this role. |

8. CONSULTATION

| Action | Timetable | Performance/Measure/Outcome | Lead Officer | Current Position |
| --- | --- | --- | --- | --- |
| Consultation on the options appraisal to be held with Directors Community Committees Hard to Reach Groups Youth and Minority Groups Crime and Disorder partners Scrutiny Committees Cabinet | By 31st December 2001 | Completed report including views from all groups consulted with, presented to Scrutiny Committee, Cabinet and Community Committees | GD/Crime Reduction Partnership | To be undertaken. Currently considering options to develop this role. |
| Implementation of agreed strategy for consultation. | April 2002 – March 2005 | Bi-annual monitoring and evaluation reports to Lead Member/Cabinet/Crime Reduction Partnership | GD/Crime Reduction Partnership | To be undertaken. Currently considering options to develop this role. |
| More effective use of existing networks i.e. Salford People SALI shop All Regeneration Initiatives Clientele of all Home Office Crime Reduction Programme’s, etc. | Ongoing until March 2002 | Consultation undertaken | Relevant Project Managers/GD | Utilised to consult on audit findings and draft strategy |
| Use above networks to consult on the following:- C & D Audit and Strategy Effectiveness of crime and disorder initiatives within all Regeneration programmes and Home Office Crime Reduction Programmes | Ongoing until March 2002 | Reports provided to Lead Member/Crime Reduction Partnership Result of consultation will inform performance management process. | Relevant Project Managers/GD | Utilised to consult on audit findings and draft strategy Further consultation to be undertaken |

9. GLOSSARY

ABBREVIATION OF LEAD OFFICER ROLES

| ABBREVIATION | NAME | TITLE |
| --- | --- | --- |
| AE | Alan Eastwood | Head of Law and Administration |
| AM | Angela Montgomery | Crime and Disorder Solicitor |
| AW | Ann Williams | Director of Community and Social Services |
| BO | Bob Osborne | Assistant Director of Housing Services (Strategy) |
| CG | Charles Green | Director of Strategy and Regeneration |
| DH | David Horsler | Principal Personnel Officer |
| DMB | Debbie Brown | Principal Personnel Officer |
| GR | Gary Rearden | Lead Principal Officer (Best Value) |
| HT | Howard Taylor | Assistant Director of Personnel and Performance Services |
| IA | Ian Andrew | Communications and Public Relations Manager |
| JS | Janice Samuels | Principal Officer (Supported Tenancies) |
| MBS | Martin Smith | Director of Personnel and Performance |
| MC | Mark Carriline | Director of Education and Leisure |
| MJ | Matt Jones | Anti Social Behaviour Unit Manager |
| NS | Nigel Sedman | Principal Officer (Contracts Administration) |
| OWG |  | Officer Working Group |
| PL | Pam Lowe | Assistant Director (Best Value and Performance) |
| RSB | Russell Bernstein | Assistant Director (Police and Scrutiny Support) |
| SCRP | Salford Crime Reduction Partnership | Salford Crime Reduction Partnership |
| SSM | To be confirmed | Safer Salford Manager |
| ST | Steve Thompson | Assistant Director of Community and Social Services |
| TM | Tom McDonald | Youth Offending Team Manager |