Strategy Monitoring Report

3rd Quarter October to December 2002

SALFORD CRIME AND DISORDER PARTNERSHIP

CRIME & DISORDER REDUCTION STRATEGY

2002 - 2005

STRATEGY PERFORMANCE INDICATORS

### Key:

.

Not on Target		= Not on target for delivery and unlikely to be achieved in next quarter

.

Near to Target		= Not on target for delivery, but may be achieved in next quarter

On Target			= On or exceeding target for delivery

| OBJECTIVE 1. RESPONDING EFFECTIVELY TO NUISANCE AND DISORDER |
| --- |
| Target | On target for Delivery | Comments / Action | Third Quarter Comparisons | Cumulative Comparisons |
|  |  |  | Oct to Dec 2001 | oct to dec 2002 | % Change | Apr to Dec 2001 | Apr to dec 2002 | % Change |
| Reduce the number of Juvenile Nuisance incidents citywide by 6% to 9,704 by 2005. Baseline: 10,323 incidents. Target to be reached by March 2003. Reduce baseline figure by 2% to 10,117. Refer to below Graph ‘A’ | On Target | If we continue performing as we have done during April to December, the projected figure for the number of juvenile nuisance incidents by March 2003 will be 9,059 incidents. This would exceed the 2003 target figure by 10%. | 2,721 | 2,182 | -20% | 8,117 | 6,794 | -16% |
| Reduce the number of Malicious Calls to Greater Manchester County Fire Service by 10% to 528 by 2005. Baseline: 587 Malicious Calls Target to be reached by March 2003. Reduce baseline figure by 3.5% to 566. Refer to below Graph ‘B’. | On Target | If we continue performing as we have done during April to December, the projected figure for the number of malicious calls by March 2003 will be 517. This would exceed the 2003 target figure by 9%. | 131 | 94 | -28% | 438 | 388 | -11% |
| Increase the participation of young people in sporting activities from 50% to 55.5% by 2005. Baseline: 56.3%. Survey conducted May 2002 | On Target | This target was set before the baseline figure had been established. Education and Leisure department now have a PSA target to increase the participation of young people in sporting activities by 25% from the baseline (ie; to 70.3% by 2005) |  | This PSA target has recently been agreed and discussions are underway to identify how it will be monitored. |

| OBJECTIVE 2. TACKLING VIOLENT CRIME |
| --- |
| Target | On target for Delivery | Comments / Action | Third Quarter Comparisons | Cumulative Comparisons |
|  |  |  | Oct to Dec 2001 | oct to dec 2002 | % Change | Apr to Dec 2001 | Apr to dec 2002 | % Change |
| Reduce the number of Violent Crimes by 18% to 3,729 by 2005. Baseline: 4,547 violent crimes. Target to be reached by March 2003. Reduce baseline figure 6% to 4,274. Refer to below Graph ‘C’. | Not on Target | If we continue performing as we have done during April to December, the projected figure for the number of violent crimes by March 2003 will be 5,176 crimes. This would be 21% higher than the 2003 target figure. | 1,212 | 1,396 | +15% | 3,460 | 3,882 | +12% |
| Reduce the number of Robberies by 38% to 639 by 2005. Baseline: 1,030 robberies Target to be reached by March 2003. Reduce baseline figure by 13% to 896. Refer to below Graph ‘D’. | Not on Target | If we continue performing as we have done during April to December, the projected figure for the number of robberies by March 2003 will be 1,040 crimes. This would be 16% higher than the 2003 target figure. | 334 | 225 | -33% | 835 | 780 | -7% |
| Reduce the number of Repeat Domestic Incidents by 10% to 645 by 2005. Baseline: 717 repeat incidents. Target to be reached by March 2003. Reduce baseline figure by 3.5% to 692. | Not on Target | If we continue performing as we have done during April to December, the projected figure for the number of repeat domestic incidents by March 2003 will be 1,255 crimes. This would be 81% higher than the 2003 target figure. | 196 | 344 | +76% | 205 | 941 | +359% |

| OBJECTIVE 3. REDUCING VEHICLE CRIME |
| --- |
| Target | On target for Delivery | Comments / Action | Third Quarter Comparisons | Cumulative Comparisons |
|  |  |  | Oct to Dec 2001 | oct to dec 2002 | % Change | Apr to Dec 2001 | Apr to dec 2002 | % Change |
| Reduce the number of Vehicle Crimes (both theft of and from) by 20% to 5,809 by 2005. Baseline: 7,261 Vehicle Crimes. Target to be reached by March 2003. Reduce baseline figure by 7% to 6,753. Refer to below Graph ‘E’. | Near to Target | If we continue performing as we have done during April to December, the projected figure for the number of vehicle crimes by March 2003 will be 6,877 crimes. This would be 2% higher than the 2003 target figure | 2,195 | 1,884 | -14% | 5,952 | 5,158 | -13% |
| Increase Detection Rate in relation to Vehicle Crime by 10% to 5.72% by 2005. Baseline: 5.2% Detection Rate. Target to be reached by March 2003. Reduce baseline figure by 3.5% to 5.4% | On Target | If we continue performing as we have done during April to December, the projected figure for the number of vehicle crime detections by March 2003 will be 7%. This would exceed the 2003 target figure by 30%. | 4.4% | 4.5% | +2% | 5.0% | 5.3% | +6% |
| Reduce the number of Malicious Vehicle Fires by 20% to 837 by 2005. Baseline: 1,046 Malicious Vehicle Fires. Target to be reach by March 2003. Reduce baseline figure by 7% to 973. Refer to below Graph ‘F’ | On Target | If we continue performing as we have done during April to December, the projected figure for the number of malicious vehicle fires by March 2003 will be 812. This would exceed the 2003 target figure by 17%. | 307 | 208 | -32% | 743 | 609 | -18% |

| OBJECTIVE 4. REDUCING BURGLARY DWELLING AND BURGLARY OTHER |
| --- |
| Target | On target for Delivery | Comments / Action | Third Quarter Comparisons | Cumulative Comparisons |
|  |  |  | Oct to Dec 2001 | oct to dec 2002 | % Change | Apr to Dec 2001 | Apr to dec 2002 | % Change |
| Reduce the number of Burglary Dwellings by 21% to 3,200 by 2005. Baseline: 4,051 Burglary Dwellings. Target to be reached by March 2003. Reduce baseline figure by 7% to 3,767. Refer to below Graph ‘G’. | Not on Target | If we continue performing as we have done during April to December, the projected figure for the number of burglary dwellings by March 2003 will be 4,188 crimes. This would be 11% higher than the 2003 target figure | 1,279 | 1,090 | -15% | 3,231 | 3,141 | -3% |
| No area in Salford to have more than three times the national average of 55.8 Burglary Dwellings per 1,000 households. (Current national average = 18.6 per 1,000 households) Area – Ward |  | The data to monitor this target is unaudited data direct from Operation Policing Units, MapInfo computer. At present upgrades are being made to this system and data is unavailable. Requests have been made to prioritise the required upgrades. |  |  |  |  |  |  |
| Reduce the number of burglary others by 15% to 2,751 by 2005. Baseline: 3,236 Burglary others. Target to be reached by March 2003. Reduce baseline figure by 5% to 3,074. Refer to below Graph ‘H” | Not on Target | If we continue performing as we have done during April to December, the projected figure for the number of burglary others by March 2003 will be 3,656 crimes. This would be 19% higher than the 2003 target figure. | 984 | 956 | -3% | 2,682 | 2,742 | +2% |

| OBJECTIVE 5. EFFECTIVELY RESPOND TO HATE CRIME |
| --- |
| Target | On target for Delivery | Comments / Action | Third Quarter Comparisons | Cumulative Comparisons |
|  |  |  | Oct to Dec 2001 | oct to dec 2002 | % Change | Apr to Dec 2001 | Apr to dec 2002 | % Change |
| Implement an effective third party reporting network for hate crimes by March 2003. | Not on Target | Work currently being undertaken to re-design 730D reporting form. Community forums have been established to develop the self reporting form and links for reporting centers. Subject to the executive group’s approval of the approach identified, we would anticipate the implementation of this target by August 2003. | Not Applicable |
| Increase the number of reported hate crimes by 30% to 398 by 2005. Baseline: 306 Hate Crimes Target to be reached by March 2003. Increase baseline figure by 10% to 337. Refer to below Graph ‘I” | Near to Target | If we continue performing as we have done during April to December, the projected figure for the number of hate crimes by March 2003 will be 319 crimes. This would be 5% less than the 2003 target figure. | 100 | 99 | -1% | 229 | 239 | +4% |