| Progress Update, March 2004 ENCOURAGING INVESTMENT IN THE CITY – Objectives 1-4 |  |
| --- | --- |

| Objective | Action | Timescale | Position March 2004 | Comments |
| --- | --- | --- | --- | --- |
| 1 Formalisation of communication protocols between SCC Development Planning and SCC Economic Development to improve partnership working | Workshop to develop joint work programmes and define roles and responsibilities Strengthen partnership with Development Services to establish a formal mechanism to bring forward Inward Investment opportunities Investigate the possibility of co–location of development surveyors within the Economic Development Section | Ongoing Ongoing Aug 2003 – Mar 2004 | Partially achieved Partially Achieved Possibility explored but not taken forward at this time | Development Services staff attended an ED Section meeting to discuss their work areas. Monthly meetings established with Forward Planning Section. Cross directorate working at monthly Development Team Approach meetings (Development Control) Development work ongoing meeting with Steve Gwatkin (Chapel St. Project team) to coordinate inward enquiries. Regular meetings with other officers to be arranged. It has not been possible to identify and secure the necessary funding and accommodation required in order to progress this idea further |
|  | Designated officer for Economic Development and Development Services established |  | ACHIEVED | E Colledge from Economic Development liases with Forward Planning team, whilst S Noonan liaises with development control section through Development Team Approach |
| Objective | Action | Timescale | Position March 2004 | Comments |
| 2 Improve partnership working arrangements with MIDAS: Put in place an improved Property Pilot database Create a Service level agreement with MIDAS | Agree operational procedures with MIDAS |  | Partially Achieved | Protocols under discussion |
|  | Develop partnership working at operational level to ensure continuity of service and aftercare Database updated more frequently and the development of a more systematic mechanism for local partners to validate the data Review progress after six months, if further improvement needed appraise option of inputting properties internally Formalise monitoring and evaluation with MIDAS to ensure resources maximised |  | ACHIEVED ACHIEVED ACHIEVED ACHIEVED | Database reviewed and improved. Review completed, no need for further appraisal. New service level agreement and protocols under discussion following expansion of MIDAS to include all Greater Manchester Authorities. |

| Objective | Action | Timescale | Position March 2004 | Comments |
| --- | --- | --- | --- | --- |
| 3 Analyse existing employment areas to ensure that sites and premises retain and attract businesses | Survey stock including older industrial stock and managed workspace provision. Consider above in light of plans for Central Salford, Salford West and Economic Development Zones Implement recommendations of review for existing stock Develop a strategy for the disposal and development of new products with targets to be established annually | Sep 2003 – Apr 2004 Dec 2003 – Mar 2005 Dec 2003 – Mar 2008 Dec 2003 – Mar 2008 | Brief prepared in consultation with colleagues in Development Services. Pending NWDA approval Pending the results of initial study Pending the results of initial study | Despite having been out to tender twice no interest was received for the work. Panel decided to split the project into two distinct phases. The results of the first phase due at the end of the first quarter 2004/05. A bid for match funding to enable the Study to be expanded Citywide has been incorporated within the Central Salford and Citywide Bids. Discussions to be held on the findings of the Study, with the Strategic Property Review Team and consequently corporate finance. |
| 4 Improve quality of property information for users (businesses, estate agents, developers) | Consultation exercise with property agents and developers Conduct survey of users of the property search facility Establish working group to implement an Investment Consultation Group Consider annual promotion of Salford’s properties and sites | Sep 2003 – Dec 2004 Dec 2003 – Aug 2004 Dec 2004 – Mar 2005r Dec 2004 | Will be undertaken via Investment Consultation Group. Questionnaires designed to incorporate equalities and freedom of information acts On hold | Due to staff shortages this has not been progressed. Electronic survey planned for first quarter 2004/05. Due to a current lack of resources not progressed Due to budget implications unlikely to proceed on Salford only basis – will look to maximise opportunities through MIDAS. |

| Progress Update, March 2004 BUSINESS SUPPORT – Objectives 5-9 |  |
| --- | --- |

| Objective | Action | Timescale | Position March 04 | Comments |
| --- | --- | --- | --- | --- |
| 5 - “Statement of Intent” which clearly expresses the aims and aspirations for the Business Liaison Team The ‘Statement of Intent’ should project a proactive business support team, which will deliver a service at a minimum equivalent to Beacon Council status | Evaluate the potential of co-location of the Business Liaison Team within Salford Innovation Park or a similar business development To raise the profile of Economic Development and services delivered. Devise publicity and Marketing Strategy | Mar 2004 Jul 03 – Mar 04 |  | Costs have been identified, and a possible partner identified. Further discussions needed in terms of accommodation specification and timescales. Draft Marketing Strategy work ongoing. Annual report was produced for 2002/03 and circulated to partners and at events. Material is Currently being collated to produce Annual report for 2003/04. |
|  | Attend a minimum of three Beacon Council Business Support events (Knowsley, Eastleigh, Rotherham) and determine best practice Creation of a clearly defined set of aims and objectives, which will fulfil the requirements identified through the statement of intent Produce Quarterly ED newsletter |  | Achieved Achieved ACHIEVED | Four issues of Eden produced and circulated to businesses and partners |

| Objective | Action | Timescale | Position March 04 | Comments |
| --- | --- | --- | --- | --- |
| 6 - To set up a central Salford Business Support mechanism through the purchase, installation and development of a Client Relationship Management System. To fully e-enable Business Support services and those of ED. | To improve the capture of data and its use in building business confidence through enhanced customer service. Medium term to link/offer use to partner organisations including Salford Hundred Venture and Salford Community Venture Run system up to fully operational and review additional ‘bolt on packages’ Devise Action Plan to implement e -enablement of all ED services | Aug 2004 – Aug 2005 Jan 2003 – Aug 2004r Jul 2003 – Dec 2004 | Partially achieved Partially achieved Partially achieved | Process being considered as part of the E-Gov agenda - ’Single Business Account ‘. Various options identified and require further exploration. On going – requires final transfer of data. Draft action plan agreed by E-Gov Team. Each enablement now requires implementation. |
|  | Identify suitable Customer Relationship Management System Obtain quotations and secure funding for CRM Place order, take delivery, installation Carry out internal audit to review services that can be e- enabled |  | ACHIEVED ACHIEVED ACHIEVED ACHIEVED | Basic training has been given assessment of reports required now being made prior to design time being allocated. Training on report production will then follow. |

| Objective | Action | Timescale | Position October 2003 | Comments |
| --- | --- | --- | --- | --- |
| 7 - Facilitate an Economic Development Forum sub group ‘Business Support’ Engage the private sector in driving the economic development debate viz. business support based on the model used at Knowsley | To attain agreement from Economic Development Forum to consider a ‘Business Support’ sub group of the ED Forum Seek assistance from Salford Chamber Executive to develop private sector led ‘Business Support sub group of the ED Forum Hold exploratory forum with companies who have accessed business support over the past three years and chamber members |  | ACHIEVED ACHIEVED ACHIEVED | Three Business Support Consultative groups have been held in October 2003, Jan and May 2004. Over 67 companies have attended these events. The Annual business survey also consulted with businesses. |
| 8 - Redefine linkages between partners to ensure a more joined up approach to business support. To create a virtual ‘one-stop-shop’ approach to business support | Developing tailored CBE information events for SCC and others | Jun 2003 - Dec 2004r | Pending | Presentations on partners roles at ME Away Day in September 2003. Next event is to take place in June 2004. |
|  | Develop an enhanced awareness programme for Chamber Business Enterprise, Salford City Council, Salford Hundred Venture and Salford Community Venture of support systems and mechanisms to ensure better understanding of “product”: Exploring the idea of an area focused CBE contact to create a gateway interface between the sector approach to business support of CBE and area focus of SCC Map responsibilities of all partner organisations |  | ACHIEVED ACHIEVED ACHIEVED | A number of secondees have a presence within the ED Section. These include representatives from Groundwork, Employment & Regeneration Partnership and the Chamber. Consultation exercises with partners for Citywide bid and revision of ED Strategy carried out in December 2003 and January 2004. |

| Objective | Action | Timescale | Position October 2003 | Comments |
| --- | --- | --- | --- | --- |
| 9 - Expand the existing network of business support forums to include other target audiences as identified both locally and nationally | Salford Entrepreneurs Club Woman In Business | Sep 2003 – Jun 2004r Sep 2003 – Jun 2005r |  | Unfortunately due to lack of staff the planned Salford Entrepreneurs Club and Women In Business Forum have been put on hold. |
|  | Creation and continuation of the following business forums: Ethnic Minority Businesses Salford Export Forum |  | ACHIEVED ACHIEVED | Identification of existing organisation, which Salford will link into rather than set up a separate Forum. 3 export forums held, a total of 78 companies attended with 6 companies exporting into new markets. |

| Progress Update, February 2004 EMPLOYABILITY – Objectives 10-18 |  |
| --- | --- |

| Objective | Action | Timescale | Position October 2003 | Comments |
| --- | --- | --- | --- | --- |
| 10 - Develop a Basic Skills Plan for the City and work with the Lifelong Learning Partnership (LLP) and Salford Partnership Employability Steering Group (SPESG) to drive implementation | Basic skills group to develop services/projects to achieve objectives and targets outlined in the final report and to monitor progress Establish baseline for ED 8a) (i) & (ii) and improvement targets according to findings of final report | Apr 2004 – Mar 2006 Jan 2004 – Apr 2005 | PARTIALLY ACHIEVED Pending LSC information | Plan delivered and targets established LSC is expected to release information Spring 2005 |
|  | To set-up a Basic Skills Sub Group to oversee the process, to include representation from SPESG Draw up a brief and circulate to consultants Deadline for submission of proposals by consultants Consultants to undertake: Mapping of basic skills provision Drawing up of basic skills plan for Salford Deadline for completion of work |  | Achieved Achieved Achieved Achieved ACHIEved |  |

| Objective | Action | Timescale | Position October 2003 | Comments |
| --- | --- | --- | --- | --- |
| 11 - Develop a continuation strategy for Salford Employment Charter post European Social Fund (ESF) funding, which ended in July 2002, and contributed 45% to the wage subsidy element. | Develop Continuation Plan to take account of recommendations made by the ESF Unit. Identify suitable/available funding for continuation beyond March 2003. Submit proposal for funding. If successful: Consult with local training providers to set up systems and procedures for referrals. Undertake pre-launch marketing and publicity Event to re-launch Salford Employment Charter Start to sign up Employers to the new Charter Code of Practice and provide advice and support with recruitment and development of staff Draw up enquiries proforma to enable the counting of business enquiries received Implement new monitoring and business enquiry system Work with the Business Liaison Team (BLT) to consider integration of Business monitoring systems | Apr 2003 – Mar 2006 Jul – Dec 2003 | Achieved Achieved Achieved/ongoing Achieved ACHIEVED ACHIEVED/ongoing Achieved Achieved ongoing | Training providers form part of the Salford Construction Partnership and as such closely link with the Charter for referrals. Charter Celebration took place 11/12/03 Ongoing (130) |

| Objective | Action | Timescale | Position October 2003 | Comments |
| --- | --- | --- | --- | --- |
| 12 – Develop a strategy to consider how the Local Labour Construction Initiative can link into the Housing Market Renewal Fund and how construction job opportunities can be created in construction for local residents | Develop baseline and targets in relation to number of people given advice and guidance and numbers of people assisted into jobs by December 2003, numbers of business advised and number of local people into jobs * Identify & Apply for Match Funding. Recruit a team of project management staff Invite partners to contract for the delivery of a designated centre for construction / or to expand existing facilities to provide the additional capacity necessary to meet the gaps and opportunities identified above | Dec 2003 Feb – Oct 2003 Apr - June 2004 Apr – June 2004 | Pending funding Pending funding | The partnership are still in the process of securing essential funds from NWDA but are working towards interim actions plans that aim to maximise mainstream funds as a contingency. Negotiations have progressed on the interim location of the Construction Hub and arrangements are now in place to locate at the Trafford Road Job Centre. |
|  | Consultation with partners /stakeholders in construction training delivery and employability services Produce a provisional outline bid. Undertake Gap Analysis to identify gaps and opportunities in terms of local training provision Identify suitable sites for building a new training centre if applicable and undertake site feasibility study. Develop Comprehensive Partnership Proposal. |  | Achieved Achieved Achieved Achieved ACHIEVED | The Business Plan has been finalised and endorsed by the partnership group. |

| Objective | Action | Timescale | Position October 2003 | Comments |
| --- | --- | --- | --- | --- |
| 13 – Improve integration of job creation and job preparation activities and create effective linkages between inward investment and major development activities and initiatives to provide workers to fill potential new posts. Consider use of Section 106 Developer Agreements to stimulate job creation and generate employment opportunities for local residents. | Work with Manchester Enterprises to undertake research into the legalities of 106 Agreements Create a framework for use of 106 Agreements across the City of Salford Develop baseline and projections for number of local people into jobs and Number of adults receiving advice and guidance, accessing education / training and employment* Provide links between local job preparation agencies and employment opportunities to ensure that local people benefit from local development, particularly those who are unemployed/furthest from the labour market Develop a Service Level Agreement with the aforementioned providers in order to ensure that they can deliver suitable / motivated potential recruits | Jul – Sep 2003 Jul – Sep 2003 Jul – Oct 2004 Jul - Dec 2004 Jul 2004 | Possibility explored but not take forward at this time Partially achieved Pending funding as in obj 12 Partially ACHIEVED Partially ACHIEVED | Visited Greenwich to explore using good practice in place for Greenwich. This system is recommended for adoption by Salford. Discussions taking place with Jobcentre Plus to establish SLA. |
|  | Examine literature and case studies to determine how 106 Agreements can be used Recruit a new Employment Charter Manager with expertise / knowledge in this field to work with other departments, particularly Development Services to lead on 106 Agreements |  | Achieved Achieved |  |

| Objective | Action | Timescale | Position October 2003 | Comments |
| --- | --- | --- | --- | --- |
| 14 – To build and maintain effective relationships with local partners through the Salford Partnership Employability Steering Group, in order to “champion” joined-up thinking, partnership working and the sharing of good practice to enable the effective implementation of Salford’s Employability Plan | Consider use of website as means for mapping services, maintaining up to date service and contact details, sharing information and best practice, | Jan – Apr 2004 |  |  |
|  | Employability Team Leader to act as “champion” for the Salford Employment Plan to: Chair and co-ordinate Steering group Meetings Manage the Employability Team Help set-up/coordinate a range of Sub Groups to focus on specific key areas To ensure that projects are developed to address the weakness/gaps in provision and meet the aims and objectives identified within the Plan Monitor progress towards objectives, and Oversee an annual review Undertake mapping of local employability services to determine potential areas of duplication/overlap and opportunity | Nov 2003–Mar 2007 Apr 2003 – Mar 2004 Jul 2002 – Jun 2005 Sep 2003, 2004, 2005 | ACHIEVED/ongoing ACHIEVED Achieved aCHIEVED/ongoing ACHIEVED/ongoing ACHIEVED 2003 Achieved | The Employability Steering Group is now re-structured and has met twice. As a priority the group are addressing; the production of a Partnership Protocol to secure a firm commitment from each organisation to the precepts of the group and the Salford Employment Plan; the development of a Performance Management System to generate a single set of employability targets in order to measure the impact of the Employment Plan; the generation of an Action Plan 2004/05. The Employability Network Group marked its inception with a ‘Barriers to Work’ event on 23rd March 2004. Key speakers delivered presentations relating 4 themes or barriers to work; ex-offenders, drugs misuse, health and childcare. Baseline data and information was collated and will be fed through to the Steering Group. |

| Objective | Action | Timescale | Position October 2003 | Comments |
| --- | --- | --- | --- | --- |
| 15 – Work with partners, particularly via the Employability Steering Group to develop future strategies and to identify potential funding for sustaining Salford’s key employability services, including: Jobshops (funded to March 2004) Employability Team (funded to June 2005) Salford Employment Charter (part funded to March 2006) | Monitor Jobshop targets on quarterly basis and discuss performance / local impact via “Keep in touch” meetings, contract reviews and team meetings Work with lead personnel and in consultation with partners via the Salford Partnership Employability Steering Group to review projects and develop strategies for continuance if applicable, or exit strategies if required Draft outline proposal and identify funding if required by: December 2003 (Jobshops) March 2005 (Employability Team) December 2005 (Salford Employment Charter) | Oct 2002 – Ongoing Oct 2002 – Ongoing Oct 2003 – Dec 2003 Jan 2005 – Mar 2005 Oct 2005 – Dec 2005 | ACHIEVED/ongoing ACHIEVED/ongoing ACHIEVED/ongoing | A meeting took place in Jan 2004 between Jobcentre Plus, Salford City Council and Employment Regeneration Partnership to map key priorities for future provision in light of jobcentre plus rollout in Salford. In principal an agreement has been reached for a 9 month extension to the current Jobshop+ contract. SRB funding of £128,000 has been secured which includes £17,000 for an independent evaluation and review of the service. In the process of sourcing other funding to enable delivery with partners, which includes an outline for £128,000 of ERDF funding. The Employability Steering Group are considering a ‘Partnership Protocol’ as a medium for sharing future resource on this project. Continuance or exit strategies should be built into the 2004/05 Action Plan due in April 2004. |

| Objective | Action | Timescale | Position October 2003 | Comments |
| --- | --- | --- | --- | --- |
| 16 – To develop a Service Level Agreement between Employment Regeneration Partnership and Jobcentre Plus in order to increase communication and sharing of information between agencies, so as to improve the quality of services provided to clients via Jobshops and Jobcentres. | Employment Regeneration Partnership/ Jobcentre Plus to draft SLA, ensuring that the Service Level Agreement encompasses delivery of the Public Service Agreement targets and includes Action Team for Jobs as a key partner Further develop SLA to encompass roles and responsibilities as Jobcentre Plus is fully rolled out in Salford and role of Jobshops is redeveloped | Apr 2003 – Mar 2005 | Achieved Ongoing | A Service Level Agreement has been agreed and signed between ERP and Jobcentre Plus. Further to this when Jobcentre Plus is fully rolled out in Salford and the role of Jobshops is redeveloped to plug the gaps, then this agreement will needed updating / amending to reflect these changes. |
| 17 - Influence & work with providers of mainstream training in order to maximise opportunities for Salford residents to improve their skills and raise aspirations of local people by working in partnership with Education and Leisure, the Lifelong Learning Partnership, Greater Manchester LSC, Jobcentre Plus and Connexions in particular. | Develop and maintain a working relationship between the Salford Employability Steering Group and the Lifelong Learning Partnership. Establish joint Basic Skills Sub Group to tackle Basic Skills agenda [See Objective10] Convene an introductory meeting to establish working relationships between the Charter and key training providers in order to develop referral procedures, arrange quarterly keep in Touch Meetings with partners and maintain effective systems for referral to training Gain commitment from local construction training providers to the training & development of Salford residents in order to reduce the skills shortages in construction [See Objective 11] | Oct – Dec 2003 | Achieved/ongoing Achieved Achieved ACHIEVED/ongoing | The reformed Employability Steering Group will have to consider how links can be maintained/developed with other strategic groups, including LLP and Basic Skills. All partners within the SCP, including training providers, have signed up to the precepts of the business plan, which includes ‘Training Augmentation’. The SCP will now focus on the delivery of this. |
| Objective | Action | Timescale | Position October 2003 | Comments |
| 18 - Develop a portfolio of success stories to be used in publicity materials. Employers need to see real examples of local success stories in order to understand how recruiting and training local people can bring real business benefits. | Review recent Charter employers to identify good practice Write case studies to be used for publicity materials Publicity materials produced Web applications explored Linkages to network activities with employers |  | Achieved Achieved ACHIEVED ACHIEVED ACHIEVED |  |