|  | PART 1 (OPEN TO THE PUBLIC) | ITEM NO. |
| --- | --- | --- |

___________________________________________________________________

## REPORT OF DEPUTY DIRECTOR ENVIRONMENT

___________________________________________________________________

## TO THE LEAD MEMBER FOR CUSTOMER AND SUPPORT SERVICES

## ON 1st October 2008

___________________________________________________________________

TITLE:  The refurbishment of the changing rooms at David Lewis Playing Fields

___________________________________________________________________

RECOMMENDATIONS:

That authorisation to expend capital be approved ___________________________________________________________________

EXECUTIVE SUMMARY:

___________________________________________________________________

BACKGROUND DOCUMENTS: (available for public inspection)

Report of Director to Lead Member Environment

Record of Key Decision made by Lead Member Environment

___________________________________________________________________

ASSESSMENT OF RISK:

Low

___________________________________________________________________

THE SOURCE OF FUNDING IS: Central Salford Urban Regeneration Company Business Plan

__________________________________________________________________

LEGAL ADVICE OBTAINED:

YES the council has agreed to exclusively purchase Works from Urban Vision. Urban Vision is to be offered the work on the basis of first refusal.

_________________________________________________________________________

FINANCIAL ADVICE OBTAINED:

Yes Environment Directorates Group accountant

____________________________________________________________

CONTACT OFFICER:

Steve Jones

___________________________________________________________________

WARD(S) TO WHICH REPORT RELATE(S)

Broughton and Cadishead

___________________________________________________________________

KEY COUNCIL POLICIES: please delete those not appropriate

Budget Monitoring

Community Strategy

Cultural Strategy

Environmental Strategy

Equalities

Health

Planning Strategy

Procurement Policies

Regeneration

___________________________________________________________________

DETAILS:

1.1 The Central Salford Urban Regeneration Company (URC) was established in 2005 to stimulate new investment and strategically co-ordinate regeneration and redevelopment in the seven wards of Kersal, Broughton, Irwell Riverside, Ordsall, Langworthy, Claremont and Weaste, and Seedley. They have ambitious proposals to transform Central Salford over the next 15-20 years.

1.2 The existing changing room building at David Lewis Playing Fields (appendix 1) was built over twenty years ago and contains two changing rooms, kitchen, boiler room, office, storeroom and toilets. The kitchen area is currently used as a mess room for Grounds Maintenance staff.

1.3 The building is now considered antiquated and the proposed development will improve the playing field provision, develop participation in sport in the area, and support the regeneration of the Broughton area.

1.4 In January 2008 Urban Vision (Architectural & Landscape Design Services)

was approached by the URC to  deliver a new changing facility at the above location with a budget of £184,000. In agreement with the Salford Community Leisure Ltd the building was to be a prefabricated four team changing unit. The contract had to be let before the end of March 2008 which was not met due to the requirements for a flood risk assessment and planning permission.

1.5 The URC managed to transfer the funding into this financial year but wished to see the new facility opened within the new football season. As design work commenced a number of issues became apparent, including concern about the security of the modular unit and the time it might take to get service connections.

1.6 It has recently come to light that the status of David Lewis playing fields has changed in that it now falls within the amended conservation area. This has meant that the proposed modular building is not acceptable without additional work to enhance its appearance. This is not possible within the URC budget.

1.7 Consideration was therefore given to refurbishing the existing  brick built changing facility and mess room which would achieve a number of additional benefits to that of a freestanding modular facility including;-

• no requirement for planning permission

• utilisation of the existing modern gas boiler

• refurbishment of the existing mess facility used by Grounds Maintenance staff

• no requirement for expensive and often time consuming service supplies

• a more secure building.

3.8 Salford URC is in agreement with spending the money on refurbishing and enhancing the existing facility.

2.0	Proposals

2.1 The most cost effective way to deliver an improved four team changing facility is to remodel the existing building which will involve the following.-

• target harden the building by bricking up the unnecessary doors and windows

• undertake general building repairs to the roof and soffits

• replacement of existing storage building (appendix 2) with a steel container

• increase the number of toilets from the existing 1 to 4 including disabled

• retention of existing modern boiler

• construction of a new kitchen

• construction of 4 new changing rooms

• The kitchen area will be used as a mess room by the Grounds Maintenance staff; consultation has been undertaken with all relevant parties and has led to an agreed layout of this provision and approval of the furniture and associated facilities   .

The drawing for the proposed building is included as appendix 3

3.0	Financial

3.1 As previously reported URC has agreed to fund the refurbishment of the changing rooms at David Lewis Playing Fields. The cost including all fees is £184,000 and the letter from the URC confirming this is attached as

appendix 4.

TENDER APPROVAL – PROFORMA

For use in seeking the approval of the Lead Member for Customer and Support services to proceed with a capital proposal

| Title of scheme: The refurbishment of the changing rooms at David Lewis Playing Fields. |
| --- |
| Recommendations (please append report to Lead Member for Directorate only if preferred) Approval is given to proceed with the above. |
| Scheme Details (please append report to Lead Member for Directorate only if preferred) Please see attached report |
| Tender details (please append report to Lead Member for Directorate only if preferred) To be undertaken in partnership with Urban Vision. Total capital cost £184,000 |
| Estimated - start Date October 08 Estimated – End Date March 09 |
| FINANCIAL DETAILS |
| Breakdown of scheme cost | 07/08 £000’s | 08/09 £000’s | 09/10 £000’s | Total £000’s |
| Contract (construction costs) |  | 157 |  | 157 |
| Fees |  | 27 |  | 27 |
| Other (specify) revenue |  |  |  |  |
| 2008/09 only – phasing of capital Expenditure (£000’s) |
| Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar |
|  |  |  |  |  |  | 10 | 25 | 5 | 50 | 10 | 84 |
| Note: The monthly cash flow above should be consistent with the contract start and end dates shown above and should allow for normal time lapses which will occur between work being done, claimed for, certified and paid, as well as retentions. Please consult your Capital Accountant if you need assistance with this or any other part of this proforma. |
| Is scheme in the Current Approved Capital programme? Yes |
| Funding identified | 07/08 £000’s | 08/09 £000’s | 09/10 £000’s | Total £000’s |
| Supported Borrowing |  |  |  |  |
| Unsupported Borrowing |  |  |  |  |
| Grant (Specify) Central Salford Urban Regeneration Company Business Plan |  | 184 |  | 184 |
| Capital Receipts |  |  |  |  |
| Other Revenue |  |  |  |  |
| Total |  | 184 |  | 184 |
| Other financial implications |
| Decision Lead Member Customer and Support services Approved/not Approved |

Appendix 1

Appendix 2

Appendix 3