Report to Environmental Scrutiny Committee

Development Control Improvement Plan

Progress Update, October 2003

The Speed of Processing of Planning Applications

Percentage of Planning Applications determined by Officers

| Indicator | 2001/2 Baseline | 2002/3 target | 2002/3 actual | April 2003 to August 2003 |
| --- | --- | --- | --- | --- |
| 1. Percentage of major planning applications given a decision within 13 weeks government target 60% - BVPI 109a) | 33% | 60% | 60.24% | 85.7% |
| 2. Percentage of minor planning applications given a decision within 8 weeks (government target 65% - BVPI 109b) | 60% | 65% | 68.08% | 86.7% |
| 3. Percentage of other planning applications given a decision within 8 weeks (government target 80% - BVPI 109c) | 77% | 80% | 82% | 91.7% |
| 4. The time from initial receipt of a planning application to and arriving with the case officer. | 11 days | Within 3 days | 7.75 days (1.04.03 to 31.05.03 is 4.83 days) | 4.7 days |
| 5. The number of decisions delegated to officers as a percentage of all decisions, (government target of 90% to be achieved by all authorities every year – BVPI 188) | 65.7% | 90% | 71.5% | 68.6% |
| 6. The number of Tree Preservation Order Applications determined within 6 weeks | 36% | 50% | 54.2% | 89% |

| Action Point | Action Required | Timetable | Actual Progress | Comments |
| --- | --- | --- | --- | --- |
| R1 Implement Oce process review to move to a digitally based service | Send out to tender Appoint FM contractor Implement action plan | August 2002 October 2002 November 2002 | Achieved Achieved Progressing - Pilot document management project being initiated | Annite commissioned to provide Eclipse software for document management project in common with other Council functions. Process review undertaken by Annite, hardware ordered and tested Staff training is currently being carried out and the process is about to start on a pilot basis. |
| R2 Extend the use of GIS to speed processes up and improve quality including:- accuracy of data reliability and consistency of data comparison of multiple data seta | Plot applications Input and correct constraint and historic data to speed up flow and improve accuracy Upgrade computer system to integrate with GIS (Uniform version 7) Introduce use of postcodes Acquire and install higher spec computers | Achieved March 2004 June 2003 2003/2004 2002/2003 | In progress In progress Included in computer system upgrade In progress | Constraints now plotted include: Coal Mining Areas Floodplain Wildlife corridors Sites of Special Biological Importance Removal of Permitted Development School Telecommunication zones Listed Buildings Conservation Areas Enforcement Pre-application enquiries Tree preservation Orders Landfill sites District/key local centres Installed September, 2003 Implementation will not begin until Document Management system is running Computers all installed |
| R3 Ensure adequate staffing levels and flexible structure | Obtain authority for DC Manager to recruit establishment posts under delegated authority Flexibility of structure achieved through use of small applications team Respond to peaks of work and specific tasks by use of contract services |  | Achieved Budget allocated | Small applications team established. This team, led by a Principal Planning Officer supports the 2 area teams (north and south). Planning Consultants engaged for planning appeal (Public Inquiry) |
| R4 Further develop the performance culture Focus staff on key improvements | Incorporate performance issues and target setting into appraisal system Staff training | October 2002 | Achieved Achieved | Speed of process of planning applications continues to improve |
| R5 Modernise how the City Council consults with regular users to secure quicker and more efficient transactions | Develop electronic consultation with consultees Commence consultation with regular customers via email E-consultation with all consultees | April 2003 September 2003 April 2004 | Limited interest, however, this will follow the establishment of document management and upgrade of planning applications computer system. Both projects have been initiated. | This will be introduced with document imaging. For example, United Utilities and Environmental Health are prepared for this. Discussions held with Environment Agency, who are changing their methods of engaging with local authorities |
| R6 Increase the percentage of planning applications determined by officers | Review scheme of delegation Report to Lead Member Report to Chair of Panel Consult all elected members Consult Planning User Panel Report to Cabinet and Council Introduce and publicise new scheme | May 2002 June 2002 July 2002 July/August 2002 September 2002 September 2002 October 2002 | Achieved Achieved Achieved Achieved Achieved Community Committee consultation substantially achieved. Introduce April 2003 | Revise Scheme of Delegation - approved by Council on 18th June 2003 Implemented 1st September 2003 – This will be monitored and reviewed |
| R7 Improve the speed of processing Tree Preservation Order applications | Additional staff (planning assistant) Use of GIS – TPO data Arboricultural advice | 2002/2003 | Achieved Digitising of TPO data has commenced. Achieved | The target for the speed of processing of applications relating to Tree Preservation Orders is being exceeded |
| R8 Improve access to service | Install public access package to Uniform version 7 Engage with corporate GIS development to facilitate customer access to service data including location of TPOs, listed buildings, conservation areas. | 2003/2004 2004 | This will follow introduction of planning applications computer system upgrade. | A Web based facility is included with the Eclipse Document Management system A Public Access package will be supplied by CAPS (part of the Uniform system) |

# Customer Relations

| Indicator | 2001/2 Baseline | 2002/3 target | 2002/3 actual | April 2003 to August 2003 |
| --- | --- | --- | --- | --- |
| 1. Number of hours the office is open to visitors | 37 hours per week | 40 hours per week | 40 hours per week | 40 hours per week |
| 2. Percentage of applications that can be submitted on line | NIL | NIL | NIL | 100% |
| 3. Planning Information available to minority groups |  | Produce multi-lingual pamphlet | Pamphlets produced and available in reception | Pamphlets produced and available in reception |
| 4. Customer Satisfaction – The percentage of customers satisfied with the service they received (Top Quartile – 81%) | 87% (2000/2001) | No target for 2002/2003 Survey to be undertaken 2003/2004 | _ | _ |

| Action Point | Action Required | Timetable | Actual Progress | Comments |
| --- | --- | --- | --- | --- |
| R9 Extend opening hours on Thursdays from 8.00am to 7.00pm | Produce protocol Consult staff Liaise with Building Managers re opening, security issues etc Publicise Staff rota Commence opening | Commence opening 26 September 2002 | Achieved Opening commenced on 3rd October, 2002. | This service is continuing |
| R10 Improve the web site | Enable applications to be submitted via the web Incorporate search facility Public access to database | January 2004 | Signed up to planning portal Upgrade of planning application computer system confirmed – this includes public access module and search facility | Planning applications can now be submitted electronically |
| R11 Improve access to the service by Black and ethnic minority groups | Produce multi-lingual leaflet and poster promoting the service Promote service with talking news | 2002/2003 | Achieved Language-line adopted by City Council | Large print documents are available on request |
| R12 Improve reception by implementing reception action plan | Highlight columns making them more visible Improve layout of reception furniture Provide better stands for documents | November 2002 to April 2003 | Achieved |  |
| R13 Publish service standards and information on planning applications on web site and poster in reception | Update website Produce poster | Achieved and review annually | Achieved and review regularly |  |
| R14 Introduce Duty Officer system | Establish protocol Train staff Produce rota | January 2003 | Achieved |  |
| Medium Term |  |  |  |  |
| R15 Submit charter mark bid to maintain continual improvement on customers issues | Produce draft Submit bid | 2003/2004 | This will be progressed when the assessment/application criteria is finalised |  |
| R16 Implement Peer Review Group 4 strategy | Monitor black and ethnic minorities Improve access to service | 2003/2004 | Monitoring commenced Impact assessment of Planning and Transportation Regulatory Panel and planning application process being undertaken. Monitoring commenced. | Monitoring took place in 2000/2001 and will be repeated in 2003/2004 Initial Assessments of Planning and Transportation Regulatory Panel completed. Draft Initial Assessments of Supplementary Planning Guidance in respect of House Extensions and Designing Out Crime drafted. Enforcement Charter and Publicity for Planning Applications to be undertaken by 30th June 2003. |
| Long Term |  |  |  |  |
| R17 Develop strategy for access to services via Contact Centre and One Stop Shop | Engage with corporate strategy | 2004/2005 | Implementing corporate document management system to link with Contact Centre and One Stop Shops | Progressing with development of ICT and information systems to facilitate this |

Quality of Outcomes/Added Value

| Indicator | 2001/2 Baseline | 2002/3 target | 2002/3 actual | April 2003 to September 2003 |
| --- | --- | --- | --- | --- |
| 1. The percentage of plans which have been amended prior to a decision being taken to improve quality of outcome | No data | 131/1326 9.9% (2002/3 actual to 31.12.02) | 206/1548 13.3% | 155/1041 14.9% |
| 2. The number of maladministration findings | 1 | 0 | 0 | 0 |
| 3. The percentage of appeals allowed | 35% | 35% | 38% | 8/32 25% |
| 4. Percentage of enforcement cases resolved within 13 weeks |  | 70% | 78.9% | 94% |
| 5. Number of formal complaints about the service (non-ombudsman & upheld) | 0 | 0 | 0 | 0 |
| 6. % of S.106 Agreements (planning gain) secured and required by policy | 100% | 100% | 100% | 100% |
| 7. Applicants of 50% of major planning applications engaged with Development Team | - | 25% | 13.4% | 22.6% |

| Action Point | Action Required | Timetable | Actual Progress | Comments |
| --- | --- | --- | --- | --- |
| Short Term |  |  |  |  |
| R18 Publicise the Development Team Approach | Publicised on the website and ongoing |  | Achieved and progressing | Development Team Approach Leaflet produced |
| R19 Proactive compliance checking | Establish framework Link with Building Control Train staff Publicise | 2003/2004 | Commence April 2003 | Draft report produced and system developed |
| R20 Adopt SPG for Telecommunications | Complete consultation Approval by Council | January 2003 March 2003 | Not Achieved Some rewording of the document necessary to use plainer language. This followed community committee consultation. Expected completion June 2003 | Consultation in progress |
| R21 Introduce members review of decisions | Produce protocol Introduce members inspection | 2002/2003 | Achieved Inspection undertaken November 2002 | This years review will take place in November |
| Medium Term |  |  |  |  |
| R22 Produce Planning Application checklist to improve quality of submission of planning applications | Adopt national planning application checklist | 2003/2004 | Prior to adoption of national planning checklist, Draft Check list has been produced | Checklist for house extensions has been produced |
| R23 Review staff manual on consultation | Produce staff manual Train Staff | 2003/2004 | Progressing Draft manual has been produced Staff training on consultation has commenced |  |
| R24 Review existing SPG for Hot Food Uses | Await issue of Government proposals in respect of revisions to Use Classes Order Report to Lead Member Consultation Address responses Lead Member Council | 2003/2004 | Government proposals on changes to Use Classes Order not yet issued |  |
| R25 Commission Greater Manchester Geological Unit to monitor major minerals and waste development and ensure compliance with conditions | Produce service agreement Implement | 2003/2004 | Progressing | GMGU commissioned on case basis |
| Long Term |  |  |  |  |
| R26 Produce new Supplementary Planning Guidance and review existing following review of Unitary Development Plan | A range of topics will be identified by the reviewed UDP which will require the production of SPG | 2003/2004/2005 | The topics identified for SPG in the first deposit draft UDP have been identified |  |

Transparency, Probity, Fairness and Consistency in Decision-Making

| Indicator | 2001/2 Baseline | 2002/3 target | 2002/3 actual to date | April 2003 to August 2003 |
| --- | --- | --- | --- | --- |
| Number of award of costs against City Council | 0 | 0 | 0 | 2 |
| Number of complaints received and upheld relating to local Code of Conduct | 0 | 1 | 1 | 0 |
| Number of complaints received and referred to National Standards Committee and upheld | 0 | 0 | 0 | 0 |

| Action Point | Action Required | Timetable | Actual Progress | Comments |
| --- | --- | --- | --- | --- |
| Short Term |  |  |  |  |
| R27 Revise Local Code of Conduct for Officers and Members dealing with planning matters in light of new publicised national and LGA guidance | Produce report Report to Lead Member Report to Council Implement and train staff and members | 2002/2003 March 2003 | Achieved Code of conduct has been revised. Reported to Lead Member 2nd December 2002 Reported to Standards Committee on 2nd December 2002 Reported to Planning and Transportation Regulatory Panel on 19th December 2002 Comments of District Audit incorporated | Adopted by Council in May, 2003. |
| R28 Produce Quality Assurance procedure for Planning and Transportation Regulatory Panel | Produce draft procedure Report to Lead Member and Chair of Regulatory Panel Consult members Train Members Implement | 2002/2003 | Achieved Achieved Achieved Achieved Achieved Achieved | April 2002 June 2002 September 2002 Reported to Lead Member with final draft December 2002 Reported to Regulatory Panel December 2002 Approved by Chairman of Regulatory Panel January 2003 Implemented January 2003 |
| Medium Term |  |  |  |  |
| R29 Produce policy on achieving a responsive dialogue with local people rather than just consultation (see Camden and Wirral) | Undertake research Produce draft policy Report to Lead Member Undertake consultation Report to Lead Member Train staff/implement and publicise | March 2003 September 2003 October 2003 November 2003 February 2003 March 2004 | Commence project in March 2003 | In progress |
| R30 Improve reporting of planning applications to Planning and Transportation Regulatory Panel | Improve layout of furniture in committee room Introduce more effective presentation techniques Improve access to committee rooms Improve customer care | 2004 |  | Reported to Lead Member and Regulatory Panel in May, 2003. This item brought forward to take advantage of ICT improvements, improve customer and customer involvement and take account of increased levels of officer delegation in respect of planning applications providing members with more time to consider major and contentious matters at the Panel. |

## Overall Conclusions

The targets relating to the processing of planning applications are generally on target and the recently acquired document management system will enable further efficiencies.

The actions in relation to Customer Relations are also generally being achieved. The Best Value Inspectors commented that the Council is providing a generally good standard of customer service, but felt that efficiency is hampered because service and business planning and prioritisation is not well developed. This is an area that is currently being examined. The Inspectors also found that information is provided in a range of formats, with some documents available in large print but not in Braille – this is also being developed.

In terms of Quality of Outcomes/Added Value, overall performance is improving. The key indicator measuring the percentage of appeals allowed is down to 25% - which is excellent. The main reason for this is the adoption of planning guidance (SPG) for house extensions. On appeal, Planning Inspectors are consistently commenting they are giving considerable weight to the Guidance. 94% of enforcement cases are resolved within 13 weeks (target 70%). Although this performance is very good, the Best Value Inspectors commented that enforcement of planning is still mainly reactive. Whilst this is true a system has now been developed for the monitoring of development to enable early intervention.

A key area is whether the Council’s decision-making is fair and effective. Whilst speed of processing planning is good and improving, the Inspectors felt the process of decision-making through the Planning and Transportation regulatory Panel is confusing and inaccessible to the public. Improvements are being developed which include a review of arrangements at Panel meetings, improved customer information and better techniques for the presentation of information - particularly in relation to ICT to enable plans to be viewed in Panel meetings. Despite the Inspectors comments about the Panel arrangements, they still felt that the Council is “making informed and well-balanced judgements and decisions on planning matters.” Costs were awarded against the Council on two occasions and whilst they are both relatively minor provide opportunities to improve our approach to planning appeals. One of them related to a house extension – permission was refused because it conflicted with the Guidance on House Extensions. The Planning Inspector granted permission and awarded costs against the Council because although the proposed house extension conflicted with the Guidance, he did not consider harm to the street-scene was sufficiently demonstrated.

The aim is to provide an excellent service for the people of Salford and the task now is to review this Improvement Plan, addressing the Inspectors recommendations, to provide the basis for future development and improvement.