CITY OF SALFORD

DEVELOPMENT PLANNING SERVICE

# SERVICE IMPROVEMENT PLAN

# Progress Update October 2003

# Executive Summary of progress

DP1. Plan Making.  The programme for delivery of the UDP is very tight to meet BVPI 200.  We are on track to deliver the Plan to Inquiry on target (autumn 2004).  There is a large amount of work required to inform the arguments at Inquiry.  That work is being undertaken, though there is a risk of some slippage, this is not critical at this stage.

DP2.  Brownfield Development. We continue to perform at a very high level against both best value and the sterner Regional Planning Guidance targets.  Last year we achieved 99% brownfield development (RPG target 90%).

DP3.  Effective Implementation of Plans, Policies.  Much work is underway in this area, and is broadly all on target (many actions are timetabled for coming years and therefore are yet to be started).  Changing legislation, requiring more timetabling of delivery of supporting planning documents will require even greater attention to this issue.

DP4.  Focus on what matters.  There has been a significant improvement in the last year on this indicator.  This demonstrates a greater clarity and focus of working against agreed priorities.

DP5.  Performance management.  This theme is central to the review of the section.  As with DP4 (shared indicators) improvement has been significant.  There remains much to be done.  In the area of work programming, more robust practices are being developed, with a view to delivering individual work programmes – no easy task in a dynamic environment.  One area of concern is the issue of benchmarking.  This has proved very difficult – Forward Planning work is very particular and there are very few nationally agreed indicators (unlike development control which is very much more process and target driven).  The Sandwell group of authorities struggled to agree a set of indicators and have found it more difficult to actually monitor progress on these.  Further work in this area may have to rely on learning from best practice.

DP6.  Customer Care.  Work in this area is progressing, but is evolving.  Given no clear demand for ‘surgery’ service (eg DC late night opening), work in this area is focussing on a more customer responsive model.  This involves attendance at public / community committee meetings to address specific issues (eg UDP Review, specific development proposals).

# AREAS FOR IMPROVEMENT

DP 1 - PROPOSED BEST VALUE PERFORMANCE INDICATOR ON PLAN MAKING – The Government is proposing to introduce a new Best Value Performance Indicator on plan making from April 2003 (BVPI 200). The current UDP was adopted in November 1995 and continues to form a robust basis for decision-making. However, the Development Planning Section is increasingly focusing its resources on reviewing the UDP to ensure an up-to-date policy framework that helps to meet the challenges facing the City.

# IMPROVEMENT TARGETS

| Indicator | Baseline 2001/02 | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 |
| --- | --- | --- | --- | --- | --- | --- |
| a) Does the authority have a development plan (or alterations to it) that has been adopted in the last 5 years and the end date of which has not expired? | No | No | No | No | Yes | Yes |
| b) If ‘No’, are there proposals on deposit for an alteration or replacement, with a published timetable for adopting those alterations or the replacement plan within three years? | No | Yes | Yes | Yes | Yes | N/a |

# PERFORMANCE IMPROVEMENT PLAN

| Action Points | Actions Required | Timescale |  |
| --- | --- | --- | --- |
| DP 1.1 Undertake key technical work to support UDP at Inquiry stage. | Urban potential work Housing needs assessment Industrial areas assessment Other Directorates (Housing/C. Exec’s) to support. | Spring 2004 Autumn2003 Winter 2003 | Urban potential study, undertaken summer 2003. Report of findings on target for spring 2004 (Pre-Inquiry meeting with Inspector) Consultants’ study completed summer 2003. Assessment of study underway. Discussions on brief commenced with Chief Execs. Completion may be delayed. |
| Medium Term |  |  |  |
| DP 1.2 The revised draft UDP is a key priority in the section’s work programme and has to be delivered to adoption by April 2006. | Direct resources from within the section and Directorate to ensure an adequate ongoing focus on UDP review work. | April 2003 – January 2006 | On target. Revised Draft due to go on Deposit 10th Nov 2003. Public Inquiry anticipated Autumn 2004. |

# AREAS FOR IMPROVEMENT

DP 2 - BEST VALUE PERFORMANCE INDICATOR ON THE PERCENTAGE OF NEW HOMES BUILT ON PREVIOUSLY DEVELOPED LAND – The City Council already achieves top quartile performance on this indicator, but it will be important to ensure that actions are taken to ensure that this excellent performance is maintained.

# IMPROVEMENT TARGETS

| Indicator | Baseline 2001/02 | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 |
| --- | --- | --- | --- | --- | --- | --- |
| Percentage of new homes built on previously developed land places the City in the top quartile (BVPI 106) & meets RPG requirement (minimum 90%) | top quartile (97%) | top quartile (98.9%) On target | top quartile (minimum 90%) | top quartile (minimum 90%) | top quartile (minimum 90%) | top quartile (minimum 90%) |

# PERFORMANCE IMPROVEMENT PLAN

| Action Points | Actions Required | Timescale |  |
| --- | --- | --- | --- |
| Short Term |  |  |  |
| DP 2.1 Improve monitoring systems | Increase the frequency of data collection from annually to quarterly | Winter 2003 | Work is in hand to improve systems to achieve quarterly monitoring. |
| DP 2.2 Involvement in NWDA pilot to test and work through the concept of “Brownfield Land Management Action Plans” | Work with NWDA & partners on delivering the pilot project. | tba | Joint working has commenced. Timetable to be confirmed. |
| DP 2.3 To actively bring forward brownfield sites for development. | identify and assemble brownfield sites proactively undertake site investigations | Ongoing Ongoing | With confirmation of HMRF funds over the next 2.5 years, a significant acceleration of this programme in Central Salford will be a priority. This will be delivered in partnership with Estates / Housing / Chief Execs colleagues. Site Investigations on assembled sites is a part of the programme. |

# AREAS FOR IMPROVEMENT

DP 3 - EFFECTIVE IMPLEMENTATION OF POLICIES, PLANS AND STRATEGIES – The Development Planning Section makes an important contribution to the development control process, and can help to ensure that it is both speedy and results in high quality development. Equally, it is important to ensure that the City Council’s planning policies continue to be successfully implemented through the development control process.

# IMPROVEMENT TARGETS

| Indicator | 2001/02 | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 |
| --- | --- | --- | --- | --- | --- | --- |
| % of responses to the Development Control Section made within 10 working days | 75% | 75% | 80% | 85% | 85% | 90% |

# PERFORMANCE IMPROVEMENT PLAN

| Action Points | Actions Required | Timescale |  |
| --- | --- | --- | --- |
| Short Term |  |  |  |
| DP 3.1 Ensure appropriate policy advice is given to applicants for planning permission in pre-application discussions. | Undertake a full assessment of the success of the Development Team Approach | Spring 2004 | To be commenced. |
| DP 3.2 Provide more written advice for prospective developers. Improve guidance given to applicants on policy requirements. | Prioritise SPG:- - Urban Open Space Strategy Open Space in housing developments - Student accommodation Broughton Park/Ellesmere Park Planning obligations MBB Canal Area Action Plans | Draft approved for consultation by Autumn 2003 Autumn 2003 Spring 2004 Spring 2006 Summer 2005 Autumn 2003 Ongoing | To Lead Members October 2003 Draft completed Draft in preparation. Draft completed. Further Progress delayed due to staff maternity leave. 2 of 9 prepared to first draft stage. |
| DP 3.3 Ensure that planning policy continues to be relevant and up-to-date | Monitor the implementation of planning policy and strategy through the development control system. Establish regular liaison meetings with Development Control, and a feedback mechanism to tell us when policy is inadequate, difficult to implement, or hard to understand. | Winter 2003 | Monitoring of planning policy applied through the DC process is underway. Liaison meeting(s) to be set up. |

# AREAS FOR IMPROVEMENT

DP 4 - FOCUS ON WHAT MATTERS – The Development Planning section supports the Community Plan and the Neighbourhood Renewal Strategy through its leading role in securing the physical regeneration of the City. Corporate priorities impact significantly on the section’s work programme and have to be effectively managed and delivered.

# IMPROVEMENT TARGETS

| Indicator | Baseline 2001/02 | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 |
| --- | --- | --- | --- | --- | --- | --- |
| Percentage of items identified in the Annual Service Plan that are: - Achieved - Substantially achieved - Partly achieved - Not achieved | 43% 0% 19% 38% | 80% 0% 13% 7% | 60% 10% 30% | 70% 10% 20% | 75% 10% 15% | 80% 10% 10% |

# PERFORMANCE IMPROVEMENT PLAN

| Action Points | Actions Required | Timescale |  |
| --- | --- | --- | --- |
| Short Term |  |  |  |
| DP 4.1 Community Plan Living Environment Forum to be developed as a Strategic Development Partnership. | Section will facilitate the Forum, with Housing and Environmental Services. Other partners may be required to service/develop the forum. | Summer 2003 | Living Environment Forum established and commencing work |
| DP 4.2 Prepare Derelict Land Strategy | Develop a derelict land strategy for Salford, which sits within the context of regional/sub-regional strategies and programmes, and connects to Salford’s own Neighbourhood Renewal Strategy. | Spring 2004 |  |
| DP 4.3 Improve mechanisms for coordination of work with Chief Executives Economic Development Service | Establish liaison structures and monitoring process. Investigate EDU joining the Development Team approach for pre application consultations on major development proposals | Autumn 2003 Summer 2003 | Discussions commenced. Structures still to be finalised. Implemented |
| Medium Term |  |  |  |
| DP 4.4 Integrate LA 21 into the Community Plan | Section will facilitate discussion with other directorates & partners to establish mechanisms for integration of LA 21 into the Community Plan at next review | Community Plan review (2005/6) | In hand. |
| Ongoing |  |  |  |
| DP 4.5 Ensure adequate staffing levels to deliver agreed work programme. | Monitor staffing needs in line with agreed work programme. Ensure speedy filling of posts that become vacant. | Ongoing | In hand. Refilling of recent vacancies have been expedited – in recognition of workload pressures. |

# AREAS FOR IMPROVEMENT

| DP 5 - PERFORMANCE MANAGEMENT – Improving the Development Planning Section’s performance management systems. |  |
| --- | --- |

# IMPROVEMENT TARGETS

| Indicator | Baseline 2001/02 | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 |
| --- | --- | --- | --- | --- | --- | --- |
| Production of an approved annual work programme | No | No | Yes | Yes | Yes | Yes |
| Percentage of items identified in the Annual Service Plan that are: - Achieved - Substantially achieved - Partly achieved - Not achieved | 43% 0% 19% 38% | 80% 0% 13% 7% | 60% 10% 30% | 70% 10% 20% | 75% 10% 15% | 80% 10% 10% |
| Percentage of annual / quarterly work programme targets achieved | tba | tba | 75% | 80% | 85% | 90% |

# PERFORMANCE IMPROVEMENT PLAN

| Action Points | Actions Required | Timescale |  |
| --- | --- | --- | --- |
| Short Term |  |  |  |
| DP 5.1 Develop a clear and deliverable work programme for the Development Planning Section. | Identify and introduce a mechanism for identifying and focussing on priorities and developing the section’s work programme, to be updated quarterly and reviewed annually, with reports to Lead Member. Produce a prioritised work programme for the section. Produce work programmes for individual members of staff. | Spring 2003 Spring 2003 Summer2004 | Being implemented. Quarterly update now due. Implemented. |
| DP 5.2 Improve the management of requests for new work | Establish a commissioning unit to manage requests for new work Briefs to be required for key pieces of work, which set clear targets / outputs Develop skills of estimating time required to undertake work. | Spring 2003 Spring 2003 Ongoing | Unit established and has commenced working. Evaluation of effectiveness to be undertaken winter 2003, and process reviewed. Implemented. Evaluation of effectiveness to be undertaken winter 2003, and process reviewed. Links to development of briefs and individual work programmes. Effectiveness to be monitored to assist in developing skills / best practice. |
| DP 5.3 Ensure that the key priorities and proposed work outcomes of the section accurately reflects the Directorate’s Annual Service Plan | Link Service Plan and Work Programming | Annually | In hand. |
| DP 5.4 Undertake process mapping for key work | Process map the UDP post 1st Deposit | Summer 2003 | Ongoing. |
| DP 5.5 Streamline monitoring of performance indicators | Identify and agree changes to the planning application form, DC reports & alterations in building control data recording required in order to speed up data collection. | Summer 2003 | Work in progress, but not yet completed, through LLPG and other mechanisms. |
| DP 5.6 Secure improvements to the way in which consultants are used | Produce a protocol on the use of consultants. | Spring 2004 |  |
| DP 5.7 Learn from Best Practice from around the country | Set up mechanism for identifying best practice from elsewhere and for ensuring that this can be used to drive further improvement. | Winter 2003 | Yet to be commenced. |
| DP 5.8 Improve the induction of new staff | Improve starters’ pack, including information on community strategy, equal opportunities policies, Council structures & decision making procedures, key contacts, charges, H&S responsibilities, etc | Autumn 2003 | Ongoing. Induction pack being transferred to CD format and content improved. Completion December 2003. |
| DP 5,9 Develop a standard approach to project management | Trial a new “project management and monitoring” approach for all significant projects Review this approach | Summer 2004 Spring 2005 |  |
| DP 5.10 Implement benchmarking with family authorities | Commence collection of the data for Sandwell Benchmarking Group indicators Identify any changes required in order to speed up data collection, such as modifications to the planning application form and DC reports, alterations in building control record keeping | Spring 2003 Autumn 2003 | Future of the Group and indicators under review. Work in progress, but not yet completed, through LLPG and other mechanisms. |
| Ongoing |  |  |  |
| DP 5.11 Seek to establish a Directorate strategic partnership | Contribute to Directorate initiative to create a strategic partnership with a private sector partner, | Summer 2004 |  |
| DP 5.12 Continue to develop time recording system | Develop time recording system in conjunction with work scheduling | Summer 2004 |  |
| DP 5.13 Develop the performance culture within the section. | Focus staff on key work programme priorities through regular updates / briefings and through the annual appraisal process etc. | ongoing | In hand. Groups developing work programme and performance culture. |

# AREAS FOR IMPROVEMENT

DP 6 - CUSTOMER CARE – Ensure a high level of customer care, in particular relating to the accessibility of the service.

# IMPROVEMENT TARGETS

| Indicator | Baseline 2001/02 | 02/03 to date | 03/04 | 04/05 | 05/06 | 06/07 |
| --- | --- | --- | --- | --- | --- | --- |
| Percentage of external customers who are dissatisfied with the availability of officers | - | 17% | - | 10% | - | 10% |
| Percentage of Councillors who are dissatisfied with the speed of responding to enquiries | - | 42% | - | 10% | - | 10% |
| Percentage of internal customers who are dissatisfied with the availability of officers and (or?) the speed of responding to enquiries | - | 15% | - | 10% | - | 10% |
| % of written correspondence (including e-mails) which is replied to within 5 working days | - | - | 90% | 90% | 95% | 95% |
| Percentage of new published documents produced by the Development Planning Section that are available on the internet | tba | 75% | 85% | 100% | 100% | 100% |

# PERFORMANCE IMPROVEMENT PLAN

| Action Points | Actions Required | Timescale |  |
| --- | --- | --- | --- |
| Short Term |  |  |  |
| DP 6.1 Provide written information on the service | Produce an information leaflet setting out what the Development Planning Section does and who does what, and including service standard. | Autumn 2003 | Leaflet not yet produced. Web site completely rewritten. Further development required. Purpose and content of service leaflet to be investigated. |
| DP 6.2 Improve cover arrangements in office. | Group Leaders to continue to ensure office cover during opening hours explore providing late night cover on Thursdays Produce protocol Consult with staff and unison Staff rota Commence cover | Ongoing Spring 2003 Summer 2003 | On going No demand for general late night cover identified. Specific demand for cover of public meetings / community committees recognised and being serviced. No demand for general late night cover identified. Specific demand for cover of public meetings / community committees recognised and being serviced. |
| DP 6.3 Ensure that those speaking/reading languages other than English are able to access the service | Incorporation of text in different languages in main documents and publicity leaflets indicating where language assistance can be found (eg via Language Line, Salford Link) | Spring 2003 | Ongoing. |
| Ongoing |  |  |  |
| DP 6.4 Develop strategy for improving feedback from customers. | Customer surveys Focus group | April 2004 |  |
| DP 6.5 Ensure that service is accessible electronically | Place copies of all major publications on the Council’s website | ongoing | Ongoing |