Report to Environmental Scrutiny Committee – 15th September 2003

Highway Maintenance / Traffic and Transportation/ Street Lighting Improvement Plan.

Progress Update, Updated for September 2003

Improving the Condition of Pavements

| Indicator | 2001/2 Baseline | 2003/4 target | 2003/4 to date |
| --- | --- | --- | --- |
| Community Perception of pavement condition | 23% good or very good 34% poor or very poor | A slight improvement | 5.6 % good or very good 67% poor or very poor Source: 2003 Re survey |
| Stabilise claims paid out | £2.1m ( 634 footway claims) | £1.9m | Est £6m stop loss figure |
| Repairing dangerous roads and pavements within 24 hours | 97% | 98% | 93% |

| Objective | Action | Timescale | Responsible Officer | Position Sept 2003 | Comments |
| --- | --- | --- | --- | --- | --- |
| R1Target planned maintenance resources to high risk areas | Analyse GIS Plans for “hot spots” | March/April 2002 |  | Achieved |  |
| R2 Seek Cabinet Agreement to using bitmac as standard except in designated areas | Obtain Cabinet view to policy change in principle | April 2002 |  | Achieved |  |
|  | Produce cabinet report seeking a resolution | May 2002 |  | Achieved |  |
| R3 Determine designated areas excluded from bitmac policy | Seek cabinet approval to designated areas | June 2002 |  | Achieved. Conservation areas and town centres excluded from bitmac policy | Further work required to produce maps and plans setting out specific areas. |
| R4 Improve the Inspection regime | Introduce new computer system incorporating hand held devices | April 2002 |  | Achieved |  |
|  | Increase Inspector numbers | During 2002 |  | Achieved. | Staff recently appointed |
|  | Re- define inspector roles | April 2002 |  | Achieved |  |
|  | Trial various methods of actioning repairs | During 2002 |  | Partly achieved. | Trials undertaken but not yet reviewed. Associated with the service development work of Accord plc. |
| R5 Merge the highway client and DLO | Devise and consult on staffing | May 2002 |  | Achieved July 2002. | Refer to progress summary at the end of this report |
|  | Determine facilities required | June 2002 |  | Achieved |  |
|  | Design and Construct building | December 2002 |  | Achieved |  |
|  | Move client staff to depot site | March 2003 |  | Achieved |  |
|  | Re engineer Processes | December 2003 |  | Progressing |  |
|  | Operate New Structure | January 2004 |  | Progressing |  |
| R6 Establish a consultancy with a construction company to introduce fresh thinking, prior to seeking tenders for an operational partner | Prepare Brief | July 2002 |  | Achieved |  |
|  | Advertise for expressions of interest | October 2002 |  | Not now considered to be required as firms interviewed during the BV review |  |
|  | Shortlist | January 2003 |  | Achieved |  |
|  | Seek tenders | August 2003 |  | Achieved |  |
|  | Evaluate and appoint |  |  | Achieved |  |
| R7 Introduce a Rapid Repair Service | Carry out further trials | April. May 2002 |  | Achieved .Accord Plc have produced report recommending service changes |  |
|  | Consider implications of trials on Code of Practice | May/June 2002 |  | Achieved. Accord Plc have produced report recommending service changes |  |
|  | Implement/publicise Rapid Repair service | August 2002 |  | Achieved but not fully publicised |  |
| R8 Establish closer liaison with Environmental Services via an Officer Partnership Board | Agree Constitution | April 2002 |  | Achieved |  |
|  | First Meeting | May 2002 |  | Achieved |  |
| R9 Revise Risk Management Process | Change claims handling process | Ongoing |  | Progressing. | Press release issued July 2003 |
|  | Implement SBS | August 2002 |  | Achieved |  |
|  | Improve communication with claims handling agents | Ongoing |  | Progressing |  |
|  | Produce Highway maintenance risk document | April 2003 |  | Not achieved |  |

Improving  Response Times to Non Urgent Works Orders

| Indicator | 2001/2 Baseline | 2002/3 | 2003/4 target | 2002/3 actual to date |
| --- | --- | --- | --- | --- |
| Percentage of non dangerous defects repaired within 2 weeks | 65% within 2 weeks | 90% within 3 months | 100% within 3 months | 88% in 3 months Note Target changed to 3 months to reflect standards used by many other local authorities, ( findings of Accord Plc) NB: The service has concentrated its efforts on improving the inspection regime, thereby increasing the volume of repairs to reduce the potential for accidents. |

| Objective | Action | Timescale | Responsible Officer | Position SEPT 2003 | Comments |
| --- | --- | --- | --- | --- | --- |
| R10 Revise practices | Purchase infra red patching system | April 2002 |  | Achieved |  |
|  | Staff training on system | June 2002 |  | Achieved |  |
|  | Launch Operation | July 2002 |  | Achieved | Coverage in Salford Advertiser |
|  |  |  |  |  | Results of a six week review |
|  |  |  |  |  | A 58% time and cost saving on repairing a pothole 50mm deep |
|  |  |  |  |  | A 17% time and cost saving on a pothole 25mm deep. |
|  |  |  |  |  | £25,000 per year has been freed up to fund more improvements |
|  |  |  |  |  | 14 tonne of dense bitumen used in 26 days. Used to be 118 tonne. |
|  |  |  |  |  | 88% of old carriageway surface retained and recycled |
|  |  |  |  |  | 104 tonne less of excavated carriage way to be disposed of, reducing disposal and land fill tax cost |
|  | Improve clarity of information produced through SBS | April 2002 |  | Achieved |  |
|  | Consider response implications of the Code of Practice | July 2002 |  | Achieved |  |

Reducing  the Number of People Killed or Seriously Injured on Roads

| Indicator | 2001 Baseline | 2002 | 2003 objective | 2003 actual to date |
| --- | --- | --- | --- | --- |
| Number of people Killed or seriously injured on roads (KSI’s). | 97 | 80 | <89 | 35 ( Jan – May) . |

| Objective | Action | Timescale | Responsible Officer | Position SEPT 2003 | Comments |
| --- | --- | --- | --- | --- | --- |
| R11 Seek resources through a PSA bid | Prepare background to bid | February 2002 |  | Achieved |  |
|  | Present to Cabinet | February 2002 |  | Achieved |  |
|  | Submit bid | March 2002 |  | Achieved. | Bid was successful. Two road Safety officers recruited March 2003 |

The Provision of Customer Information

| Indicator | 2001/2 Baseline | 2002/3 | 2003/4 target | 2003/4 actual to date |
| --- | --- | --- | --- | --- |
| Highway routing information for disabled people | No information | No information | Full information | No Information |

| Objective | Action | Timescale | Responsible Officer | Position SEPT 2003 | Comments |
| --- | --- | --- | --- | --- | --- |
| R12 Improve information for disabled people in conjunction with the Disability Access Forum | Disability Access Forum to identify suitable ways of publicising routes | By June 2002 |  | Not achieved. | Steven Lee and Trupti Patel have liaised with the City Councils Access Officer Judith Irving. Research of good practice in publicising routing information is continuing. Highway routing design for facilities for Disabled people is carried out in accordance with DfT guidance |
| R13 Improve public communication through the web site | Post on the web site a schedule of major utility works being carried out within the City Prepare on line forms to allow the reporting of defects via the web site Prepare on line application forms for approvals of skips, scaffolds, vehicle crossings and opening up permits | May 2002 December 2002 April 2003 |  | Achieved Not achieved Not achieved | Also posted Traffic Regulation orders on the web ( with maps) The web site is currently being redeveloped to accept on line reporting. Due Sept 2003. An IT Business Process Re-engineering team is to work closely with City Highways from September 2003 to progress this work. |
| R14 Produce alley gating guide | Complete consultation on the guide | September 2002 |  | Achieved |  |

# Reducing Opportunites to Commit Crime

| Indicator | 2001/2 Baseline | 2002/3 | 2003/4 target | 2003/4 actual to date |
| --- | --- | --- | --- | --- |
| The number of alley gating projects completed | 2 | No schemes handled by City Highways in 2002/3 | Approx 6 | 6 schemes developed so far this year: 1) Rear of Tootal Drive New Cross Street Barff Road & Glendore Salford 5 2) Rear of 233 to 257 Bolton Road & 46 -70 Fairfield Street Slaford 6 3) Rear of 193 - 231 Bolton Road 2-44 Fairfield Street including the passageway between 22-24 Fairfield Street and 211-213 Bolton Road 4) Passageway at the rear of 30-46 Milford Street & the side of 46 Milford Street 5) Passageway at the rear of 2- 26 Wychbury Street 1-25 Deyne Street 170-178 Derby Road & passageway at the r/o 170-178 Derby Road & r/o 170-178 Derby Road 6) Footpath at the side of 47 Kingsley Drive Lower Kersal |

| Objective | Action | Timescale | Responsible Officer | Position MAY 2003 | Comments |
| --- | --- | --- | --- | --- | --- |
| R15 Progress further alley gating projects in conjunction with community committees | Programme of work to be determined in conjunction with partners | On going |  | Progressing |  |

Improving Facilities for Disabled People

| Indicator | 2001/2 Baseline | 2002/3 | 2003/4 target | 2003/4 actual to date |
| --- | --- | --- | --- | --- |
| The percentage of pedestrian crossings with facilities for disabled people | 59% Previous definition | 72% ,4tth quartile | 73% | To be assessed later in the year |

| Objective | Action | Timescale | Responsible Officer | Position MAY 2003 | Comments |
| --- | --- | --- | --- | --- | --- |
| R16 LTP monies to be redirected at this PI | Procure a survey of work required and phasing options Commission Projects on a phased basis | April 2003 Ongoing |  | Achieved Partly achieved | Ahead of schedule A prioritised list is currently being produced |

Improving Ease  of Use of Footpaths

| Indicator | 2001/2 Baseline | 2002/3 | 2003/4 target | 2003/4 actual to date |
| --- | --- | --- | --- | --- |
| Percentage of footpaths easy to use | 50% | 68% , 3rd quartile, ( based on a 25% sample size) | 85% | Currently 30% ( apparent deterioration due to different random sample results – it is clear more signs are required). |

| Objective | Action | Timescale | Responsible Officer | Position SEPT 2003 | Comments |
| --- | --- | --- | --- | --- | --- |
| R17 That measures are taken to improve this PI | Ordering of new footpath signs | March 2002 |  | Achieved |  |
|  | Commence installation | June 2002 |  | Achieved |  |

# Improving the Condition of Street Lighting Columns

| Indicator | 2001/2 Baseline | 2002/3 | 2003/4 target | 2002/3 actual to date |
| --- | --- | --- | --- | --- |
| The percentage street lighting columns in need of urgent replacement | 10% | Est 11% | 12% | Not yet known |

| Objective | Action | Timescale | Responsible Officer | Position SEPT 2003 | Comments |
| --- | --- | --- | --- | --- | --- |
| R18 Produce a business case for PFI funding | Survey street lighting stock | June 2002 |  | Partially Achieved | Will now be a part of the PFI work |
|  | Consult with Unison Prepare Outline business Case Options report to Lead member Action preferred Option | April 2002 December 2002 February 2003 April 2003 |  | Achieved | The government has established a new process for the submission of PFI bids. Consultants have been appointed May 2003 to assist with the PFI Bid. Submission to the Government July 2003 with a view to entering into a contract in 2005. |

# Improving the Management of the Service

| Indicator | 2001/2 Baseline | 2003/4 target | 2003/4 actual to date |
| --- | --- | --- | --- |
| Staff attitude rating on whether poor performing colleagues are dealt with satisfactorily | 63 % would like to see more done 13% are content with current practice 24% are neutral | Improve on 2001/2 staff rating | 53 % would like to see more done 25% are content with current practice 22% are neutral |
| Improve quality of Highway Information Records | Satisfactory | Move towards Good | On target for long term objective |
| Degree of compliance with Code of Practice for Highway Maintenance | 55% full 27% partial 18% none | 61% full 33% partial 6%none | 64% full 27% partial 9%none |

| Objective | Action | Timescale | Responsible Officer | Position SEPT 2003 | Comments |
| --- | --- | --- | --- | --- | --- |
| R19 Improve staff appraisal system | Agree Improvements, action and monitor | June 2003 |  | Partially Achieved. | Re-launched sickness absence procedure guidance in July 2003 |
| R20 Improve Highway records | Complete National Street gazetteer level 1 | June 2002 |  | Achieved |  |
|  | Carry out study of existing record systems compatibility with SBS | April 2002 and ongoing |  | On target |  |
|  | Further progress the implementation of the SBS system |  |  | On target |  |
| R21 Further progress position against the Highway Maintenance Code of Practice | Further progress | ongoing |  | Progressing |  |

Increasing the level of Investment in the Highway

| Indicator | 2001/2 Baseline | 2003/4 target | 2003/4 actual to date |
| --- | --- | --- | --- |
| Increase baseline expenditure | 100% | 100% | 100% |
| Maintain levels of capital investment | 100% | 100% | 100% |
| Obtain capital investment from external partnership | Nil | Nil | Nil |

| Objective | Action | Timescale | Responsible Officer | Position Sept 2003 | Comments |
| --- | --- | --- | --- | --- | --- |
| R22 Ensure joint working with Regeneration Teams | Seek clarification of the bidding process | May 2002 |  | Achieved |  |
|  | Put forward ideas to include in bids | June 2002 onwards |  | Progressing |  |
| R23 Director of Corporate Services to instigate a process that models the SSA allocation to verify it | Review process with Director of Corporate Services | May 2002 |  | Achieved |  |

| R24 Explore long term Strategic partnership arrangements | Consultation, brief preparations etc. | September 2002 |  | Achieved |  |
| --- | --- | --- | --- | --- | --- |
|  | Advertise for expression s of interest Appoint partner | October 2002 July 2003 |  | Achieved July/August 2004 | OJEC Notice placed May 2003. 11 Responses to pre qualification questionnaire received 17th June 2003. Shortlisted companies to be invited to tender in October 2003 ( pending approval of Cabinet) |

# Progress Summary

The Service Improvement Plan is progressing well in most areas. Some slippage has occurred in one or two areas however progress continues to be made.

The  major “step change” aspect of the Service Improvement Plan was to merge and reconfigure  the previously separate  client and contractor functions into a modern and streamlined and customer focussed organisation. This step change is taking place in advance of the timescales set out in the Service Improvement Plan.

The Plan was threefold:

- Physical integration ( moving all staff to a single site)

- RE-Branding

- Re-engineering of job role, processes and systems

A pioneering feature of the modernisation and change management process was to engage, (following a tendering exercise )  a major private sector highway contracting company Accord Plc to act as a consultant and facilitator for these changes.

To date the newly merged organisation has:

- Designed, built and successfully relocated to a new depot on Swinton Hall Road

- Been re-branded as “City Highways”. The service will become the first to fully adopt and incorporate into its livery  Salford’s new “IN Salford “ logo following extensive work with the City    Councils Creative Consultants Hemisphere.

- developed a new high level structure

- Developed a new set of primary objectives for City Highways which closely link to and therefore maximise the contribution towards the achievement of the City Councils pledges.

- Set a timescale to November 2003 for the development and testing of new management control systems