Regulatory Reform Order – Housing Renewal Policy

Milestones 2003/04

| 1st Period April – June | 2nd Period July – September | 3rd Period Oct – Dec | 4th Period Jan – March | Future Milestones |
| --- | --- | --- | --- | --- |
| Policy framework outline Versions 1 & 2 produced Final draft policy produced by end of June 2003 Elected members questionnaire produced for members session with Keegans Group W/C 12th May 2003 Public questionnaire produced Commencement of consultation process on draft policy interventions with key internal & external partners May/June 2003 Publicity & marketing of New policy summary commencement in Salford people, Council website, Salford Advertiser, Roadshow, Staff newsletter. Collation of consultation results, supportive evidence May/June 2003 Reports to Lead member for housing services and Cabinet completed. Equality Impact Assessment to commence initial partial assessments to determine if full EIA required. Consultation carried out as part of planned process | Final HR Policy draft completed ready for approval with supporting evidence, results etc.30/06/03 Cabinet Approval sort of new policy 9th July 2003. Council adopts new policy 18th July 2003. Policy published & Equality Impact Assessment on website, local press coverage & formal launch Identification of Key Lead Officers for continued Policy development within the division. Develop draft Business Plan for coming 12 months Lead member report(s) on outline of new interventions to be explored. Define criteria for measuring performance of new interventions to be monitored, reviewed and implemented Devise operational plans Publication of Business Plan Monitor Business plan & operational plans Staff training & development review on new policy tools Establish work on new procedures to support policy tools | Research and development of new policy tools linked with the work of Housing Market Renewal work Establish preferred partners and methods of implementation of new tools 1st review of policy implementation to be completed by December 2003 1st Housing strategy/ Housing Renewal Policy review on cyclical programme Publicity on new policy tools to be developed Staff training & development ongoing | Research and development of new policy tools linked with the work of Housing Market Renewal work 2nd review of policy implementation, monitoring, evaluation & Housing Strategy/ performance monitoring Define/ Redefine overall strategic aims (including stakeholder views) Reports to Lead member for Housing on performance to date Publicity on new policy tools available | Complement the Housing Strategy and Business plan programmes to ensure synergy of processes for performance monitoring Develop long term policy tools for implementation to enhance the delivery of housing, regeneration and corporate objectives to secure overall sustainability of the City Complement the work of the Housing Market Renewal Fund Toolkit of Interventions to address the causes of housing market failure and homeownership Develop a range of policy tools with preferred council partners & agencies to secure access to financial assistance to identified groups/areas to maintain their homes/areas Complement the work of other corporate strategies such as Crime & Disorder, Health, Planning, Environment to contribute to overall sustainability of the City. Attract further private investment to the City through the policy development |